## Pavement
INSPECTION & TEST PLAN
Contract No 7/21/186 Work Area P1 - P18 |  | Contract Name: |  |  |  |  | Rev: | Originator | Date | Approved | Date
|  | Ruapekapeka Road Seal Extension |  |  | Pavement |  | 0 | Rian Du Plessis | 2021-10-13 | Bruce McDermott | 2021-10-13
ITP No: 04 | [6 empty] | 1
TASK | SPECIFICATION REFERENCE | TEST REQUIRED | INSPECTION BY | TASK TIMING OR TASK FREQUENCY | ACCEPTANCE CRITERIA | HOLD POINT (H) OR WITNESS POINT (W) | SIGNATURE | DATE | COMMENTS
Cement Stabilisation and Correct application Rate
Cement Supply | TNZ B5 | Supplier Documentation | Visual Inspection | TNZ M/15 / AS1672 Compliance Certificate to accompany all batches of cement delivered to site. | Meets NZS 3122 | W
Record Depth | Email from Engineer | Visual Inspection | UCC Rep | Application rate shall be recorded for each run | Depth must be equal to 150mm | W
Application Rate | Email from Engineer | Mat Test | UCC Rep/ Engineer | Every 400m2 | Within +- 0.5kg/m2 of the specified rate | W
| Email from Engineer | Average Usasge Test | UCC Rep/ Engineer | Upon Emptying the spreader and bulk truck | Within +- 2.5% of the specified rate | W
Compaction of Cement Stabilised Material | TNZ B5 | MDD using NDM | UCC Rep | Compaction must commence the same day as mixing. Nuclear densometer dry density tests to NZS 4402:1986 Test 4.1.2 (NZ Heavy Compaction) at randomly staggered transverse positions at 20 m intervals on each lane. | Value of density tests shall be an avergae of 95% of MDD with no single test below 92% | H