## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | ITP - Stabilising |  |  |  |  | Yes | ITP - Stabilising | 7bcce166-9972-467f-9938-0502240961ec
checkpoint-status |  |  | checkpoint | Cement Supply
label | f934fa5d-8622-55e5-b2e5-1267722ae3d4 |  | note | SPECIFICATION REFERENCE - TNZ B5
label | 62cb2cea-7d04-5fc4-bc8b-89b4a257b868 |  | note | TEST REQUIRED - Supplier Documentation
label | be10169d-23d4-52f1-94ad-c64ebd5fb8af |  | note | INSPECTION BY - Visual Inspection
label | 40d7371f-3b29-5cb6-a52e-e74a1a3ca416 |  | note | TASK TIMING OR TASK FREQUENCY - TNZ M/15 / AS1672 Compliance Certificate to accompany all batches of cement delivered to site.
label | 563afad0-e6da-5741-99e5-65b515f63436 |  | note | ACCEPTANCE CRITERIA - Meets NZS 3122
label | 55b9ede7-9202-50bb-90eb-a4a383320147 |  | note | W
checkpoint-status |  |  | checkpoint | Record Depth
label | 4475964c-0376-5298-98ba-0f99d36ac05e |  | note | SPECIFICATION REFERENCE - Email from Engineer
label | 63030adc-00fa-56ca-8c2f-ad0d3934818e |  | note | TEST REQUIRED - Visual Inspection
label | fbe63b43-dd6e-5379-9fcc-599baa01870a |  | note | INSPECTION BY - UCC Rep
label | 2c7abe7a-df3c-57bd-819c-ce6f76335d69 |  | note | TASK TIMING OR TASK FREQUENCY - Application rate shall be recorded for each run
label | 70e1183a-4839-5841-9ffa-6170ecb08f86 |  | note | ACCEPTANCE CRITERIA - Depth must be equal to 150mm
label | 1073a4fe-a294-5bb0-830b-6fce55edd880 |  | note | W
checkpoint-status |  |  | checkpoint | Application Rate
label | 214e2660-4f2b-5010-b625-0f33ef81ba04 |  | note | SPECIFICATION REFERENCE - Email from Engineer
label | bbdb9a99-e632-5f26-977e-040af66bf313 |  | note | TEST REQUIRED - Mat Test
label | bc7e8b87-dfa9-5ae9-a9de-dfc0d73d85d5 |  | note | INSPECTION BY - UCC Rep/ Engineer
label | 5d7b1deb-f114-58b9-98d6-9cfb4a84edaf |  | note | TASK TIMING OR TASK FREQUENCY - Every 400m2
label | f6ecf61b-0765-5086-9745-43f5d772dc51 |  | note | ACCEPTANCE CRITERIA - Within +- 0.5kg/m2 of the specified rate
label | 4d813dae-75c1-5a29-ba37-4c8a9fa20eec |  | note | W
checkpoint-status |  |  | checkpoint | Application Rate (1)
label | ec6f22b4-4fbc-5d89-862d-f43c268731a2 |  | note | SPECIFICATION REFERENCE - Email from Engineer
label | 26f1ea3a-688d-5599-b41a-76689b8cc57f |  | note | TEST REQUIRED - Average Usage Test
label | 35738dd9-c8ef-5908-8c4b-eeeb442bc71b |  | note | INSPECTION BY - UCC Rep/ Engineer
label | 410857ef-9ac7-5b76-a24b-4bd354afd9c5 |  | note | TASK TIMING OR TASK FREQUENCY - Upon Emptying the spreader and bulk truck
label | a647da2e-8bb8-55c2-aafd-df376b8b30ca |  | note | ACCEPTANCE CRITERIA - Within +- 2.5% of the specified rate
label | 0fa9812e-3722-5861-ac54-75523857a612 |  | note | W
checkpoint-status |  |  | checkpoint | Compaction of Cement Stabilised Material
label | 26538710-e5d6-5032-8637-3deb2f9558f5 |  | note | SPECIFICATION REFERENCE - TNZ B5
label | d872fe18-c952-525e-b79c-26608f924144 |  | note | TEST REQUIRED - MDD using NDM
label | dc4a0d95-d29d-523b-8e2c-6c198456cc36 |  | note | INSPECTION BY - UCC Rep
label | 5ff069ff-b73a-5362-8e86-70ee957fa13b |  | note | TASK TIMING OR TASK FREQUENCY - Compaction must commence the same day as mixing. Nuclear densometer dry density tests to NZS 4402:1986 Test 4.1.2 (NZ Heavy Compaction) at randomly staggered transverse positions at 20 m intervals on each lane.
label | 1c2ff394-2312-5bcb-99ad-a2ccd79df43b |  | note | ACCEPTANCE CRITERIA - Value of density tests shall be an average of 95% of MDD with no single test below 92%
label | 0fd08551-0cdd-54e5-bac0-05d9514fd76a |  | note | H
holdpoint |  |  | signoff | HOLD POINT