## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned | 7dcd98da-d942-4dbd-93c7-72461b0d60f2 |  | checklist | Partitions |  |  |  |  | Yes | Partitions | 25c6aea3-9b9a-49f5-9faa-4a8424d77e2f
checkpoint-group | adbb5d1c-472b-432c-9972-f825b75eff54 |  | section | Set out
checkpoint-status | 9ac93337-8b05-4e47-874f-4dfb9587fd75 |  | checkpoint | Partitions set out plans current revisions checked and wall set out completed as per the current plans
label | f881f1c6-50c8-52b6-9e44-f8eb92a9ea84 |  | note | Discussed/established with supervisor the minimum/critical dimensions (face to face) on drawings
checkpoint-group | 858406d8-56a3-46ce-956c-a15df110ec66 |  | section | Stud Framing
checkpoint-status | 538a2a92-9062-4c9e-a60e-cabdf75f946a |  | checkpoint | Check sizes and spaces as per the partition types. Stud spacing: 600mm generally & 450mm in wet areas
checkpoint-status | fb2f5107-111f-4f4f-8259-9d1f65a66f50 |  | checkpoint | Fix tracks ≤600mm centres and 100mm from ends, or as per project specific details.
label | e7f4ea98-725d-51f0-a75c-a7c89aac8be8 |  | note | Door frame openings as per Supplier design
checkpoint-status | 1a6671e7-03ea-460e-ae41-229cbde0b56e |  | checkpoint | Full height partitions: Fix deflection head tracks to the floor slab soffit to allow a minimum deflection capacity of 20mm.
checkpoint-status | 889d6cb8-e3f0-44f4-8cc2-9c00894049ff |  | checkpoint | Rotate intermediate studs into tracks for friction fixing
checkpoint-status | 51081549-98b4-4217-9a14-3cee5fd6b745 |  | checkpoint | Structural floor control joints: Disconnect partitions over joints with detached double studs and ensure bottom tracks, bracing and top tracks are not fastened across joints
checkpoint-status | 64acb54e-702c-411f-869e-64b171cc663a |  | checkpoint | Noggins: Fix Noggins as required for the framing system and to accommodate in-wall and in-ceiling services and fixtures
checkpoint-status | 5fd57074-1c34-4372-8381-9f0438ec08d2 |  | checkpoint | Door frames: Installed
checkpoint-group | 1f6b6f77-80c3-4262-bd40-6ebd86ae13b3 |  | section | Furring Channels
checkpoint-status | 4339525d-dbdf-4eca-8320-b81318f11d54 |  | checkpoint | Use powder actuated fasteners or masonry anchors of the expansion or chemical grout type
checkpoint-status | 7ea69fd6-ad0d-4bba-aab0-e6156427c894 |  | checkpoint | Place furring channels at ≤ 600mm centres and as to suit wall sheeting, or as per project specific details.
label | 7f6225d0-2e62-5f46-abb2-8020907751be |  | note | Where necessary pack using metal spacers to provide plumb and straight fixing background
checkpoint-group | b9a1138a-d939-4fc8-bf2f-ad60edbacdae |  | section | Bulk Insulation
checkpoint-status | ef3a0313-1bac-40e2-9511-0e399e2b65bf |  | checkpoint | Install acoustic and thermal insulation.
checkpoint-group | 058fd23a-0831-4bb4-b1e5-91c774c84ee7 |  | section | Hold Point
checkpoint-status | 8e87570a-c29f-4e4b-98f3-c5ab7fb6c956 |  | checkpoint | Framing system completed – Ready for installation of sheets.
checkpoint-status | 950040f6-1ce0-493b-a822-e1d7701ffa1d |  | checkpoint | Confirm all service trades are complete & ready for closing of walls.
checkpoint-status | f3deb385-c771-4bc1-b130-6d210a6222d5 |  | checkpoint | Obtain sign off by Lendlease
checkpoint-group | 856dce5d-3103-4c2b-b5e5-684795fa7de6 |  | section | Board Lining
checkpoint-status | 5df345fe-d034-4f0f-a1fa-985554e683d9 |  | checkpoint | Run sheets across the framing members
checkpoint-status | 0c452f0a-6720-48fd-8957-6989f0a3eea0 |  | checkpoint | Stagger end joints in a brick pattern and locate them on framing members away from the corners of large opening
checkpoint-status | 65798c3e-2ab4-4313-b2ad-986533cdeeec |  | checkpoint | Multiple sheet layers: Fill & flush up all joints and fixings as per Suppliers specifications and caulk up perimeters and penetrations before commencing succeeding layers.
checkpoint-status | 82f7fd0a-00ed-4b79-85ac-d0c31c1e270a |  | checkpoint | Stagger all sheet joints as per Suppliers specifications
checkpoint-status | 8e118d68-6696-4ecd-ae9f-01b9a06d7038 |  | checkpoint | Board joints: Do not fix the lining to abutting building surfaces
checkpoint-status | d27610bc-ecd6-46fe-a68d-4db0a8975154 |  | checkpoint | Butt joints: Provide perforated paper reinforcing tape
checkpoint-status | 0d8934e2-f903-4c53-8236-da7687faaf09 |  | checkpoint | External corners: Provide matching purpose made beads
checkpoint-status | e38f4625-87aa-4444-9fa6-e3e663a6734c |  | checkpoint | Internal corners: Provide paper tape and bedding compound
checkpoint-status | 1cfa3d07-f370-4aab-9a4a-aa3acbbd0068 |  | checkpoint | Provide fire, smoke and Acoustic sealing where indicated on the drawings/details.
checkpoint-status | 0c0bedd3-8f30-4858-8c43-659536f2ebf5 |  | checkpoint | Provide sealants at junctions between partition systems and with other building elements.
checkpoint-status | b45e3fb0-5e2f-4244-9327-3d0c85e353da |  | checkpoint | Provide trim such as beads, moulding and stops to make neat junctions between lining components, finishes and adjacent surfaces
checkpoint-group | e6a4e535-d317-4594-9d2a-1f9c3575c0e3 |  | section | Control Joints
checkpoint-status | d0d3a1bc-121f-41a8-b231-cb502b89eeac |  | checkpoint | Provide PVC or metallic coated control joint beads.
checkpoint-status | ab9a484b-c24c-4913-a3bf-7f905f9bd809 |  | checkpoint | Control joints to coincide with structural control joints
label | a607a043-1ed6-59a1-8049-8bfc0fdf2503 |  | note | Provide control joints as follows:
label | 6507f869-f7d1-59d7-90aa-1571d0186b88 |  | note | Plasterboard lined partitions: 12m centres
label | 8ee27e8d-a036-5851-9cd0-7f2dedd84c83 |  | note | Fibre-cement board lined partitions: 7.2m centres
checkpoint-status | eec928f4-3e64-437d-8958-75350be6b3c5 |  | checkpoint | Board lined partitions in wet areas: To suit joints required in tiling and at max 4.2m centres
checkpoint-group | 7fbe6178-795e-4a7a-b730-8bbaca07dd22 |  | section | Tolerances
checkpoint-status | afd43af4-0cad-4086-9c9b-d4f8ffea6458 |  | checkpoint | Flatness, twist, winding and bow: Maximum 1.5mm deviation from a 1.5m straightedge
checkpoint-group | 568fdd5f-421a-4d45-84a4-3e67a165f268 |  | section | Additional checks for Fire Walls
checkpoint-status | 515f3abb-e20c-4c19-8f85-4fda2fdc0ae0 |  | checkpoint | Installed as per board suppliers design & install specification
checkpoint-status | ae02e898-5792-4044-9035-9bb5912dc9c9 |  | checkpoint | Correct FRL achieved
checkpoint-status | eeb55ead-5fe9-496e-81e4-343e966318d5 |  | checkpoint | Deflection heads and all joints sealed, taped and set (Fire Sealant is approved prior)
checkpoint-status | 47e601bd-9f7b-49a7-9593-029582635eee |  | checkpoint | All penetrations through fire walls below and above ceiling protected/sealed – Service penetrations sealing by others
checkpoint-status | 7c502f59-ff8b-4ba5-ba87-ae35a92602e4 |  | checkpoint | Fire door frames installed
checkpoint-group | 588cd6d8-703c-40bd-912b-a53ac87ab513 |  | section | Additional Checks for Smoke Walls
checkpoint-status | a799a717-edbd-42fc-b0d9-7f2c5666d7a2 |  | checkpoint | Deflection heads and all joints sealed, taped and set (Sealant is approved prior)
checkpoint-status | d7d24f04-24b9-4ff8-8079-a1f4cc2f0ef2 |  | checkpoint | All penetrations through smoke walls below and above ceiling protected/sealed - Service penetrations sealing by others
checklist-sectioned | a34688e5-93b5-48b2-bb44-9fe28a5720c0 |  | checklist | Door & Frames ITP |  |  |  |  | Yes | Door & Frames ITP | 2da4b76b-707b-4b1a-a5a3-963086fbab07
checkpoint-group | d33751de-7fc4-4a14-8f6f-791798854463 |  | section | Paperwork Approval
checkpoint-status | 20080469-a8a1-4623-bbed-bc561af51117 |  | checkpoint | Area ready & accessible
checkpoint-status | 5774d32a-6e5a-4790-82d8-b570d561da1b |  | checkpoint | Frames as per design documents
checkpoint-group | 4a081d9d-476d-48ed-b27d-dd705a413a2a |  | section | Set Out
checkpoint-status | 0a493f81-12d1-4d58-929f-3dd2167b8c72 |  | checkpoint | Ensure Frames are set out as per Partition plans.
label | 3f6373d4-2361-582f-a6c4-ed31914dcc22 |  | note | Set out is to be read in conjunction with Door Schedule.
checkpoint-group | a7f5eb34-3173-40f8-b667-09edad7f0e62 |  | section | Execution
checkpoint-status | 7e7cb0ec-508a-4b9f-bb0d-c0b9bd576162 |  | checkpoint | Frames are plumbed, levelled, straight and within acceptable tolerances
checkpoint-status | 76b9d28d-ad48-4056-b565-c01691882997 |  | checkpoint | Frames are adequately fixed or anchored to the building structure
checkpoint-status | 66de86c9-4bc8-4d32-bbf0-ae1c48730723 |  | checkpoint | Frames are installed so that they do not carry any building loads
checkpoint-status | 5301a8c4-9c42-4248-92d2-420b24cb0224 |  | checkpoint | Joints are made accurately fitted tight so that neither fasteners nor fixing devices such as pins, screws, adhesives and pressure indentation are visible on exposed surfaces
checkpoint-status | f247bf08-52ef-4e96-a380-409ef3e8e9bb |  | checkpoint | Moving parts operate freely and smoothly, without binding or striking, at correct tensions or operating forces and are lubricated.
checkpoint-status | 2e46fb02-2fbe-49ef-a7f8-c39ed8b9a6aa |  | checkpoint | Fixings, rebates, grooves and clearances as necessary for installation and operation of the seals are provided.
checklist-sectioned | 8881136e-7e1c-4fe3-be95-7db8083ebdd4 |  | checklist | Paint ITP |  |  |  |  | Yes | Paint ITP | 2e44b720-ec2e-44cf-934c-faee5bc3d8f5
checkpoint-group | 22bb15fd-8b39-42cd-a161-8ab00a9f1a4d |  | section | Paperwork Approval
checkpoint-status | 292978eb-c53f-434b-8108-7fb5f6fafcdb |  | checkpoint | Area ready & accessible
checkpoint-status | 301a9685-a45b-4912-98ef-f2fd08262d15 |  | checkpoint | Are all SWMS approved and signed by all workers
checkpoint-status | 82c3a633-5e9e-478b-b16c-e158bbd70763 |  | checkpoint | Are all permits to work signed off by Lendlease
checkpoint-status | 09b0a038-ad8c-43cd-8383-a6e4b6b22879 |  | checkpoint | Are all technical samples approved via Aconex Workflow
checkpoint-group | 0cf0e0a6-d45d-41cf-964e-11cf4e1d1d52 |  | section | Spray Out Internal
checkpoint-status | 23e18959-bb1c-4620-b10b-6c030e443c42 |  | checkpoint | All plastering sanded and internal junctions free from dust prior to sealer undercoat
checkpoint-status | 75367823-de11-4a01-9730-e942beff16b6 |  | checkpoint | Full protection to joinery, window frames etc prior to painting. Any overspray is cleaned off prior to completion of spray out.
checkpoint-status | 058ec57b-8708-476f-810a-8948fc97b717 |  | checkpoint | All nail holes, joints and gaps are filled prior to painting.
checkpoint-status | 079817ba-626c-43c5-892a-3635d4c80acc |  | checkpoint | All edges to internal / external doors are sealed and painted as per manufacturer's specification.
checkpoint-status | 7e377097-ee0b-4559-82e6-eff60f1b32aa |  | checkpoint | All hinges, door furniture, latches and striker plates if removed are to be retained and re-installed prior to completion.
checkpoint-status | 28c34a02-f8b5-4ee0-82a3-f9fcfa9bf429 |  | checkpoint | All ceilings are lightly sanded in between all coats and are back rolled and laid off in reasonable fine stipple finish.
checkpoint-status | f16ed372-bb26-4b83-842e-d2c142d7e338 |  | checkpoint | All wall coasts are back rolled and laid off in a reasonable fine stipple finish.
label | 14f71b6e-d4c1-57c7-b0a7-9708973ceadf |  | note | All paint is NOT site tinted or any other liquid added or altered without written approval.
label | 8f1935ec-3d9c-5ec6-8dd3-b25fd63212f6 |  | note | Clean up is completed ONLY in the supplied wash out area.
checkpoint-status | 84dc9c24-7fce-4ba3-a5c1-ffeaae23a42e |  | checkpoint | All rubbish is to be placed in the bins provided and the area is to be left clean and tidy and void of rubbish and excess materials.
checkpoint-status | 73450beb-0023-4769-bed2-cfa2a91cb8ae |  | checkpoint | Ensure no damage is done to other trades work (if so, you Must Report to the Supervisor and Wadsworth Project Manager immediately).
checkpoint-status | 7246c0b7-f0ae-46c3-9fde-800430e3a6b3 |  | checkpoint | All completed works are consistent with the scope of works supplied by Lend Lease, the supplied paint specification, and approved samples.
checkpoint-group | a1d5a75f-82fc-446d-ab03-12a8d90738dd |  | section | First Coat & Final Paint
checkpoint-status | 556f29a8-1628-42c9-bdc2-25ab73f07658 |  | checkpoint | All Plastering sanded and all internal junctions are free from dust prior to sealer undercoat.
checkpoint-status | ed6ac5fe-5cde-40fd-96e2-c55b9434c11a |  | checkpoint | All Pre-paint plastering and damage defects are rectified and sealed up correctly prior to commencing painting.
checkpoint-status | 43cec0f8-6400-47ab-97a9-bae663789212 |  | checkpoint | Full protection to joinery, window frames etc prior to painting. Any overspray is cleaned off prior to completion.
checkpoint-status | 9b0ffadb-96a7-488b-864b-f049ad110d9c |  | checkpoint | All nail holes, joints and gaps are filled prior to painting.
checkpoint-status | c9092d39-fe68-41b0-a9b7-53e1a07a31bc |  | checkpoint | All edges to internal / external doors are sealed and painted as per manufacturer's specification.
checkpoint-status | 4aaf3705-cc04-40ab-9ec9-80c17182d387 |  | checkpoint | All hinges, door furniture, latches and striker plates if removed are to be retained and re-installed prior to completion.
checkpoint-status | 29d42d83-4eb6-4c2d-8fbb-9cd244cb4a75 |  | checkpoint | All walls are lightly sanded between coats.
checkpoint-status | 3d0fe986-807a-4e7c-8561-330abdeda6df |  | checkpoint | All wall coasts are back rolled and laid off in a reasonable fine stipple finish.
label | 9737f196-3839-5522-86e5-04be3b606388 |  | note | All paint is NOT site tinted or any other liquid added or altered without written approval.
label | a1601a04-5bf2-586e-bb93-5fc05d37040b |  | note | All cutting work is consistent is consistent and complete in a tradesman like manor.
label | af5ef151-1dfe-5cad-8d6c-6eaaaae328c2 |  | note | Clean up is completed ONLY in the supplied wash out bay.
checkpoint-status | 962d4f89-4d01-4a55-8f81-aeca5e44002f |  | checkpoint | All rubbish to be placed in bins provided and the area is to be left clean and tidy and void of rubbish and excess material.
checkpoint-status | 93ba0c87-05e1-4e9a-a931-ed118e139191 |  | checkpoint | Ensure no damage is done to other trades work (if so, you Must Report to the Supervisor and Wadsworth Project Manager immediately).
checkpoint-status | b6a1e9ff-6da2-425c-be9e-2c409457403b |  | checkpoint | All completed works are consistent with the scope of works supplied by Lend Lease, the supplied paint specification, and approved samples.
checklist-flat | 312f9e3e-1706-41e6-ad33-83d9f6491877 |  | checklist | INS 105 Martini HD50 Underslab Insulation |  |  |  |  | Yes | INS 105 Martini HD50 Underslab Insulation | 3e1359d7-d7ac-487b-b248-d66a11395b02
checkpoint-status | d4cb14a8-d988-4553-8a36-3186f31c603b |  | checkpoint | Area ready & accessible
checkpoint-status | a813ee16-7fac-43b1-a9e5-b6842aa69b43 |  | checkpoint | SWMS are Approved Prior to Commencement
checkpoint-status | a487de21-4bc9-4922-85a3-b13ead2d27d9 |  | checkpoint | Sample Submission approved via Aconex
checkpoint-status | 3b2c654e-fff4-41ac-af5a-21122dd3ad87 |  | checkpoint | Insulation panels arrive as per Design Documents and defect free.
checkpoint-status | 41fbe01b-c762-43db-8820-6c4abe60a73e |  | checkpoint | Ensure most up to date drawings are being utilised
checkpoint-status | 93ee20a8-b67b-4093-b7e3-1ae8753d2475 |  | checkpoint | Mechanically fix panels to manufacturer's Specifications
checkpoint-status | 5eff23d2-85ce-414c-ac72-96c2d9587123 |  | checkpoint | Lend Lease to Sign off on completed area
checklist-sectioned | 95396c4f-d1d2-4a5a-9245-dacdef188f75 |  | checklist | Ceiling ITP |  |  |  |  | Yes | Ceiling ITP | 5dacab3e-5342-409c-9f65-440c9878d707
checkpoint-group | c8df6560-e3b8-4bee-a3d4-dd645ef2b465 |  | section | Paperwork Approval
checkpoint-status | b3126cb7-713a-4d5b-8585-1f8dc0c958ab |  | checkpoint | Area ready & accessible
checkpoint-status | 71af4a7c-ef22-4f7c-ac8b-b168181c9aba |  | checkpoint | Are all SWMS approved and signed by all workers
checkpoint-status | ad0aad44-6d67-4492-b721-d3cbcbc94389 |  | checkpoint | Are all permits to work signed off by Lendlease
checkpoint-status | 9674393f-6ea6-4286-9e98-8320a98c5d81 |  | checkpoint | Are all in-situ mockups approved by consultants
checkpoint-status | 727fbe7e-bd50-4a7a-8fb6-ce493a705037 |  | checkpoint | Latest endorsed drawings available (attach below)
checkpoint-status | 876e7e04-371a-4271-be1a-62582cfecc20 |  | checkpoint | Reflected ceiling plans current revisions checked and ceiling set out completed as per the current plans
checkpoint-group | 29d4a5cc-a41a-4783-8477-f133b54edb0d |  | section | Construction Generally
checkpoint-status | ae78347b-62d0-464a-b2e0-78b2de898905 |  | checkpoint | Install & fix to prevent looseness or rattling of ceiling components
checkpoint-status | 1333fa54-dedc-4f46-92c8-ccd5e3864702 |  | checkpoint | Ceiling systems do not amplify structural-borne sounds.
checkpoint-status | 5ed52bf8-67ac-454e-bf70-59e5a39fe05a |  | checkpoint | Install the ceiling to allow for differential movement at abutting surfaces
checkpoint-group | 235a9e86-090b-419d-9980-38e96b620512 |  | section | Suspension System
checkpoint-status | dedd172f-d5f4-4b8a-a61e-5664d6b6d9a0 |  | checkpoint | Provide suspension system and workmanship as per supplier installation guides.
checkpoint-status | aeaeac2e-5e82-43d5-a197-f445ba1d3823 |  | checkpoint | Provide additional back support or suspension members to prevent distortion, overloading or excessive vertical deflection.
checkpoint-status | 63b9d5f9-7e22-41da-af8e-7911a2697cae |  | checkpoint | Ensure that the failure of any one suspension point does not cause a progressive failure of the ceiling.
checkpoint-status | e0b3a536-2012-4e9f-9f42-f7aec1466ca9 |  | checkpoint | Provide height adjustment with a length adjustment device at each suspension point
checkpoint-status | 483f83ad-5343-4fed-9ca5-7f4091292dd2 |  | checkpoint | Services: Do not fix to the installed services. Where services obstruct the ceiling supports, provide bridging and suspension on each side of the services.
checkpoint-status | eed02048-7fd9-42f0-be7c-4b3e59cf5926 |  | checkpoint | Uplift: Suspension system and framing to resist uplift.
label | 6167456e-6817-5651-9f98-fe4482f0875a |  | note | Tolerances: Flatness, twist, winding and bow: 1.5mm deviation from a 1.5m straightedge places in any position
checkpoint-status | 438a5dd1-561b-4671-8de7-8e879e74aab8 |  | checkpoint | Suspension system completed – Ready for installation of ceiling tiles, lining and panels.
checkpoint-status | 60ba73c6-4b80-443a-a804-b96f5f9934a4 |  | checkpoint | Confirm all service trades are complete & ready for closing in of ceilings.
checkpoint-group | 83ea2d1a-7461-4744-96d0-b2bcf789dda5 |  | section | Ceiling Lining
checkpoint-status | 2820c258-32a8-4255-b1ba-c435270b51e8 |  | checkpoint | Provide board lining to a finish and workmanship as per supplier installation guides.
checkpoint-status | 4cc6c99a-3f20-4a0a-be50-583dc4a65229 |  | checkpoint | Fit accurately and neatly, without distortion.
checkpoint-status | ae0fe8ef-296a-49c4-a502-8a550b5d32af |  | checkpoint | Cut ceiling unit edges: conceal, or finish to match prefinished edges.
checkpoint-status | 4918a5b6-ae14-4d14-bb5e-48a7cb9bfbe9 |  | checkpoint | Multiple sheet layers: Fill & flush up all joints and fixings as per Suppliers specifications and caulk up perimeters and penetrations before commencing succeeding layers.
checkpoint-status | 046772e9-8a9d-44f3-b502-d036e2f6e9c8 |  | checkpoint | Stagger all sheet joints as per Suppliers specifications
checkpoint-status | c9837533-f103-4c04-a202-74b1e8169f57 |  | checkpoint | Board joints support: Provide appropriate framing to support sheet joints
checkpoint-status | 01519743-58dd-4643-93db-4091a590561c |  | checkpoint | Flush joints: Provide recessed edge sheets and finish flush using perforated paper reinforcing tape.
label | 87e235cd-5506-5bac-a7b9-70bd4f043147 |  | note | Tolerances: Suspension system bearing surface for flush lined ceiling to AS/NZS 2589
checkpoint-status | 29cb0c4a-531c-4105-8875-318486c1399d |  | checkpoint | Levelness: Max tolerance of ±5mm relative to the documented height datum for the ceiling in each room or space.
checkpoint-status | 9fc8e838-7454-44d3-8e89-3886be2e0bfe |  | checkpoint | Trims & accessories: Provide trims at junctions with other building elements and surfaces, including walls, beams and penetrations as documented
checkpoint-group | 8c4e0c96-ec06-4357-8df4-27873359b98d |  | section | Control Joints
checkpoint-status | 87b9e62f-82f2-45f8-ad6f-affa512f21e0 |  | checkpoint | Align ceiling control joints with the structural control joints. Do not bridge structural control joints.
checkpoint-status | db0270e0-256c-422e-ad6b-594ac18d49a5 |  | checkpoint | Provide control joint beads where documented.
label | 4b41b705-ce16-5d08-98da-9c5bda0fd2d3 |  | note | Provide framing parallel to the joint on each side.
label | 77cc0d4f-d087-566b-81e3-13126b1edf3e |  | note | Plasterboard lining: 12m centres
label | 52495ec0-807d-598f-9748-4c86467a147c |  | note | Fibre cement lining: 7.2m centres
checkpoint-group | a5375cda-4c45-4865-a6ea-854c45dd70ca |  | section | Bulk Heads
checkpoint-status | a688b402-34c3-4ecd-8807-3f11c3b3a514 |  | checkpoint | Integrate bulkheads with the ceiling structure and brace to prevent lateral movement. Where ceiling is terminated at the bulkhead, provide for seismic requirements
checkpoint-group | da92b8a3-c7c8-4027-8f12-04b99a7d7cd3 |  | section | Tolerances
checkpoint-status | eee9bd44-e291-427f-a9a8-8b9ad05ceca2 |  | checkpoint | Flatness, twist, winding and bow: Maximum 1.5mm deviation from a 1.5m straightedge
checkpoint-group | 863a50ec-7d6f-4913-99d1-33eca19b8014 |  | section | Acoustic installation
checkpoint-status | 10d15206-a09a-4a0b-b300-eb54e17e0c7f |  | checkpoint | Where documented, place acoustic batts on top of ceilings system and butt to each other and to partitions.
checkpoint-status | c2512c57-18af-4583-8364-14d7ee5d0f4d |  | checkpoint | Tightly butt and trim neatly around services items and other items.
checkpoint-group | d7934a02-88a6-4eda-a96c-14851aabbb5c |  | section | Smoke baffles and acoustic baffles
checkpoint-status | 370513dc-ffd1-4ae1-9948-f9d8502d639c |  | checkpoint | Provide approved smoke and acoustic baffles secured fixed to metal angles and smoke sealed at board joints and to adjoining building elements
checkpoint-group | 7aa561d9-6374-483a-bbd1-2233fadd9225 |  | section | Additional checks for fire-protective board lining
checkpoint-status | 049321cb-8ead-4267-b8ac-859546a25ebb |  | checkpoint | Check the fire resistance levels on RCP
checkpoint-status | d4099ca0-b00c-4bea-a181-8fdbd8cdf3fe |  | checkpoint | Penetrations: Seal penetrations in the board lining to maintain the integrity of the required fire resistance level including suspended ceiling hangers and suspension systems for services. – Service penetrations sealing by others
checkpoint-status | 6599a5dd-0428-4e17-9428-390e92abd160 |  | checkpoint | Board perimeter: Provide fire sealant and trims at junctions with other building elements and surfaces, including walls, beams and penetrations to maintain the required fire resistance levels.
checkpoint-group | 65f56af2-f5b7-473a-9822-3f6b35de24d7 |  | section | Access Panels
checkpoint-status | ac1dd797-350e-40f8-aebd-0ad5563d4a5f |  | checkpoint | Match the access panels to the ceiling in appearance and performance
checkpoint-status | b0efa5aa-53f3-408f-a3d7-36943224375c |  | checkpoint | Provide access panels supported and anchored to permit ready removal and refixing
checkpoint-status | f37d7aa3-dd2a-4336-a394-3dc1de552df2 |  | checkpoint | Provide fire rated and acoustic rated panels where documented or where required to maintain the designated rating of the ceiling element
checklist-flat | 10c8f19b-e4c8-45cf-9d57-5bdbbe7ae4a0 |  | checklist | INS 207 Underslab Insulation |  |  |  |  | Yes | INS 207 Underslab Insulation | 64bfd887-2d82-4a4b-9f8a-f7cea58efbe5
checkpoint-status | 422f1058-4136-4ee5-abef-e6368e8b4e63 |  | checkpoint | Area ready & accessible
checkpoint-status | b32838b7-4e1a-4c47-94ce-506564aecc0e |  | checkpoint | SWMS are Approved Prior to Commencement
checkpoint-status | 5854502e-2b39-4c5b-ae75-0164fc4d26f7 |  | checkpoint | Sample Submission approved via Aconex
checkpoint-status | a059e496-601f-4e61-a666-4f436891042f |  | checkpoint | Insulation panels arrive as per Design Documents and defect free.
checkpoint-status | c2a3d04c-d49c-4c76-bf36-30f55341aab9 |  | checkpoint | Ensure most up to date drawings are being utilised
checkpoint-status | 6ed6ad84-f63d-4392-8a77-dcb4eff1de05 |  | checkpoint | Mechanically fix panels to manufacturer's Specifications
checkpoint-status | 5d3d0e4a-2b78-4f65-9a07-5c98bda748e1 |  | checkpoint | Tape all joints and exposed edges with a minimum of 75mm wide silver tape
checkpoint-status | 47ebe02f-7209-48cf-bb97-4bb58ceb4f9e |  | checkpoint | Lend Lease to Sign off on completed area
checklist-sectioned | b5614b85-e2e5-4c88-8bd5-40721476a0ea |  | checklist | Two Pack Paint ITP |  |  |  |  | Yes | Two Pack Paint ITP | 891362d5-e1b5-4674-9133-d89bfb766fca
checkpoint-group | ef902a4a-6385-4254-a0d8-e02c510cdf72 |  | section | Paperwork Approval
checkpoint-status | c804926b-8a23-4528-af93-608fef5515e9 |  | checkpoint | Area ready & accessible
checkpoint-status | e048e3b2-3270-48ca-9cb3-2d10d2c2fd8b |  | checkpoint | Are all SWMS approved and signed by all workers
checkpoint-status | 947f9ff1-963c-456c-b99f-a14f1ec3db91 |  | checkpoint | Are all permits to work signed off by Lendlease
checkpoint-status | 9389d7d1-af38-49c5-98e6-7402a9aae8b9 |  | checkpoint | Are all technical samples approved via Aconex Workflow
checkpoint-group | 8f6d3855-3f8f-4846-9545-ac4836c69ff1 |  | section | Spray Primer
checkpoint-status | e528ff56-7a0f-43f0-b379-c723f27635cc |  | checkpoint | All Steel prepped, sanded and dust free prior to commencement
checkpoint-status | 0ab31cbf-b0bf-4221-9000-10bb9de45917 |  | checkpoint | Full protection to glazing, window frames etc prior to painting. Any overspray is cleaned off prior to completion of spray out.
checkpoint-status | 26387764-f394-4d77-9fcf-ea615d3340bf |  | checkpoint | All edges to internal / external doors are sealed and painted as per manufacturer's specification.
label | cf304d25-2697-5ea9-a954-9d32ac91da9f |  | note | All paint is NOT site tinted or any other liquid added or altered without written approval.
label | ac50bcac-7c5c-593f-87d0-7a132094c8e3 |  | note | Clean up is completed ONLY in the supplied wash out area.
label | d19593ba-bad1-518f-9c67-a2ff791ca573 |  | note | All rubbish is to be placed in the bins provided and the area is to be left clean and tidy and void of rubbish and excess materials.
checkpoint-status | cc6f947e-f078-462e-b367-621ac5d77306 |  | checkpoint | Ensure no damage is done to other trades work (if so, you Must Report to the Supervisor and Wadsworth Project Manager immediately).
checkpoint-status | 0a81f3b1-c0e7-4a5f-b1ed-8575f8f18c6d |  | checkpoint | All completed works are consistent with the scope of works supplied by Lend Lease, the supplied paint specification, and approved samples.
checkpoint-group | 55a2b774-3980-47ba-8edf-4483685978d7 |  | section | First Coat & Final Paint
checkpoint-status | a6718352-09f7-4beb-8497-230f6fd3b1c3 |  | checkpoint | All steel is prepped and dust free prior to first coat
checkpoint-status | fec8cd7c-fc7a-415b-9109-7dc41d75e754 |  | checkpoint | Full protection to glazing, window frames etc prior to painting. Any overspray is cleaned off prior to completion.
checkpoint-status | a4ef2656-207e-4d6c-bbda-142d2e186fcd |  | checkpoint | All Steel are lightly sanded between coats.
checkpoint-status | e3d787b7-efea-4507-8e90-c05ff1fcc139 |  | checkpoint | All coats are sprayed with a HVLP spray gun to give uniform spray finish.
label | 0c14cce8-e13f-56b3-a4a1-2b1103cf9434 |  | note | All paint is NOT site tinted or any other liquid added or altered without written approval.
label | 1916caa7-b6c0-59ba-b537-906783a0de8d |  | note | Clean up is completed ONLY in the supplied wash out bay.
label | d41d5ad9-1f9b-5948-af8c-e98e62813d82 |  | note | All rubbish to be placed in bins provided and the area is to be left clean and tidy and void of rubbish and excess material.
checkpoint-status | b78db207-79f2-426d-9745-f2fe2d8bb887 |  | checkpoint | Ensure no damage is done to other trades work (if so, you Must Report to the Supervisor and Wadsworth Project Manager immediately).
checkpoint-status | 5a6e7931-0ef6-47f0-885d-2508ba9f121a |  | checkpoint | All completed works are consistent with the scope of works supplied by Lend Lease, the supplied paint specification, and approved samples.
checklist-flat | 54e75329-afcf-452e-90aa-38f49cd68d33 |  | checklist | INS 106 Martini XHD100 Underslab Insulation |  |  |  |  | Yes | INS 106 Martini XHD100 Underslab Insulation | 8a50b6cb-0472-4fa2-b1c0-409bfebef1c9
checkpoint-status | b2883a8f-187d-4b86-9a9c-a791a23116ae |  | checkpoint | Area ready & accessible
checkpoint-status | 26f7f120-c7c4-4894-9a18-af5d7cf645e2 |  | checkpoint | SWMS are Approved Prior to Commencement
checkpoint-status | 493aad3d-65f9-413f-8152-ef1fd1938284 |  | checkpoint | Sample Submission approved via Aconex
checkpoint-status | 428e3aed-2518-42df-802d-b2939dbc37e6 |  | checkpoint | Insulation panels arrive as per Design Documents and defect free.
checkpoint-status | 43f64337-0fc9-41b7-b6b9-a865341b3fd0 |  | checkpoint | Ensure most up to date drawings are being utilised
checkpoint-status | ed1fc212-bd5b-40e8-9ceb-575925559cd3 |  | checkpoint | Mechanically fix panels to manufacturer's Specifications
checkpoint-status | 5ecbc835-b94b-421a-999e-65307acf449d |  | checkpoint | Lend Lease to Sign off on completed area
checklist-flat | f07227a7-39a8-47a8-af7d-2bbc3e49eb87 |  | checklist | Megasorber |  |  |  |  | Yes | Megasorber | c8d563cb-d68c-4577-890a-8c60e363d899
checkpoint-status | 6d33baff-4d6c-4256-ad2e-a2043ae00176 |  | checkpoint | Area ready & accessible
checkpoint-status | ee2b9e27-f53c-4269-8c8d-bdf99dfffc65 |  | checkpoint | Insulation panels arrive as per Design Documents and defect free.
checkpoint-status | 81ed1cbf-e5ba-447e-8735-7d86d0dde065 |  | checkpoint | Ensure most up to date drawings are being utilised
checkpoint-status | ce12e7a3-ce05-4ea3-bf3c-6b1707ddc940 |  | checkpoint | Ensure panels are set out as per expansion joint requirements.
checkpoint-status | 6ab49ebb-af3b-4634-9b37-615de01d61a3 |  | checkpoint | Install Flashings around perimeter of Slab Expansion Joints
checkpoint-status | 185085b9-10ed-4566-bb2a-ec37ecc396f5 |  | checkpoint | Mechanically fix panels to manufacturer's Specifications
label | d50c15d2-6f67-50fb-b38d-7b30e31caee4 |  | note | Using G8 tape, tape up all joints and cut outs, then heat treat Tape to activate glue with either an iron or Heat Tool.
checkpoint-status | 7f3301d3-2550-40cf-94e6-fa71e8c4f2e9 |  | checkpoint | Lend Lease to Sign off on completed area
checkpoint-status | a718915b-4fc6-425a-9d43-2f819314dd33 |  | checkpoint | Attach copy of delivery docket
checklist-sectioned | e33e01fb-f606-4abb-94a7-1c3f4aed7264 |  | checklist | Partitions Home Affairs ITP |  |  |  |  | Yes | Partitions Home Affairs ITP | e1bee15a-efe0-49e4-8816-4546a036b958
checkpoint-group | e067645e-9343-4797-bae1-0ba9f9c53174 |  | section | Paperwork Approval
checkpoint-status | 7fb10573-b791-417f-b1d0-68f143c62bc9 |  | checkpoint | Area ready & accessible
checkpoint-status | 09133eea-78f9-496e-9a6b-ba3530cf9aed |  | checkpoint | Are all SWMS approved and signed by all workers
checkpoint-status | 93ab3047-57cd-4c3d-9856-a9720b9285b9 |  | checkpoint | Are all permits to work signed off by Lendlease
checkpoint-status | 50c83403-2bee-4842-97ed-b6854eff6b09 |  | checkpoint | Are all technical samples approved via Aconex Workflow
checkpoint-status | b40831fe-15a6-4e46-95d4-04d02bfbf7cb |  | checkpoint | Are all in-situ mockups approved by the consultants
checkpoint-group | dc1795e7-730b-49f1-94d6-3558082b856f |  | section | Set Out
checkpoint-status | 4e199f45-f2cb-4681-8018-2effd5366bb7 |  | checkpoint | Partitions set out plans current revisions checked and wall set out completed as per the current plans
label | baf7f3c2-2f22-5a48-88d0-32ed2e7e6620 |  | note | Discussed/established with supervisor the minimum/critical dimensions (face to face) on drawings
checkpoint-status | 85f5cd0e-0438-45f4-8294-aaf83c1cc376 |  | checkpoint | Zone Types Checked
checkpoint-group | 64900951-89c0-4c1e-baf2-e599bc512a48 |  | section | Stud Framing
checkpoint-status | cb21fbd3-1d27-4901-aa00-34addd55accf |  | checkpoint | Check sizes and spaces as per the partition types. Stud spacing: 600mm generally & 450mm in wet areas
checkpoint-status | e9565ddd-f5ba-4404-b095-6361b40d64a6 |  | checkpoint | Fix tracks ≤600mm centres and 100mm from ends, or as per project specific details.
checkpoint-status | 88ac6bdd-6fed-4657-8168-ce5a24e8676d |  | checkpoint | Door frame openings as per Supplier design
checkpoint-status | ced724a0-6644-48f9-8e52-cac33792300c |  | checkpoint | Full height partitions: Fix deflection head tracks to the floor slab soffit to allow a minimum deflection capacity of 20mm.
label | 8dafe5af-7739-5a02-b494-1cf2162540a1 |  | note | Rotate intermediate studs into tracks for friction fixing
checkpoint-status | bca66f91-79af-430f-b92d-e3702c25be32 |  | checkpoint | Structural floor control joints: Disconnect partitions over joints with detached double studs and ensure bottom tracks, bracing and top tracks are not fastened across joints
checkpoint-status | b597763d-465c-478f-b7cb-bb74ba6d5a0e |  | checkpoint | Noggins: Fix Noggins as required for the framing system and to accommodate in-wall and in-ceiling services and fixtures
checkpoint-status | c0e3f3b7-5108-4361-8248-5539988f8dd7 |  | checkpoint | Door frames: Installed and in line with current door schedule
checkpoint-group | ae25ff23-643c-4cf9-b1ca-6bd2d9259a8c |  | section | Furring Channels
checkpoint-status | 61d2723f-5584-41ef-b63b-787a1f12e5fc |  | checkpoint | Use powder actuated fasteners or masonry anchors of the expansion or chemical grout type
checkpoint-status | 7f9a9da1-7b1d-4eef-bd29-9e57ef9d9215 |  | checkpoint | Place furring channels at ≤ 600mm centres and as to suit wall sheeting, or as per project specific details.
label | 3a2d70f9-5832-50bd-9d86-70e71b0a2ef2 |  | note | Where necessary pack using metal spacers to provide plumb and straight fixing background
checkpoint-group | b9648a6f-8d97-41cc-b62f-8f081bece6d5 |  | section | Bulk Insulation
checkpoint-status | c84e1d5e-41b7-4d7a-a204-0b24058151be |  | checkpoint | Install acoustic and thermal insulation.
checkpoint-group | 9c12b5cb-bcd0-4fe7-8eb6-1a8502596c1f |  | section | Hold Point
checkpoint-status | 714b3f9b-3aaf-4512-bb66-e4555e0ee26f |  | checkpoint | Framing system completed – Ready for installation of sheets.
checkpoint-status | 5d60d4b6-996c-4960-8552-c131d0de2cfc |  | checkpoint | Confirm all service trades are complete & ready for closing of walls.
checkpoint-group | d863b925-e591-4729-a5c5-a512fa3ad122 |  | section | Board Lining
checkpoint-status | 5592da2b-a4a6-4ed8-8619-3618bd238cff |  | checkpoint | Run sheets across the framing members
checkpoint-status | 8e84ada7-6309-41c0-b7ce-e5a7cb8493e8 |  | checkpoint | Stagger end joints in a brick pattern and locate them on framing members away from the corners of large opening
checkpoint-status | 0f6efbf6-450d-4670-9fd3-a51b0a280efb |  | checkpoint | Multiple sheet layers: Fill & flush up all joints and fixings as per Suppliers specifications and caulk up perimeters and penetrations before commencing succeeding layers.
checkpoint-status | 13baceb0-9e46-4f8f-99ee-14f38d833510 |  | checkpoint | Stagger all sheet joints as per Suppliers specifications
checkpoint-status | a29918c2-3d91-4e82-a8c6-99173050b492 |  | checkpoint | Board joints: Do not fix the lining to abutting building surfaces
checkpoint-status | c04a910d-2869-4073-a3f7-c767b8ef1c54 |  | checkpoint | Butt joints: Provide perforated paper reinforcing tape
label | 50822abe-fcb8-5179-94df-e32fcf1a607b |  | note | External corners: Provide matching purpose made beads
label | 0a531168-101f-53da-97df-36a86e44fcc2 |  | note | Internal corners: Provide paper tape and bedding compound
checkpoint-status | 6a034822-cda9-46a6-8e5d-246d6231e60e |  | checkpoint | Provide fire, smoke and acoustic sealing where indicated on the drawings/details.
checkpoint-status | 7426fc82-ca61-405b-90b6-ef87a1ecf56a |  | checkpoint | Provide sealants at junctions between partition systems and with other building elements.
checkpoint-status | 03c07810-f97d-42c3-a30d-373479ec2961 |  | checkpoint | Provide trim such as beads, moulding and stops to make neat junctions between lining components, finishes and adjacent surfaces
checkpoint-group | e53dc624-1652-4888-ba41-81466e5dbc05 |  | section | Control Joints
checkpoint-status | 1b60925e-5775-4e91-b524-f93cf50fac56 |  | checkpoint | Provide PVC or metallic coated control joint beads.
checkpoint-status | 32ee78ba-aaf0-4962-81ea-de6985466967 |  | checkpoint | Control joints to coincide with structural control joints
label | 6916cd8c-3ea2-50eb-943d-625531bbe3a3 |  | note | Provide control joints as follows:
label | 13bc6aae-3902-5605-bd88-1572ee3349f0 |  | note | Plasterboard lined partitions: 12m centres
label | d41e484e-1e76-5487-8c64-c64f05e47a6d |  | note | Fibre-cement board lined partitions: 7.2m centres
checkpoint-status | ccd685e8-cd68-48a2-9994-e44fd67731e4 |  | checkpoint | Board lined partitions in wet areas: To suit joints required in tiling and at max 4.2m centres
checkpoint-group | 165478a0-aa76-430b-8f77-e32be91c97ab |  | section | Tolerances
checkpoint-status | c48058c3-4101-4f9c-82ab-6c528777a1a5 |  | checkpoint | Flatness, twist, winding and bow: Maximum 1.5mm deviation from a 1.5m straightedge
label | 13acc308-646c-5009-8749-4a934e7e863f |  | note | Where full height partitions and linings are installed at top of partition minimum 20mm has been allowed between partition and slab for deflections
checkpoint-group | adbf4813-7e75-4f89-a208-b0ade50eb7f3 |  | section | Additional checks for Fire Walls
checkpoint-status | c1f09d37-d140-4405-8efa-b526a9786c84 |  | checkpoint | Installed as per board suppliers design & install specification
checkpoint-status | 86044e39-bf40-449f-bc85-78d3ca811784 |  | checkpoint | Correct FRL achieved
checkpoint-status | 5841ec9c-d675-4617-b173-ab2804fec179 |  | checkpoint | Deflection heads and all joints sealed, taped and set (Fire Sealant is approved prior)
checkpoint-status | 088ceb53-3b80-41b7-9d4e-43de1d216809 |  | checkpoint | All penetrations through fire walls below and above ceiling protected/sealed – Service penetrations sealing by others
checkpoint-status | fa161bef-814f-47c5-ab90-689f77f0ff37 |  | checkpoint | Fire door frames installed
checkpoint-group | d398979f-f897-4232-9fb9-8eda6329f07a |  | section | Additional Checks for Smoke Walls
checkpoint-status | aa67c018-c8bc-49ae-8a3e-c1a1414bdf51 |  | checkpoint | Deflection heads and all joints sealed, taped and set (Sealant is approved prior)
checkpoint-status | ef2086a6-c789-45ca-b0f9-a6bb1c65c4f7 |  | checkpoint | All penetrations through smoke walls below and above ceiling protected/sealed - Service penetrations sealing by others
checkpoint-group | 2fa69fab-ee62-4834-ba66-95504bd4a5df |  | section | Additional Checks for Acoustic Walls
checkpoint-status | 9a6bc526-9ccb-4bbb-b226-27f0cb464e0b |  | checkpoint | Deflection heads and all joints sealed, taped and set (Sealant is approved prior)
label | 8119bc89-b369-5821-9ff7-0dd1aef45083 |  | note | All penetrations through acoustic walls below and above ceiling protected/sealed - Service penetrations sealing by others
checkpoint-group | 2d52e45e-4886-4475-beb7-f5da822e2846 |  | section | Additional Checks for Home Affairs Security Walls
checkpoint-status | ce6a2420-41f8-4bfe-8605-cfe11b5cf3a0 |  | checkpoint | Framing Inspection – Framed as per Security Zone Requirements
checkpoint-status | 33b56fc1-9aea-488f-86c0-732780d0fcce |  | checkpoint | Noggins set out as per Security Zone Requirements
label | a149bedc-a6e6-503c-a9c5-801c1f10d93e |  | note | Zone Type Checked
checkpoint-status | 6a35c89f-d91b-44b4-808a-10f24bf12858 |  | checkpoint | Sheeting Inspection for full height walls
checkpoint-status | 8b64f586-1017-42d5-92b8-41d370b5126c |  | checkpoint | Final Finish Of Walls
checkpoint-group | e8dd8f10-7756-458d-bdc6-084a417c7d0b |  | section | Access panels
checkpoint-status | 0c1c00de-1550-4470-bffd-42d23cee6d6b |  | checkpoint | Provide proprietary items comprising locking doors side hung to frames, including hardware and accessories
checkpoint-status | 3a07652f-890d-4da0-9ec2-f1d2951da0ef |  | checkpoint | Fire & acoustic rating: Provide assemblies that are certified to maintain the required rating
checkpoint-group | 78e4ff71-a2fc-41ed-a47b-ca830de24578 |  | section | Testing
checkpoint-status | 44a7a96e-5d6d-4692-89ab-87ad2fe3c84d |  | checkpoint | Installed as per board suppliers design & install specification
checkpoint-status | 3e935c1d-eac7-4fe2-8e39-ce91d07beb96 |  | checkpoint | Correct FRL achieved