## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | eff962b1-94ef-4d9e-a7c3-480af6c67bfa |  | checklist | Service Nogs General |  |  |  |  | Yes | Service Nogs General | 01d8a2fa-235e-483e-be12-469f26bbeae1
checkpoint-status | abcb77c0-0191-45e6-9fbb-6658e0b03502 |  | checkpoint | Nogs / Service Nogs installed correctly as per plan
checklist-sectioned | 6cca8ee2-fd97-4472-ab68-c2faa59e7ae8 |  | checklist | PRE - S - Nogs |  |  |  |  | Yes | B05 - PRE - S - Nogs | 052c21b5-419a-41ff-ac2a-779351b63d72
checkpoint-group | 4d419579-4ce8-4e8c-bd4c-a7b195ed2f64 |  | section | Service Nogs Toilet
checkpoint-status | a8bc9bbe-d276-43fc-a6fe-dd756a27908b |  | checkpoint | Wall Vanity nogs installed
checkpoint-status | fd540e74-4f7b-44ca-a193-e15de07f2e46 |  | checkpoint | Handrail and Toilet roll holder Nogs installed
checkpoint-group | a1535642-f833-40b1-bed0-d94bb1a91554 |  | section | Bathroom
checkpoint-status | 2e5a5a6e-4492-4fb1-897e-fa6b8e0586e0 |  | checkpoint | Mirror cabinet nogs installed
checkpoint-status | ae6ccb62-cfd1-4d21-b601-36079138b3e3 |  | checkpoint | Wall Vanity nogs installed
checkpoint-status | 6a1df8f0-7f66-4708-982c-73d51ebaf0e8 |  | checkpoint | Toilet: Handrail nogs Installed
checkpoint-status | 5fadbd8b-594c-4a9b-acee-74aeec01fe5a |  | checkpoint | Shower: Handrails nogs (3 areas) installed
checkpoint-status | 26ce5c74-4597-4302-b294-37dc05d302b7 |  | checkpoint | Wall Mounted Heater nog installed
checkpoint-status | 3f00df92-c7b9-4648-9d14-2ad04dc32fbb |  | checkpoint | Towel rail nogs installed
checkpoint-status | 2d0364a6-a84c-47eb-8706-92400c1ff44d |  | checkpoint | Shower head nog installed
checkpoint-status | 3802a9e8-eddf-4927-ba34-78c790363d3b |  | checkpoint | Shower mixer nog installed
checkpoint-group | 0a64fcda-c669-4ec8-8e33-a2049d873caf |  | section | Laundry
checkpoint-status | 984582e1-ac0c-4fb4-bdb7-93951aecb361 |  | checkpoint | Dryer nogs installed
checkpoint-status | bce86e63-ea80-4cd5-baa4-30769ee5b6fd |  | checkpoint | Cupboard nogs installed
checkpoint-group | 1022c05b-9f76-4a45-91cf-651d065f30ea |  | section | Service Nogs General
checkpoint-status | e362c060-540c-4604-b450-525a48d348ba |  | checkpoint | Nogs / Service Nogs installed correctly as per plan
checkpoint-status | c8afce70-ff7a-4865-a2c1-2813c09f8434 |  | checkpoint | Inspections completed and issued to Foreman
holdpoint | bb1a5058-e69a-475b-b4a9-a9b67db91346 |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat | 1668b338-0bd0-48a5-8b4d-96fe32bd13d6 |  | checklist | Balconies |  |  |  |  | Yes | Balconies | 0edd7660-52af-4a22-ab45-86e162cb0cd6
checkpoint-status | 6db6764c-157b-4b62-8083-d4c35ad5c884 |  | checkpoint | Waterproofing and saddle flashing checked
holdpoint | daa2a03f-158e-48a1-a3bd-4946761c67da |  | signoff | Raise Remedials / REQUEST SIGN OFF FROM FOREMEN - QA
checklist-sectioned | 2db3a86d-2d6f-4f9e-964a-2c8a2a7878b1 |  | checklist | Service Nogs Bathroom |  |  |  |  | Yes | Service Nogs Bathroom | 155166bd-89c5-49c3-82a6-10637a672af8
checkpoint-group | fbac2cae-5d57-4ae5-9931-990a4751da3c |  | section | Bathroom
checkpoint-status | c192666e-522c-43b6-b9d6-da8f918a2eb9 |  | checkpoint | Mirror cabinet nogs installed
checkpoint-status | 160064dc-3b94-4458-8dc2-1aed6364ee1d |  | checkpoint | Wall Vanity nogs installed
checkpoint-status | 4e32ae62-3ae3-429b-94e3-e04ee6b23f33 |  | checkpoint | Toilet: Handrail nogs Installed
checkpoint-status | d42549a7-48f8-4d4b-aec9-4a30a3661124 |  | checkpoint | Shower: Handrails nogs (3 areas) installed
checkpoint-status | e869ebcc-e0ad-44e9-abf9-4d1f615422d2 |  | checkpoint | Wall Mounted Heater nog installed
checkpoint-status | d71e057f-f88e-47cb-a206-dc10ad2480dd |  | checkpoint | Towel rail nogs installed
checkpoint-status | ed67408a-e41e-4a6a-a9a2-ec55bc8a2f08 |  | checkpoint | Shower head nog installed
checkpoint-status | a4687102-b286-436f-a0ac-0b29aebddecd |  | checkpoint | Shower mixer nog installed
checkpoint-group | 392188e2-c76f-4beb-9d6d-0c6efa5c3b54 |  | section | Laundry
checkpoint-status | b1b2baf6-97fe-42b4-a7ac-8016b122ecbd |  | checkpoint | Dryer nogs installed
checkpoint-status | e9be6413-f475-45a2-aaa4-49d0afa0d6d8 |  | checkpoint | Cupboard nogs installed
checklist-flat | 07d79814-444e-412c-a18e-fd7a54e10b9e |  | checklist | CST - S - Completion Documents |  |  |  |  | Yes | B05 - CST - S - Completion Documents | 2ad0e8d6-1491-4020-9680-eb6eeafdc4d4
checkpoint-status | 7ed3edc0-0edb-4f5d-9c14-cc5423b79544 |  | checkpoint | All relevant Compliance Documentation completed and attached above
boolean | bdc33019-f909-54dc-a2af-f14bd669e673 |  | tickbox | Any Additional Compliance Documentation (Required under Section C and by Consultants) - Completed and Attached
label | 8d95ddbe-cf73-5901-8753-b3304eefaf74 |  | note | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint | 2da92f5a-e8ca-477d-aa70-f2353986724f |  | signoff | Request Signoff
checkpoint-status | 6161419f-f409-468e-aa65-f0910d686dc3 |  | checkpoint | Inspections completed and issued to Foreman
holdpoint | 0cda9e51-5368-475e-a0de-c450ad4dfde9 |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-sectioned | 1f9c1c4f-6ff3-4731-8d7f-2255bef0e6b7 |  | checklist | Interior Framing |  |  |  |  | Yes | Interior Framing | 314d6154-9356-4e88-918b-497fcade4115
checkpoint-group | 0589b840-6ae1-42a9-9895-0fffd13b1a38 |  | section | Framing QA
checkpoint-status | 3abdb3e9-5214-4552-89c9-16e7885f67a7 |  | checkpoint | Area & Substrate Acceptable
checkpoint-status | 825ec557-fcdb-45a1-9762-1be7cc9d67aa |  | checkpoint | Dimensions / locations checked and Accurate
checkpoint-status | 02030ed8-c838-4cf4-a1f6-d99ebf371da4 |  | checkpoint | All frames are square
checkpoint-status | 794c7d35-073f-4b0d-b29b-09b18775ec47 |  | checkpoint | Frames are straight and level
checkpoint-status | 4d551e4c-de98-432e-ba55-b68ed1abf7db |  | checkpoint | Fixings are correct
checkpoint-status | 04a9caa9-468a-4c9e-aaba-c3eac6973030 |  | checkpoint | Any Bracing requirements installed
checkpoint-status | 7c9499aa-68d6-4af5-90ed-1ca74eb6cfd5 |  | checkpoint | Nogs / Service Nogs installed correctly as per plan
checkpoint-status | 7cd36e90-68f8-4d93-b65f-0c90e764675f |  | checkpoint | Any Additional photos, comments and observations
checkpoint-group | dbfccd42-4bd3-4612-be5a-d2d380b68d3c |  | section | Handover
checkpoint-status | b5b8c756-89ae-4a07-bd13-25e641de2504 |  | checkpoint | All Framing completed correctly within location in respective Area
checkpoint-status | d7554d66-a9aa-471a-b162-b526515bd0ce |  | checkpoint | QA had been reviewed and approved
holdpoint | 414b72cd-7097-4c2c-ac3e-a2c30d381ed5 |  | signoff | Raise Remedial/Request Sign Off
checklist-flat | 0b91535a-fdc7-4844-8183-410e5371960f |  | checklist | RAB Board |  |  |  |  | Yes | RAB Board | 401cbbd6-ff63-452f-ade4-bb0f0ddc6492
checkpoint-status | 99da71c7-79ca-4277-a7c9-9c3c4baf6d9d |  | checkpoint | General photos (fixing and spacing with 3m gap, penetrations and punctures sealed with flashing tape)
checkpoint-status | 1ea78d08-d933-462d-a2a5-d7b340b927b9 |  | checkpoint | White WS sealant for air seals between RAB Board and concrete horizontal and vertical joints
holdpoint | 7f5bcda9-b56d-47b7-84b4-14d170309e5b |  | signoff | Raise Remedials / REQUEST SIGN OFF FROM FOREMEN - QA
checklist-flat | db2dfc84-351b-4af5-b728-674a4486544e |  | checklist | FC - S - Windows, Sliders and Sealants |  |  |  |  | Yes | B05 - FC - S - Windows, Sliders and Sealants | 49995908-26fc-4a3d-9f0a-d294821491a1
checkpoint-status | 97ac6ced-ca9e-4c9e-a0b7-39312612ee2f |  | checkpoint | Fixings and clearance around opening min 6mm & max 18mm and PEF rod/air seal are within acceptable tolerance level
checkpoint-status | b97d84f0-4de6-430d-94d5-e63fbf023873 |  | checkpoint | Check taping around, before installing the windows and sliders
checkpoint-status | 0ee03051-5407-4e3a-a6b4-23e5f33b11d0 |  | checkpoint | Packers to be correctly used and set back to allow continuous air seal
checkpoint-status | ee34024a-dd98-4956-87d6-335ef045c18a |  | checkpoint | Jambs level and straight for finishing lines on the side
checkpoint-status | 9ff79357-b991-4e41-abd9-d6a32e2e9914 |  | checkpoint | Door and window jambs flush to GIB Board
checkpoint-status | 91ac6c0b-6606-482f-bf1c-ccbc39cff227 |  | checkpoint | Check air seal is provided at the rear of the window reveal
checkpoint-status | 0f4de65e-2bb8-4643-aae5-c00339a4539f |  | checkpoint | All joints detailed as per attached Detail Document
checkpoint-status | 25ed66d3-f771-4abb-a1dd-3c4a928b09a0 |  | checkpoint | All framing completed correctly within tolerance in respective area
checkpoint-status | 43caaf8f-4020-4ef5-97a3-c954eac96064 |  | checkpoint | Sill support fixing bars installed for all joinery within acceptable tolerance level
checkpoint-status | 1bd06115-8fc9-4ff0-bc21-9cbd73e32137 |  | checkpoint | All windows, sliders and sealant installation completed to specification & within tolerance in respective area(s)
checkpoint-status | 5f392be0-9217-43ce-af7e-8aac04cbd7ad |  | checkpoint | Inspections completed and issued to Foreman
holdpoint | 97e831a5-54e1-4c0e-b0ba-025146813eb3 |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat | fc3b9e10-62b2-478d-af80-6215df60354b |  | checklist | FC - S - Flashing installation |  |  |  |  | Yes | B05 - FC - S - Flashing installation | 86e1127f-e3fb-441a-a776-997eca075f75
checkpoint-status | ed4fbac5-66e2-4cb6-952f-5b33caa52d61 |  | checkpoint | Head flashing installed with sealant at windows and doors (STO system)
checkpoint-status | 81f33f7e-f754-4951-9481-6bf132d7d7e3 |  | checkpoint | Rainshield installed between joinery and lintel (brick)
checkpoint-status | 8250bace-8649-4cd4-8a80-d1a0fa305c7b |  | checkpoint | DPC and WANZ bar installed at the bottom of the joinery (see fixing) as per manufacturer's spec
checkpoint-status | 5c63ebcc-3008-417e-b1f9-b0a2a0f8de41 |  | checkpoint | Aluminium window jamb side flashings are installed
checkpoint-status | 7ff4326c-93c1-4da0-a442-a07220531ae2 |  | checkpoint | All flashing installed at windows and doors to specification & within tolerance in respective area(s)
checkpoint-status | f67871af-a840-4cce-bea3-399b5722d606 |  | checkpoint | Inspections completed and issued to Foreman
holdpoint | 05e45d66-72be-421a-bb44-1ff70fe2091f |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat | 8a29311f-ff48-4b81-aad5-831bf6d1743e |  | checklist | FC - S - Gutters |  |  |  |  | Yes | B05 - FC - S - Gutters | 8c88aadd-7e79-48ba-a136-c7a37702ee1d
checkpoint-status | bd666827-9888-4ae8-9217-7fddf5cdd1bb |  | checkpoint | Setout completed, checked & accurate (no clashes & wall locations clearly marked)
checkpoint-status | a8cd3483-1748-4ac7-b39c-6120a7375f16 |  | checkpoint | Framing Dimensions / locations checked & accurate (openings considered where applicable)
checkpoint-status | 1d4d21e4-ca0c-46c3-b975-9421c8e749c7 |  | checkpoint | All frames have been installed square, straight and plumb
checkpoint-status | 5c44b158-8459-4472-806e-a3e6b245ba86 |  | checkpoint | DPC installed (if required) correctly
checkpoint-status | 22bf709b-0447-4773-a07b-dbb17a428480 |  | checkpoint | Fixings are correct to specification including any seismic/bracing requirements (attach relevant photos)
checkpoint-status | 39cc35f2-4665-4f47-a77d-f94d2f96bf85 |  | checkpoint | All Nogs (Service/Specialty) & penetrations - installed, checked & correct (consider acoustic & fire rating requirements)
checkpoint-status | 8b78d153-4abc-4d20-8203-0508d610d2ce |  | checkpoint | All timber framing completed correctly to specification & within tolerance in respective area(s)
checkpoint-status | 8b91772b-d5b6-450e-910f-da2bc94ba59d |  | checkpoint | Inspections completed and issued to Foreman
holdpoint | bcc45218-dbeb-4623-8f28-eea9bbc6d4d4 |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat | b5fae79a-286e-4967-ab9d-8d5dd4e60b07 |  | checklist | Box Gutters |  |  |  |  | Yes | Box Gutters | 8d1641dc-0e7e-4578-925a-fcdce2003954
checkpoint-status | 5a2bef2c-065d-4158-9249-ffe3e233e83a |  | checkpoint | Box Gutters installation as per specs
checkpoint-status | 1be28af9-e9d4-460f-858d-de9608f02290 |  | checkpoint | Gutters, falls, screws centers, sumps outlets checked (Photos)
holdpoint | 4e83669f-8788-4cae-9b97-5312218d774d |  | signoff | Raise Remedials / REQUEST SIGN OFF FROM FOREMEN - QA
checklist-flat | 568ea106-d86e-4cec-937c-09cac0ca7c76 |  | checklist | B04 - Interior Framing |  |  |  |  | Yes | B04 - Interior Framing | a2ec3865-0d3c-4cd6-bf88-b9504191e051
checkpoint-status | 89673427-77d2-4a07-bceb-ca2987feeaa5 |  | checkpoint | Area & Substrate Acceptable
checkpoint-status | 38db342d-605e-48c4-8db2-99e0b83735a0 |  | checkpoint | Dimensions / locations checked and Accurate
checkpoint-status | ecd8b94a-90b7-4429-bb7f-85db2d6d6b94 |  | checkpoint | All frames are square
checkpoint-status | bb27ad90-3463-4ca6-861f-0c170db14430 |  | checkpoint | Frames are straight and level
checkpoint-status | 136d5499-4407-4b11-870f-07d14d4b6b2a |  | checkpoint | Fixings are correct
checkpoint-status | 912eff58-d53c-4b0a-b2a5-ce75eadd4d4c |  | checkpoint | Any Bracing requirements installed
checkpoint-status | 27877f5b-a7d7-4553-9f44-65ee94cb8fba |  | checkpoint | Nogs / Service Nogs installed correctly as per plan
checkpoint-status | 67e0d47e-e595-43e2-a114-e700758933b3 |  | checkpoint | Any Additional photos, comments and observations
checkpoint-status | ae8b604f-0bc2-4d20-9055-ebcaeed2ad0c |  | checkpoint | All Framing completed correctly within location in respective Area
checkpoint-status | 4d02f059-698d-4723-9ed8-527414280398 |  | checkpoint | QA had been reviewed and approved
holdpoint | b26f1983-86d9-4d8f-85cf-d7cbaf4f2f76 |  | signoff | Raise Remedial/Request Sign Off
checklist-flat | e2acfd1a-b99c-48e9-a1d2-5158d9d622a5 |  | checklist | Windows, Sliders and Sealant |  |  |  |  | Yes | Windows, Sliders and Sealant | add31f65-b394-41bc-a554-36f43288ec98
checkpoint-status | 9135044d-d7e0-4348-bba0-365e0bf916fe |  | checkpoint | Check fixing and clearance around opening min 10mm/ max 20mm
checkpoint-status | cdd445ab-36e9-4207-a2f7-3e5116ae895a |  | checkpoint | PEF road installation
checkpoint-status | e5de8a3e-3af4-4726-8dec-778fd7c0782b |  | checkpoint | Installed AT-Façade sealant inside of the joinery as per detail
holdpoint | 50bb1a24-3063-44e0-a871-f420034e1c7d |  | signoff | Raise Remedials / REQUEST SIGN OFF FROM FOREMEN - QA
checklist-flat | 9642f2c6-65c2-4b44-9722-c1494804d332 |  | checklist | Tapes |  |  |  |  | Yes | Tapes | afaa4e88-a3dc-4f3f-ac32-6b6d88467c37
checkpoint-status | bac3f475-2dec-4cff-bfc7-2e7e318beaa0 |  | checkpoint | 3M taping around windows and sliders around the exterior framings as per the manufacturer specifications
holdpoint | 1b05fa37-e7d5-4b9e-ab51-f646a9f04bc1 |  | signoff | Raise Remedials / REQUEST SIGN OFF FROM FOREMEN - QA
checklist-flat | 3ca88a15-a022-47aa-818b-7e13ae58c13a |  | checklist | B04 - Completion Documents - BCO10328723 |  |  |  |  | Yes | B04 - Completion Documents - BCO10328723 | b661bce9-a78a-4fcb-beed-d7178e01f14b
checkpoint-status | e7b4a3d5-c772-4fce-84a5-bd9fe97424eb |  | checkpoint | PS3 - Windows and Doors Installation
checkpoint-status | 879db01e-df03-44f8-890b-12e7daa9b2a8 |  | checkpoint | PS3 - James Hardie Rigid Air Barrier System
checkpoint-status | 931fd8b4-1713-4fac-bc31-9a524f25761e |  | checkpoint | James Hardie Rigid Air Barrier System Warranty
checkpoint-status | 941e1b2d-8e39-40e2-8d2b-ccbcad1c4bd7 |  | checkpoint | Warranties compiled and attached
checkpoint-status | 2a1dbeb2-56a9-4452-a4d3-3e0fc04197d8 |  | checkpoint | Material Schedule
holdpoint | d53d8418-3195-4a0e-8e6b-e81b18bb330e |  | signoff | Send to Quality Assurance when completed
checklist-flat | 9d13a5be-029c-496e-8c17-acdd09628ccb |  | checklist | Service Nogs Toilet |  |  |  |  | Yes | Service Nogs Toilet | bad0e4f3-34a8-42a9-9012-e971e5fa8495
checkpoint-status | e7d9e9a6-a634-4366-92bb-47bb0aa2c3c6 |  | checkpoint | Wall Vanity nogs installed
checkpoint-status | 86c30aa6-afbe-45e2-90d8-5551e8fde1dd |  | checkpoint | Handrail and Toilet roll holder Nogs installed
checklist-flat | 5f6d15c7-fce5-4c4c-825d-d74b191318cd |  | checklist | FC - S - Tapes |  |  |  |  | Yes | FC - S - Tapes | c2941469-9110-4cd8-ab0b-5815b8a2e629
checkpoint-status | 734b6704-1a34-4218-9f24-5488b643044c |  | checkpoint | 3m taping around windows and sliders around the exterior framings as per the manufacturer specifications
holdpoint | 65db3f6a-cdcb-4854-85cd-fdcaf6460419 |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat | b73a2ee9-77a9-4c4a-bbc8-9064c82966b6 |  | checklist | Flashing at Windows and Doors |  |  |  |  | Yes | Flashing at Windows and Doors | c435cbcc-f8e8-4426-877a-333a2bc290a0
checkpoint-status | 49a9b7c5-4f18-4d63-9b4f-2375d8a950a5 |  | checkpoint | Install rainshield between joinery and lintel (brick)
checkpoint-status | 3d9b86bf-78b5-4c12-b50a-d7fcca15d9bc |  | checkpoint | DPC installed and WANZ bar install at the bottom of the joinery (see fixing) as per manufacturer's specs
checkpoint-status | 25c8ae67-e3b7-40e5-a024-23791a3a6eb0 |  | checkpoint | Framing, side flashing
checkpoint-status | 2bf11c0f-a1ce-4da8-bd46-e7f3e72dd6fb |  | checkpoint | Aluminium window jamb side flashing are installed
holdpoint | 07d45e00-37f9-49e9-8662-772bff8ff698 |  | signoff | Raise Remedials / REQUEST SIGN OFF FROM FOREMEN - QA
checklist-flat | ec49c4aa-82b8-49f0-948d-1b2a5712b705 |  | checklist | Envelope Penetrations |  |  |  |  | Yes | Envelope Penetrations | c921e603-38b6-4e71-8e92-2eda6ee791e7
checkpoint-status | f62ea88b-b011-48d3-86e2-7471d80e93b4 |  | checkpoint | All the trade seals are installed in all penetrations through RAB board and concrete installed (Tap, Ventilation, Air con, Electrical, Sprinklers etc).
holdpoint | ef88945b-3d3c-4b5e-9989-824961f82a73 |  | signoff | Raise Remedials / REQUEST SIGN OFF FROM FOREMEN - QA
checklist-flat | 039810dc-a6fe-4b9f-a219-bbc5c68d65e3 |  | checklist | Completions Documents |  |  |  |  | Yes | Completions Documents | cf2a3dfd-4ae6-46e6-b062-00d7612f9b31
checkpoint-status | 448a2a6d-7da9-4381-acc9-87262cef23ce |  | checkpoint | PS3 - Windows and Doors Installation
checkpoint-status | 430473a4-356a-4c81-b24c-b0d797ad2e59 |  | checkpoint | PS3 - James Hardie Rigid Air Barrier System
checkpoint-status | 208c6f23-6b34-4a8c-9c6b-e37a70a6bc3c |  | checkpoint | James Hardie Rigid Air Barrier System Warranty
checkpoint-status | 75dd45c4-7e00-43c2-ad7e-b0a42d7be4ac |  | checkpoint | Warranties compiled and attached
checkpoint-status | b369ebac-89f7-4cd2-9082-720960e5f11d |  | checkpoint | Material Schedule
holdpoint | f7621497-63ac-460d-85c3-55853667e488 |  | signoff | Send to Quality Assurance when completed
checklist-flat | 2c151ffb-5ca0-4a22-99b6-c5c46d22b7b8 |  | checklist | FC - S - Roofing Iron/Flashings |  |  |  |  | Yes | FC - S - Roofing Iron/Flashings | d4883753-f636-4f3b-bb65-ca8e4788f289
checkpoint-status | 01b5b705-8419-4ca0-850b-371d7ed3442e |  | checkpoint | Correct drawing revision checked,referenced and attached
text | 5b4c1569-fa27-5026-a4de-038d7f13611f |  | textbox | Drawing number(s) & Revisions
checkpoint-status | 3f84857f-dcb2-4b86-b0e9-b44c2f3f98bd |  | checkpoint | Area Accessible, Substrate Acceptable & Approval to start work
checkpoint-status | da251363-7973-4c97-b791-6f135a8e1985 |  | checkpoint | Roof underlay checked and accurate
checkpoint-status | b7bde387-b1b8-4bd4-ad25-46529afe492d |  | checkpoint | Roofing Material fixed correctly/checked and accurate (2-3 photos attached)
checkpoint-status | 0b68edd1-2393-4e4e-9a63-9e8e33d4615d |  | checkpoint | Flashing/capping checked and accurate (2-3 Photos attached)
checkpoint-status | bfe7a5c6-ad7f-470a-933f-70ca14d4a678 |  | checkpoint | Area left clean and tidy (Photos attached)
label | 9df8c0d5-12b8-593b-8b8f-7f70d3e34976 |  | note | Roof and gutters/surrounding area clean and rubbish/fillings removed
checkpoint-status | 2564b947-c3d7-401f-9783-b40bb8cc684b |  | checkpoint | All Roof works completed, reviewed and approved (Photos attached)
holdpoint | 046c395a-1f87-4f1f-ae8e-b74259d114b9 |  | signoff | Request sign off
checkpoint-status | a0dbd031-bb88-42ce-8caa-1db94375074f |  | checkpoint | Inspections completed and issued to Foreman
holdpoint | f3d95d19-3d5b-495b-a866-2ed509566aa3 |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat | 56361c4e-1c35-4af5-9e20-d11d999f072d |  | checklist | FC - S - Exterior Timber Framing |  |  |  |  | Yes | B05 - FC - S - Exterior Timber Framing | d547971b-2ff8-43b0-887b-dba04abb8a50
checkpoint-status | d878ee79-943e-496d-b481-e083f7103077 |  | checkpoint | Setout completed, checked & accurate (no clashes & wall locations clearly marked)
checkpoint-status | 744b9677-9a17-400c-be87-822e2d8b6d4d |  | checkpoint | Framing Dimensions / locations checked & accurate (openings considered where applicable)
checkpoint-status | ac2e7934-02d7-4c31-9bfd-b86db2be4110 |  | checkpoint | All frames have been installed square, straight and plumb
checkpoint-status | 267790fb-fc9a-4366-855d-a0eceae99ecd |  | checkpoint | DPC installed (if required) correctly
checkpoint-status | 307b9398-0181-4ba1-b3da-5e4fd1c0dc46 |  | checkpoint | Fixings are correct to specification including any seismic/bracing requirements (attach relevant photos)
checkpoint-status | 84bdb533-2d04-4a6e-a861-dca9e6e95507 |  | checkpoint | All Nogs (Service/Specialty) & penetrations - installed, checked & correct (consider acoustic & fire rating requirements)
checkpoint-status | 8e2b14d3-6def-4dc0-83ba-c88cdaa92ebc |  | checkpoint | All timber framing completed correctly to specification & within tolerance in respective area(s)
checkpoint-status | ae8c9c95-931f-4eef-9380-0d797fe20810 |  | checkpoint | Inspections completed and issued to Foreman
holdpoint | a3b30ee5-43ef-42af-9109-d36e5a759cc0 |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat | 830f9ee9-9a30-4d5c-815b-36219abfe25e |  | checklist | FC - S - RAB |  |  |  |  | Yes | B05 - FC - S - RAB | d62adfc4-cdce-4cc3-884d-40453fe501f0
checkpoint-status | 314e742d-6248-4c22-8e72-7d72e5cc9778 |  | checkpoint | Fixing and spacings checked in accordance with manufacturers specs
checkpoint-status | 95282175-01c6-4193-802a-9870db48e91b |  | checkpoint | White MS sealant for air seals between RAB board and concrete horizontal and vertical joints
checkpoint-status | 63181165-e219-4839-b58f-c2bacc6b7de8 |  | checkpoint | 3M taping around windows and external corners and vertical joints and horizontal flashing checked
checkpoint-status | 67be052d-06c0-4d8f-8d12-c511a61dfe37 |  | checkpoint | Vaproshield to interfloor installed after vertical taping
checkpoint-status | 2472b5cf-aca1-452f-919e-fdbef55ca3a3 |  | checkpoint | Bracing checked and accurate
checkpoint-status | 04ddaf69-5356-46b4-ab59-39207a971021 |  | checkpoint | Penetrations and punctures sealed with flashing tape
checkpoint-status | c795deea-4b69-430e-94cf-b334001ff3e2 |  | checkpoint | Sealing joints over internal and external joints
checkpoint-status | 296726d6-02aa-4c07-9ff5-f957a42b9744 |  | checkpoint | Battern on RAB Board for cladding fixings
checkpoint-status | 715d4b37-2952-471b-8ddd-c1654bf27938 |  | checkpoint | All RAB board installation completed to specification & within tolerance in respective area(s)
checkpoint-status | 89c4e9a0-9fbb-47af-81c3-1713b2359961 |  | checkpoint | Inspections completed and issued to Foreman
holdpoint | 596be71d-091d-4ad5-aff7-68cb44740a74 |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat | b2206bdf-9e91-40b2-8796-502f03aaedfb |  | checklist | Lintels |  |  |  |  | Yes | Lintels | f1abad09-832f-4f16-aa0a-892ec9befec1
checkpoint-status | 2356c197-bcf3-42d1-bfe2-a23cb7212890 |  | checkpoint | Construction Lintels: Positioning, Fixing, Sealant and taping checked
checkpoint-status | 0f6f9d47-ee02-4c4c-be65-28b00879d866 |  | checkpoint | Windows and Sliders: Positioning, Fixing, Sealant and taping checked
checkpoint-status | 8a5f4614-a1c2-40df-8c80-7dadb5a9e0ee |  | checkpoint | Lintels in Balconies and Decks: Positioning, Fixing, Sealant and taping checked
holdpoint | 3d5ac82e-0291-45cd-a19f-563c9831ca28 |  | signoff | Raise Remedials / REQUEST SIGN OFF FROM FOREMEN - QA
checklist-flat | 86a36df1-c1b7-4afb-bc89-a93408655429 |  | checklist | Exterior Framing |  |  |  |  | Yes | Exterior Framing | fcc09aa1-6a71-477e-bf38-52ac9ac3f2d9
checkpoint-status | 4abc451f-566a-402e-a7f0-bc69a6f2a7e1 |  | checkpoint | General Photos of the Exterior Framing (DPC, Fixing, Etc)
checkpoint-status | d917e17d-d0de-47f1-91e4-fe9954a66f8c |  | checkpoint | PEF rod between floor and bottom plate installed correctly
checkpoint-status | e8fdd1c3-75db-49e0-8c13-403cca7ef9d6 |  | checkpoint | Survey check openings prior rab board installation
checkpoint-status | a7752e6b-1d8d-461f-a5a0-14026b360aef |  | checkpoint | Soffit Framing Checked
holdpoint | 63e6179b-0b41-4b83-9498-92774300c770 |  | signoff | Raise Remedials / REQUEST SIGN OFF FROM FOREMEN - QA