## Breakdown
Waterproofing Concepts - 045 Kevin Hickman (Riccarton Park)
Stage 01 - B01
Façade
Area B level
|  |  |  | North Elevation (Grid 12, P-V) | Balconies - Sarnafil & Deck Drainage | Pre-populate | F - S - Waterproofing
|  |  |  | South Elevation ( Grid 17, P-S & T-U) | Balconies - Sarnafil & Deck Drainage | Pre-populate | F - S - Waterproofing
Area C
|  |  |  | East Elevation (Grid 3, I-J) | Balconies - Sarnafil & Deck Drainage | Pre-populate | F - S - Waterproofing
Compliance Documents
|  | Stage 01 - B01 |  | Pre-populate | CST - S - Completion Documents

## Checklist
Type | Name | Value
checklist-flat | F - S - Waterproofing
checkpoint | Lap distance for sheet membrane complies with manufacturers specification
checkpoint | Upstand/ perimeter detail installed as specified
checkpoint | Adhesives fully applied as specified and acceptable
checkpoint | Check for air pockets, wrinkles, holes, tears & note and remediated if required
checkpoint | Checked for penetrations/ pipework/ upstands sealed to specified detail
checkpoint | Checked membrane detail at expansion/ construction joints and acceptable
checkpoint | Flood test conducted and no leaks found
checkpoint | Waterproofing membrane installed and correct and any remedial works completed
bool | Specified membrane protection is in place
Type | Name | Value
checklist-flat | CST - S - Completion Documents
checkpoint | All relevant Compliance Documentation completed and attached above
bool | Any Additional Compliance Documentation (Required under Section C and by Consultants) - Completed and Attached
label | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint | Request Signoff