## Breakdown
Waterproofing Concepts (Kevin Hickman - Riccarton Park)
Project Build QA
Stage 3 - THB11, THB13
THB11 (TH37, 38, 39)
|  |  |  | Flatroof A | Pre-populate | FC - S - Roofing
|  |  |  | Flatroof B | Pre-populate | FC - S - Roofing
THB13 (TH37, 38, 39)
|  |  |  | Flatroof A | Pre-populate | FC - S - Roofing
|  |  |  | Flatroof B | Pre-populate | FC - S - Roofing
Compliance Documentation
|  | Stage 3 - THB11, THB13 |  |  | Pre-populate | CST - S - Completion Documents

## Checklist
Type | Name
Checklist | FC - S - Roofing
Section | Pre-installation checks
checkpoint | Substrate acceptable (clean, dry and stable). Edge protection and safety installed. Perimeter support installed if metal deck substrate.
Section | Metcom7
checkpoint | Falls deemed acceptable by Council
checkpoint | Purlins and roof structure ready for Metcom 7 and approval given to lay
checkpoint | Fix steel to manufacturers specifications in compliance with NZBC
checkpoint | The metal profile installed upside down and the specified fastenings installed in the trough
checkpoint | Flashings installed on hips and valleys
checkpoint | Insulation protected from crushing (edge of gutter, timber edging, etc.)
checkpoint | The timber height is exact height of the insulation and the outside edge of the timber has a generous radius to ensure maximum bond of the membrane when dressed over it
checkpoint | Outlets framed and plywood routed out
checkpoint | Metcom7 installed as per spec and completed. Any general observations made
Section | Polyiso
checkpoint | All Polyiso sheets butt jointed - no gaps created
checkpoint | Polyiso Sheets glued down with Viking FAST Adhesive (STP900B) using a proprietary dual cartridge caulking gun
checkpoint | STP900B adhesive applied in sweeping ribbons on every steel rib and then left to ‘foam-up’ over the next few minutes
checkpoint | Polyiso boards laid in a brick-bond pattern.
checkpoint | Butt the polyiso sheets up to the pre-formed timber edging where applicable
checkpoint | Entire roof inspected upon completion to ensure a uniform flat surface
checkpoint | Polyiso installed as per spec and completed. Any general observations made
Section | Membrane
checkpoint | Polyiso thoroughly cleaned and checked prior to priming or membrane application
checkpoint | Checked to ensure no dye-batch colour variation
checkpoint | Ensure the specified membrane thickness and colour is used on site
checkpoint | All products installed with a Viking Membrane comply with Viking Specifications e.g. the tested ‘system’ - Drains and accessories supplied by Viking Roofspec
checkpoint | All welded seams and proprietary items to to be seam probed.
checkpoint | Membrane installed as per spec and completed. Any general observations made
checkpoint | All roofing and waterproofing completed to specification & within tolerance in respective area(s)
Section | Hatches
checkpoint | Setout completed, checked & accurate (no clashes & wall locations clearly marked)
checkpoint | Framing Dimensions / locations checked & accurate (openings considered where applicable)
checkpoint | All frames have been installed square, straight and plumb
checkpoint | DPC installed (if required) correctly
checkpoint | Fixings are correct to specification including any seismic/bracing requirements (attach relevant photos)
checkpoint | All Nogs (Service/Specialty) & penetrations - installed, checked & correct (consider acoustic & fire rating requirements)
checkpoint | All timber framing completed correctly to specification & within tolerance in respective area(s)
Section | Gutters
checkpoint | Setout completed, checked & accurate (no clashes & wall locations clearly marked)
checkpoint | Framing Dimensions / locations checked & accurate (openings considered where applicable)
checkpoint | All frames have been installed square, straight and plumb
checkpoint | DPC installed (if required) correctly
checkpoint | Fixings are correct to specification including any seismic/bracing requirements (attach relevant photos)
checkpoint | All Nogs (Service/Specialty) & penetrations - installed, checked & correct (consider acoustic & fire rating requirements)
checkpoint | All timber framing completed correctly to specification & within tolerance in respective area(s)
Type | Name
Checklist | CST - S - Completion Documents
checkpoint | All relevant Compliance Documentation completed and attached above
checkpoint | LBP Memorandum/ Record of works filled out, signed and attached
checkpoint | Any Additional Compliance Documentation - Completed and Attached
checkpoint | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint | Request Signoff