## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | F - S - Waterproofing |  |  |  |  | Yes | F - S - Waterproofing | 202413e4-4b30-44c1-b155-e938ab6d1c26
checkpoint-status |  |  | checkpoint | Lap distance for sheet membrane complies with manufacturers specification
checkpoint-status |  |  | checkpoint | Upstand/ perimeter detail installed as specified
checkpoint-status |  |  | checkpoint | Adhesives fully applied as specified and acceptable
checkpoint-status |  |  | checkpoint | Check for air pockets, wrinkles, holes, tears & note and remediated if required
checkpoint-status |  |  | checkpoint | Checked for penetrations/ pipework/ upstands sealed to specified detail
checkpoint-status |  |  | checkpoint | Checked membrane detail at expansion/ construction joints and acceptable
checkpoint-status |  |  | checkpoint | Flood test conducted and no leaks found
checkpoint-status |  |  | checkpoint | Waterproofing membrane installed and correct and any remedial works completed
boolean | 1f2ed14f-2951-5841-8d06-ed4c7eea2dfc |  | tickbox | Specified membrane protection is in place
checklist-flat |  |  | checklist | Viking membrane system - |  |  |  |  | Yes | QA - Viking membrane system (V1) | 22b8cb61-3f54-4681-8d5b-abd3a5a91e43
checkpoint-status |  |  | checkpoint | Correct drawing revision referenced and attached
text | 9707fecf-ce3a-4c96-b68b-cd8cb53a1f80 |  | textbox | Drawing number(s) & Revisions
checkpoint-status |  |  | checkpoint | Area Accessible, Substrate Acceptable & Approval to start work
boolean | cf5089d7-6e79-4519-b424-30c6b1efb0cd |  | tickbox | Plywood substrate checked and accurate
checkpoint-status |  |  | checkpoint | Moisture check to substrate before Enviroclad to be installed / checked and accurate/ documentation, photos attached
checkpoint-status |  |  | checkpoint | Hatches checked and accurate (2-4 Photos attached)
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | No Damages to membrane (cuts & holes)
checkpoint-status |  |  | checkpoint | Work completed, reviewed and approved
holdpoint |  |  | signoff | Request Sign Off
checklist-flat |  |  | checklist | CST - S - Completion Documents |  |  |  |  | Yes | SYS - CST - S - Completion Documents (old version) | 38217206-b32d-4638-8c08-03f2acf24915
checkpoint-status |  |  | checkpoint | All relevant Compliance Documentation completed and attached above
button | 6d01e200-6f43-52da-943e-08f7a29cd159 | DataPoint is missing 'button' values | button | LBP Memorandum/ Record of works filled out, signed and attached
button | f31e658a-75b8-53a4-a67f-85c568569f38 | DataPoint is missing 'button' values | button | Any Additional Compliance Documentation - Completed and Attached
label | 0109b6b6-4e84-537e-9681-31f73ad76a93 |  | note | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint |  |  | signoff | Request Signoff
checklist-sectioned |  |  | checklist | FC - S - Roofing |  |  |  |  | Yes | FC - S - Roofing | 47591aef-6bbc-4f4d-8ce5-8877b68b6a68
checkpoint-group |  |  | section | Pre-installation checks
checkpoint-status |  |  | checkpoint | Substrate acceptable (clean, dry and stable). Edge protection and safety installed. Perimeter support installed if metal deck substrate.
checkpoint-group |  |  | section | Metcom7
checkpoint-status |  |  | checkpoint | Falls deemed acceptable by Council
checkpoint-status |  |  | checkpoint | Purlins and roof structure ready for Metcom 7 and approval given to lay
checkpoint-status |  |  | checkpoint | Fix steel to manufacturers specifications in compliance with NZBC
checkpoint-status |  |  | checkpoint | The metal profile installed upside down and the specified fastenings installed in the trough
checkpoint-status |  |  | checkpoint | Flashings installed on hips and valleys
checkpoint-status |  |  | checkpoint | Insulation protected from crushing (edge of gutter, timber edging, etc.)
checkpoint-status |  |  | checkpoint | The timber height is exact height of the insulation and the outside edge of the timber has a generous radius to ensure maximum bond of the membrane when dressed over it
checkpoint-status |  |  | checkpoint | Outlets framed and plywood routed out
checkpoint-status |  |  | checkpoint | Metcom7 installed as per spec and completed. Any general observations made
checkpoint-group |  |  | section | Polyiso
checkpoint-status |  |  | checkpoint | All Polyiso sheets butt jointed - no gaps created
checkpoint-status |  |  | checkpoint | Polyiso Sheets glued down with Viking FAST Adhesive (STP900B) using a proprietary dual cartridge caulking gun
checkpoint-status |  |  | checkpoint | STP900B adhesive applied in sweeping ribbons on every steel rib and then left to ‘foam-up’ over the next few minutes
checkpoint-status |  |  | checkpoint | Polyiso boards laid in a brick-bond pattern.
checkpoint-status |  |  | checkpoint | Butt the polyiso sheets up to the pre-formed timber edging where applicable
checkpoint-status |  |  | checkpoint | Entire roof inspected upon completion to ensure a uniform flat surface
checkpoint-status |  |  | checkpoint | Polyiso installed as per spec and completed. Any general observations made
checkpoint-group |  |  | section | Membrane
checkpoint-status |  |  | checkpoint | Polyiso thoroughly cleaned and checked prior to priming or membrane application
checkpoint-status |  |  | checkpoint | Checked to ensure no dye-batch colour variation
checkpoint-status |  |  | checkpoint | Ensure the specified membrane thickness and colour is used on site
checkpoint-status |  |  | checkpoint | All products installed with a Viking Membrane comply with Viking Specifications e.g. the tested ‘system’ - Drains and accessories supplied by Viking Roofspec
checkpoint-status |  |  | checkpoint | All welded seams and proprietary items to to be seam probed.
checkpoint-status |  |  | checkpoint | Membrane installed as per spec and completed. Any general observations made
checkpoint-status |  |  | checkpoint | All roofing and waterproofing completed to specification & within tolerance in respective area(s)
checkpoint-group |  |  | section | Hatches
checkpoint-status |  |  | checkpoint | Setout completed, checked & accurate (no clashes & wall locations clearly marked)
checkpoint-status |  |  | checkpoint | Framing Dimensions / locations checked & accurate (openings considered where applicable)
checkpoint-status |  |  | checkpoint | All frames have been installed square, straight and plumb
checkpoint-status |  |  | checkpoint | DPC installed (if required) correctly
checkpoint-status |  |  | checkpoint | Fixings are correct to specification including any seismic/bracing requirements (attach relevant photos)
checkpoint-status |  |  | checkpoint | All Nogs (Service/Specialty) & penetrations - installed, checked & correct (consider acoustic & fire rating requirements)
checkpoint-status |  |  | checkpoint | All timber framing completed correctly to specification & within tolerance in respective area(s)
checkpoint-group |  |  | section | Gutters
checkpoint-status |  |  | checkpoint | Setout completed, checked & accurate (no clashes & wall locations clearly marked)
checkpoint-status |  |  | checkpoint | Framing Dimensions / locations checked & accurate (openings considered where applicable)
checkpoint-status |  |  | checkpoint | All frames have been installed square, straight and plumb
checkpoint-status |  |  | checkpoint | DPC installed (if required) correctly
checkpoint-status |  |  | checkpoint | Fixings are correct to specification including any seismic/bracing requirements (attach relevant photos)
checkpoint-status |  |  | checkpoint | All Nogs (Service/Specialty) & penetrations - installed, checked & correct (consider acoustic & fire rating requirements)
checkpoint-status |  |  | checkpoint | All timber framing completed correctly to specification & within tolerance in respective area(s)
checklist-flat |  |  | checklist | Block wall Bentonite |  |  |  |  | Yes | QA - Block wall Bentonite | 491a0646-5167-47b3-bfea-503e42be0c55
checkpoint-status |  |  | checkpoint | Area on-site
checkpoint-status |  |  | checkpoint | Applicators
checkpoint-status |  |  | checkpoint | Substrate
checkpoint-status |  |  | checkpoint | Surface preparation if required
button | faab4583-56ad-5813-8db0-735670bdbc72 |  | button | Bentonite sheet to lap with DPM approx 700mm down the face of the block formwork with a mechanical fixed termination bar | Yes, N/A
button | f81a964a-580e-530f-b4eb-7bf652f1dd63 |  | button | Bentonite sheet does not lap under the strip footing | Yes, N/A
holdpoint |  |  | signoff | Request Sign Off
checklist-flat |  |  | checklist | Internal Gutter - |  |  |  |  | Yes | QA - Internal Gutter (V1) | 52bdc93f-b2af-4d4b-baa3-78c448b4a1c8
checkpoint-status |  |  | checkpoint | Correct drawing revision referenced and attached
text | 9fe09887-289d-4a7f-80df-56b15e0d7e31 |  | textbox | Drawing number(s) & Revisions
checkpoint-status |  |  | checkpoint | Area Accessible, Substrate Acceptable & Approval to start work
checkpoint-status |  |  | checkpoint | Gutters checked and accurate (2-4 Photos attached)
checkpoint-status |  |  | checkpoint | Screw heads and ply joints all flush (2-4 Photos attached)
checkpoint-status |  |  | checkpoint | Correct fall (2-4 Photos attached)
checkpoint-status |  |  | checkpoint | Membrane checked, Lapped and accurate (2-4 Photos attached)
checkpoint-status |  |  | checkpoint | No bubbles or bulges (2-4 Photos attached)
checkpoint-status |  |  | checkpoint | All joints sealed and accurate (2-4 Photos attached)
checkpoint-status |  |  | checkpoint | Water test done and results attached
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | Work completed, reviewed and approved
holdpoint |  |  | signoff | Request Sign Off
checklist-flat |  |  | checklist | Completion Documentation |  |  |  |  | Yes | Completion Documents Checklist (V1) | 567a5492-cefa-413d-b9f1-fe6c178b5cb9
checkpoint-status |  |  | checkpoint | All relevant Compliance Documentation completed and attached above
button | 9f3c8be1-4f6e-4ffe-a1b6-a6fe82b6b874 |  | button | LBP Memorandum/ Record of works filled out, signed and attached | YES, N/A
button | 271e2c41-a118-437b-ae10-87cc33baaa46 |  | button | Viking Roof spec checklist completed and attached | YES, N/A
button | 54c00ebb-b7db-43f7-970d-d83410ecdca4 |  | button | Any Additional Compliance Documentation - Completed and Attached | YES, N/A
label | 65958708-9836-4fd8-b25c-7d3fcf71508a |  | note | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | Job Details |  |  |  |  | Yes | Job Details Checklist (V1) | 6b6ed0fd-3328-4fd7-875f-823af7444745
checkpoint-no-status |  |  | checkpoint | Site Information Recorded
label | fc43c6d5-6ebc-4421-b67e-a0c61785f9b6 |  | note | Site Address - Riccarton Park - 25 Steadman Rd, Riccarton
label | a127314c-25e2-4d3b-afb3-4027afc5bd1a |  | note | Main Contractor Details - Ryman Healthcare
label | ffb7596d-cdcf-49b4-be9d-922c3d34cbef |  | note | Project Managers Details - Andrew Inch - andrew.inch@rymanhealthcare.com
label | f22a33c0-52a3-4d18-afbe-e8db147797fe |  | note | Site Manager Details - Martin Collins - martin.collins@rymanhealthcare.com
label | dc0cb0fd-ec7a-4f01-8d0a-12a775ec91a9 |  | note | QA Admin Details - Leshani Gunawardana - Leshani.Gunawardana@rymanhealthcare.com
checkpoint-status |  |  | checkpoint | Scope of Works Attached
checkpoint-status |  |  | checkpoint | Additional Pre Start Docs
checkpoint-status |  |  | checkpoint | All relevant job details entered above
label | 37c967b0-b04d-4a2d-a7ab-08b1ba1e3f8b |  | note | Do not select "Pass" HERE until all above requirements have been marked as "PASS" or "N/A"
checklist-flat |  |  | checklist | Precast Panel Bentonite |  |  |  |  | Yes | QA - Precast Panel Bentonite | 782f4640-5af0-4ac1-9c41-3049dbf29f6e
checkpoint-status |  |  | checkpoint | Area on-site
checkpoint-status |  |  | checkpoint | Applicators
checkpoint-status |  |  | checkpoint | Substrate
checkpoint-status |  |  | checkpoint | Surface preparation if required
button | a49a5724-4291-5c63-9a62-57ab7306da5d |  | button | Bentonite for the precast panels to be laid prior to panel pours | Yes, N/A
button | 3a96b62e-0ee1-56ad-a301-904327082dd9 |  | button | Precast wall panel bentonite sheet to lap 300mm minimum | Yes, N/A
holdpoint |  |  | signoff | Request Sign Off
checklist-flat |  |  | checklist | In-situ joints Bentonite |  |  |  |  | Yes | QA - In-situ joints Bentonite | 9227bc64-e001-469e-93cc-4782ef71be25
checkpoint-status |  |  | checkpoint | Area on-site
checkpoint-status |  |  | checkpoint | Applicators
checkpoint-status |  |  | checkpoint | Substrate
checkpoint-status |  |  | checkpoint | Surface preparation if required
button | edfa5cda-2be4-5e0d-943a-cac775a77e62 |  | button | Bentonite to be applied to 600mm wide in-situ concrete stitch joints lapping 300mm beyond stitch joint Bentonite sheet | Yes, N/A
holdpoint |  |  | signoff | Request Sign Off
checklist-flat |  |  | checklist | CST - S - Completion Documents |  |  |  |  | Yes | CST - S - Completion Documents | 97125922-cd45-4af5-a520-71bbc324b9da
checkpoint-status |  |  | checkpoint | All relevant Compliance Documentation completed and attached above
boolean | c3b4f4e5-1d8f-5d5d-bf9a-7c1b775f6e8d |  | tickbox | Any Additional Compliance Documentation (Required under Section C and by Consultants) - Completed and Attached
label | 5039140d-8bf3-54d8-8506-87a084fcbccb |  | note | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | H&S Upload - |  |  |  |  | Yes | H&S - Upload of Daily H&S Paperwork (V1) | 9bed8227-1c01-486f-aa3c-e76b0c7d13d1
checkpoint-status |  |  | checkpoint | Paperwork filled out & attached
label | 711a9fad-41c4-4e9a-9cce-64eadcc32049 |  | note | Select "PASS" once the paperwork is completed and uploaded here
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | Penetration |  |  |  |  | Yes | QA - Penetration | a53b4762-c209-4b66-83b0-b8fcd88f1388
checkpoint-status |  |  | checkpoint | Penetration Details
label | 9a263fba-8f40-57b1-84f2-b2e1d2e4f8b3 |  | note | Area of Installation
boolean | e8e711a0-3b37-50a8-8833-4c60cda04a9e |  | tickbox | Penetration Type | Mechanical, Sanitary, Power, Cable tray, Water
text | cd67d4b5-c63c-55fb-8fae-d629ed8bdbda |  | textbox | If other - specify here:
holdpoint |  |  | signoff | Request Sign Off
checklist-flat |  |  | checklist | Compliance / Completion Documentation Checklist |  |  |  |  | Yes | Compliance / Completion Documentation Checklist | b88b79b6-9d74-46a9-a396-eb0eaaf6c44d
checkpoint-status |  |  | checkpoint | All Compliance / Completion Documentation - Completed & Attached
button | 9335514c-f3fa-52ec-8498-87a1af9c4459 |  | button | PS3 - Completed and Attached | Yes, N/A
button | 3386e6e1-b5ba-5067-8293-e736be2eaf8a |  | button | Any Additional Compliance Documentation - Completed and Attached | Yes, N/A
label | c5058b04-fd21-5026-893d-8a54b4c90e3e |  | note | Do not select "Pass" HERE until all above requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint |  |  | signoff | Request Sign Off
checklist-sectioned |  |  | checklist | Pre-Commencement Checks |  |  |  |  | Yes | Pre-Commencement Checklist (V3) | cd25dc1e-ace5-4dc3-bedb-2840b294232f
checkpoint-group |  |  | section | Health & Safety Pre-Commencement Checks
checkpoint-status |  |  | checkpoint | Trade Contractor H&S Policy - Completed & Attached
checkpoint-status |  |  | checkpoint | Trade Contractor Site Specific Safety Plan (SSSP) - Completed & Attached
checkpoint-status |  |  | checkpoint | Trade Contractor Work safe NZ Notification - Completed & Attached (if applicable)
label | 2afc03cf-c542-4a9d-9c09-eace0345b897 |  | note | If not required select N/A
checkpoint-status |  |  | checkpoint | Any Additional Prestart H&S Documentation uploaded
label | 20220033-a085-40d7-a6b9-45160856d90d |  | note | "Pass" once uploaded or select "N/A" if there are no additional requirements to those listed above
checkpoint-status |  |  | checkpoint | All Health & Safety Pre-Commencement Checks Completed
label | 1398df7f-5f32-4d4a-85d5-6d6c8842877d |  | note | Do not select "Pass" HERE until all above requirements have been marked as "PASS" or you have selected "N/A"
boolean | 0d0cfac5-f980-44c2-ad56-ebbf177dbd7d |  | tickbox | Report with all Health & Safety Pre-Commencement checks sent to Main Contractor
label | c8a18e70-307f-4315-8fcc-b987f4fd3cba |  | note | Click the three dots in the top right of the Conqa app to send this completed documentation to the respective Main Contractor
holdpoint |  |  | signoff | Request Review
checkpoint-group |  |  | section | Quality Pre-Commencement Checks
checkpoint-status |  |  | checkpoint | Trade Contractor Quality Management Plan Completed, Agreed & Attached
checkpoint-status |  |  | checkpoint | Trade Contractor Inspection & Test Plan Completed, Agreed & Attached
checkpoint-status |  |  | checkpoint | Trade Contractor Licences/Tickets attached and current
label | 72a165f1-3599-4876-bf60-acd1f2fca987 |  | note | If required (plumbing, waterproofing, electrical etc), if not select NA
checkpoint-status |  |  | checkpoint | Trade Insurances attached and current
label | 448409f2-d132-4740-a00f-5ed4a393076e |  | note | If required, if not select NA
checkpoint-status |  |  | checkpoint | Relevant Breakdown & Checklists Setup on Conqa & Reviewed by Main Contractor
boolean | e18c0bfe-3419-454b-896d-30428dc0e0e4 |  | tickbox | Conqa EXCEL breakdown & checklists attached
button | eeb37c79-deb1-4ece-bacb-34d70ac883e5 |  | button | Does your breakdown & checklists meet the Main Contractor requirements & have they been reviewed | YES, NO, N/A
checkpoint-status |  |  | checkpoint | Conqa Setup & Trade Contractor Project Team Trained & Given Access
label | 5188d20f-61d3-4fc4-a610-98709d4af24c |  | note | Conqa Support Contact Details - support@conqa.nz, 09 886 4647 or use the live chat in app
checkpoint-status |  |  | checkpoint | Review Access Granted to Main Contractor & Any Relevant Third Parties
label | 35481c69-8322-4a45-8cbf-b1c24b672486 |  | note | Contact the Conqa Support team to assist in providing access to relevant parties
checkpoint-status |  |  | checkpoint | Matrix/Insights Setup (if required)
label | 0a9c6052-01a2-44de-8d30-30ae918ea43d |  | note | login to account.con.qa & click on "insights" to see a summary of your work - if incomplete please contact the Conqa support team to assist
checkpoint-status |  |  | checkpoint | Any Additional Prestart Quality Documentation uploaded
label | 7d601d68-0174-4082-a467-9897cf97aa9a |  | note | "Pass" once uploaded or select "N/A" if there are no additional requirements to those listed above
checkpoint-status |  |  | checkpoint | All Quality Pre-Commencement Checks Completed
label | 2779cc1e-0818-4032-8c0a-db63abbd6921 |  | note | Do not select "Pass" HERE until all above requirements have been marked as "PASS" or you have selected "N/A"
boolean | 1675bf7c-3e5f-4e17-abb4-47626728c564 |  | tickbox | Report with all Quality Pre-Commencement checks sent to Main Contractor
label | d78c95a3-3f2c-4667-aeec-5ebf68a696e9 |  | note | Click the three dots in the top right of the Conqa app to send this completed documentation to the respective Main Contractor
holdpoint |  |  | signoff | Request Review
checklist-sectioned |  |  | checklist | Sarnafil balcony |  |  |  |  | Yes | QA - Sarnafil balcony | d5ddf6de-01c3-49ea-b01d-3d85e0cf9b57
checkpoint-group |  |  | section | Area Preparation
checkpoint-status |  |  | checkpoint | Area clean and accessible (attach photos)
checkpoint-status |  |  | checkpoint | Concrete ground
checkpoint-status |  |  | checkpoint | Edges bevelled
checkpoint-status |  |  | checkpoint | Concrete in acceptable condition, dry and free from dust and other contaminants
checkpoint-group |  |  | section | Application QA
checkpoint-status |  |  | checkpoint | Correct Sika Products used (attach photos)
checkpoint-status |  |  | checkpoint | Work completed as per specifications and area left clean and tidy
checkpoint-status |  |  | checkpoint | Leak detection test completed - test results attached
holdpoint |  |  | signoff | Request Sign Off
checklist-flat |  |  | checklist | Final Checks |  |  |  |  | Yes | QA - Final Checks | ec57ba8c-6f34-4975-b530-1630ec17b0f9
checkpoint-status |  |  | checkpoint | All laps completed
checkpoint-status |  |  | checkpoint | Termination bar installed
checkpoint-status |  |  | checkpoint | Membrane completed as per specification
holdpoint |  |  | signoff | Request Sign Off