## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Coloursteel Roofing |  |  |  |  | Yes | QA - Coloursteel Roofing Checklist | 0185d538-bf60-4b72-b68e-a78ba2ca7004
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Edge protection/scaffold in place
holdpoint |  |  | signoff | Raise remedial / request review
checkpoint-status |  |  | checkpoint | Safety nets installed
holdpoint |  |  | signoff | Raise remedial / request review
checkpoint-status |  |  | checkpoint | Purlins/battens & all necessary timberwork complete
holdpoint |  |  | signoff | Raise remedial / request review
checkpoint-group |  |  | section | Substrate Checklist : Enviroclad Plywood
checkpoint-status |  |  | checkpoint | Framing supports at 400mm centres (in one direction). All plywood edges must also be supported.
label | 85db5d9d-2877-487d-99d6-1850a4e741fb |  | note | Do not use tongue and groove plywood. Viking Roofspec can accept the maximum support spacings provided in Table 15C of CHH Ecoply Specification Guide.
checkpoint-status |  |  | checkpoint | Minimum thickness 17mm, F8, CCA H3.2 treated, structural plywood (not LOSP treated).
checkpoint-status |  |  | checkpoint | Minimum CD grade with the sanded C face upwards.
checkpoint-status |  |  | checkpoint | Plywood laid with face grain at right angles to supports.
checkpoint-status |  |  | checkpoint | Plywood is to be laid with staggered joints in a brick bond pattern with a 3mm expansion gap between plywood sheet edges.
checkpoint-status |  |  | checkpoint | Plywood is screw-fixed with 10g x 50mm SS counter-sunk screws at 150mm centres on all sheet edges and at 200mm centres through the body of the sheet. All screws to be counter sunk 1-2mm.
checkpoint-status |  |  | checkpoint | Chamfer all external edges with a minimum radius of 5mm.
label | 0eba1011-abf5-414c-95d2-dcd86e6c985b |  | note | *Plywood is to be kept dry at all times during construction. Blow/ torch drying the plywood surface prior to membrane application does not comply. Plywood and framing supports to be at no more than 18%moisture content.
checkpoint-status |  |  | checkpoint | For Roofs and Roof Decks over living spaces, all cavities must be ventilated and insulated in compliance with clause H1 NZBC. Cavity ventilation is not required for a Warm Roof system which meets or exceeds the minimum R value requirements.
checkpoint-status |  |  | checkpoint | All drains and outlets are membrane compatible.
label | 9483470c-64af-4c61-ba0c-9d4294af6851 |  | note | Note that TPO membranes cannot be welded to Stainless Steel scuppers or sumps. Accessories must have Clamped Grates or be TPO weldable.
checkpoint-status |  |  | checkpoint | Ensure minimum required falls are met. E2/AS1 2011 states 2° for roofs (-1:30 or 34mm/mt), 1.5° for decks (-1:40 or 25mm/mt) and 1:100 (10mm/mt) for internal gutters.
checkpoint-group |  |  | section | Roof QA
checkpoint-status |  |  | checkpoint | Fascia straight, cut in correctly
checkpoint-status |  |  | checkpoint | Spouting installed with correct falls & outlets as per plans
checkpoint-status |  |  | checkpoint | Underlay over fascia & trimmed neatly
checkpoint-status |  |  | checkpoint | Valleys straight
checkpoint-status |  |  | checkpoint | Screws installed correctly & washers intact
checkpoint-status |  |  | checkpoint | Roof clean from debris & swarf
checkpoint-status |  |  | checkpoint | Flashing junctions tidy & sealed correctly
checkpoint-status |  |  | checkpoint | Roof laid correctly & damage free
checkpoint-status |  |  | checkpoint | Site clean, rubbish in bin or removed
checklist-sectioned |  |  | checklist | H&S - Accident and Incident Full Report |  |  |  |  | Yes | H&S - Accident / Incident Full Report | 178b9447-4672-4098-ab6d-dceb2295c532
checkpoint-group |  |  | section | Employee to Complete
checkpoint-no-status |  |  | checkpoint | Information about the employee who had the incident
text | 791e5f8b-957a-4e5c-ae2a-dbea0994ad62 |  | textbox | Name
select | 41a7f6d6-9313-487b-8dcc-9b277dd4f16f |  | dropdown | Role | Client, Contractor, Visitor,Employee
text | 1e2fe6ca-d24d-465b-9e4e-c50a681f2481 |  | textbox | Job title (if employee
text | 1a039a8f-3f21-494a-b3ac-567764d019bb |  | textbox | Contact telephone
checkpoint-no-status |  |  | checkpoint | Information about the incident
select | a5d6bb9c-5e9f-49da-aa40-247c16a5cb77 |  | dropdown | Type of incident | Accident, Property Damage, Property Loss,Near Miss
text | 4be9c3ef-228e-4be2-b5ff-fcbadcab3c31 |  | textbox | When did the incident happen?
text | 768ccefc-717f-4f1b-911d-904dc970bc9f |  | textbox | Where did the incident happen?
text | c4587cb6-e9b5-49cd-b5f1-20cb1d1029e7 |  | textbox | What happened? (Include details of any object, machine or substance involved, or property lost or damaged.)
button | 4852316b-6944-45ef-b08a-4add1a45c98e |  | button | Was a known significant hazard involved? | No,Yes
text | 6bcea14e-258b-4b74-a51a-ec00162bc35f |  | textbox | If YES - what was the significant hazard?
checkpoint-no-status |  |  | checkpoint | Name(s) of any witnesses
text | 0fc0fb37-5796-43f2-9c05-dd3677ab0063 |  | textbox | Name and contact info
text | 28590cb0-b269-4805-b18e-9d3b80ad1d32 |  | textbox | Name and contact info
text | ea53a9a7-0719-4d58-9c11-a58ca89d006f |  | textbox | Name and contact info
text | 4301b38d-8a77-470f-8246-d945eaaa03ca |  | textbox | Name and contact info
text | 5066017b-a70d-42e5-961b-bf70d88eb09f |  | textbox | Name and contact info
checkpoint-no-status |  |  | checkpoint | What injury or injuries were sustained?
text | 9326d889-dc5e-4cd2-a9f4-35d1f8ea6c64 |  | textbox | Body part injured (plase indicate which side of the body e.g. right or left)
text | d9c2ca4b-4232-4322-be1e-415ed0b69e42 |  | textbox | Type of injury (e.g. break or sprain)
button | f3be42c8-2f9b-44f5-809e-43344b38b4aa |  | button | Is this a notifiable injury? | No,Yes
text | 22597bbe-e03e-4890-a68d-02ab6fddbb63 |  | textbox | If YES - Work Safe NZ
checkpoint-no-status |  |  | checkpoint | What trearment was given?
boolean | 501e09a6-a1ab-426d-96a1-743d129bacb3 |  | tickbox | First Aid
boolean | 823f018c-9c45-45e6-9208-8a2bfd1e1f12 |  | tickbox | Physiotherapy
boolean | d8135d84-9e2b-412d-84a6-e8e8998b05f4 |  | tickbox | Massage therapy
boolean | c6b1f7dd-bf20-43b1-96ff-642735cb341f |  | tickbox | Doctor (GP)
boolean | 29bb6b52-1a1c-42b7-9398-f288ce24fc18 |  | tickbox | Hospital
boolean | 06dc9c0d-5d57-4c45-b8c0-35d2a8f0a5b4 |  | tickbox | Emergency services
boolean | 3b5602b9-da77-48cf-baa5-b84994c2cc2f |  | tickbox | Other
checkpoint-status |  |  | checkpoint | The above report provides a true, accurate and complete account of the accident / incident / near miss
label | 6fd64a8c-5a03-4fd9-813e-d2a1ea1e1fad |  | note | Employee to Sign
checkpoint-group |  |  | section | Manager to Complete with Employee
checkpoint-no-status |  |  | checkpoint | Details
text | 42b74fe1-2e33-43bb-869c-80ff911b6249 |  | textbox | What (in your opinion) were the causal factors of this incident?
checkpoint-no-status |  |  | checkpoint | Hazard identification
button | 1e0b1dc2-a946-4360-84cf-228007cf2d0c |  | button | New Hazard Identified | No,Yes
button | e34e2ae5-fde4-4cd0-83c6-95609442b7a4 |  | button | Significant | No,Yes
label | 65447533-330f-45f1-ac14-9b11376e15aa |  | note | If YES identify the hazard management process to be done e.g. update hazard register and put in recommended actions below
checkpoint-no-status |  |  | checkpoint | Recommended Actions - Has the Hazard Management Process been undertaken
button | 81cebe0c-bc93-4278-bdbe-8c13afbcf0b8 |  | button |  | No,Yes
text | e2410cb2-0178-4ccb-a8de-52c46b875fa7 |  | textbox | What has been done?
text | ec792840-9bfe-49f6-8271-b1ed28400b2c |  | textbox | Person responsible for this?
text | bfbc08e2-8f7b-488e-b308-0d20f45563b4 |  | textbox | By when?
checkpoint-no-status |  |  | checkpoint | Recommended Actions - Is a review of Safety Management System required?
button | 99ab7927-c71f-4898-a1d0-67df21f24d19 |  | button |  | No,Yes
text | e792e9e7-bf45-4a64-b192-8729d6fdb682 |  | textbox | Which part?
text | 9688f557-0559-4387-b49d-9a1c60f306a8 |  | textbox | Person responsible for this?
text | 7437ff28-6a0b-494c-aef0-270caf445ec7 |  | textbox | By when?
checkpoint-no-status |  |  | checkpoint | Other recommended actions
text | c904865d-72e1-4704-b510-dcfb8d6a04e8 |  | textbox | Specific actions to prevent recurrence
text | b091d029-5f3c-486c-bea4-be8b9d8aa3c0 |  | textbox | Person responsible for this?
text | 0bec84c9-7e23-4da5-be40-46a881e42227 |  | textbox | By when?
text | 0e731c78-4c41-4127-9aff-2316ba5c5a81 |  | textbox | Specific actions to prevent recurrence
text | 170a60de-1873-4940-a769-ec3f02eec828 |  | textbox | Person responsible for this?
text | 5c05522e-5642-4c8b-a02f-1ebfeb6900b9 |  | textbox | By when?
checkpoint-status |  |  | checkpoint | All relevant staff members have received information regarding the incident, changes of operation / procedures.
text | 212333ca-0bcf-4192-ba6d-fa63f41df598 |  | textbox | Person responsible for this?
text | 31833c13-0eb9-4c4a-8b36-3ef052dd0967 |  | textbox | By when?
checkpoint-status |  |  | checkpoint | If a notifiable incident has ocurred, have WSNZ (as relevant) reporting procedures been followed.
checkpoint-status |  |  | checkpoint | Have internal reporting systems been followed?
label | 07adee93-1283-4cda-a38f-c936c1fe52ad |  | note | E.g. Toolbox, Close out
checkpoint-status |  |  | checkpoint | Has the incident been recorded on the Accident Database
checkpoint-no-status |  |  | checkpoint | Overall comments
label | 91d68b65-398e-47c4-87ce-38dd20981ac3 |  | note | E.g. Health and Safety review actions.
checkpoint-status |  |  | checkpoint | Manager Sign Off
label | c13838b3-7aaf-4883-bd80-6bad71839a26 |  | note | Manager to sign
checklist-sectioned |  |  | checklist | QA - Kingspan Roofing Checklist |  |  |  |  | Yes | QA - Kingspan Roofing Checklist | 1cd6841a-9708-4540-83db-cf5f330b0f48
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Edge protection/scaffold in place
holdpoint |  |  | signoff | Raise remedial / request review
checkpoint-status |  |  | checkpoint | Safety nets installed
holdpoint |  |  | signoff | Raise remedial / request review
checkpoint-status |  |  | checkpoint | Purlins/battens & all necessary timberwork complete
holdpoint |  |  | signoff | Raise remedial / request review
checkpoint-group |  |  | section | Kingspan Roof QA
checkpoint-status |  |  | checkpoint | Screws tight & washers intact
checkpoint-status |  |  | checkpoint | Roof clean of roofing debris
checkpoint-status |  |  | checkpoint | Roof clean of swarf. If FAIL, mark on plan areas of concern & include photos
checkpoint-status |  |  | checkpoint | Undamaged roofing sheet profile. If FAIL, mark on plan areas of concern & include photos
checkpoint-status |  |  | checkpoint | Scratches - mark on plan areas of concern & include photos
checkpoint-status |  |  | checkpoint | Roof laid in correct sequence
checkpoint-status |  |  | checkpoint | Flashing junctions sealed & tidy
checkpoint-status |  |  | checkpoint | Lap tape installed correctly
checklist-flat |  | checklist-flat must be display flat but was progress | checklist | Roof Logic SM Membrane System |  |  |  |  | Yes | New Template | 29346cd1-c7d2-4c59-831d-af20e63b36df
checkpoint-status |  |  | checkpoint | Base deck fixings installed
checkpoint-status |  |  | checkpoint | Vapour barrier completed
checkpoint-status |  |  | checkpoint | Polystyrene flute installed
checkpoint-status |  |  | checkpoint | LW compressed PIR fixed off as per manufacturers specifications
checkpoint-status |  |  | checkpoint | S/M Membrane installed, welded correctly & damage free
checkpoint-status |  |  | checkpoint | Penetrations with diverters complete
checkpoint-status |  |  | checkpoint | All flashings installed correctly, sealed & tidy
checkpoint-status |  |  | checkpoint | Internal gutters installed with outlets & overflows
checklist-sectioned |  |  | checklist | Site Inspection Checklist |  |  |  |  | Yes | H&S - Site Safety Inspection | 3a8e7806-8d9c-4a5e-a80b-03b5c3c8b193
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Details Complete
text | 8b03cbae-c408-4ae9-a756-cca7018dea83 |  | textbox | Site/Location :
text | 52914ecc-91b7-4603-9495-6a1e5ad3bd75 |  | textbox | Date
text | 8ff362f0-afb9-45ca-87d4-347265a7e11e |  | textbox | Name of Inspector :
checkpoint-group |  |  | section | Site Control
checkpoint-status |  |  | checkpoint | Hazard Board and signage up-to-date
checkpoint-status |  |  | checkpoint | Environmental plan - issues
text | cae0f94e-0878-4302-855f-50626b9940cc |  | textbox | Toolbox talk last date:
checkpoint-status |  |  | checkpoint | Safety inductions for all on-site
checkpoint-status |  |  | checkpoint | Safety notice board current
checkpoint-group |  |  | section | Site Facilities
checkpoint-status |  |  | checkpoint | Offices clean, adequate & good lighting
checkpoint-status |  |  | checkpoint | Smoko sheds - clean, portable water
checkpoint-status |  |  | checkpoint | Toilets - clean, washing water
checkpoint-status |  |  | checkpoint | Tool /equipment sheds adequate
checkpoint-group |  |  | section | General Site Tidiness and Access ways
checkpoint-status |  |  | checkpoint | Clear, safe access to work areas
checkpoint-status |  |  | checkpoint | Stairways and accessways clear
checkpoint-status |  |  | checkpoint | Hoardings /fence and gates secure
checkpoint-status |  |  | checkpoint | Loose materials secure from wind
checkpoint-group |  |  | section | Personal Safety Equipment
checkpoint-status |  |  | checkpoint | Signage displayed and legible
checkpoint-status |  |  | checkpoint | Hardhats being worn
checkpoint-status |  |  | checkpoint | Correct footwear being worn
checkpoint-status |  |  | checkpoint | Glasses /ear muffs /vests /masks used
checkpoint-group |  |  | section | First Aid/Fire Prevention
checkpoint-status |  |  | checkpoint | First Aid Box Available
checkpoint-status |  |  | checkpoint | Accident register
checkpoint-status |  |  | checkpoint | Fire Extinguishers
boolean | 12bab111-d5d2-4ba9-87f2-979c842a9df6 |  | tickbox | Available
boolean | 61ea2b23-6ac8-44f8-9d40-86c8daf1dd62 |  | tickbox | Current (12mth)
boolean | 3f3e012d-918a-4137-9689-dcced1049dcc |  | tickbox | Sufficient number
checkpoint-status |  |  | checkpoint | Evacuation
boolean | 7aa1d51b-82ee-46ea-a2d8-8922b951f5d1 |  | tickbox | Procedure current
boolean | 62e3bbb3-5108-4954-b02d-7071877274bd |  | tickbox | All emergencies incl
checkpoint-group |  |  | section | Cranes/hoist/lifting equipment
checkpoint-status |  |  | checkpoint | Proper lift assessment plan done
checkpoint-status |  |  | checkpoint | Crane certification current
checkpoint-status |  |  | checkpoint | Slings/chains certified
checkpoint-status |  |  | checkpoint | Operator procedures in place
checkpoint-status |  |  | checkpoint | Inspections being done
checkpoint-status |  |  | checkpoint | Man cage available
checkpoint-status |  |  | checkpoint | Emergency plan in place
checkpoint-group |  |  | section | Compressed air equipment
checkpoint-status |  |  | checkpoint | In good condition
checkpoint-status |  |  | checkpoint | Appropriate guards fitted
checkpoint-status |  |  | checkpoint | Trained user
checkpoint-group |  |  | section | Excavations
checkpoint-status |  |  | checkpoint | Correctly Shored
checkpoint-group |  |  | section | Welding/gas cutting
checkpoint-status |  |  | checkpoint | Hot work permits being issued
checkpoint-status |  |  | checkpoint | Fire extinguishers on hand
checkpoint-status |  |  | checkpoint | Operators using PPE
checkpoint-group |  |  | section | Electrical Equipment
checkpoint-status |  |  | checkpoint | Main board lockable /weatherproof
checkpoint-status |  |  | checkpoint | Current tagged and damage-free leads
checkpoint-status |  |  | checkpoint | Current tagged plant
checkpoint-status |  |  | checkpoint | Current tagged lifeguards
checkpoint-status |  |  | checkpoint | Leads safely placed
checkpoint-status |  |  | checkpoint | Equipment in good condition
checkpoint-status |  |  | checkpoint | Appropriate guards on equipment
checkpoint-status |  |  | checkpoint | Adequate temporary lighting
checkpoint-group |  |  | section | Chemicals
checkpoint-status |  |  | checkpoint | Correctly stored
checkpoint-status |  |  | checkpoint | Safety Data Sheet (SDS) available
checkpoint-status |  |  | checkpoint | Operators using PPE
checkpoint-group |  |  | section | Tools
checkpoint-status |  |  | checkpoint | PAT tool WoF current and secure
checkpoint-status |  |  | checkpoint | Staff trained in tool use (SWPS)
checkpoint-status |  |  | checkpoint | PAT signage on site
checkpoint-group |  |  | section | Scaffolding
checkpoint-status |  |  | checkpoint | Notifiable weekly Scaftag/current
checkpoint-status |  |  | checkpoint | Handrails/mid-rails
checkpoint-status |  |  | checkpoint | Toe boards
checkpoint-status |  |  | checkpoint | Platforms
checkpoint-status |  |  | checkpoint | Ladders/stairs
checkpoint-status |  |  | checkpoint | Base sound
checkpoint-status |  |  | checkpoint | Work platforms clear
checkpoint-status |  |  | checkpoint | Platforms trip free
checkpoint-status |  |  | checkpoint | Planks tied down
checkpoint-status |  |  | checkpoint | Headroom clear
checkpoint-status |  |  | checkpoint | Ties/bracing adequate
checkpoint-group |  |  | section | Ladders
checkpoint-status |  |  | checkpoint | Good condition
checkpoint-status |  |  | checkpoint | Secured top and bottom
checkpoint-status |  |  | checkpoint | Stays to step ladders
checkpoint-status |  |  | checkpoint | Working 2 steps down
checkpoint-group |  |  | section | Fall Hazards
checkpoint-status |  |  | checkpoint | Fall Hazards
checkpoint-status |  |  | checkpoint | Floor openings
checkpoint-status |  |  | checkpoint | Lift shafts
checkpoint-status |  |  | checkpoint | Stairs
checklist-flat |  |  | checklist | Flood Testing Record |  |  |  |  | Yes | Flood Test Record | 4eed1279-d9c5-46c1-a7c9-1db5a42149ae
checkpoint-no-status |  |  | checkpoint | Details
text | 79f8bac1-a316-4160-a763-d0e8bf330cc3 |  | textbox | Roof zone area
select | 49d519a0-43a1-4af5-aaab-5ef44cf1acf6 |  | dropdown | Time under testing | 48 hours, 72 hours,24 hours
checkpoint-status |  |  | checkpoint | Outcome of flood test
checkpoint-no-status |  |  | checkpoint | Roofing contractor's signature (use paperclip to sign on screen)
text | 2aecc4ae-bf85-4eb8-8529-0126292206d6 |  | textbox | Company
text | 45d1e654-8171-457e-9503-ae273f0e361c |  | textbox | Company rep
checkpoint-no-status |  |  | checkpoint | Main contractor's signature (use paperclip to sign on screen)
text | 093875ef-77da-4f5c-925e-823a0b66c2d0 |  | textbox | Company
text | c5660b8c-252e-41d0-9a3d-07fd8ef4b78a |  | textbox | Company rep
checklist-sectioned |  |  | checklist | Coloursteel with R2.6 Insulation Checklist |  |  |  |  | Yes | QA - Coloursteel with R2.6 Insulation Checklist | 5626ba06-dd62-4992-a198-b08c7893158e
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Edge protection/scaffold in place
checkpoint-status |  |  | checkpoint | Safety nets installed
checkpoint-status |  |  | checkpoint | Purlins/battens & all necessary timberwork complete
checkpoint-status |  |  | checkpoint | Other trades works damage free & protected
checkpoint-group |  |  | section | Roof QA
checkpoint-status |  |  | checkpoint | Safety mesh installed correctly
checkpoint-status |  |  | checkpoint | Covertex 407 installed correctly
checkpoint-status |  |  | checkpoint | 75mm Bayonet installed correctly
checkpoint-status |  |  | checkpoint | 140mm Insulation installed correctly
checkpoint-status |  |  | checkpoint | 20mm Cavity bat installed correctly
checkpoint-status |  |  | checkpoint | Screws installed correctly.
checkpoint-status |  |  | checkpoint | Roof clean from debris & swarf
checkpoint-status |  |  | checkpoint | Flashing junctions tidy & sealed correctly
checkpoint-status |  |  | checkpoint | Roof laid correctly & damage free
checkpoint-status |  |  | checkpoint | Site clean, rubbish in bin or removed
checklist-sectioned | 35a03af6-44ac-4e1b-8ee4-f5f9bc19f67d |  | checklist | Site Inspection Checklist |  |  |  |  | Yes | Z - SYS - Site Inspection Checklist v2 (old version) | 57265639-3248-4d2b-813d-ae8f491b7cd3
checkpoint-group | 26827fff-9040-438e-a58d-9c0dc3b7c688 |  | section | Details
checkpoint-status | 6e02537a-d559-4ecd-83a5-8144ac316c9e |  | checkpoint | Details Complete
text | 4d5266b2-521c-56c8-945a-a04c7fbfb6f2 |  | textbox | Site/Location :
text | e84e6aef-b6e9-5d97-b995-dc66732103e3 |  | textbox | Date
text | 9bc650f6-4d5f-50f1-92ec-aae41cb0df49 |  | textbox | Name of Inspector :
checkpoint-group | abe17431-aad6-484b-9ddf-19d7e89c6315 |  | section | Site Control
checkpoint-status | 29522473-303a-4df2-a1d7-771814af4c1e |  | checkpoint | Hazard Board and signage up-to-date
checkpoint-status | df9b0bf1-69c7-423c-8dd8-5be5d94e47c6 |  | checkpoint | Environmental plan - issues
text | c76d0e54-0f53-5dac-8662-577f0aecb19d |  | textbox | Toolbox talk last date:
checkpoint-status | 782def76-c82a-4933-86ee-f99b6246ec1c |  | checkpoint | Safety inductions for all on-site
checkpoint-status | 64f0b9ef-6e64-4ffc-abde-06b8e837c06b |  | checkpoint | Safety notice board current
checkpoint-group | cd255c20-37c0-4a10-b119-1c2ff8a8ca0c |  | section | Site Facilities
checkpoint-status | 4277f182-6134-4894-a432-72c2630a8540 |  | checkpoint | Offices clean, adequate & good lighting
checkpoint-status | 7344ee5b-6332-48ce-afa3-ac3a1deeab59 |  | checkpoint | Smoko sheds - clean, portable water
checkpoint-status | a9f93cab-51cf-45dd-93ea-1c4865ffc673 |  | checkpoint | Toilets - clean, washing water
checkpoint-status | b5de8d34-457b-4ce8-8c05-24c71a7c808d |  | checkpoint | Tool /equipment sheds adequate
checkpoint-group | 360240b0-656e-4c05-bb87-21bcb6e859a6 |  | section | General Site Tidiness and Access ways
checkpoint-status | 9a2e3328-d53b-4347-8e45-7df99346ac1b |  | checkpoint | Clear, safe access to work areas
checkpoint-status | 16dbe052-5778-49d0-990b-3e8e0142cf97 |  | checkpoint | Stairways and accessways clear
checkpoint-status | fa7c26d6-b3c1-49ae-b96e-8e3240016f8b |  | checkpoint | Hoardings /fence and gates secure
checkpoint-status | 26d41c3b-a39a-4022-aa08-15bfadef448a |  | checkpoint | Loose materials secure from wind
checkpoint-group | 5f507db4-519c-4547-bdfb-3aed3990c158 |  | section | Personal Safety Equipment
checkpoint-status | fbe0d763-67ea-4e9b-8e1e-8b8f6d50105a |  | checkpoint | Signage displayed and legible
checkpoint-status | 961de11f-7df4-49eb-9c3d-a6f416ef76a4 |  | checkpoint | Hardhats being worn
checkpoint-status | 257184d1-3183-4f46-8c07-20562dfaf384 |  | checkpoint | Correct footwear being worn
checkpoint-status | 8d1ea3b1-8d7d-42fc-be91-8669ff726e8a |  | checkpoint | Glasses /gloves /ear muffs /vests /masks used
checkpoint-group | 2c0f1d1f-e4fd-413f-842b-8be19d81ac69 |  | section | First Aid/Fire Prevention
checkpoint-status | f3ba15e6-5879-4230-b813-a8af341094dc |  | checkpoint | First Aid Box Available
checkpoint-status | 1ccea6fc-bf5f-4fdb-8415-f55caf59b98a |  | checkpoint | Accident register
checkpoint-status | d3745b63-e499-4a20-9cd6-5fc50d6eecf4 |  | checkpoint | Fire Extinguishers
boolean | da01bb76-7ea4-582c-af53-87df47beaa73 |  | tickbox | Available
boolean | 2dc3681c-7dc7-5314-a33c-d4865d1e0e29 |  | tickbox | Current (12mth)
boolean | 49d57763-6479-5390-8154-f561b3ae4e70 |  | tickbox | Sufficient number
checkpoint-status | a47bd686-5953-4fbd-80e1-114bd99a0115 |  | checkpoint | Evacuation
boolean | aef1f654-d7c4-5ab2-bbf8-9c7cd4100c7a |  | tickbox | Procedure current
boolean | 7d3ed84a-2e46-52dd-9915-e154d31c010b |  | tickbox | All emergencies incl
checkpoint-group | b41aee1d-1418-4534-aee3-87c6eed6a5af |  | section | Cranes/hoist/lifting equipment
checkpoint-status | 9f5c0620-036b-47a9-af77-8867050c9407 |  | checkpoint | Proper lift assessment plan done
checkpoint-status | add69983-afe3-4495-9da9-3fd4a4986791 |  | checkpoint | Crane certification current
checkpoint-status | 78d9830a-faa6-4906-961c-355c191014ee |  | checkpoint | Slings/chains certified
checkpoint-status | e42baffd-8e16-4eaa-a1fe-455e377be52e |  | checkpoint | Operator procedures in place
checkpoint-status | e465f3c4-7bbe-4ff0-9679-878a573e7d9a |  | checkpoint | Inspections being done
checkpoint-status | 1360f9eb-6527-4ace-b5d3-19dec68ef101 |  | checkpoint | Man cage available
checkpoint-status | 5cd7dc4c-7df4-4361-a3c5-dff463ba5a5a |  | checkpoint | Emergency plan in place
checkpoint-group | 02563d60-a7f8-47e8-a7f4-0077fa9a47b7 |  | section | Compressed air equipment
checkpoint-status | bf3f877c-2e7e-4bc1-8936-6fd09d1546d9 |  | checkpoint | In good condition
checkpoint-status | 92250c1e-c4af-4b97-b6e5-89b27cfd4f05 |  | checkpoint | Appropriate guards fitted
checkpoint-status | 14a7efb4-2095-475c-ac71-6880b3c8d535 |  | checkpoint | Trained user
checkpoint-group | 8b1c6754-e739-4614-8864-6e61f745f6c6 |  | section | Excavations
checkpoint-status | 5e74cf63-1a55-4a18-8b11-63c7b0ff0e7a |  | checkpoint | Correctly Shored
checkpoint-group | f505389a-76de-4c46-835a-55a10f72686a |  | section | Welding/gas cutting
checkpoint-status | 0fa2f92d-03bd-41f0-a3aa-ea0faec72df1 |  | checkpoint | Hot work permits being issued
checkpoint-status | 7af58984-45b1-4b30-b606-e7ff4780913e |  | checkpoint | Fire extinguishers on hand
checkpoint-status | c23335d7-8520-4a25-b3f8-31c049ef2ba2 |  | checkpoint | Operators using PPE
checkpoint-group | bbb5b712-47d9-4faa-a59b-fed5b5803446 |  | section | Electrical Equipment
checkpoint-status | 141b47c3-b365-43ff-a492-c1d0a11b8553 |  | checkpoint | Main board lockable /weatherproof
checkpoint-status | 540d482f-a874-4335-8aff-79287e7737d9 |  | checkpoint | Current tagged and damage-free leads
checkpoint-status | 44e9b6d9-a831-42d2-86b1-56740203186f |  | checkpoint | Current tagged plant
checkpoint-status | 68bc246f-2f71-4560-b748-926b46e28759 |  | checkpoint | Current tagged lifeguards
checkpoint-status | 1cf0600f-17b5-4fec-9676-490e62d5dbfd |  | checkpoint | Leads safely placed
checkpoint-status | f152cae2-34a7-4eca-85c2-34d00b544216 |  | checkpoint | Equipment in good condition
checkpoint-status | 85ce7d7d-97b9-4e2a-a073-daefe34b4ca4 |  | checkpoint | Appropriate guards on equipment
checkpoint-status | f75359cf-f588-487a-8135-805ad731dbfc |  | checkpoint | Adequate temporary lighting
checkpoint-group | f91fa162-bf03-4b08-8690-5fa1d12b8d92 |  | section | Chemicals
checkpoint-status | d24de88a-5ade-470c-acea-864f0aad84f3 |  | checkpoint | Correctly stored
checkpoint-status | b0ee7f27-7daf-4b37-9a9a-beef77c79a95 |  | checkpoint | Safety Data Sheet (SDS) available
checkpoint-status | 92b9e131-5f08-42e2-947d-0be94a1c935c |  | checkpoint | Operators using PPE
checkpoint-group | a64d8c61-fb69-4765-90d3-16ac6babcb14 |  | section | Tools
checkpoint-status | d985a7e5-83a4-45bd-bb97-c327fe842450 |  | checkpoint | PAT tool WoF current and secure
checkpoint-status | ed704bee-3080-47f2-a40f-dc3cffda44a8 |  | checkpoint | Staff trained in tool use (SWPS)
checkpoint-status | 43333359-462d-467f-aca4-4a969b7f8821 |  | checkpoint | PAT signage on site
checkpoint-group | c7d2b1a4-88a1-49b3-be7f-7169a5514b3b |  | section | Scaffolding
checkpoint-status | fac06da7-98da-497a-8456-747fba0532ca |  | checkpoint | Notifiable weekly Scaftag/current
checkpoint-status | f026fc4c-d910-4e5c-92f0-5de784c2667b |  | checkpoint | Handrails/mid-rails
checkpoint-status | 3c1b1791-109a-4fcc-891f-7b6c76c2a6ea |  | checkpoint | Toe boards
checkpoint-status | 088d5823-6001-4020-93b3-e50727a9e476 |  | checkpoint | Platforms
checkpoint-status | 57ee5eda-9c39-4811-84a2-cf71b8a4330f |  | checkpoint | Ladders/stairs
checkpoint-status | be0cb189-28c8-4256-9246-2450d9d7d341 |  | checkpoint | Base sound
checkpoint-status | 0bca0531-be8b-4402-832c-bb8c26e89276 |  | checkpoint | Work platforms clear
checkpoint-status | e6f6ea9f-3e37-456b-9d4b-ab4668c8f688 |  | checkpoint | Platforms trip free
checkpoint-status | d0859be9-f852-4b0d-8303-92f4c3006117 |  | checkpoint | Planks tied down
checkpoint-status | f1c44f6c-425c-44a5-aac6-36a96d215456 |  | checkpoint | Headroom clear
checkpoint-status | 0c1a5079-d020-49ee-b02b-e7c8c7750518 |  | checkpoint | Ties/bracing adequate
checkpoint-group | c3fc41b6-894d-406d-aebf-316830454381 |  | section | Ladders
checkpoint-status | 04320c4e-0ba4-4d14-b4ac-a390fa59caff |  | checkpoint | Good condition
checkpoint-status | 92889c9f-d5b7-4718-a7b6-49588101e50a |  | checkpoint | Secured top and bottom
checkpoint-status | 3150434d-73cb-4a77-abe2-b284bc269bb6 |  | checkpoint | Stays to step ladders
checkpoint-status | 7d250d57-15ea-48a5-a3a2-9cb886c3b2d2 |  | checkpoint | Working 2 steps down
checkpoint-group | 72fcfea6-15ab-46e2-a46e-6b2498b5964f |  | section | Fall Hazards
checkpoint-status | 584930ac-77a1-4b89-bddd-a474196b867e |  | checkpoint | Fall Hazards
checkpoint-status | 1b5064f8-e9e2-4ba6-8f25-8d85c06cddfe |  | checkpoint | Floor openings
checkpoint-status | b0147b50-a968-4e2e-8ffc-1e44db63b138 |  | checkpoint | Lift shafts
checkpoint-status | 6274c5b1-cfcb-45dd-91e2-a017e181c323 |  | checkpoint | Stairs
checklist-sectioned |  |  | checklist | Rooflogic UltraTherm Xtreme Roofing System with Fibretite Membrane |  |  |  |  | Yes | QA - Rooflogic UltraTherm Xtreme Roofing System with Fibretite Membrane | 5809f145-0504-4f3a-aaea-d00ba557cd56
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Area accessible
holdpoint |  |  | signoff | Raise remedial / request review
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
holdpoint |  |  | signoff | Raise remedial / request review
checkpoint-status |  |  | checkpoint | Substrate acceptable (clean, dry and stable)
holdpoint |  |  | signoff | Raise remedial / request review
checkpoint-group |  |  | section | Surface Preparation
checkpoint-status |  |  | checkpoint | All purlins are in place
holdpoint |  |  | signoff | Raise remedial / request review
checkpoint-status |  |  | checkpoint | Under flashings installed
holdpoint |  |  | signoff | Raise remedial / request review
checkpoint-status |  |  | checkpoint | Sheets in good condition for roof installation
holdpoint |  |  | signoff | Raise remedial / request review
checkpoint-group |  |  | section | RL Base Deck
checkpoint-status |  |  | checkpoint | Installed in accordance with specification
checkpoint-status |  |  | checkpoint | Installed in accordance with project specific and Rooflogic standard details
checkpoint-status |  |  | checkpoint | Correct fasteners used and installed with correct frequency (i.e. 1 fastener per trough along every purlin line
checkpoint-group |  |  | section | Vapour Control Layer
checkpoint-status |  |  | checkpoint | Vapour Control Layer installed to top face of acoustic board
checkpoint-status |  |  | checkpoint | Correct side laps (80mm) and end laps (100mm)
checkpoint-status |  |  | checkpoint | Vapour Control Layer to be installed in accordance with project details. Ensure Vapour Control Layer is correctly terminated to ensure vapour control continuity at roof openings, transitions and at horizontal to vertical roof/cladding junctions
checkpoint-status |  |  | checkpoint | Any damage to vapour control layer repaired to ensure vapour control layer 100% continuous.
checkpoint-group |  |  | section | Install RL PIR Board and RL Roof Board HD
checkpoint-status |  |  | checkpoint | RL PIR Board insulation to be installed continuously over vapour control layer to roof and gutter in accordance with architectural drawings
checkpoint-status |  |  | checkpoint | Any damaged insulation board to be cut out and replaced with new, tightly butted piece of PIR Board (minimum 300mm x 300mm piece.)
checkpoint-status |  |  | checkpoint | PIR insulation to be dry prior to application of RL Roof Board and Fibertite membrane.
checkpoint-status |  |  | checkpoint | Roof Board HD to be installed over PIR Board and mechanically attached to the substrate. Fasteners to be installed in accordance with the prescribed fixing pattern.
checkpoint-group |  |  | section | Adhering Fibertite Membrane
checkpoint-status |  |  | checkpoint | Install Fibertite membrane in strict accordance with Project Specification.
checkpoint-status |  |  | checkpoint | Ensure substrate (e.g. Roof Board) is dry and free from dirt, debris or contamination.
checkpoint-status |  |  | checkpoint | Select adhesive as specified
button | e8bb6c91-7e88-4eed-9140-a258ac5743eb |  | button |  | 190E, 490U, 690U,490E
checkpoint-status |  |  | checkpoint | Adhesive applied as per specification -Ref specification cl .3.13 in project specification
checkpoint-status |  |  | checkpoint | Take into account ambient air temperatures and humidity levels
checkpoint-group |  |  | section | Welding Fibertite Membrane
checkpoint-status |  |  | checkpoint | Test welds carried out daily with hand-held welders
checkpoint-status |  |  | checkpoint | Test welds carried out when commencing and re-commencing welding with robotic welder (e.g. start of day, after break.)
checkpoint-status |  |  | checkpoint | Seams to be welded clear of dirt, debris, moisture and adhesive residues.
checkpoint-status |  |  | checkpoint | Seams wiped clean (both surfaces to be welded) with Acetone and clean, white cotton rag
checkpoint-status |  |  | checkpoint | Hand and Robotic welding to be carried out by trained personnel familiar with equipment and membrane
checkpoint-status |  |  | checkpoint | Daily inspections of all completed work by way of seam probing to ensure all welds are secure, fully closed and watertight
checkpoint-status |  |  | checkpoint | Any welding deficiencies rectified on the same day they are seam probed
checkpoint-status |  |  | checkpoint | Night joints are installed daily, as required, to ensure that no moisture is allowed to migrate under the installed membrane.
checkpoint-group |  |  | section | Final Inspection
checkpoint-status |  |  | checkpoint | System installation is complete
checkpoint-status |  |  | checkpoint | All membrane terminated with either thermoplastic weld or mechanical clamp/termination (drain clamps with no missing bolts)
checkpoint-status |  |  | checkpoint | No exposed membrane terminations that could allow water behind
checkpoint-status |  |  | checkpoint | All terminations (details in accordance with project specific and standard RL construction plans and detail drawings.
checkpoint-status |  |  | checkpoint | Any damage to system and/or membrane have been recorded/ rectified
checkpoint-status |  |  | checkpoint | All construction equipment and materials removed from roof/site.
checkpoint-status |  |  | checkpoint | Maintenance Documents submitted to Main Contractor/Building Owner
checklist-flat |  |  | checklist | Notice of Delay/Damage |  |  |  |  | Yes | Add Delay / Damage | 5ea6c43e-a057-4f7b-931b-294fb30a2492
checkpoint-no-status |  |  | checkpoint | Notice of Delay/Damage
text | 04d652de-4dce-46c0-a1ef-3432b444bcae |  | textbox | Reference Point
text | e72120d4-51ec-451b-856c-a513bf3b3c98 |  | textbox | Description
holdpoint |  |  | signoff | Request Review / Send for Acknowledgement
checkpoint-no-status |  |  | checkpoint | Delay/Damage Acknowledged
button | 967ee202-a218-46c4-98c8-b6d773c666b2 |  | button |  | No,Yes
checklist-flat | 4d199656-dbc0-4fab-b028-62acda593d1d |  | checklist | QA - Ultratherm Warm Wall Checklist |  |  |  |  | Yes | QA - Ultratherm Warm Wall Checklist | 68b2676a-9b87-4bde-8bee-c3a7d1b13a6a
checkpoint-status | b142e0cf-07e8-402e-9bec-2a92a2230e1d |  | checkpoint | VCL in place
checkpoint-status | cf86784f-7ac4-4343-9112-dda7e581e052 |  | checkpoint | PIR in place and tapped as per specifications
checkpoint-status | bf59ec85-6be3-4edb-8199-2c68bfea3ad7 |  | checkpoint | Rhom rails installed and fixed of as per specifications
checkpoint-status | 0207dbe5-cd31-489b-9709-2d1eefa37da5 |  | checkpoint | Cladding installed and damage free
checkpoint-status | cd1960ac-3010-48c1-b918-c3a9fe24a650 |  | checkpoint | Flashings installed as per detail
checkpoint-status | da8ba13f-5e6b-4dfb-8183-52049d84a982 |  | checkpoint | Area clean from debris and swarf
checklist-sectioned |  |  | checklist | Rooflogic UltraTherm MSR Roofing System |  |  |  |  | Yes | QA - Rooflogic UltraTherm MSR Roofing System | 776adb81-3a17-4a21-b324-b3c91b7a2ff7
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Area accessible
holdpoint |  |  | signoff | Raise remedial / request review
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
holdpoint |  |  | signoff | Raise remedial / request review
checkpoint-status |  |  | checkpoint | Substrate acceptable (clean, dry and stable)
holdpoint |  |  | signoff | Raise remedial / request review
checkpoint-group |  |  | section | Surface Preparation
checkpoint-status |  |  | checkpoint | All purlins are in place
holdpoint |  |  | signoff | Raise remedial / request review
checkpoint-status |  |  | checkpoint | Under flashings installed
holdpoint |  |  | signoff | Raise remedial / request review
checkpoint-status |  |  | checkpoint | Sheets in good condition for roof installation
holdpoint |  |  | signoff | Raise remedial / request review
checkpoint-group |  |  | section | RL Base Deck
checkpoint-status |  |  | checkpoint | Installed in accordance with specification
checkpoint-status |  |  | checkpoint | Installed in accordance with project specific and Rooflogic standard details
checkpoint-status |  |  | checkpoint | Correct fasteners used and installed with correct frequency (i.e. 1 fastener per trough along every purlin line
checkpoint-group |  |  | section | Vapour Control Layer
checkpoint-status |  |  | checkpoint | Vapour Control Layer installed to top face of acoustic board
checkpoint-status |  |  | checkpoint | Correct side laps (80mm) and end laps (100mm)
checkpoint-status |  |  | checkpoint | Vapour Control Layer to be installed in accordance with project details. Ensure Vapour Control Layer is correctly terminated to ensure vapour control continuity at roof openings, transitions and at horizontal to vertical roof/cladding junctions
checkpoint-status |  |  | checkpoint | Any damage to vapour control layer repaired to ensure vapour control layer 100% continuous.
checkpoint-group |  |  | section | RL Acoustic Board, PIR Board and FRU 36 Underlay
checkpoint-status |  |  | checkpoint | Acoustic Board installed over Vapour Barrier and mechanically attached to the substrate
checkpoint-status |  |  | checkpoint | Correct thickness input
checkpoint-status |  |  | checkpoint | Any damaged insulation board has been cut out and replaced with new tightly butted piece of acoustic board (minimum 300mm x 300mm piece.)
checkpoint-status |  |  | checkpoint | RL PIR Board insulation to be installed continuously over vapour control layer to roof and gutter in accordance with architectural drawings
checkpoint-status |  |  | checkpoint | Any damaged insulation board to be cut out and replaced with new, tightly butted piece of PIR Board (minimum 300mm x 300mm piece.)
checkpoint-status |  |  | checkpoint | Install Dristud FRU 36 underlay with 150mm side laps and, if required, 200mm end laps
label | b20eaa7c-3595-4fe9-90c1-0a4ed29d1e8d |  | note | NB. The underlay can be installed in line with the fall of the roof and there is no requirement to install safety netting beneath the underlay or use a self-supporting grade underlay. The underlay is fully supported by the high density rigid insulation layers and will not sag or deflect either during application or over the life of the system.
checkpoint-group |  |  | section | Top Deck
checkpoint-status |  |  | checkpoint | Visually inspect material delivered to site. Confirm all delivered materials correspond with order and specification.
checkpoint-status |  |  | checkpoint | Fix according to specified fixing pattern to achieve required wind uplift resistance
checkpoint-status |  |  | checkpoint | Correct fixings/profiled washer assembly used.
checkpoint-status |  |  | checkpoint | Allowance for thermal expansion when fixing sheets
checkpoint-status |  |  | checkpoint | Sheet set out square
checkpoint-status |  |  | checkpoint | Sheet length as required to achieve specified gutter overhang
checkpoint-status |  |  | checkpoint | Stop-ends and turn-downs to sheets
checkpoint-group |  |  | section | Final Inspection
checkpoint-status |  |  | checkpoint | System installation is complete
checkpoint-status |  |  | checkpoint | Installation of fixings in accordance with specification and appropriate wind zone
checkpoint-status |  |  | checkpoint | All flashing details in accordance with specifications, plans and details with correct type and spacing of fixings and placement of seals and sealants
checkpoint-status |  |  | checkpoint | All construction equipment and materials removed from roof/site
checkpoint-status |  |  | checkpoint | Any damage to top skin or associated flashings rectified by repair or replacement
checkpoint-status |  |  | checkpoint | Debris, sward and other contamination cleared/removed from roof
checkpoint-status |  |  | checkpoint | Maintenance Documents submitted to Main Contractor/Building Owner
checklist-sectioned |  |  | checklist | Ardex Butynol |  |  |  |  | Yes | QA - Ardex Butynol | 7a35b872-1e8d-45e8-afb1-0af8bc419380
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Area Accessible
checkpoint-status |  |  | checkpoint | Substrate must be dry with max 18% moisture content
checkpoint-status |  |  | checkpoint | Sheeting laid staggered joints (brick bond), the edge of sheet supported with framing.
checkpoint-status |  |  | checkpoint | Plywood fix S/S screw countersunk with a 3mm gap between all sheets, 150mm centre on edges & 200mm in the body.
checkpoint-status |  |  | checkpoint | All joints of plywood and junctions with other materials covered with 25mm release
checkpoint-group |  |  | section | Roof QA
checkpoint-status |  |  | checkpoint | Installed so that laps facing down
checkpoint-status |  |  | checkpoint | Correct adhesive used as per spec
checkpoint-status |  |  | checkpoint | Membrane fully adhered to plywood
checkpoint-status |  |  | checkpoint | Adhesive evenly spread
checkpoint-status |  |  | checkpoint | Overlaps at lease 50mm
checkpoint-status |  |  | checkpoint | Seam tape and seam primer used
checkpoint-status |  |  | checkpoint | All lap, penetrations and details fully closed and tested.
checklist-flat |  |  | checklist | Roof Report |  |  |  |  | Yes | Add Roof Report | 8e56ebb3-4fe1-4c60-892b-c4f5048cc8c4
checkpoint-no-status |  |  | checkpoint | Details
text | 932f2e55-8701-599b-b68a-67ab1db52096 |  | textbox | Reviewed By
text | 359c3721-c6d9-5c38-ae50-7d1f6966fa5e |  | textbox | Address
checkpoint-status |  |  | checkpoint | Building Age/Specs/documents
text | 582282c4-de1a-5b2a-8f00-9c0991816d1a |  | textbox | Type of roof
text | 95b006b8-c809-5140-848c-6369eec550db |  | textbox | m2
text | 00e1028e-c042-5619-8805-71af284e12d3 |  | textbox | Purlin/Material/Spacing
checkpoint-status |  |  | checkpoint | Flashings and Gutters
checkpoint-status |  |  | checkpoint | Services
checkpoint-status |  |  | checkpoint | Observations
text | 7f7b13e1-0f1e-5672-a9db-90b7c199313b |  | textbox | Expectancy
text | 2c2dcbb1-ef45-559e-93f3-bce76bef67cb |  | textbox | Recommendations
text | f27d0bdb-1411-5be0-909d-81fe3d341078 |  | textbox | Estimate
checklist-sectioned |  |  | checklist | Nu Wall |  |  |  |  | Yes | QA - Nu Wall | 8e77a0c0-1d76-4772-8f46-57fca2d4dee7
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Substrate - Inspected and Straight
checkpoint-status |  |  | checkpoint | Single Castellated Batten 600mm Centres
checkpoint-status |  |  | checkpoint | Separation Barrier Installed
checkpoint-status |  |  | checkpoint | Windows Installed and Set 18 - 20mm out from Batten
checkpoint-group |  |  | section | Cladding QA
checkpoint-status |  |  | checkpoint | Head flashing Installed Taped and Stop ended
checkpoint-status |  |  | checkpoint | Window / Door/ Base Flashing Screwed at 300mm Centres
checkpoint-status |  |  | checkpoint | Window / Door Foam Tape Installed
checkpoint-status |  |  | checkpoint | Plastic Soakers Installed Around Window / Door Jams
checkpoint-status |  |  | checkpoint | Cladding Brackets Installed evry 600mm
checkpoint-status |  |  | checkpoint | Cladding Free from Damage / Scratches
checkpoint-status |  |  | checkpoint | Site Clean - Rubbish Removed
checklist-flat |  |  | checklist | H&S - Incident / Accident for Register |  |  |  |  | Yes | H&S - Accident / Incident for Register | a27f8f3d-fd93-402b-9ec3-6979691100c6
checkpoint-no-status |  |  | checkpoint | Details
text | 098452e5-d069-46c0-9d11-e48ded44de74 |  | textbox | Date & time
text | f5d6221a-be29-43db-a76e-0efc3eec0267 |  | textbox | Name of Person
text | 62a7bbfc-a5af-4304-ba34-7a52c3ec97db |  | textbox | Description of accident/near miss
text | 2444d92f-38da-4398-ad89-99abc0fad85c |  | textbox | Cause of harm (if any)
text | cef7fdd5-daf8-49a0-a8f8-5d54ce8cdb32 |  | textbox | Type of injury or disease
checkpoint-no-status |  |  | checkpoint | Immediate Action Taken
boolean | a2e32397-02b6-4ea1-ad92-7e9e8878df67 |  | tickbox | First Aid
boolean | 9a06d84e-495e-4b0e-8948-3c3a5d81f8c2 |  | tickbox | Corrective Action
boolean | dd7f796e-ca8c-4720-af5c-4b37c017e71c |  | tickbox | Review Risk Register
checkpoint-no-status |  |  | checkpoint | Does the incident require Work Safe notification
boolean | 47fe41ce-f1b2-41e2-9c77-c88a32e125f3 |  | tickbox | Yes
checkpoint-no-status |  |  | checkpoint | Is the incident the subject of a Toolbox Talk
boolean | b084278b-7f60-4812-9b0f-9242cb2f8eab |  | tickbox | Yes
checkpoint-status |  |  | checkpoint | Signed Off
checklist-sectioned |  |  | checklist | Coloursteel Cladding |  |  |  |  | Yes | QA - Coloursteel Cladding Checklist | a627e0b0-e3e9-42c2-869c-5f4b4734332a
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Edge protection/scaffold in place
holdpoint |  |  | signoff | Raise remedial / request review
checkpoint-status |  |  | checkpoint | Safety nets installed
holdpoint |  |  | signoff | Raise remedial / request review
checkpoint-status |  |  | checkpoint | Purlins/battens & all necessary timberwork complete
holdpoint |  |  | signoff | Raise remedial / request review
checkpoint-group |  |  | section | Substrate Checklist : Enviroclad Plywood
checkpoint-status |  |  | checkpoint | Framing supports at 400mm centres (in one direction). All plywood edges must also be supported.
label | a071e9e8-2fb8-47c3-8ab3-facf1f1adfc2 |  | note | Do not use tongue and groove plywood. Viking Roofspec can accept the maximum support spacings provided in Table 15C of CHH Ecoply Specification Guide.
checkpoint-status |  |  | checkpoint | Minimum thickness 17mm, F8, CCA H3.2 treated, structural plywood (not LOSP treated).
checkpoint-status |  |  | checkpoint | Minimum CD grade with the sanded C face upwards.
checkpoint-status |  |  | checkpoint | Plywood laid with face grain at right angles to supports.
checkpoint-status |  |  | checkpoint | Plywood is to be laid with staggered joints in a brick bond pattern with a 3mm expansion gap between plywood sheet edges.
checkpoint-status |  |  | checkpoint | Plywood is screw-fixed with 10g x 50mm SS counter-sunk screws at 150mm centres on all sheet edges and at 200mm centres through the body of the sheet. All screws to be counter sunk 1-2mm.
checkpoint-status |  |  | checkpoint | Chamfer all external edges with a minimum radius of 5mm.
label | 86ef0ee6-cd4e-49f6-b30c-4a3d5b5c5ac1 |  | note | *Plywood is to be kept dry at all times during construction. Blow/ torch drying the plywood surface prior to membrane application does not comply. Plywood and framing supports to be at no more than 18%moisture content.
checkpoint-status |  |  | checkpoint | For Roofs and Roof Decks over living spaces, all cavities must be ventilated and insulated in compliance with clause H1 NZBC. Cavity ventilation is not required for a Warm Roof system which meets or exceeds the minimum R value requirements.
checkpoint-status |  |  | checkpoint | All drains and outlets are membrane compatible.
label | 555f09ff-90cd-47eb-9fc4-39069aea55d0 |  | note | Note that TPO membranes cannot be welded to Stainless Steel scuppers or sumps. Accessories must have Clamped Grates or be TPO weldable.
checkpoint-status |  |  | checkpoint | Ensure minimum required falls are met. E2/AS1 2011 states 2° for roofs (-1:30 or 34mm/mt), 1.5° for decks (-1:40 or 25mm/mt) and 1:100 (10mm/mt) for internal gutters.
checkpoint-group |  |  | section | Wall Cladding QA
checkpoint-status |  |  | checkpoint | Base flashing installed & taped with correct fall
checkpoint-status |  |  | checkpoint | Cladding installed correct sequence
checkpoint-status |  |  | checkpoint | Screws uniform & intact
checkpoint-status |  |  | checkpoint | Foam installed where required
checkpoint-status |  |  | checkpoint | Flashing junctions cut correctly & uniformed - as rev details
checkpoint-status |  |  | checkpoint | Cladding clean & damage free
checkpoint-status |  |  | checkpoint | Site clean, rubbish in bin or removed
checklist-sectioned |  |  | checklist | Toolbox Checklist |  |  |  |  | Yes | H&S - Toolbox Talk | a705e632-f186-4bb3-b937-ff2d24a76b33
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Details Complete
text | 305f2185-4e3a-4417-ae95-885bb0b1de8a |  | textbox | Office location:
text | b2fd07dc-8f92-4010-8a71-46e71c03ff63 |  | textbox | Who is running this meeting:
text | 1d3d0b15-a56a-498c-b16b-2afa5f8e2573 |  | textbox | Company
text | 88e78785-0eea-4ad8-a896-1622379eacfc |  | textbox | Agenda items:
text | ce0224f5-54b8-47a5-b890-7a5416c69623 |  | textbox | Theme of the week (topic for focus):
checkpoint-group |  |  | section | Health and safety issues
checkpoint-status |  |  | checkpoint | 1.
text | 2ec0fc9e-b14f-43a5-bb60-4df5d5ab3ab4 |  | textbox | Issues raised from site safety inspection:
text | 1b5fcc97-f30c-4727-a783-29c22206fa41 |  | textbox | Actions:
text | b5107b7c-d991-4507-a1a9-6180db10057c |  | textbox | By who and when:
checkpoint-status |  |  | checkpoint | 2.
text | 8978adff-e266-4646-b125-178fba33a0dd |  | textbox | Issues outstanding from previous briefings:
text | 507afe6b-4ee7-4485-bd4b-99698d8e8f47 |  | textbox | Actions:
text | 7d92f59d-ce24-4ec9-8428-a92c87f559e3 |  | textbox | By who and when:
checkpoint-status |  |  | checkpoint | 3.
text | 305b3039-3f3d-45b4-8536-fb028ee2010b |  | textbox | Employee-raised issues:
text | c98f50a5-1fb4-45b7-86e0-301132ec8b7c |  | textbox | Actions:
text | c250b53e-5070-459c-b01f-af8fcce5cdb7 |  | textbox | By who and when:
checkpoint-status |  |  | checkpoint | 4.
text | 26f6b1aa-3048-4106-a64b-dc4e2cf75ec3 |  | textbox | Positive safe-action observations:
text | dd2ab926-5b94-46f6-a93f-eed5fa00233e |  | textbox | Actions:
text | 464cc30b-c155-4299-b08c-242a1821bd72 |  | textbox | By who and when:
checkpoint-status |  |  | checkpoint | 5.
text | ba0166ff-1cef-49fe-a54e-fce60528feea |  | textbox | Incidents or injuries:
text | 8f9035d5-30e5-4ea2-9ec4-4d19df05b3fd |  | textbox | Actions:
text | 1a84fee3-7466-42bd-a3ff-39c2785201a3 |  | textbox | By who and when:
checkpoint-group |  |  | section | Job plans reviewed
checkpoint-status |  |  | checkpoint | Job/Task & Action/Outcome
text | cb9c1ca7-7b79-4c62-8f74-3a1d70af5886 |  | textbox | 1.
text | d396585a-1ce3-4d1e-b838-375ab4165dd0 |  | textbox | 2.
text | 4657beed-8141-41c2-926d-0d7204a497a2 |  | textbox | 3.
text | 1e162112-08ad-40c3-9d33-6c4bac52a906 |  | textbox | 4.
text | fd629f21-4050-47b3-b236-26daf8c94903 |  | textbox | 5.
text | a08ea05c-aa58-425b-9cb6-e2fa8951a414 |  | textbox | 6.
checkpoint-group |  |  | section | Operational issues
checkpoint-status |  |  | checkpoint | Issue & Action
text | 301f9ad4-6682-45c0-aa57-7b074b0e8a13 |  | textbox | 1.
text | 1373bee6-816f-408a-97a0-72f99b461b6e |  | textbox | 2.
text | c487e999-fa82-493c-b540-e056d94778fb |  | textbox | 3.
text | 5341a99d-52f8-4c86-8e11-6e8adfb0627e |  | textbox | 4.
text | 8e55092c-df52-43d0-b019-a8e67550ae09 |  | textbox | 5.
text | b87136a8-71c4-41f7-9cdb-74d4b55b5521 |  | textbox | 6.
checkpoint-group |  |  | section | Other business
checkpoint-status |  |  | checkpoint | Item & Action
text | 2e63def1-4462-4998-b972-d5125960181e |  | textbox | 1.
text | 044404a1-6065-4d33-8f96-7da9ab2eaf3a |  | textbox | 2.
text | 1e321545-4537-44dd-9443-3ae2c58d572b |  | textbox | 3.
text | e3214f18-5e4b-42bf-856b-435adffda167 |  | textbox | 4.
checkpoint-group |  |  | section | Attendees
checkpoint-status |  |  | checkpoint | Add name and Photo of attendees
checkpoint-group |  |  | section | Review by management
checkpoint-status |  |  | checkpoint | Reviewed and signed off
text | 054479d9-523d-4c50-88ce-626d6600059d |  | textbox | 1.
text | e1ea14ce-04e9-4c55-b0e6-131f75ee169d |  | textbox | 2.
checklist-flat |  |  | checklist | Roof Logic SM Membrane System |  |  |  |  | Yes | QA - Roof Logic SM Membrane System | a713ca87-6202-4668-9e08-f5548c899c9c
checkpoint-status |  |  | checkpoint | Base deck fixings installed
checkpoint-status |  |  | checkpoint | Vapour barrier completed
checkpoint-status |  |  | checkpoint | Polystyrene flute installed
checkpoint-status |  |  | checkpoint | LW compressed PIR fixed off as per manufacturers specifications
checkpoint-status |  |  | checkpoint | S/M Membrane installed, welded correctly & damage free
checkpoint-status |  |  | checkpoint | Penetrations with diverters complete
checkpoint-status |  |  | checkpoint | All flashings installed correctly, sealed & tidy
checkpoint-status |  |  | checkpoint | Internal gutters installed with outlets & overflows
checklist-sectioned |  |  | checklist | Ardex Plywood Substrates |  |  |  |  | Yes | QA - Ardex Plywood Substrates | b36c1b21-e2b2-441c-8beb-184419edb470
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Edge protection/scaffold in place
checkpoint-status |  |  | checkpoint | Safety nets installed
checkpoint-status |  |  | checkpoint | Purlins/battens & all necessary timberwork complete
checkpoint-status |  |  | checkpoint | Other trades works damage free & protected
checkpoint-group |  |  | section | Roof QA
checkpoint-status |  |  | checkpoint | A minimum of 17mm complying with AS/NZS 2269. CD Structural Grade plywood with the sanded C face upwards, and H3 with Waterborne treatment
checkpoint-status |  |  | checkpoint | Substrates must be dry when an ARDEX waterproofing membrane is applied. The plywood and the timber substructure shall have a maximum moisture content of 18% when an ARDEX waterproofing membrane is adhered
checkpoint-status |  |  | checkpoint | Plywood panels shall be laid with staggered joints (brick bond), the edge of sheets shall be supported with dwangs or framing
checkpoint-status |  |  | checkpoint | Plywood shall be laid with the face grain at right angles to the supports. A 20mm triangular fillet shall be used at the base of any 90° upstand. External edges shall be chamfered with a minimum radius of 5mm
checkpoint-status |  |  | checkpoint | Plywood shall be fixed with 10 gauge x 50mm stainless steel countersunk head screws with 3mm gaps between all sheets, at 150mm centres on edges, and 200mm in the body of the sheets
checkpoint-status |  |  | checkpoint | All joints in the plywood and junctions of plywood with other materials must have a 25mm release tape applied before application of the membrane
checkpoint-status |  |  | checkpoint | Framing supports at a maximum 400mm centres (in one direction). All plywood edges must also be supported. Do not use tongue and groove plywood. If thicker plywood is to be used support spacing needs tomeet NZBC and NZS3064, or engineer specific design
checkpoint-status |  |  | checkpoint | Clarify for how long the plywood has been exposed?
checkpoint-status |  |  | checkpoint | Minimum17mmF8 CCA H3.2 treated structural plywood (not LOSP treated).
checkpoint-status |  |  | checkpoint | Minimum CD grade with the sanded C face upwards
checkpoint-status |  |  | checkpoint | Minimum required falls are met , Correct falls to outlets
checkpoint-status |  |  | checkpoint | Plywood laid with face grain at right angles to supports
checkpoint-status |  |  | checkpoint | Plywood is to be laid with staggered joints in a brick bond pattern with a 3mm expansion gap between plywood sheet edges. Bond breaker tape to be applied to all plywood sheet joints prior to membrane application
checkpoint-status |  |  | checkpoint | All outlets and overflows fitted and rebated into the substrate
checkpoint-status |  |  | checkpoint | Plywood is screwed with 10g x 50mm SS counter sunk screws at 150mmcentres on all sheet edges and at 200mm centres through the body of the sheet. All screws to be counter sunk 1-2mm
checkpoint-status |  |  | checkpoint | Provide 20mmtimber fillets at the base of all upstands
checkpoint-status |  |  | checkpoint | Chamfer all external edges with aminimumradius of 5mm
checkpoint-status |  |  | checkpoint | Plywood is to be kept dry at all times during construction. Blow/ torch drying the plywood surface prior to membrane application does not comply. Plywood and framing supports to be at no more than 18% moisturecontent
checkpoint-status |  |  | checkpoint | All drains and outlets aremembrane compatible
checkpoint-status |  |  | checkpoint | Has the installer accepted the condition of the plywood?
checkpoint-status |  |  | checkpoint | Please ensure you have clearly ordered the correctmembrane, colour and thickness for your project
checklist-sectioned | b5e732a0-f135-4682-8223-b416199c1469 |  | checklist | Site Inspection Checklist |  |  |  |  | Yes | Site Inspection Checklist | b711badf-4e7e-44c6-8436-6ed594f1fbd3
checkpoint-group | aa81f6ee-bda2-4b32-bdb4-31b489cd5634 |  | section | Site Control
checkpoint-status | 97df6cb9-bfb4-4ebf-895b-22a643c8b98e |  | checkpoint | Hazard Board and signage up-to-date
checkpoint-status | 0b24be56-2aba-439d-b06d-2a2ad0c098f4 |  | checkpoint | Environmental plan - issues
text | 8def6e38-4e1c-5fd1-a0fe-056d60857e3c |  | textbox | Toolbox talk last date:
checkpoint-status | 62641f87-6ab9-4d38-82e1-5fe42b000df9 |  | checkpoint | Safety inductions for all on-site
checkpoint-status | 81032e78-3776-462e-9ae7-336acf3ab520 |  | checkpoint | Safety notice board current
checkpoint-status | f329e2bb-710b-47e4-b454-75819868082b |  | checkpoint | Task Analysis up to date
checkpoint-status | b290df86-b18a-4d88-9963-13046439a22c |  | checkpoint | Procedures in Task Analysis being followed
checkpoint-group | b1278753-fb10-457d-bbcf-db59a2e5ca66 |  | section | Site Facilities
checkpoint-status | 6f6c08d2-fabd-4f39-8b2b-2e3286e61e6e |  | checkpoint | Offices clean, adequate & good lighting
checkpoint-status | 5a6859f4-88e9-4f08-9b66-5422350374da |  | checkpoint | Smoko sheds - clean, portable water
checkpoint-status | 33c8137b-ada0-40d7-9834-50bfa2de4871 |  | checkpoint | Toilets - clean, washing water
checkpoint-status | e30f0144-946b-47b7-acd4-4f1c21b0df44 |  | checkpoint | Tool /equipment sheds adequate
checkpoint-group | b4136884-425b-458d-b53e-85a074f43bd8 |  | section | General Site Tidiness and Access ways
checkpoint-status | 546241b3-1c2b-48a8-84fe-fd6bf04ae448 |  | checkpoint | Clear, safe access to work areas
checkpoint-status | 42d14c4c-a60c-49e8-a3be-e94fea482eb5 |  | checkpoint | Stairways and accessways clear
checkpoint-status | 864ebb1d-740e-40cd-835c-cfd1b643a81f |  | checkpoint | Hoardings /fence and gates secure
checkpoint-status | 76a3b5e8-9d45-4e19-8c22-647fafda8f0e |  | checkpoint | Loose materials secure from wind
checkpoint-group | df94d5a5-0753-4acc-b2e2-b1c76234e559 |  | section | Notice of Delay/Damage
checkpoint-status | 8fa841ae-c61e-42e2-80ab-ccf3914702fd |  | checkpoint | Notice of Delay/Damage
text | 4a677907-a9ad-51de-9768-8733fdb95af8 |  | textbox | Reference Point
text | 3e969485-6523-5ed0-9072-db60556becce |  | textbox | Description
holdpoint | 2a998332-bade-43b2-94c6-2076fc4ebeff |  | signoff | Request Review / Send for Acknowledgement
checkpoint-status | 30539131-abd5-456a-9b7e-7f1f0680e08a |  | checkpoint | Delay/Damage Acknowledged
checkpoint-group | 08ef6855-1200-4e95-b414-429285e5238b |  | section | Personal Safety Equipment
checkpoint-status | e568f535-dabc-444e-9e02-19177a3c19b4 |  | checkpoint | Signage displayed and legible
checkpoint-status | 46c19569-dba9-4603-b6d0-cfd8040028f4 |  | checkpoint | Hardhats being worn
checkpoint-status | 3cba52aa-7711-4af9-84e7-b3a08b3fcaf0 |  | checkpoint | Correct footwear being worn
checkpoint-status | 8a2ef709-eb28-4a97-9cbf-5e9993b251d2 |  | checkpoint | Glasses /gloves /ear muffs /vests /masks used
checkpoint-group | 71602ab5-848e-4240-9a9a-ac299f5506bb |  | section | First Aid/Fire Prevention
checkpoint-status | a297ba7f-61ce-4049-8b72-982f0d2da079 |  | checkpoint | First Aid Box Available
checkpoint-status | e4e39659-efa0-4c38-8b6d-3a5d88d75f87 |  | checkpoint | Accident register
checkpoint-status | a1eed727-ad02-425a-bb49-1d49e657acee |  | checkpoint | Fire Extinguishers
boolean | fa10bfbe-fcac-5c9d-9b92-f6e3e64b2dad |  | tickbox | Available
boolean | 9c8f9ebc-0552-5c3c-9dc8-77946e8c54ea |  | tickbox | Current (12mth)
boolean | 2f1f140c-bf4b-555c-a57a-484b03862f56 |  | tickbox | Sufficient number
checkpoint-status | e34469e1-195b-49b5-bf3b-e4f481efabf1 |  | checkpoint | Evacuation
boolean | 4b80b8c9-f6ca-5e86-ba6a-7a6bcfa887f4 |  | tickbox | Procedure current
boolean | 7ea1e22e-50b0-57e6-abff-ee205f499467 |  | tickbox | All emergencies incl
checkpoint-group | 23f6d4cd-98b1-47eb-9709-7f1769021c23 |  | section | Cranes/hoist/lifting equipment
checkpoint-status | 76a9cec2-52ac-4a87-8e3f-e520087d1240 |  | checkpoint | Proper lift assessment plan done
checkpoint-status | 21eadbc1-d763-4cee-a49b-cb27888cc658 |  | checkpoint | Crane certification current
checkpoint-status | 3cf8f245-2296-45e6-8597-17480f5cdfb9 |  | checkpoint | Slings/chains certified
checkpoint-status | 4d4fafd4-c326-4b15-9fe5-4c1ba5d598ad |  | checkpoint | Operator procedures in place
checkpoint-status | 53e4f715-dc73-4c75-a532-4451d43882b9 |  | checkpoint | Inspections being done
checkpoint-status | 4e815bc5-1a0f-4fba-a426-bea8ed498652 |  | checkpoint | Man cage available
checkpoint-status | 2f125b34-3d95-4537-8b81-a1a79a69aa10 |  | checkpoint | Emergency plan in place
checkpoint-group | accc38b6-486e-4189-86d8-ec6aeab0e40d |  | section | Compressed air equipment
checkpoint-status | 591b9cdd-7760-4b23-ac2f-32375e5ecbd6 |  | checkpoint | In good condition
checkpoint-status | ea6bc7b6-0756-4b65-9b41-d082ef318300 |  | checkpoint | Appropriate guards fitted
checkpoint-status | 25e06add-9983-43a2-b828-1d4fc092d6a0 |  | checkpoint | Trained user
checkpoint-group | b36f5157-8a06-4724-b95c-e2e4e8b9dd1a |  | section | Excavations
checkpoint-status | 7387d7c0-cd6b-4739-954c-f25b2acd43cc |  | checkpoint | Correctly Shored
checkpoint-group | 690910ec-c01d-4189-ac1c-1e12560ecc96 |  | section | Hot Works
checkpoint-status | aa147aa1-82d9-44c8-b8c9-0acd34a49bd1 |  | checkpoint | Hot work permits being issued
checkpoint-status | fddc82d4-9711-4e79-8ad3-bf1160469679 |  | checkpoint | Fire extinguishers on hand
checkpoint-status | b31d74ae-df72-4f2b-acb1-49717d781887 |  | checkpoint | Operators using PPE
checkpoint-group | 2fe24de0-1732-4659-a212-1df493218578 |  | section | Electrical Equipment
checkpoint-status | a5ca588c-6da9-4e0c-930e-e8739e29b0cb |  | checkpoint | Main board lockable /weatherproof
checkpoint-status | 51dee71a-373a-4f6d-9232-a0417b9e631a |  | checkpoint | Current tagged and damage-free leads
checkpoint-status | ededd0ad-5c1f-4cce-82ed-09cbdbbaac81 |  | checkpoint | Current tagged plant
checkpoint-status | 94c12133-7b2f-4848-81b8-85644f953b23 |  | checkpoint | Current tagged lifeguards
checkpoint-status | 074c323b-2638-4887-944d-07e4fe5471cd |  | checkpoint | Leads safely placed
checkpoint-status | 5d2e1b2e-37a2-4562-bea1-92b7296b7c02 |  | checkpoint | Equipment in good condition
checkpoint-status | 0e2f5204-806a-4d5d-a21f-99617f4af8a2 |  | checkpoint | Appropriate guards on equipment
checkpoint-status | 6edec0f2-f597-481c-a579-7809218bfbc0 |  | checkpoint | Adequate temporary lighting
checkpoint-group | a50c381a-daa8-4e34-8e35-e27901db2b7c |  | section | Chemicals
checkpoint-status | 66dea392-cb97-43fc-a094-12f98b625a13 |  | checkpoint | Correctly stored
checkpoint-status | 93a45ff5-ad98-4e69-8183-0fcc9c3d9dc3 |  | checkpoint | Safety Data Sheet (SDS) available
checkpoint-status | bffa0cc1-a776-4429-831d-0cbf55e05a9f |  | checkpoint | Operators using PPE
checkpoint-group | e3f91d15-b1a9-44d2-b3df-c7798f2944d7 |  | section | Tools
checkpoint-status | ded68003-fb8b-4dc5-8b07-cb13ced2c1ae |  | checkpoint | PAT tool WoF current and secure
checkpoint-status | 26a71084-aaee-4566-8788-1c2e698ff8e8 |  | checkpoint | Staff trained in tool use (SWPS)
checkpoint-status | 3eed4551-298f-461c-bbac-ccf6e9218501 |  | checkpoint | PAT signage on site
checkpoint-group | f9f614d5-3b8c-458d-a8b7-dc7fa2f8f494 |  | section | Scaffolding
checkpoint-status | 6ccd4c89-f10a-4bbb-a2ca-cfaf03988db2 |  | checkpoint | Notifiable weekly Scaftag/current
checkpoint-status | 66b0efb7-95e5-4153-8efd-959033fe5d63 |  | checkpoint | Handrails/mid-rails
checkpoint-status | b06f12bf-cf6f-4904-8308-616e0c8558bc |  | checkpoint | Toe boards
checkpoint-status | c7eb89fe-09f4-4ccc-a8a9-111495f18aa4 |  | checkpoint | Platforms
checkpoint-status | 1ecf1129-89e1-463f-8286-e372589971f4 |  | checkpoint | Ladders/stairs
checkpoint-status | c319f095-cb97-48e7-af5b-80a338f4a609 |  | checkpoint | Base sound
checkpoint-status | e557d6d9-1d4f-4228-85fc-23cfa911c73b |  | checkpoint | Work platforms clear
checkpoint-status | 0cc06d87-a7f5-418d-a169-9c6c5c26937c |  | checkpoint | Platforms trip free
checkpoint-status | aa2c26eb-2071-4efe-83b3-efc07d24bb9c |  | checkpoint | Planks tied down
checkpoint-status | 321784d2-5681-4f07-a0f5-87483a07ffc4 |  | checkpoint | Headroom clear
checkpoint-status | cd2bfc09-f908-4178-80b1-454613f1dc38 |  | checkpoint | Ties/bracing adequate
checkpoint-group | cb072eff-6e87-40d0-a153-619ad71bcaa9 |  | section | Ladders
checkpoint-status | 218eed4c-7bba-492e-99ea-6e971e259a00 |  | checkpoint | Good condition
checkpoint-status | a9736243-067c-45a1-a0ae-4a58f23eb061 |  | checkpoint | Secured top and bottom
checkpoint-status | 1f3bf8fb-84ae-4669-9fda-0ef1c5a7d579 |  | checkpoint | Stays to step ladders
checkpoint-status | 8c2a329b-c071-4f60-b2cf-043cf2266880 |  | checkpoint | Working 2 steps down
checkpoint-group | ad640667-864b-4e82-b3b1-f582a5072501 |  | section | Fall Hazards
checkpoint-status | c091033b-057f-4929-873a-e7ba93f5a0c6 |  | checkpoint | Fall Hazards
checkpoint-status | b703eb4b-f873-4392-a26f-9c33290fd969 |  | checkpoint | Floor openings
checkpoint-status | 3b9edf0e-e284-416c-b0e3-d3089bb9c60b |  | checkpoint | Lift shafts
checkpoint-status | a864e2df-020d-4978-b45f-9f7b6eb5f502 |  | checkpoint | Stairs
checklist-sectioned |  |  | checklist | QA - Hilton Roof Sheeting Checklist |  |  |  |  | Yes | QA - Hilton Roof Sheeting Checklist | be3637b2-782c-4d4f-b9d5-eb733fbe7315
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Edge protection/scaffold in place
holdpoint |  |  | signoff | Raise remedial / request review
checkpoint-status |  |  | checkpoint | Safety nets installed
holdpoint |  |  | signoff | Raise remedial / request review
checkpoint-status |  |  | checkpoint | Purlins/battens & all necessary timberwork complete
holdpoint |  |  | signoff | Raise remedial / request review
checkpoint-group |  |  | section | Checklist : Roof Sheeting
checkpoint-status |  |  | checkpoint | Safety mesh installed correctly
checkpoint-status |  |  | checkpoint | Vapour barrier installed correctly
checkpoint-status |  |  | checkpoint | Timber batten with ventilation holes installed correctly
checkpoint-status |  |  | checkpoint | 50mm Insulation installed correctly
checkpoint-status |  |  | checkpoint | 75mm Bayonet installed correctly
checkpoint-status |  |  | checkpoint | Covertex 407 installed correctly
checkpoint-status |  |  | checkpoint | Fascia straight, cut in correctly
checkpoint-status |  |  | checkpoint | Spouting installed with correct falls & outlets as per plans
checkpoint-status |  |  | checkpoint | Underlay over fascia & trimmed neatly
checkpoint-status |  |  | checkpoint | Valleys straight
checkpoint-status |  |  | checkpoint | Screws installed correctly & washers intact
checkpoint-status |  |  | checkpoint | Roof clean from debris & swarf
checkpoint-status |  |  | checkpoint | Flashing junctions tidy & sealed correctly
checkpoint-status |  |  | checkpoint | Roof laid correctly & damage free
checkpoint-status |  |  | checkpoint | Site clean, rubbish in bin or removed
checklist-flat |  |  | checklist | Task Analysis |  |  |  |  | Yes | H&S - Task Analysis 2 | c862012a-0c50-4b99-9c79-5a9b7fb84a2b
checkpoint-status |  |  | checkpoint | Details complete
boolean | eb71c109-9a20-4ae7-b8d1-19109cb0a034 |  | tickbox | This Task Analysis has an Emergency response plan
text | f2b8228c-8f2c-45b6-9393-ed1be6d34c96 |  | textbox | Subcontractor company name
text | eb289dfe-932a-4e1d-b91a-363eafcc0e7a |  | textbox | Name of subcontractor
text | faec460a-1259-4930-ae50-66236d2b804a |  | textbox | Phone
text | 6a1c8faf-98b1-4000-b7ac-18cb1fc8134c |  | textbox | Office address
text | cc3ecea4-1ce0-4639-8200-3462c98859d8 |  | textbox | Site name
text | 039ddf60-e679-4b78-b1ca-78fbed32bb34 |  | textbox | Site address
text | 4909f21d-5fa1-45c5-ba0d-27fca4415c8e |  | textbox | Work activity - task description
text | 101728fa-9191-4945-890e-5ee43c3514bb |  | textbox | PPE required for activity/task
text | 3f0de631-dada-4bb9-9ddc-09f59c096e14 |  | textbox | Administrative controls
checkpoint-status |  |  | checkpoint | Step / task described
text | 07c6232f-5b45-499b-94df-218ab973c4a3 |  | textbox | Step /task
checkpoint-status |  |  | checkpoint | Key Hazard A
text | 22c6c94d-7347-4c9d-ac1a-026ec8b5d20b |  | textbox | Describe Key Hazard
select | 531c7b87-7f96-4637-a265-4a0d0c14c133 |  | dropdown | Initial risk assessment of hazard | 2 Low, 3 Moderate, 4 High, 5 Critical,1 Very Low
text | a2ad000b-464d-499e-9db7-92747aac8184 |  | textbox | 1 Describe the key/significant ways to control the risk and then refer to the hierarchy of controls
select | 239ca2e2-3512-4c65-be0e-7a0635273442 |  | dropdown | 1 Level of control | 2 Substitute, 3 Isolate, 4 Use engineering controls, 5 Use administrative controls, 6 Use PPE,1 Eliminate
text | 2a14c19c-75b1-43db-98a5-3d1b8d940949 |  | textbox | 2 Describe the key/significant ways to control the risk and then refer to the hierarchy of controls
select | d88c4c1c-10dd-431e-af2e-85b425fb6988 |  | dropdown | 2 Level of control | 2 Substitute, 3 Isolate, 4 Use engineering controls, 5 Use administrative controls, 6 Use PPE,1 Eliminate
text | 602113e0-736d-4b03-b444-3866b631ae00 |  | textbox | 3 Describe the key/significant ways to control the risk and then refer to the hierarchy of controls
select | 831a5e04-1554-471d-9646-78dfaeda27b8 |  | dropdown | 3 Level of control | 2 Substitute, 3 Isolate, 4 Use engineering controls, 5 Use administrative controls, 6 Use PPE,1 Eliminate
select | d9748011-4d19-4d5c-835d-fd947555cc66 |  | dropdown | Residual risk assessment. After all controls are in place. Refer to the risk assessment matrix. | 2 Low, 3 Moderate, 4 High, 5 Critical,1 Very Low
checkpoint-status |  |  | checkpoint | Key Hazard B
text | ce7b999b-5231-4273-9770-ae6a0d626c53 |  | textbox | Describe Key Hazard
select | bdbb39a0-4842-4e5a-839e-dc22debe0a7a |  | dropdown | Initial risk assessment of hazard | 2 Low, 3 Moderate, 4 High, 5 Critical,1 Very Low
text | a2f7ae43-01f8-47a5-a930-c69302dc0a6b |  | textbox | 1 Describe the key/significant ways to control the risk and then refer to the hierarchy of controls
select | d5ff7b67-969d-4696-a1c5-5aaa6e23b76d |  | dropdown | 1 Level of control | 2 Substitute, 3 Isolate, 4 Use engineering controls, 5 Use administrative controls, 6 Use PPE,1 Eliminate
text | 0c7678fa-0bd4-4d9e-bcb8-8bc9797aea52 |  | textbox | 2 Describe the key/significant ways to control the risk and then refer to the hierarchy of controls
select | ef3a48e0-8e6e-4400-9b9d-569d93c8ea67 |  | dropdown | 2 Level of control | 2 Substitute, 3 Isolate, 4 Use engineering controls, 5 Use administrative controls, 6 Use PPE,1 Eliminate
text | 975694b4-0282-4949-b15c-36344a06a966 |  | textbox | 3 Describe the key/significant ways to control the risk and then refer to the hierarchy of controls
select | 152b0ef1-b09f-4d4f-92a6-6df2dfab2145 |  | dropdown | 3 Level of control | 2 Substitute, 3 Isolate, 4 Use engineering controls, 5 Use administrative controls, 6 Use PPE,1 Eliminate
select | c5f5f07e-a99d-4367-8226-7be86ad1a1c2 |  | dropdown | Residual risk assessment. After all controls are in place. Refer to the risk assessment matrix. | 2 Low, 3 Moderate, 4 High, 5 Critical,1 Very Low
checkpoint-status |  |  | checkpoint | Key Hazard C
text | d572342f-18d7-4494-b8ec-3171040e811d |  | textbox | Describe Key Hazard
select | 1d12667d-3d7b-43a2-9e1d-d9d4fb7c0c94 |  | dropdown | Initial risk assessment of hazard | 2 Low, 3 Moderate, 4 High, 5 Critical,1 Very Low
text | 68b75b9b-d79f-4744-b8de-7b7e70a9ca52 |  | textbox | 1 Describe the key/significant ways to control the risk and then refer to the hierarchy of controls
select | 5ee52853-292e-4d12-949b-d52dbea25158 |  | dropdown | 1 Level of control | 2 Substitute, 3 Isolate, 4 Use engineering controls, 5 Use administrative controls, 6 Use PPE,1 Eliminate
text | ce8c39a0-a0b8-4d08-9cdf-0e6a7ca0bf59 |  | textbox | 2 Describe the key/significant ways to control the risk and then refer to the hierarchy of controls
select | e8e5ceb7-18b6-49c7-a78e-8b3a2ce851e4 |  | dropdown | 2 Level of control | 2 Substitute, 3 Isolate, 4 Use engineering controls, 5 Use administrative controls, 6 Use PPE,1 Eliminate
text | 9c726ff0-76a3-49e1-bd8b-193d91cbd570 |  | textbox | 3 Describe the key/significant ways to control the risk and then refer to the hierarchy of controls
select | cb7ab87b-8dc1-4803-8ba8-9cb2a0b9b312 |  | dropdown | 3 Level of control | 2 Substitute, 3 Isolate, 4 Use engineering controls, 5 Use administrative controls, 6 Use PPE,1 Eliminate
select | 2284d894-081c-4faf-ba70-cb4e8937bf7c |  | dropdown | Residual risk assessment. After all controls are in place. Refer to the risk assessment matrix. | 2 Low, 3 Moderate, 4 High, 5 Critical,1 Very Low
checkpoint-status |  |  | checkpoint | Key Hazard D
text | 17f23899-fddd-4109-b6ae-624f07e2b03b |  | textbox | Describe Key Hazard
select | cd9b0748-1944-4be6-af52-0ca62ca4b761 |  | dropdown | Initial risk assessment of hazard | 2 Low, 3 Moderate, 4 High, 5 Critical,1 Very Low
text | a9c92dd3-e74b-4220-a65c-6ecf177ef6fe |  | textbox | 1 Describe the key/significant ways to control the risk and then refer to the hierarchy of controls
select | c440c18f-9a26-4e4c-9468-cb6d85024308 |  | dropdown | 1 Level of control | 2 Substitute, 3 Isolate, 4 Use engineering controls, 5 Use administrative controls, 6 Use PPE,1 Eliminate
text | e7e51864-adff-4672-8501-3e0189a98d96 |  | textbox | 2 Describe the key/significant ways to control the risk and then refer to the hierarchy of controls
select | 3402bc8e-7cff-4d71-b242-7f9bf36d5cb1 |  | dropdown | 2 Level of control | 2 Substitute, 3 Isolate, 4 Use engineering controls, 5 Use administrative controls, 6 Use PPE,1 Eliminate
text | b66a368c-4803-4c20-9238-55dcaad543ab |  | textbox | 3 Describe the key/significant ways to control the risk and then refer to the hierarchy of controls
select | 45759f15-9cb7-42f8-b687-31dae86cb245 |  | dropdown | 3 Level of control | 2 Substitute, 3 Isolate, 4 Use engineering controls, 5 Use administrative controls, 6 Use PPE,1 Eliminate
checkpoint-status |  |  | checkpoint | All workers signed on to register to show that they have been trained in the processes and will work to the requirements of this TA/SWMS.
label | 901b3ad5-97f7-46f9-a3d2-7777e2464cd6 |  | note | Sign on by using the Sign On Screen feature on Conqa
checklist-flat |  |  | checklist | Variation Details - |  |  |  |  | Yes | Add Variation | ccb9b7d6-4209-437e-abdc-77a0896860db
checkpoint-status |  |  | checkpoint | Variation Details Approved
text | 28d26279-c304-4689-8317-1deb797dc8fe |  | textbox | Reference/Drawing/Instruction Number
text | 2247155b-6de8-434c-a1e1-058d724a6a62 |  | textbox | Variation Area
text | ae7fc046-dca9-4fab-98f8-374caeb044ec |  | textbox | Materials & labour breakdown
holdpoint |  | Invalid dependant | signoff | Request Variation Acknowledgement
checkpoint-status |  |  | checkpoint | Variation Completed
holdpoint |  | Invalid dependant | signoff | Request Variation Signoff
checklist-flat | f1f663ed-7fc7-4e13-a91f-9e56eafcd3a6 |  | checklist | Ultratherm Xtreme Derbigum membrane system |  |  |  |  | Yes | QA - Ultratherm Xtreme Derbigum membrane system | cd414371-509a-436e-8d7b-1785547678c4
checkpoint-status | 0d4bdfc9-2364-4c69-81e3-579de60ca73e |  | checkpoint | Substrate
checkpoint-status | b17a0c8f-7fa8-418d-bd30-cd699eeb128d |  | checkpoint | RL Base sheet Liner deck
checkpoint-status | 0dbb605a-2eb3-45e5-a65e-9283d07b2558 |  | checkpoint | Fixings
checkpoint-status | f8ddf59e-8d18-42e7-bee6-516d17537f7b |  | checkpoint | Vapour Control Layer
checkpoint-status | b7638123-9de4-4743-ba41-2e3e29dc7b80 |  | checkpoint | PIR Board
checkpoint-status | 653bd473-69c9-43f0-a5b7-2bb12f93f879 |  | checkpoint | Securock installed correctly
checkpoint-status | 1283bde1-e837-4a76-ba47-1641bac4c7e8 |  | checkpoint | Fixings to specification
checkpoint-status | 7a8e0128-26ab-469d-8934-d6b174a2ca86 |  | checkpoint | Primer is used with correct application sequences
checkpoint-status | 94c9e922-b216-472b-b38f-17320326c089 |  | checkpoint | Leak Detection installed correctly
checkpoint-status | 2d65c57d-0d47-4b25-b80b-c158fd550299 |  | checkpoint | RL Derbicoat HP base sheet (fully adhered)
checkpoint-status | d115f14e-65e5-4d3a-b908-a414225fe922 |  | checkpoint | RL Derbicolour FR Cap sheet
checkpoint-status | 7cf082c1-f134-4365-8a92-a632d34c1e22 |  | checkpoint | Penetrations
checkpoint-status | 94e9412a-2733-44e7-8fe8-7e409044448e |  | checkpoint | QA (laps, damages, trade interuptions, repairs)
holdpoint | 1b4a1b81-5c3a-422b-aab0-e09cccfe966f |  | signoff | Sign off
checklist-sectioned |  |  | checklist | Enviroclad |  |  |  |  | Yes | QA - Enviroclad | d40f55f5-da16-4c34-a407-61e4a9b8996e
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Framing support at max 400mm. All plywood edges supported
checkpoint-status |  |  | checkpoint | Plywood laid with face grain at right angles to support
checkpoint-status |  |  | checkpoint | Plywood screwed with S/S counter sunk screws at 150mm centres on all sheet edges and 200mm through body
checkpoint-status |  |  | checkpoint | Chamfer all external edges with a minimum radius 5mm
checkpoint-status |  |  | checkpoint | Substrate must be dry with max 18% moisture content
checkpoint-status |  |  | checkpoint | All drains and outleds are membrane complatible
checkpoint-group |  |  | section | Cladding QA
checkpoint-status |  |  | checkpoint | Installed so that laps facing down
checkpoint-status |  |  | checkpoint | Correct adhesive used as per spec
checkpoint-status |  |  | checkpoint | Membrane fully adhered to plywood
checkpoint-status |  |  | checkpoint | Adhesive evenly spread
checkpoint-status |  |  | checkpoint | Install adjoining sheets in the same manner, overlapping edges a minimum of 50mm to provide for a minimum 40mm hot air weld
checkpoint-status |  |  | checkpoint | All lap, penetrations and details fully closed and tested
checklist-sectioned | 66f7a32b-22a6-4a4b-9e5d-1759e56ae599 |  | checklist | Site Inspection Checklist |  |  |  |  | Yes | Z - SYS - Site Inspection Checklist (old version) | d717254a-86df-4355-8d6c-608a052d3297
checkpoint-group | c0ff30fc-5007-4a5e-ad82-85417510a22e |  | section | Site Control
checkpoint-status | b0e51779-aea5-4770-b6a2-166bd34cd879 |  | checkpoint | Hazard Board and signage up-to-date
checkpoint-status | f14c7657-426c-44de-b753-5610a6bab882 |  | checkpoint | Environmental plan - issues
text | b4f98a99-1c4f-5e04-80e5-8749ab4b3317 |  | textbox | Toolbox talk last date:
checkpoint-status | b45d307a-81ce-4bef-9f7a-eb5993d49324 |  | checkpoint | Safety inductions for all on-site
checkpoint-status | ffe74285-c284-4238-84f4-ce3b3cf4d1bc |  | checkpoint | Safety notice board current
checkpoint-group | 84801aa5-095a-4a3a-9669-6231df5589ee |  | section | Site Facilities
checkpoint-status | 347061e7-1f94-4957-b62f-859bc3e4a9db |  | checkpoint | Offices clean, adequate & good lighting
checkpoint-status | 3764eacf-acec-4299-a0ff-d480bd778c73 |  | checkpoint | Smoko sheds - clean, portable water
checkpoint-status | 032637ba-200c-4a30-b752-64baaa8d6545 |  | checkpoint | Toilets - clean, washing water
checkpoint-status | bc0f3e33-8703-44fe-baef-9dad2aeefc78 |  | checkpoint | Tool /equipment sheds adequate
checkpoint-group | 0546ac16-ff08-4dc0-b7d4-0221eb74d684 |  | section | General Site Tidiness and Access ways
checkpoint-status | 498df4c0-a7af-4fa8-ac76-11a884a44bde |  | checkpoint | Clear, safe access to work areas
checkpoint-status | 06d3baa1-02a8-45bd-b603-e83ed25a012e |  | checkpoint | Stairways and accessways clear
checkpoint-status | 6f826955-ee24-4035-8609-e82adbc56f96 |  | checkpoint | Hoardings /fence and gates secure
checkpoint-status | 31b635bc-be51-4bbf-892f-968d12e2a996 |  | checkpoint | Loose materials secure from wind
checkpoint-group | db04840f-a04b-4781-8121-6910bf91ff2b |  | section | Notice of Delay/Damage
checkpoint-status | 3340c20f-005e-4915-9997-7c577c5d2fe9 |  | checkpoint | Notice of Delay/Damage
text | b8a052ba-fc5b-5aa8-aab5-fa53fe675942 |  | textbox | Reference Point
text | faf1e34a-d74e-5cbb-bd68-a81f4dacc0f6 |  | textbox | Description
holdpoint | 0c28f234-61ff-416c-ae7e-0dbd7f102ba6 |  | signoff | Request Review / Send for Acknowledgement
checkpoint-status | c2dfa433-d7d2-45ca-afae-257baba6b670 |  | checkpoint | Delay/Damage Acknowledged
checkpoint-group | 900a343a-9fc7-45e8-b297-2391a9646bf4 |  | section | Personal Safety Equipment
checkpoint-status | fccb35d5-df1a-4161-a18c-c729fa1a52a4 |  | checkpoint | Signage displayed and legible
checkpoint-status | a33eae7c-bac1-456f-8afa-4aa5724f69b0 |  | checkpoint | Hardhats being worn
checkpoint-status | 70e0edee-eb75-43bc-97f8-9394ba70ae71 |  | checkpoint | Correct footwear being worn
checkpoint-status | ab4f3faf-3cfb-4cd0-b2ce-7073db7135b7 |  | checkpoint | Glasses /ear muffs /vests /masks used
checkpoint-group | ef0bbc88-29df-4f2f-9d58-94592a19e09f |  | section | First Aid/Fire Prevention
checkpoint-status | 17f853ab-6f08-4f0d-a8bb-1379ae5c6728 |  | checkpoint | First Aid Box Available
checkpoint-status | 5e56cec3-f4a5-4196-8790-32de0743118a |  | checkpoint | Accident register
checkpoint-status | c658fb97-71cb-4cb5-a840-0cc03e5db4ff |  | checkpoint | Fire Extinguishers
boolean | 2f52c304-09bf-53cc-9322-6c3bfb31fe89 |  | tickbox | Available
boolean | a9418ec1-9c72-54c6-9185-57fb88765cf5 |  | tickbox | Current (12mth)
boolean | c37affe7-05a2-536f-ad78-9a95126ae123 |  | tickbox | Sufficient number
checkpoint-status | 6fe56068-8406-4a61-b473-b10cd33197c9 |  | checkpoint | Evacuation
boolean | 4d189fdb-67f1-50ed-b13b-90bd9baa74ac |  | tickbox | Procedure current
boolean | cd34b1c9-cf48-5ea3-a57b-5fa1c428b04c |  | tickbox | All emergencies incl
checkpoint-group | 386529ac-d27f-4651-b765-69aecfdcce6c |  | section | Cranes/hoist/lifting equipment
checkpoint-status | 68e2fceb-9e5c-4aa3-b6ae-b243a7ce9691 |  | checkpoint | Proper lift assessment plan done
checkpoint-status | f6666474-5ae4-4b2f-aed3-c41bca6942f0 |  | checkpoint | Crane certification current
checkpoint-status | 31a71301-460c-4a4b-8027-9aef215f1b64 |  | checkpoint | Slings/chains certified
checkpoint-status | 3d39e3f5-8c7e-4de9-bedd-a8d7827c6d85 |  | checkpoint | Operator procedures in place
checkpoint-status | f42cb258-c30e-425b-81ac-606078f41d57 |  | checkpoint | Inspections being done
checkpoint-status | 9741a79e-7ad6-4b27-aef3-c9a3d4fd89a8 |  | checkpoint | Man cage available
checkpoint-status | 94e57e4e-b716-40b5-aede-9b7320ae03df |  | checkpoint | Emergency plan in place
checkpoint-group | 97b39fe2-c233-4552-83bb-f35ab2c38312 |  | section | Compressed air equipment
checkpoint-status | f87ddf65-28c8-4d33-9bc5-2b0580efd9a8 |  | checkpoint | In good condition
checkpoint-status | 94c0c996-cf4b-4bd1-8e81-2a8ed73fbd38 |  | checkpoint | Appropriate guards fitted
checkpoint-status | 768ece19-756e-43a8-aaa0-83481026d886 |  | checkpoint | Trained user
checkpoint-group | db10891e-7bef-4543-98d3-12a1c5f33354 |  | section | Excavations
checkpoint-status | f4c593a2-f93e-41c4-986c-ec300d8ac666 |  | checkpoint | Correctly Shored
checkpoint-group | e976a77b-6d94-4f04-ba1e-564faefe3592 |  | section | Welding/gas cutting
checkpoint-status | 74762ca3-1bed-4508-998e-b043159fa29b |  | checkpoint | Hot work permits being issued
checkpoint-status | f26eb653-bc98-44a5-a7ed-951aa9821726 |  | checkpoint | Fire extinguishers on hand
checkpoint-status | 8fc5d321-8880-4f04-b2f4-7edfafbab31b |  | checkpoint | Operators using PPE
checkpoint-group | 5d18beae-8ab0-4197-82c7-c07a1db02059 |  | section | Electrical Equipment
checkpoint-status | a7ff6082-5dfe-468f-a57b-816ca4921a31 |  | checkpoint | Main board lockable /weatherproof
checkpoint-status | 7fbeafff-7a96-48c6-91ff-613fb9267636 |  | checkpoint | Current tagged and damage-free leads
checkpoint-status | 124d05b6-824b-4caa-baa8-bb7e4f017dc8 |  | checkpoint | Current tagged plant
checkpoint-status | b1b70f27-56b0-4100-b7d4-bf0e059c3ae0 |  | checkpoint | Current tagged lifeguards
checkpoint-status | 273f5b0d-c3b1-4a54-9f56-5cce3b5d11b6 |  | checkpoint | Leads safely placed
checkpoint-status | 4d22733e-68b9-45a4-94d5-56d3cad734d1 |  | checkpoint | Equipment in good condition
checkpoint-status | 0645b226-2401-437a-b674-1d24715a8c01 |  | checkpoint | Appropriate guards on equipment
checkpoint-status | 4f130c47-c956-4ca7-8e8a-46f434f9b9ad |  | checkpoint | Adequate temporary lighting
checkpoint-group | b30da7a3-07fa-4f21-9cc3-b730aa73f618 |  | section | Chemicals
checkpoint-status | 668ec579-7070-415b-904c-920377de226f |  | checkpoint | Correctly stored
checkpoint-status | 06e990dd-7401-48a3-84e0-1bb2ae87b932 |  | checkpoint | Safety Data Sheet (SDS) available
checkpoint-status | 7e19f3d0-dadc-4db7-b1f5-0e8b0a239118 |  | checkpoint | Operators using PPE
checkpoint-group | 24d98e47-4485-4ad2-aa5e-6b1441dc9095 |  | section | Tools
checkpoint-status | 6e53a9af-be73-42fd-abd8-f340786977e3 |  | checkpoint | PAT tool WoF current and secure
checkpoint-status | 2769a72c-ed0f-49de-856c-144f188647b4 |  | checkpoint | Staff trained in tool use (SWPS)
checkpoint-status | ea823ec4-72bd-4197-bb52-a5826a784540 |  | checkpoint | PAT signage on site
checkpoint-group | 2edd1df2-34c1-4c75-901e-fe88eb4fe51c |  | section | Scaffolding
checkpoint-status | 95f2e959-392b-45b4-86a8-cf9952ef5c17 |  | checkpoint | Notifiable weekly Scaftag/current
checkpoint-status | 4c78c647-4f22-4507-9cad-fcfa77158360 |  | checkpoint | Handrails/mid-rails
checkpoint-status | efacf7bb-a5ad-4892-813f-058a47a68e18 |  | checkpoint | Toe boards
checkpoint-status | 5dacea56-ec70-4f3b-9962-85fa0d31fe9e |  | checkpoint | Platforms
checkpoint-status | 05968951-9802-4f24-ad97-e3bc3155fc10 |  | checkpoint | Ladders/stairs
checkpoint-status | e83ce979-05e5-4e72-b172-ff92014960b2 |  | checkpoint | Base sound
checkpoint-status | cdc64eda-fbe4-4662-903b-1ad673942b73 |  | checkpoint | Work platforms clear
checkpoint-status | 77a547f5-26b5-4de5-92a1-503cb29fffe8 |  | checkpoint | Platforms trip free
checkpoint-status | 9c13511d-9cf1-4178-b8d6-7545d21bea27 |  | checkpoint | Planks tied down
checkpoint-status | 54451aa1-8f95-496c-8537-afc1666a5f5c |  | checkpoint | Headroom clear
checkpoint-status | 124c759a-97e2-49a8-b848-6054a80a7920 |  | checkpoint | Ties/bracing adequate
checkpoint-group | 003c3611-08c3-4dfd-be21-c2e8ba86160a |  | section | Ladders
checkpoint-status | 8580ea74-50e9-40bf-bc38-eb7827a89cfd |  | checkpoint | Good condition
checkpoint-status | 942b4f22-fab0-4c9d-8ebe-782e0f744e90 |  | checkpoint | Secured top and bottom
checkpoint-status | 3f417c61-67b1-4d84-8d48-4a7c0d5f6b57 |  | checkpoint | Stays to step ladders
checkpoint-status | 5292eefc-2231-471d-b85b-5bac12e77084 |  | checkpoint | Working 2 steps down
checkpoint-group | 9cbe8a66-35bf-470e-a961-978f94f40ac4 |  | section | Fall Hazards
checkpoint-status | faf95df8-3511-4259-8d24-5a90cb21d682 |  | checkpoint | Fall Hazards
checkpoint-status | 9f204443-eeec-4c14-abea-eaeb9fb6d64c |  | checkpoint | Floor openings
checkpoint-status | 34dc0597-2fb5-429a-965d-7ddc5d8f7ee9 |  | checkpoint | Lift shafts
checkpoint-status | 73179c22-263e-43b7-ac5b-6266f9b353ed |  | checkpoint | Stairs
checklist-sectioned |  |  | checklist | Membrane |  |  |  |  | Yes | QA - Membrane Checklist | e82810ee-0320-410b-970e-3f460bddcdc2
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Edge protection/scaffold in place
checkpoint-status |  |  | checkpoint | Safety nets installed
checkpoint-status |  |  | checkpoint | Purlins/battens & all necessary timberwork complete
checkpoint-status |  |  | checkpoint | Other trades works damage free & protected
checkpoint-group |  |  | section | Roof QA
checkpoint-status |  |  | checkpoint | Plywood substrate correct
checkpoint-status |  |  | checkpoint | Substrate clean
checkpoint-status |  |  | checkpoint | Drip edge/gutter line flashing installed
checkpoint-status |  |  | checkpoint | Membrane laid in accordance with suppliers details
checkpoint-status |  |  | checkpoint | No visible damage to membrane
checkpoint-status |  |  | checkpoint | All laps welded correctly
checkpoint-status |  |  | checkpoint | Flashings installed where required for termination/weathertightness
checkpoint-status |  |  | checkpoint | Penetrations welded correctly
checkpoint-status |  |  | checkpoint | Roof/Site clean of rubbish and excess materials
checklist-sectioned |  |  | checklist | Kingspan Roofing |  |  |  |  | Yes | QA - Kingspan Roof Checklist | ef92f079-7fdc-4d83-b4bf-567c7a090ca2
checkpoint-group |  |  | section | Prestart
checkpoint-status |  |  | checkpoint | Edge protection/scaffold in place
holdpoint |  |  | signoff | Raise remedial / request review
checkpoint-status |  |  | checkpoint | Safety nets installed
holdpoint |  |  | signoff | Raise remedial / request review
checkpoint-status |  |  | checkpoint | Purlins/battens & all necessary timberwork complete
holdpoint |  |  | signoff | Raise remedial / request review
checkpoint-group |  |  | section | Kingspan Roof QA
checkpoint-status |  |  | checkpoint | Screws tight & washers intact
checkpoint-status |  |  | checkpoint | Roof clean of roofing debris
checkpoint-status |  |  | checkpoint | Roof clean of swarf. If FAIL, mark on plan areas of concern & include photos
checkpoint-status |  |  | checkpoint | Undamaged roofing sheet profile. If FAIL, mark on plan areas of concern & include photos
checkpoint-status |  |  | checkpoint | Scratches - mark on plan areas of concern & include photos
checkpoint-status |  |  | checkpoint | Roof laid in correct sequence
checkpoint-status |  |  | checkpoint | Flashing junctions sealed & tidy
checkpoint-status |  |  | checkpoint | Lap tape installed correctly