## Project Structure
Folder Structure |  |  | Checklists
Site QA
Job Name:
Job Number:
| Elevation / Zone | Window # | Suite
| 2 | W.203-01 | Seismic Suite (non curtain wall)
|  | W.203-01 (2?) | Seismic Suite (non curtain wall)
|  | W.203-03 | Seismic Suite (non curtain wall)
|  | W.203-04 | Seismic Suite (non curtain wall)
|  | W.203-05 | Seismic Suite (non curtain wall)
| 3 | W.301-01 | Seismic Suite (non curtain wall)
|  | W.305-02 | Seismic Suite (non curtain wall)
|  | W.305-03 | Seismic Suite (non curtain wall)
|  | W.306-02 | Seismic Suite (non curtain wall)
|  | W.306-03 | Seismic Suite (non curtain wall)
|  | W.306-04 | Seismic Suite (non curtain wall)
|  | W311-02 | Seismic Suite (non curtain wall)
| 4 | W.401-01 | Seismic Suite (non curtain wall)
|  | W.401-02 | Seismic Suite (non curtain wall)
|  | W.401-03 | Seismic Suite (non curtain wall)
|  | W.405-02 | Seismic Suite (non curtain wall)
|  | W.405-03 | Seismic Suite (non curtain wall)
|  | W.405-04 | Seismic Suite (non curtain wall)
|  | W.405-05 | Seismic Suite (non curtain wall)
|  | W.405-02 | Seismic Suite (non curtain wall)
|  | W.407-03 | Seismic Suite (non curtain wall)
|  | W.408-02 | Seismic Suite (non curtain wall)
|  | W.408-03 | Seismic Suite (non curtain wall)
|  | W.408-04 | Seismic Suite (non curtain wall)
| 5 | W.506-06 | Seismic Suite (non curtain wall)
|  | W.507-01 | Seismic Suite (non curtain wall)
|  | W.505-02 | Seismic Suite (non curtain wall)
|  | W.506-02 | Seismic Suite (non curtain wall)
|  | W.506-03 | Seismic Suite (non curtain wall)
|  | W.506-04 | Seismic Suite (non curtain wall)
|  | W.506-05 | Seismic Suite (non curtain wall)
| 6 | W.601-01 | Seismic Suite (Curtain Wall)
|  | W.605-02 | Seismic Suite (non curtain wall)
|  | W.605-03 | Seismic Suite (non curtain wall)
|  | W.605-04 | Seismic Suite (non curtain wall)
|  | W.606-01 | Seismic Suite (non curtain wall)
|  | W.606-02 | Seismic Suite (non curtain wall)
|  | W.607-01 | Seismic Suite (non curtain wall)
|  | W.605-01 / D.605-02 | Seismic Suite (non curtain wall)
| 7 | W.702-01 | Seismic Suite (Curtain Wall)

## Resources
type | name | values | type | name | values
checklist-flat | 100mm Flushglaze |  | checklist-flat | 100mm Flushglaze
checkpoint | Opening Prepared By Main Contractor |  | checkpoint | Opening Prepared By Main Contractor
checkpoint | Setout/Grids/Datum Lines |  | checkpoint | Setout/Grids/Datum Lines
checkpoint | Seismic Installed As Per Shop Drawings |  | checkpoint | Seismic Installed As Per Shop Drawings
checkpoint | DL Brackets Fitted & Welded correct location |  | checkpoint | DL Brackets Fitted & Welded correct location
checkpoint | Panel Fitted & Locked Off |  | checkpoint | Panel Fitted & Locked Off
checkpoint | Splicers & Soakers Sealed (provide photo reference) |  | checkpoint | Splicers & Soakers Sealed (provide photo reference)
checkpoint | Airseal and Internal Flashings |  | checkpoint | Airseal and Internal Flashings
checkpoint | External Flashings / Weather Seals (provide photo reference) |  | checkpoint | External Flashings / Weather Seals (provide photo reference)
checkpoint | Site Glazing Completed |  | checkpoint | Site Glazing Completed
checkpoint | Trade Clean |  | checkpoint | Trade Clean
checkpoint | Wights - Sign Off |  | checkpoint | Wights - Sign Off
checklist-flat | 125mm Flushglaze |  | checklist-flat | 125mm Flushglaze
checkpoint | Opening Prepared By Main Contractor |  | checkpoint | Opening Prepared By Main Contractor
checkpoint | Setout/Grids/Datum Lines |  | checkpoint | Setout/Grids/Datum Lines
checkpoint | Seismic Installed As Per Shop Drawings |  | checkpoint | Seismic Installed As Per Shop Drawings
checkpoint | DL Brackets Fitted & Welded correct location |  | checkpoint | DL Brackets Fitted & Welded correct location
checkpoint | Panel Fitted & Locked Off |  | checkpoint | Panel Fitted & Locked Off
checkpoint | Splicers & Soakers Sealed (provide photo reference) |  | checkpoint | Splicers & Soakers Sealed (provide photo reference)
checkpoint | Airseal and Internal Flashings |  | checkpoint | Airseal and Internal Flashings
checkpoint | External Flashings / Weather Seals (provide photo reference) |  | checkpoint | External Flashings / Weather Seals (provide photo reference)
checkpoint | Autodoor Unit Installed - Dormakaba |  | checkpoint | Autodoor Unit Installed - Dormakaba
checkpoint | Autodoor Unit Commisioned - Dormakaba |  | checkpoint | Autodoor Unit Commisioned - Dormakaba
checkpoint | Site Glazing Completed |  | checkpoint | Site Glazing Completed
checkpoint | Trade Clean |  | checkpoint | Trade Clean
checkpoint | Wights - Sign Off |  | checkpoint | Wights - Sign Off
checklist-flat | 150mm Flushglaze |  | checklist-flat | 150mm Flushglaze
checkpoint | Opening Prepared By Main Contractor |  | checkpoint | Opening Prepared By Main Contractor
checkpoint | Setout/Grids/Datum Lines |  | checkpoint | Setout/Grids/Datum Lines
checkpoint | Seismic Installed As Per Shop Drawings |  | checkpoint | Seismic Installed As Per Shop Drawings
checkpoint | DL Brackets Fitted & Welded correct location |  | checkpoint | DL Brackets Fitted & Welded correct location
checkpoint | Panel Fitted & Locked Off |  | checkpoint | Panel Fitted & Locked Off
checkpoint | Splicers & Soakers Sealed (provide photo reference) |  | checkpoint | Splicers & Soakers Sealed (provide photo reference)
checkpoint | Airseal and Internal Flashings |  | checkpoint | Airseal and Internal Flashings
checkpoint | External Flashings / Weather Seals (provide photo reference) |  | checkpoint | External Flashings / Weather Seals (provide photo reference)
checkpoint | Site Glazing Completed |  | checkpoint | Site Glazing Completed
checkpoint | Trade Clean |  | checkpoint | Trade Clean
checkpoint | Wights - Sign Off |  | checkpoint | Wights - Sign Off
checklist-flat | Magnum Suite |  | checklist-flat | Magnum Suite
checkpoint | Opening Wraped & Prepared Correctly By Others |  | checkpoint | Opening Wraped & Prepared Correctly By Others
checkpoint | Setout/Grids/Datum Lines |  | checkpoint | Setout/Grids/Datum Lines
checkpoint | External Flashings / Weather Seals As Per Shop Drawing (provide photo reference) |  | checkpoint | External Flashings / Weather Seals As Per Shop Drawing (provide photo reference)
checkpoint | Installed / Fixed As Per Shop Drawings |  | checkpoint | Installed / Fixed As Per Shop Drawings
checkpoint | Airseals Completed |  | checkpoint | Airseals Completed
checkpoint | Trade Clean |  | checkpoint | Trade Clean
checkpoint | Wights - Sign Off |  | checkpoint | Wights - Sign Off
checklist-flat | 40mm Seismic |  | checklist-flat | 40mm Seismic
checkpoint | Opening Prepared By Main Contractor |  | checkpoint | Opening Prepared By Main Contractor
checkpoint | Setout/Grids/Datum Lines |  | checkpoint | Setout/Grids/Datum Lines
checkpoint | Seismic Installed As Per Shop Drawings |  | checkpoint | Seismic Installed As Per Shop Drawings
checkpoint | DL Brackets Fitted & Welded correct location |  | checkpoint | DL Brackets Fitted & Welded correct location
checkpoint | C.W Visual Panel Insert Check |  | checkpoint | C.W Visual Panel Insert Check
checkpoint | Panel Fitted & Locked Off |  | checkpoint | Panel Fitted & Locked Off
checkpoint | Splicers & Soakers Sealed (provide photo reference) |  | checkpoint | Splicers & Soakers Sealed (provide photo reference)
checkpoint | Airseal and Internal Flashings |  | checkpoint | Airseal and Internal Flashings
checkpoint | External Flashings / Weather Seals (provide photo reference) |  | checkpoint | External Flashings / Weather Seals (provide photo reference)
checkpoint | Site Glazing Completed |  | checkpoint | Site Glazing Completed
checkpoint | Trade Clean |  | checkpoint | Trade Clean
checkpoint | Wights - Sign Off |  | checkpoint | Wights - Sign Off
checklist-flat | 168mm Structural glazed |  | checklist-flat | 168mm Structural glazed
checkpoint | Opening Prepared By Main contractor |  | checkpoint | Opening Prepared By Main contractor
checkpoint | Setout/Grids/Datum Lines |  | checkpoint | Setout/Grids/Datum Lines
checkpoint | Seismic Installed As Per Shop Drawings |  | checkpoint | Seismic Installed As Per Shop Drawings
checkpoint | DL Brackets Fitted & Welded correct location |  | checkpoint | DL Brackets Fitted & Welded correct location
checkpoint | C.W Visual Panel Insert Check |  | checkpoint | C.W Visual Panel Insert Check
checkpoint | Panel Fitted & Locked Off |  | checkpoint | Panel Fitted & Locked Off
checkpoint | Splicers & Soakers Sealed (provide photo reference) |  | checkpoint | Splicers & Soakers Sealed (provide photo reference)
checkpoint | Airseal and Internal Flashings |  | checkpoint | Airseal and Internal Flashings
checkpoint | External Flashings / Weather Seals (provide photo reference) |  | checkpoint | External Flashings / Weather Seals (provide photo reference)
checkpoint | Site Glazing Completed |  | checkpoint | Site Glazing Completed
checkpoint | Trade Clean |  | checkpoint | Trade Clean
checkpoint | Wights - Sign Off |  | checkpoint | Wights - Sign Off
checklist-flat | Thermal Heart Suite |  | checklist-flat | Thermal Heart Suite
checkpoint | Opening Wraped & Prepared Correctly |  | checkpoint | Opening Wraped & Prepared Correctly
checkpoint | External Flashings / Weather Seals As Per Shop Drawing (provide photo reference) |  | checkpoint | External Flashings / Weather Seals As Per Shop Drawing (provide photo reference)
checkpoint | Installed / Fixed As Per Shop Drawings |  | checkpoint | Installed / Fixed As Per Shop Drawings
checkpoint | Airseals Completed |  | checkpoint | Airseals Completed
checkpoint | Site Glazing Completed |  | checkpoint | Site Glazing Completed
checkpoint | Trade Clean |  | checkpoint | Trade Clean
checkpoint | Wights - Sign Off |  | checkpoint | Wights - Sign Off
checklist-flat | 100mm Shopfront |  | checklist-flat | 100mm Shopfront
checkpoint | Opening Prepared By Main contractor |  | checkpoint | Opening Prepared By Main contractor
checkpoint | Setout/Grids/Datum Lines |  | checkpoint | Setout/Grids/Datum Lines
checkpoint | Installed / Fixed as per Shop Drawings |  | checkpoint | Installed / Fixed as per Shop Drawings
checkpoint | Panel installed and working . Locking correctly |  | checkpoint | Panel installed and working . Locking correctly
checkpoint | Airseals Completed |  | checkpoint | Airseals Completed
checkpoint | Site Glazing Completed |  | checkpoint | Site Glazing Completed
checkpoint | External Flashings / Weather Seals (provide photo reference) |  | checkpoint | External Flashings / Weather Seals (provide photo reference)
checkpoint | Trade Clean |  | checkpoint | Trade Clean
checkpoint | Wights - Sign Off |  | checkpoint | Wights - Sign Off
checklist-flat | 40mm Metro |  | checklist-flat | 40mm Metro
checkpoint | Opening Wraped & Prepared Correctly By Others |  | checkpoint | Opening Wraped & Prepared Correctly By Others
checkpoint | Setout/Grids/Datum Lines |  | checkpoint | Setout/Grids/Datum Lines
checkpoint | External Flashings / Weather Seals (provide photo reference) |  | checkpoint | External Flashings / Weather Seals (provide photo reference)
checkpoint | Installed / Fixed As Per Shop Drawings |  | checkpoint | Installed / Fixed As Per Shop Drawings
checkpoint | Airseals Completed |  | checkpoint | Airseals Completed
checkpoint | Site Glazing Completed - Metro Glass |  | checkpoint | Site Glazing Completed - Metro Glass
checkpoint | Trade Clean |  | checkpoint | Trade Clean
checkpoint | Wights - Sign Off |  | checkpoint | Wights - Sign Off
checklist-flat | Architectural |  | checklist-flat | Architectural
checkpoint | Opening Wraped & Prepared Correctly By Others |  | checkpoint | Opening Wraped & Prepared Correctly By Others
checkpoint | Setout/Grids/Datum Lines |  | checkpoint | Setout/Grids/Datum Lines
checkpoint | External Flashings / Weather Seals (provide photo reference) |  | checkpoint | External Flashings / Weather Seals (provide photo reference)
checkpoint | Installed / Fixed As Per Shop Drawings |  | checkpoint | Installed / Fixed As Per Shop Drawings
checkpoint | Airseals Completed |  | checkpoint | Airseals Completed
checkpoint | Site Glazing Completed - Metro Glass |  | checkpoint | Site Glazing Completed - Metro Glass
checkpoint | Trade Clean |  | checkpoint | Trade Clean
checkpoint | Wights - Sign Off |  | checkpoint | Wights - Sign Off
checklist-flat | Residential Suite |  | checklist-flat | Residential Suite
checkpoint | Opening Wraped & Prepared Correctly |  | checkpoint | Opening Wraped & Prepared Correctly
checkpoint | External Flashings / Weather Seals As Per Shop Drawing (provide photo reference) |  | checkpoint | External Flashings / Weather Seals As Per Shop Drawing (provide photo reference)
checkpoint | Installed / Fixed As Per Shop Drawings |  | checkpoint | Installed / Fixed As Per Shop Drawings
checkpoint | Airseals Completed |  | checkpoint | Airseals Completed
checkpoint | Site Glazing Completed |  | checkpoint | Site Glazing Completed
checkpoint | Trade Clean |  | checkpoint | Trade Clean
checkpoint | Wights - Sign Off |  | checkpoint | Wights - Sign Off
checklist- flat | Skylite |  | checklist- flat | Skylite
checkpoint | Opening Wraped & Prepared Correctly |  | checkpoint | Opening Wraped & Prepared Correctly
checkpoint | Roof frame Installed / Fixed As Per Shop Drawings |  | checkpoint | Roof frame Installed / Fixed As Per Shop Drawings
checkpoint | Airseal and Internal Flashings |  | checkpoint | Airseal and Internal Flashings
checkpoint | External Flashings / Weather Sealas ( Provide photo reference) |  | checkpoint | External Flashings / Weather Sealas ( Provide photo reference)
checkpoint | Site Glazing Completed |  | checkpoint | Site Glazing Completed
checkpoint | Trade Clean |  | checkpoint | Trade Clean
checkpoint | Wights - Sign Off |  | checkpoint | Wights - Sign Off

## Resources (2)
type | name | values
checklist-flat | Seismic Suite (non curtain wall)
checkpoint | Opening Prepared, Wrapped & Datums
checkpoint | Seismic Installed As Per Shop Drawings
checkpoint | Splicers & Soakers Sealed (provide photo reference)
checkpoint | Panel Fitted & Locked Off
checkpoint | Airseal and Internal Flashings (Photo)
checkpoint | External Flashings / Weather Seals / Drainage
checkpoint | Site Glazing Completed
checkpoint | Trade Clean
checkpoint | Wights - Sign Off
checklist-flat | Seismic Suite (Curtain Wall)
checkpoint | Opening Prepared By Main Contractor
checkpoint | Setout/Grids/Datum Lines
checkpoint | Seismic Installed As Per Shop Drawings
checkpoint | DL Brackets Fitted & Welded correct location
checkpoint | Panel Fitted & Locked Off
checkpoint | Splicers & Soakers Sealed (provide photo reference)
checkpoint | Airseal and Internal Flashings (photo)
checkpoint | Smoke Seal Complete (photo)
checkpoint | External Flashings / Weather Seals/Drainage
checkpoint | Trade Clean & Sign Off
checklist-flat | Commercial/Domestic
checkpoint | Opening Wraped & Prepared Correctly
checkpoint | External Flashings / Weather Seals As Per Shop Drawing
checkpoint | Installed / Fixed As Per Shop Drawings
checkpoint | Airseals Completed (photo)
checkpoint | Site Glazing Completed
checkpoint | Trade Clean & Sign off