## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | a35addd6-29cb-4c0e-9bc7-f812ddfcfcec |  | checklist | Mailbox |  |  |  |  | Yes | Mailbox | 4bb51f4c-c604-495d-b40f-16bd20c630c9
checkpoint-status | 0256ac8a-f56b-4313-8a7d-35a71c4cad81 |  | checkpoint | Area Ready for TK Works
checkpoint-status | c5bbaf3d-57c2-45ac-a646-8c79ba6f5407 |  | checkpoint | Brackets installed (If Applicable)
checkpoint-status | 9b349bc6-a324-4963-ba69-59d59d76d576 |  | checkpoint | Concrete bolts installed and Mailbox Secure
checkpoint-status | 5fa1e22b-6edb-4619-b5bc-c0cda1d0201d |  | checkpoint | Install complete - Defect Free
checklist-flat | d1425cb8-a1b4-43cb-ac83-97ee47eaef8b |  | checklist | Skirting |  |  |  |  | Yes | Skirting | 5aa846a5-2224-4fda-9645-af4cf87aea50
checkpoint-status | e85e6380-3e08-44e1-b72c-f31eec68a21c |  | checkpoint | Area Clean & Acceptable
checkpoint-status | e30e1760-a881-4d96-bce5-2872ff1a6590 |  | checkpoint | Walls Ready and Primed
checkpoint-status | 3eabd39f-9aa8-45fc-8234-b6c399a7040f |  | checkpoint | Skirting Complete and Damage Free
checklist-sectioned | c83aa605-257a-45be-ae00-0b15e4a9629f |  | checklist | Sanitary Hardware |  |  |  |  | Yes | Sanitary Hardware | 87870b94-56be-40ef-98ab-19273d963d40
checkpoint-group | a0fc56f5-1b70-4a92-970d-f7d2f9bf2037 |  | section | Nogs
checkpoint-status | 565331e2-74c7-450d-befb-2a7868aff9e5 |  | checkpoint | Wall Framing Complete
checkpoint-status | 86171383-7915-46dc-aa3d-c6ac2f2cbb64 |  | checkpoint | Wall Framing Fixed of Secure
checkpoint-status | c8c77101-fcd3-4fb9-a61c-ae20c9316cba |  | checkpoint | Noggins Marked Out by Top Knot
checkpoint-status | 411c52c5-2dd1-4302-b8ff-de57ecbedddb |  | checkpoint | Noggins Installed by Others.
checkpoint-group | 87f42962-a136-4186-8bf5-a8f09b59edb5 |  | section | Hardware
checkpoint-status | 9bab8884-6196-4dcf-b811-5ac870a6b763 |  | checkpoint | Installed as per Latest Elevations
checkpoint-status | 00e22ae4-d08c-4b12-a891-896c047c0a46 |  | checkpoint | Installed and Fixed off Securely
checklist-sectioned | c509f0dd-2d11-4e81-bd44-0ab971e2b309 |  | checklist | Doors & Frames |  |  |  |  | Yes | Doors & Frames | e197139c-4894-46de-82a1-5a9446f7a893
checkpoint-group | 7b9cf194-8e04-4022-ac34-de80f328db73 |  | section | Frames
checkpoint-status | 4a125139-4c43-4d69-a5be-13b766027c0c |  | checkpoint | Frame Installed Level and Securely. (If Applicable)
checkpoint-status | d97361cb-4063-4caf-bbec-fe141dc60dc2 |  | checkpoint | Frame Installed Damage Free (If Applicable) (photo)
checkpoint-status | de5e64fc-93e6-4a0d-8c77-6dd501494d6a |  | checkpoint | Framing Caulked and Filled (If Applicable)
checkpoint-group | 2f9821fe-0994-41db-ac58-a4bddcb11bfd |  | section | Doors
checkpoint-status | 446d9ba4-7a8d-471f-9c19-c9834470cb2c |  | checkpoint | Door Installed with Correct Margins
checkpoint-status | 99b93d88-d308-4f49-8ee8-30acb1eebcaa |  | checkpoint | Door Installed with Correct Hardware and Operating.
checkpoint-status | c3008fc3-653f-4b70-b256-160de678c401 |  | checkpoint | All Hinge Screws Installed
checkpoint-status | 66dd2fb6-380b-4324-9b13-8d7d9202d9dc |  | checkpoint | Door Installed Damage Free (photo)
checkpoint-group | 9f61fa9d-c521-442a-b383-56d917bd6fde |  | section | Hardware
checkpoint-status | 3218eddb-16e8-41cd-bf87-4b82daeb2850 |  | checkpoint | Face Plate Fitted Square
checkpoint-status | 3daf0fac-d377-4b78-88d1-83b5f639b692 |  | checkpoint | Escutcheons Installed
checkpoint-status | 15346044-4b5d-48d9-bfc7-e0cc6036f10e |  | checkpoint | Lock Fitted As Required
checkpoint-status | f22d21c7-7506-40c9-b442-50a9b95cc7b0 |  | checkpoint | Closer Speed Checked
checkpoint-status | 2ba67153-d52b-45f8-80a1-d9eb001dd166 |  | checkpoint | Door Latches Into Frame
checkpoint-status | e4fa1631-c2d8-45ac-91c7-9dbda5153593 |  | checkpoint | Batwing Seal Installed
checkpoint-status | d7644c79-226a-4662-a1bc-56e95e1193dd |  | checkpoint | 3mm Margin or Under to All Uprights and Across the Head
checkpoint-status | d1b36051-34da-45fe-8d72-3a9ec55d9dc8 |  | checkpoint | Margin to Underside of the FR Door within 6-10mm
checkpoint-status | 9a1667d1-6f7e-4bb0-8d23-356445c60d0b |  | checkpoint | Meeting Stiles Even & Neat (If Applicable)
checkpoint-status | 4a9c0f5b-a276-4dbc-b6c1-a799b34f021b |  | checkpoint | Fire Tag Installed
checkpoint-status | f9455baf-d8d3-4054-9cc4-b63c9e514e79 |  | checkpoint | Top and Bottom Edge of Door Painted