## T2 Parents room
MECH ELEC AIRMASTER
Rough In
|  | A1211 FCU | STANDARD EQUIPMENT (Fan, AHU, FCU, PUMP, Boiler etc). Rough-in Checklist
Fit Off
|  | A1211 FCU | WC FCU Fit off checklist
Energisation
|  | A1211 FCU | Circuit Energisation from switchboard checklist
|  | A1211 FCU | Circuit Energisation from Isolator checklist
Commissioning
|  | A1211 FCU | WC FCU Commissioning checklist

## Switchboard ITP
type | name | values | type | name | values
Checklist | Switchboard Installation |  | Checklist | Switchboard Fit-off
checkpoint | Wall Avaliable for Mounting Switchboard |  | checkpoint | All field cabling terminated
checkpoint | Switchboard Installed on Wall |  | checkpoint | Fire Signal supplied by others and terminated
checkpoint | Ensure all rubbish and materials have been picked up and area is clean |  | checkpoint | Sub-mains supplied by others and terminated
|  |  | checkpoint | BMS cables installed and terminated
|  |  | checkpoint | All Field Tests completed
|  |  | checkpoint | Ready for Energisation
type | name | values
Checklist | Switchboard Energisation |  | type | name | values
checkpoint | All field cabling terminated |  | Checklist | Switchboard Commissioning
checkpoint | All field tests completed |  | checkpoint | All circuits operational
checkpoint | Power provided at Main Switch and tested |  | checkpoint | Power meter tested
|  |  | checkpoint | Fire Trip Tested
type | name | values
Checklist | BMS Cubicle Installation |  | type | name | values
checkpoint | Wall Avaliable for Mounting Switchboard |  | Checklist | BMS Cubicle Fit-off
checkpoint | Cubicle Installed on Wall |  | checkpoint | All BMS cabling terminated
checkpoint | Ensure all rubbish and materials have been picked up and area is clean |  | checkpoint | Network cabling terminated
|  |  | checkpoint | Ready for power
type | name | values
Checklist | BMS Cubicle Commissioning
checkpoint | BMS Cubicle powered up
checkpoint | All Cards Online
checkpoint | All labels, drawings etc installed
checkpoint | BMS Cubicle cleaned out and ready for Handover
type | name | values
Checklist | Fire Control Panel Installation |  | type | name | values
checkpoint | Wall Avaliable for Mounting Switchboard |  | Checklist | Fire Control Panel Fit-off
checkpoint | Cubicle Installed on Wall |  | checkpoint | All interconnecting cabling to MSSB installed and terminated
checkpoint | Ensure all rubbish and materials have been picked up and area is clean |  | checkpoint | Fire cabling by others installed and terminated
type | name | values
Checklist | Fire Control Panel Commissioning
checkpoint | All fire relays and points test with fire contractor
checkpoint | All labels, drawings etc installed
checkpoint | Fire Control Panel cleaned out and ready for Handover

## Rough-in ITP
type | name | values
checklist | Central Controller Rough In checklist
checkpoint | All transmission cabling installed
checkpoint | Central controller cable roughed in to correct wall position
type | name | values
checklist | Cable Tray Install Checklist
checkpoint | Hangars Installed
checkpoint | Cable Tray Installed
checkpoint | Bolted down, ready for rough-in
type | name | values
Checklist | STANDARD EQUIPMENT PBO Rough-in Checklist
checkpoint | Equipment installed in final position
checkpoint | Isolator installed by others
checkpoint | Control cabling roughed in
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
type | name | values
Checklist | STANDARD EQUIPMENT (Fan, AHU, FCU, PUMP, Boiler etc). Rough-in Checklist
checkpoint | Equipment installed in final position
checkpoint | Power cabling roughed in
checkpoint | Control cabling roughed in
checkpoint | Cables through roof
checkpoint | Conduit, decktites installed, penetration watersealed
checkpoint | Ensure all rubbish and materials have been picked up and room is clean
Checklist | Essential FAN Rough-in Checklist
checkpoint | Roof penetration marked out
checkpoint | Fire Rated Supply rouged-in
checkpoint | Fire Rated Control cable roughed-in
checkpoint | Stainless Steel cable ties installed
checkpoint | Cables through roof
checkpoint | Conduit, decktites installed, penetration watersealed
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
type | name | values
VRF Condensing unit Rough In Checklist
checkpoint | Condensing unit installed in final position
checkpoint | Power supply roughed in
checkpoint | Transmission/Interconnecting cabling Roughed In
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
type | name | values
Checklist | VRF FCU/BB Rough-in Checklist
checkpoint | FCU/BB Installed
checkpoint | Transmission cabling Roughed In
checkpoint | Hard-wired controller Roughed In
checkpoint | Floor marked for plasterer
type | name | values
Checklist | SPLIT AC Rough-In Checklist
checkpoint | Area ready & accessible
checkpoint | Outdoor unit installed in final position
checkpoint | Power supply to Outdoor unit roughed in
checkpoint | Interconnecting cabling installed
checkpoint | Hard-wired controller roughed in
checkpoint | Floor marked for plasterer
checkpoint | Ensure all rubbish and materials have been picked up and room is clean
type | name | values
Checklist | Remote sensor Rough In checklist
checkpoint | Wall installed
checkpoint | Remote sensor cable roughed in
checkpoint | Ensure all rubbish and materials have been picked up and room is clean
type | name | values
Checklist | BMS Zone Sensor/AHPB Rough-in Checklist
checkpoint | Wall installed
checkpoint | 3 pair cable roughed in
checkpoint | Ensure all rubbish and materials have been picked up and room is clean
type | name | values
Checklist | Remote Sensor/AHPB Rough-in Checklist
checkpoint | Wall installed
checkpoint | Remote sensor and 2 pair cable roughed in
checkpoint | Ensure all rubbish and materials have been picked up and room is clean
type | name | values
Checklist | BMS Zone Sensor Rough In checklist
checkpoint | Wall installed
checkpoint | 1 pair cable roughed in
checkpoint | Ensure all rubbish and materials have been picked up and room is clean
type | name | values
Checklist | AHPB Rough in Checklist
checkpoint | Wall installed
checkpoint | 2 pair cable roughed in
checkpoint | Ensure all rubbish and materials have been picked up and room is clean
type | name | values
Checklist | DOL FAN Rough-in Checklist
checkpoint | Fan Installed
checkpoint | Local switch roughed in
checkpoint | Cables through roof
checkpoint | Conduit, decktites installed, penetration watersealed
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
type | name | values
Checklist | DOL FAN PBO Rough-in Checklist
checkpoint | Fan Installed
checkpoint | Isolator installed by others
checkpoint | Local switch roughed in
checkpoint | Cables through roof
checkpoint | Conduit, decktites installed, penetration watersealed
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
type | name | values

## Fitoff ITP
type | name | values
checklist | Central Controller Fit off checklist |  | Central Controller Fit off checklist
checkpoint | All transmission cabling and interfcae cards installed and fitoff
checkpoint | Central controller controller Fit off to correct wall position |  | VSD FAN PBO Fit off Checklist
VRF Condensing unit PBO Fit off Checklist
type | name | values | VSD FAN Fit off Checklist
Checklist | DOL FAN/PUMP Fit off Checklist |  | EC FAN Rough-in Checklist
checkpoint | Isolator installed |  | Remote sensor Fit off checklist
checkpoint | Power supply terminated |  | BMS Zone Sensor/AHPB Fit off Checklist
checkpoint | Control cable fit off |  | BMS Zone Sensor Fit off checklist
checkpoint | Ready for energisation |  | Remote Sensor/AHPB Fit off Checklist
checkpoint | Ensure all rubbish and materials have been picked up and area is clean |  | SPLIT AC Fit off Checklist
AHPB Fit off Checklist
VRF FCU PBO Fit off Checklist
type | name | values | VSD FAN Fit off Checklist
Checklist | VSD FAN/PUMP Fit off Checklist |  | EC FAN Rough-in Checklist
checkpoint | VSD installed |  | WC FCU Fit off checklist
checkpoint | Power supply terminated/Isolator installed |  | Remote sensor Fit off checklist
checkpoint | EMC cable fit off |  | BMS Zone Sensor/AHPB Fit off Checklist
checkpoint | Control cable fit off |  | BMS Zone Sensor Fit off checklist
checkpoint | Ready for energisation |  | Remote Sensor/AHPB Fit off Checklist
checkpoint | Ensure all rubbish and materials have been picked up and area is clean |  | SPLIT AC Fit off Checklist
AHPB Fit off Checklist
type | name | values
Checklist | EC FAN Fit off Checklist
checkpoint | Power supply terminated
checkpoint | Control cable fit off
checkpoint | Ready for energisation
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
type | name | values
Checklist | SEF VSD FAN Fitoff Checklist
checkpoint | VSD installed
checkpoint | Power supply terminated
checkpoint | EMC cable fit off
checkpoint | Control cable fit off
checkpoint | Ready for energisation
checkpoint | Conduit, decktites installed, penetration watersealed
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
VRF Condensing unit Fitoff Checklist
checkpoint | Condensing unit installed
checkpoint | Isolator and power supply installed
checkpoint | Power supply fit off
checkpoint | Transmission cabling Fit off
checkpoint | Ready for energisation
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
type | name | values
Checklist | VRF FCU Fit off Checklist
checkpoint | VRF Indoor unit installed
checkpoint | Isolator and power supply installed
checkpoint | Power supply fit off
checkpoint | Wall plastered/painted
checkpoint | Hard-wired controller fit off both ends
checkpoint | Transmission cabling Fit off
checkpoint | Interface card installed
checkpoint | OA Damper installed and wired
checkpoint | Ready for energisation
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
type | name | values
Checklist | SPLIT AC Fit off Checklist
checkpoint | Outdoor unit installed in final position and piped
checkpoint | Power supply to condensing unit Fit off
checkpoint | Interconnecting cabling Fit off
checkpoint | Local thermostat Fit off
checkpoint | Ready for energisation
checkpoint | Ensure all rubbish and materials have been picked up and room is clean
type | name | values
Checklist | WC FCU Fit off checklist
checkpoint | FCU installed in final location
checkpoint | Power supply fit off
checkpoint | Wall sensors fit-off
checkpoint | All control points fit-off (Valves, sensors etc.)
checkpoint | Ready for energisation
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
type | name | values
Checklist | Remote sensor Fit off checklist
checkpoint | Wall plastered/painted
checkpoint | Remote sensor cable Fit off on wall
checkpoint | Ensure all rubbish and materials have been picked up and room is clean
type | name | values
Checklist | BMS Control Point Wall Mounted off Checklist
checkpoint | Wall plastered/painted
checkpoint | Fit off on wall
checkpoint | Ensure all rubbish and materials have been picked up and room is clean
type | name | values
Checklist | BMS Control Point Field off Checklist
checkpoint | Control Point fitoff
checkpoint | Any penetrations sealed
checkpoint | Ensure all rubbish and materials have been picked up and room is clean
Checklist | DOL FAN PBO Fit-off Checklist
checkpoint | Fan Fitoff
checkpoint | Local switch fitoff
checkpoint | Conduit, decktites installed, penetration watersealed
checkpoint | Ready for energisation
checkpoint | Ensure all rubbish and materials have been picked up and area is clean

## Energisation ITP
type | name | values
checklist | Circuit Energisation from switchboard checklist |  | Circuit Energisation from switchboard checklist
checkpoint | Power cable installed in switchboard |  | Circuit Energisation from Isolator checklist
checkpoint | Power cable tests completed
checkpoint | Circuit breaker installed
checkpoint | Power cable terminated at switchboard
checkpoint | Power cable terminated at Equipment
checkpoint | All AS3000 Tests complete and passed
checkpoint | Circuit energised
checkpoint | Voltage Tested at equipment
type | name | values
checklist | Circuit Energisation from Isolator checklist
checkpoint | Isolator installed in correct position
checkpoint | Power cable terminated by others
checkpoint | Power cable terminated at Equipment
checkpoint | All AS3000 Tests complete and passed
checkpoint | Circuit energised by others
checkpoint | Voltage Tested at equipment

## Commissioning ITP
type | name | values
checklist | Central Controller Commissioning checklist |  | Central Controller Commissioning checklist
checkpoint | Power supply tested |  | VSD FAN PBO Commissioning Checklist
checkpoint | Central controller online |  | VRF Condensing unit PBO Commissioning Checklist
VRF FCU PBO Commissioning Checklist
type | name | values | VSD FAN Commissioning Checklist
Checklist | VSD/EC FAN Commissioning Checklist |  | WC FCU Commissioning checklist
checkpoint | Check all terminations |  | AHPB Commissioning Checklist
checkpoint | Power supply tested Voltage |  | SPLIT AC Commissioning Checklist
checkpoint | AOM, local switch tested
checkpoint | Run light tested
checkpoint | Fault light tested
checkpoint | Speed tested
checkpoint | Rotation tested
checkpoint | AMP Draw tested
checkpoint | Labels installed on all equipment
type | name | values
VRF Condensing unit Commissioning Checklist
checkpoint | Check all terminations
checkpoint | Power supply Tested Voltage
checkpoint | AMP Draw Tested
checkpoint | Labels installed on all equipment
type | name | values
Checklist | VRF FCU Commissioning Checklist
checkpoint | Check all terminations
checkpoint | Power supply Tested Voltage
checkpoint | AMP Draw Tested
checkpoint | Controller Online
checkpoint | Heat tested
checkpoint | Cool Tested
checkpoint | Labels installed on all equipment
type | name | values
Checklist | DOL FAN Commissioning Checklist
checkpoint | Check all terminations
checkpoint | Power supply tested Voltage
checkpoint | Enable tested
checkpoint | Run Proof tested
checkpoint | Fault Tested
checkpoint | Fan rotation tested
checkpoint | AMP Draw tested
checkpoint | Labels installed on all equipment
type | name | values
Checklist | EC FAN Commissioning Checklist
checkpoint | Power supply tested Voltage
checkpoint | AOM, local switch tested
checkpoint | Run light tested
checkpoint | Fault light tested
checkpoint | Speed tested
checkpoint | Fan rotation tested
checkpoint | AMP Draw tested
checkpoint | Labels installed on all equipment
type | name | values
Checklist | WC FCU Commissioning checklist
checkpoint | Check all terminations
checkpoint | Power supply Tested
checkpoint | Space temp Tested
checkpoint | Supply air temp Tested
checkpoint | Cooling Valve Tested
checkpoint | Heating Valve Tested
checkpoint | Air DP Tested
checkpoint | SAF Enable Tested
checkpoint | AMP Draw tested
checkpoint | Labels installed on all equipment
type | name | values
Checklist | AHPB Commissioning
checkpoint | AHPB operating
checkpoint | Neon working
checkpoint | Label installed
type | name | values
Checklist | SPLIT AC Commissioning Checklist
checkpoint | Check all terminations
checkpoint | Power supply to condensing unit Voltage
checkpoint | Power on indoor unit
checkpoint | Local controller operational
checkpoint | Cool Tested
checkpoint | Heat Tested
checkpoint | AMP draw tested
checkpoint | Labels installed on all equipment
type | name | values
Checklist | FAN Commissioning Checklist
checkpoint | Power supply tested Voltage
checkpoint | Fan rotation tested
checkpoint | Local switch tested
checkpoint | Fan rotation tested
checkpoint | AMP Draw tested
checkpoint | Labels installed on all equipment
type | name | values
Checklist | FAN PBO Commissioning Checklist
checkpoint | Power supply tested Voltage
checkpoint | Fan rotation tested
checkpoint | Local switch tested
checkpoint | Fan rotation tested
checkpoint | AMP Draw tested
checkpoint | Labels installed on all equipment
type | name | values
Checklist | SEF VSD FAN Commissioning Checklist
checkpoint | Power supply tested Voltage
checkpoint | Start relay tested
checkpoint | Firemans Start tested
checkpoint | Firemans Stop tested
checkpoint | Run Proof tested
checkpoint | Fault Tested
checkpoint | Speed tested
checkpoint | Fan rotation tested
checkpoint | AMP Draw tested
checkpoint | Fire label and padlock installed