## Proj Structure
Tier 1 | Tier 2 | Tier 3 | Tier 4 | resource
SP2A - L2 Lounge Extension & Fire Egress Stairs
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-100001
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-100001 | Internal First Fix
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-100001 | Internal First Fix | Area 1 | QA - First Fix
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-100001 | Internal Second Fix
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-100001 | Internal Second Fix | Area 1 | QA - Second Fix
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-100001 | External First Fix
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-100001 | External First Fix | Area 1 | QA - First Fix
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-100001 | External Second Fix
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-100001 | External Second Fix | Area 1 | QA - Second Fix
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-100001 | External Conduits
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-100001 | External Conduits | Conduit | QA - Conduit Installation
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-100001 | External Termination Box
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-100001 | External Termination Box | Termination Box 1 | QA - External Box Installation
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-101001
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-101001 | Internal First Fix
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-101001 | Internal First Fix | Area 1 | QA - First Fix
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-101001 | Internal Second Fix
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-101001 | Internal Second Fix | Area 1 | QA - Second Fix
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-101001 | External First Fix
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-101001 | External First Fix | Area 1 | QA - First Fix
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-101001 | External Second Fix
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-101001 | External Second Fix | Area 1 | QA - Second Fix
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-101001 | External Conduits
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-101001 | External Conduits | Conduit | QA - Conduit Installation
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-101001 | External Termination Box
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-101001 | External Termination Box | Termination Box 1 | QA - External Box Installation
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-200001
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-200001 | Internal First Fix
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-200001 | Internal First Fix | Area 1 | QA - First Fix
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-200001 | Internal Second Fix
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-200001 | Internal Second Fix | Area 1 | QA - Second Fix
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-200001 | External First Fix
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-200001 | External First Fix | Area 1 | QA - First Fix
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-200001 | External Second Fix
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-200001 | External Second Fix | Area 1 | QA - Second Fix
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-200001 | External Conduits
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-200001 | External Conduits | Conduit | QA - Conduit Installation
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-200001 | External Termination Box
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-200001 | External Termination Box | Termination Box 1 | QA - External Box Installation
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-201001
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-201001 | Internal First Fix
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-201001 | Internal First Fix | Area 1 | QA - First Fix
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-201001 | Internal Second Fix
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-201001 | Internal Second Fix | Area 1 | QA - Second Fix
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-201001 | External First Fix
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-201001 | External First Fix | Area 1 | QA - First Fix
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-201001 | External Second Fix
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-201001 | External Second Fix | Area 1 | QA - Second Fix
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-201001 | External Conduits
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-201001 | External Conduits | Conduit | QA - Conduit Installation
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-201001 | External Termination Box
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-201001 | External Termination Box | Termination Box 1 | QA - External Box Installation
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-202001
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-202001 | Internal First Fix
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-202001 | Internal First Fix | Area 1 | QA - First Fix
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-202001 | Internal Second Fix
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-202001 | Internal Second Fix | Area 1 | QA - Second Fix
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-202001 | External First Fix
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-202001 | External First Fix | Area 1 | QA - First Fix
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-202001 | External Second Fix
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-202001 | External Second Fix | Area 1 | QA - Second Fix
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-202001 | External Conduits
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-202001 | External Conduits | Conduit | QA - Conduit Installation
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-202001 | External Termination Box
SP2A - L2 Lounge Extension & Fire Egress Stairs | TE001-BECA-DWG-CD-C3-202001 | External Termination Box | Termination Box 1 | QA - External Box Installation
COC |  |  |  | COC

## Proj Resources
type | name | values | prefix | postfix | Template Name | Template Id
checklist | QA - External Box Installation |  |  |  | QA - External Box Installation | 0632eebd-657f-4a83-85ea-2380fc4d48c7
checkpoint | Fixed securely
checkpoint | Lid securely fixed
checklist | QA - First Fix |  |  |  | QA - First Fix | 26ecd8ee-5c18-42fb-b39a-217575daff15
section | Flush Boxes
checkpoint | Fire Rated or Acoustic
checkpoint | Height as per plan
checkpoint | Location as per plan
checkpoint | Intumescent Pad In Place
checkpoint | Flush Boxes Not back to back on Acoustic Walls
section | Cabling
checkpoint | Details
textbox | Type
textbox | Size
checkpoint | Circuits clearly noteled
checkpoint | No Horizontal cabling
checkpoint | Separation between Data and Power at 300mm or as specified
checkpoint | Light Control cabling Required
section | Cat Wires
checkpoint | 300mm Separation Between Power & Data
checkpoint | Supported every 6 Meters or Adequately to avoid Sagging
checkpoint | Correctly Secured at Each End
checkpoint | Turn Buckle Installed and Accessible
checkpoint | Number of cables per cat wire. 8 maximum or as per electrical spec
checkpoint | Separation between services maintained
checkpoint | All cables secured via cable ties with ends cut
section | Cable Tray
checkpoint | Minimum 25% spare capacity left on cable tray
section | Lights
checkpoint | Setout Correct
checkpoint | Cabling in correct location
checkpoint | Control Cabling installed
checkpoint | PIR Sensors
checkpoint | Occupancy Sensors
checkpoint | Light Level Sensors
checkpoint | Emergency/ Exit Lighting
checkpoint | Nogging installed for Electrical Services
section | Seismic Bracing
checkpoint | For Lighting
checkpoint | Cable Tray
checkpoint | Switchboard
section | Ducts and Conduits
checkpoint | Correct size installed
checkpoint | Location as per plan
checkpoint | separation from other services
checkpoint | Clean inside and in good condition
checklist | QA - Second Fix |  |  |  | QA - Second Fix | 2fe34a52-cc71-457a-9a72-4dd0584390a9
section | Power Outlets
checkpoint | Weekly Toolbox
checkpoint | Correctly installed with terminations all secured properly
checkpoint | Outlet Installed level
checkpoint | Intumescent Pad In Place
checkpoint | Circuit Tested and results recorded
checkpoint | Description noteled on the outlet face with vivid and with dymo noteler on cover plate and ensure note is level
section | Light Switches
checkpoint | Correct type installed
checkpoint | Correctly installed with terminations all secured properly
checkpoint | Outlet Installed level
checkpoint | Intumescent Pad In Place
checkpoint | Circuit Tested and results recorded
checkpoint | Description noteled on the outlet face with vivid and with dymo noteler on cover plate and ensure note is level
section | Light Fixtures
checkpoint | Correct type installed
checkpoint | Correctly installed with terminations all secured properly
checkpoint | Seismic braces installed.
checkpoint | Insulation removed from over downlights and drivers
checkpoint | Tested for operation
checklist | Catenary Wires |  |  |  | Catenary Wires | 375657fc-09b9-4051-81a1-ea5c1ea733a8
checkpoint | 50mm Separation Between Power & Data
checkpoint | Supported every 6 Meters or Adequately to avoid Sagging
checkpoint | Correctly Secured at Each End
checkpoint | Turn Buckle Installed and Accessible
checklist | QA - Conduit Installation |  |  |  | QA - Conduit Installation | 3fd6ba47-5108-4ada-854e-0d9c0f8b5d69
checkpoint | Installed as plan
checkpoint | Suitable fixings installed and spaced evenly
checklist | COC |  |  |  | COC | 5a0377ae-5d99-4b29-91eb-e32c0c41cc28
checkpoint | Upload COC here and press PASS
checklist | Inground Services |  |  |  | Inground Services | 6c9c6fc4-ea69-4286-8017-76ff9ad13070
section | Ducts and Conduits
checkpoint | Correct size installed
checkpoint | Start and finish locations correct as per plan
checkpoint | separation from other services
checkpoint | Clean inside and in good condition
section | Electrical Pits
checkpoint | Set out correct
checkpoint | Correct size installed
checkpoint | Duct entry holes sealed / water proofed
checkpoint | Pits installed to correct height and level
checkpoint | Clean inside and in good condition
section | Light Pole Foundations
checkpoint | Set out correct
checkpoint | Ducting in correct position - centre of cage
checkpoint | Correct Cage Installed
checkpoint | Cage installed to correct height / level
checkpoint | Ground Plant pole installed to correct height / level
checklist | Switchboard |  |  |  | Switchboard | b4a3628e-9a03-49b4-842a-c74c114b374a
checkpoint | Spatial certificate signed if required
checkpoint | Fixings installed in wall correctly if board is wall mounted
checkpoint | All clearances sighted to ensure location is compliant
checkpoint | All cables correctly installed in protection device and earth and neutral bars and fully secured
checkpoint | Cables neatly dressed
checkpoint | Phase tabs on chassy covered
checkpoint | All earths and neutrals noteled to match phase numbers
checkpoint | Switchboard is clean on the inside and outside
checkpoint | Masking blanks installed
checkpoint | DB legend installed
checklist | Cable Tray |  |  |  | Cable Tray | e9d3c168-c5cd-4226-9fe3-dec32b330c06
checkpoint | Unistrut Filed & Painted
checkpoint | Hangers Spaced as Specified
checkpoint | Correct Size Tray Installed
checkpoint | Tray Joined Correctly
checkpoint | Hangers Seismically Restrained as per Design
checkpoint | Tray Fastened to Hangers
checkpoint | Correct Anchors used fixing to Ceiling
checkpoint | Cable Tray Bonded