## Sheet1
Checklist | Enviro AHS Injectable Hose System
Section | BATCH DETAIL NUMBER OF PRODUCTS
CheckPoint | Enviro Hydrotite
Section | PRE COMMENCEMENT CHECKLIST
CheckPoint | MATERIAL MANAGEMENT AND STORAGE
Label | Material to be stored in a dry, clean place and directly out of sunlight.
Checkpoint | ACCEPTANCE OF SUBSTRATE
Label | Obtain Clearance for work to commence. The Substrate shall be smooth, without protrusions, voids or formwork distortions. Clean Substrate so that it is free of mould, paint, sealers, coatings, curing agents, loose particles and other contamination or foreign matter that may interfere with the adhesion.
Section | APPLICATION
Checkpoint | INSTALLATION OF HYDROTITE
Label | Rectify Existing Sheet Membrane. Ensure overlap and correct bonding to existing sheets.
Label | Hose/Injection. Installation of Enviro AHS / Sika Fuko Hose in accordance with Technical Data Sheets. Ensure all hose endings are located at the top corner of the openings and secured.
Section | DETAILING
Checkpoint | Vertical / Horizontal Waterstop
Label | Installation of Enviro Hydrotite within the body of the Infill Opening
Label | Installation of Enviro Leakmaster above the Enviro Hydrotite (adjacent) within the body of the Infill Opening.
Section | TESTING
CheckPoint | QA TESTING
Label | Inspect after installation of reinforcement/finishes to check for any damage to waterproofing and rectify as required. Check all welds with spatula/screwdriver or blutn instrument to ensure all welds are correctly sealed. Any lifts, circle to return to weld to the sheet membrane.
Label | Final Builders Sign off.
HoldPoint | Builders final sign off.