## res_1630-P200-SYM-QAC-ITP-0013.
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | SYM-0388-ITP-008 Stormwater Drainage [B] | itp |  |  |  | Yes | SYM-0388-ITP-008 Stormwater Drainage [B] | 047a7c4f-4309-4343-b59a-7ef21cc4d3ac
section | 1.0 Preliminaries
checkpoint | 1.1 - Set out
label | Ref docs - Construction Drawings TfNSW R11
label | Acceptance criteria - Is the position of the culverts in accordance with the drawings?
label | • Confirm location with the superintendent.
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint-no-status | 1.1.1 - Lot Map
button | Lot map uploaded | Yes,No,N/A
checkpoint | 1.2 - Submission of Conformance Documentation
label | Ref docs - Construction Drawings TfNSW R11
label | Acceptance criteria - Full set of certified product drawings submitted prior to installation
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - H
label | Shoalhaven City Council: Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Drainage structure confirmation
label | Ref docs - Construction Drawings
label | Acceptance criteria - Has the correct class & type of drainage structure been supplied and free of defects?
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - H
label | Shoalhaven City Council: Key - H
holdpoint | AUTHORITY HOLDPOINT
section | 2.0 Excavation and bedding
checkpoint | 2.1 - Excavation
label | Ref docs - TfNSW R11
label | Acceptance criteria - The minimum width of vertically sided trenches shall be the outside diameter plus 30mm or 600mm total, whichever is greater?
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
checkpoint | 2.2 - Minimum Grade Requirements
label | Ref docs - TfNSW R11
label | Acceptance criteria - Where 0.5% gradient not achievable with sections of open drain, notification to be issued to client
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Material
label | Ref docs - IFC Drawings
label | Acceptance criteria - Material for stormwater drainage to comply with requirements of the IFC Drawings
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
label | Shoalhaven City Council: Key - W
checkpoint | 2.4 - Bedding material
label | Ref docs - TfNSW R11
label | Acceptance criteria - Is the Bedding material placed the full width of the trench and not less than:
label | • 100mm where D<1500mm
label | • 200mm where D>1500mm
label | Where D is the nominal pipe diameter or culvert height.
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
label | Shoalhaven City Council: Key - W
section | 3.0 Culvert Installation
checkpoint | 3.1a - Culvert under paving
label | Ref docs - TfNSW R11
label | Acceptance criteria - Has trench been backfilled to design subgrade level with select backfill material?
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
checkpoint | 3.1b - Culvert not under paving
label | Ref docs - TfNSW R11
label | Acceptance criteria - Has trench been backfilled to 0.3m above the top of the culvert with select backfill material?
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
checkpoint | 3.2 - Jointing
label | Ref docs - TfNSW R11
label | Acceptance criteria - Has jointing been installed to specifications?
label | • Have holes provided for lifting and handling purposes been plugged?
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
label | Shoalhaven City Council: Key - W
checkpoint | 3.3 - Compaction
label | Ref docs - TfNSW R11
label | Acceptance criteria - Backfill under pavements shall be compacted to a dry density ratio if not less than 95% modified compactive effort. General Fill shall be compacted to a dry density ratio of not less than 98% using standard compactive effort.
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - H
label | Shoalhaven City Council: Key - W
holdpoint | AUTHORITY HOLDPOINT
section | 4.0 Drop Inlet Installation
checkpoint | 4.1 - Drop Inlet Position
label | Ref docs - IFC Drawing
label | Acceptance criteria - The drop inlet structure is installed at the correct location, depth, and size per IFC Drawings
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
checkpoint | 4.2 - Connection
label | Ref docs - IFC Drawing
label | Acceptance criteria - The drop inlet structure is properly aligned and connected to the storm drain system.
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
checkpoint | 4.3 - Drop Inlet Gate
label | Ref docs - IFC Drawing
label | Acceptance criteria - Drop inlet grate is installed securely and flush with the surrounding pavement surface
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
checkpoint | 4.4 - Compaction
label | Ref docs - IFC Drawing
label | Acceptance criteria - Backfill material is properly compacted in layers per the IFC Drawing / manufacturer specifications. Verify the grading is level and slopes away from the drop inlet structure to ensure proper drainage.
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
section | 5.0 Rip Rap
checkpoint | 5.1 - Rip rap
label | Ref docs - IFC Drawing
label | Acceptance criteria - The rip rap is installed at the correct location and orientation per the project specifications.
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
label | Shoalhaven City Council: Key - W
checkpoint | 5.2 - Geotextile
label | Ref docs - IFC Drawing
label | Acceptance criteria - The geotextile is installed as per the spec.
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
label | Shoalhaven City Council: Key - W
checkpoint | 5.3 - Shotcrete
label | Ref docs - IFC Drawing
label | Acceptance criteria - The shotcrete is applied as per the spec.
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
section | 6.0 Conformance check
checkpoint | 6.1 - Survey pick up
label | Ref docs - TfNSW R11
label | Acceptance criteria - Has an As-constructed survey must be completed by a licenced or competent surveyor of the stormwater drainage system?
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
text | Surveyor
text | Date picked up
checkpoint | Works complete
text | Name:
text | Position:
text | Date Completed:
holdpoint | Sign ITP
checkpoint | Lot Conformance
select | Lot Status | Awaiting Hold Point Release,Awaiting NCR Closure,Awaiting Test Results,Awaiting Verification,Cancelled,Closed-out,Outstanding,Work In Progress
text | Lot opened date:
text | Lot opened by:
text | Date lot closed:
button | NCR raised? | Yes,No
text | NCR Raised Date:
button | NCR closed? | Yes,No
text | NCR Closed Date:
text | NCR Number:
text | Comments
holdpoint | Sign ITP
checklist | SYM-0388-ITP-005 Gabions [B] | itp |  |  |  | Yes | SYM-0388-ITP-005 Gabions [B] | 1fafa7f9-598c-41cb-bdce-642e642b6ac2
section | 1.0 Material
checkpoint | 1.1 - Gabions
label | Ref docs - TfNSW R55 Cl 2.1, IFC Drawing
label | Acceptance criteria - Gabions must have a nominal mesh size of 80 mm x 100 mm. The minimum diameter of mesh wire must be 2.7 mm.
label | • The minimum diameter of galvanized selvedge wire must be 3.4 mm. The mesh is flexible, woven, galvanized and PVC coated when required as per IFC drawings.
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
checkpoint-no-status | 1.1.1 - Lot Map
button | Lot map uploaded | Yes,No,N/A
checkpoint | 1.2 - Selvedges
label | Ref docs - TfNSW R55 Cl 2.3
label | Acceptance criteria - All edges of the gabions must be selvedged with a continuous wire in accordance with ASTM A975-97.
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
checkpoint | 1.3 - Lacing and Connecting Wire
label | Ref docs - TfNSW R55 Cl 2.5
label | Acceptance criteria - Materials must conform to ASTM A975-97.
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Alternative fastener systems such as “C” clips in place of lacing and connecting wire are permitted but must conform to the requirements of ASTM A975-97.
checkpoint | 1.4 - Rock Fill - Strength
label | Ref docs - TfNSW R55 Cl 2.6
label | Acceptance criteria - At least 100 kN and a maximum wet/dry strength variation of 35% when tested in accordance with Test Method TfNSW T215.
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
checkpoint | 1.5 - Rock Fill - Size
label | Ref docs - TfNSW R55 Cl 2.6
label | Acceptance criteria - For gabions, the minimum and maximum rock size must be 100 mm and 250 mm respectively
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - H
holdpoint | AUTHORITY HOLDPOINT
section | 2.0 Gabion Installation
checkpoint | 2.1 - Material Inspection
label | Acceptance criteria - The gabions shall be visually inspected to ensure that they are free from defects such as cracks, splits, or punctures.
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
label | Shoalhaven City Council: Key - W
checkpoint | 2.2 - Set out
label | Ref docs - IFC Drawings
label | Acceptance criteria - Setout of gabion location and level.
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
checkpoint | 2.3 - Foundation Inspection
label | Ref docs - IFC Drawings
label | Acceptance criteria - Backfill material is compacted in layers to the required density, loose material has been removed.
label | • Geotextile is placed as per the IFC drawings.
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Shoalhaven City Council: Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Assembly
label | Ref docs - TfNSW R55 Cl 4.1
label | Acceptance criteria - Visual inspection of the gabion boxes to ensure they are free from kinks and bends.
label | • Measurement of the gabion boxes and mattresses to ensure they meet the design specifications.
label | • Lacing are securely fastened.
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
label | Shoalhaven City Council: Key - W
checkpoint | 2.5 - Erection
label | Acceptance criteria - Only assembled boxes or groups of boxes are positioned in the structure.
label | • The side, or end, from which work is to proceed, must be secured either to the completed work, or by galvanized star pickets driven into the ground at 1 m spacing. The star pickets must be firmly embedded in the ground and reach at least to the top of the gabion box.
label | • Measurement of the gabion boxes and mattresses to ensure they meet the design specifications.
label | • Lacing are securely fastened.
label | • If further gabion boxes positioned in the structure are required.
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
checkpoint | 2.6 - Stretching
label | Ref docs - TfNSW R55 Cl 4.3
label | Acceptance criteria - Verification that the gabion units have been supplied and assembled in accordance with specification requirements.
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Carry out final stretching of the gabion boxes using a pull-lift of at least one tonne capacity.
checkpoint | 2.7 - Pipe Culvert Within Gabion Structures
label | Ref docs - IFC Drawings
label | Acceptance criteria - Mesh is cut and laced as per the IFC Drawings.
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - W
label | Shoalhaven City Council: Key - W
checkpoint | 2.8 - Filling
label | Ref docs - TfNSW R55 Cl 4.4
label | Acceptance criteria - Gabion boxes shall be filled with rocks only while under tension and the rocks shall be placed by hand packing to produce a neat face free from excessive bulges, depressions and voids.
label | • Internal bracing wires shall be provided to prevent distortion of the gabion units during filling and in the completed structure.
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Mechanical filling equipment may be used provided that adequate precautions are taken to protect any PVC coating from abrasion during filling operations.
checkpoint | 2.9 - Final Lacing
label | Ref docs - TfNSW R55 Cl 4.5
label | Acceptance criteria - Gabion boxes and mattresses are finally laced and secured through each mesh along all edges, ends and diaphragms.
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
label | Shoalhaven City Council: Key - W
section | 3.0 Subsoil
checkpoint | 3.1 - Subsoil Drainage Pipe
label | Ref docs - IFC Drawings
label | Acceptance criteria - DN100 Socked Subsoil Drainage Pipe installed at base of wall before backfill.
label | • Discharge through face of wall at 25m centres
label | ○ Provide clear out riser to surface
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - W
label | Shoalhaven City Council: Key - W
checkpoint | 3.2 - Subsoil Aggregate
label | Ref docs - IFC Drawings
label | Acceptance criteria - Install subsoil layer min. 200mm wide from rear face of wall before backfill.
label | • Aggregate to be nominal 20mm in dimension.
label | ○ Wrapped in approved Geotextile.
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
label | Shoalhaven City Council: Key - S
checkpoint | 3.3 - Rock fill material behind the gabion
label | Ref docs - IFC Drawings
label | Acceptance criteria - Backfill behind the gabions by compacting in 200mm layers to at least 98% of standard maximum dry density
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Shoalhaven City Council: Key - W
section | 4.0 Conformance check
checkpoint | 4.1 - Tolerances
label | Ref docs - IFC Drawings
label | Acceptance criteria - Surface Level: the top surface level must be as per design levels or as approved.
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
label | Shoalhaven City Council: Key - S
checkpoint | Works complete
text | Name:
text | Position:
text | Date Completed:
holdpoint | Sign ITP
checkpoint | Lot Conformance
select | Lot Status | Awaiting Hold Point Release,Awaiting NCR Closure,Awaiting Test Results,Awaiting Verification,Cancelled,Closed-out,Outstanding,Work In Progress
text | Lot opened date:
text | Lot opened by:
text | Date lot closed:
button | NCR raised? | Yes,No
text | NCR Raised Date:
button | NCR closed? | Yes,No
text | NCR Closed Date:
text | NCR Number:
text | Comments
holdpoint | Sign ITP
checklist | SYM-0388-ITP-010 Guardrail [B] | itp |  |  |  | Yes | SYM-0388-ITP-010 Guardrail [B] | 2d4dea37-d3e3-4b36-b1fe-bb428e7a78d3
section | 1.0 Preliminaries
checkpoint | 1.1 - Survey set-out
label | Ref docs - Construction drawings
label | Acceptance criteria - Has the work area been set out for line and level?
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
section | 2.0 Installation of guard rail
checkpoint | 2.1 - Location and length
label | Ref docs - Construction drawings
label | Acceptance criteria - Has length and location been confirmed with the Superintendent?
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - H
label | Shoalhaven City Council: Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint-no-status | 1.1.1 - Lot Map
button | Lot map uploaded | Yes,No,N/A
checkpoint | 2.2 - Material
label | Ref docs - Construction drawings
label | Acceptance criteria - Galvanised steel components are compliance with the requirements of AS/NZS 4680.
label | • Manufacturer certificates are provided to the client.
label | • Visual inspection.
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - W
label | Shoalhaven City Council: Key - W
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
boolean | Material certificates
checkpoint | 2.3 - Install
label | Ref docs - Construction drawings
label | Acceptance criteria - Has the guard rail run been installed as per the relevant specifications and drawings?
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - W
label | Shoalhaven City Council: Key - W
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
boolean | Subcontractors ITP
section | 3.0 Completion
checkpoint | 3.1 - Tolerances
label | Ref docs - TfNSW D&C R132
label | Acceptance criteria - Has the guard rail been installed to the specified tolerances?
label | (a) For height of barrier: ± 20 mm;
label | (b) For line of safety barrier system: ± 20 mm in plan view; and
label | (c) For departures from the upright axis (vertical or normal to the surface as applicable - see Clause 4.1): ± 15 mm at the top of the barrier.
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - H
label | Shoalhaven City Council: Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Certificate of compliance
label | Ref docs - TfNSW D&C R132
label | Acceptance criteria - Has a safety barrier compliance audit taken place with records of findings available?
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
boolean | Compliance certificate
checkpoint | Works complete
text | Name:
text | Position:
text | Date Completed:
holdpoint | Sign ITP
checkpoint | Lot Conformance
select | Lot Status | Awaiting Hold Point Release,Awaiting NCR Closure,Awaiting Test Results,Awaiting Verification,Cancelled,Closed-out,Outstanding,Work In Progress
text | Lot opened date:
text | Lot opened by:
text | Date lot closed:
button | NCR raised? | Yes,No
text | NCR Raised Date:
button | NCR closed? | Yes,No
text | NCR Closed Date:
text | NCR Number:
text | Comments
holdpoint | Sign ITP
checklist | SYM-0388-ITP-001 Site Clearing [B] | itp |  |  |  | Yes | SYM-0388-ITP-001 Site Clearing [B] | 31e6eb5f-3299-40f7-840b-10ae78d55633
section | 1.0 Preliminaries
checkpoint | 1.1 - Traffic management
label | Ref docs - MoA
label | Acceptance criteria - Has Traffic Management been installed in accordance with the MoA?
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
checkpoint-no-status | 1.1.1 - Lot Map
button | Lot map uploaded | Yes,No,N/A
checkpoint | 1.2 - Limit of works
label | Ref docs - Construction drawings
label | Acceptance criteria - Have all areas required to be cleared/stripped been marked out onsite?
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
checkpoint | 1.3 - Excavation permit
label | Ref docs - Symal Infrastructure GPP
label | Acceptance criteria - Have services within the works area been identified and a group penetration permit covers the area, is current and signed onto by the works crew?
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - H
label | Shoalhaven City Council: Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - Tree protection
label | Ref docs - Construction drawings, Cultural Heritage Management Plan (CHMP), Protection of the environment policies (PEPs)
label | Acceptance criteria - Have all trees / native flora and fauna been protected including the establishment of no go zones as indicated in the construction documentation?
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - H
label | Shoalhaven City Council: Key - H
holdpoint | AUTHORITY HOLDPOINT
section | 2.0 Clearing and grubbing
checkpoint | 2.1 - Notification of intention to clear
label | Ref docs - TfNSW G40 CL.2.4
label | Acceptance criteria - Before clearing commences, identify the limits of clearing by clearly visible markers placed at 25 m intervals on each side of the road formation and bridges as shown on the Design Documentation drawings. Also provide a report which:
label | (a) includes a statement from an Ecologist that identifies the species and location of any weeds growing anywhere in the road reserve over the length to be cleared and grubbed;
label | (b) identifies all locations of threatened flora species and trees which have been marked or otherwise identified for preservation; and
label | (c) lists any trees outside the limits of clearing which are unsound and likely to fall upon the roadway or onto private property. Plan and carry out all operations to ensure that there is no damage to any trees outside the limits of clearing specified.
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - H
label | Shoalhaven City Council: Key - H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Clearing and Grubbing Plan (Annexure G40/D) and report on the presence of weeds and unsound trees together with written notice that limits of clearing and areas of weed infestation identified in the ecologist report (Clause 2.4 (a) are marked), at least seven days before starting any clearing
boolean | Clearing & Grubbing Plan
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Tree removal
label | Ref docs - TfNSW G40 CL.3
label | Acceptance criteria - Can the trees be brought down in a way that avoids danger to personnel, traffic and other trees and vegetation?
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Workers (who are removing trees on the slope) to be appropriately restrained and harnessed during tree removal works.
checkpoint | 2.3 - Disposal of materials
label | Ref docs - TfNSW G40 CL.5
label | Acceptance criteria - Have all tree trunks and large branches been removed from site? Small branches, shrubs and other materials excluding noxious weeds shall be disposed of by chipping and mulching.
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
section | 3.0 Topsoil stripping
checkpoint | 3.1 - Stripping
label | Ref docs - TfNSW G40 CL.2
label | Acceptance criteria - Has the area been stripped to an appropriate depth removing surface topsoil in a way to leave the surface evenly graded and free-draining?
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
checkpoint | 3.2 - Topsoil export
label | Ref docs - PEPS
label | Acceptance criteria - Has the topsoil being exported been approved by Shoalhaven City Council (where applicable)
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
label | Shoalhaven City Council: Key - S
checkpoint | 3.3 - Stockpiling
label | Ref docs - TfNSW G40 CL.2
label | Acceptance criteria - Has any stripped topsoil to be reused onsite been stockpiled in an agreed stockpile area with environmental protections (silt fence) in place where required?
button | Acceptance | Yes, No, N/A
label | • Have stockpiles been situated in a location which does not affect sight distance for both road users and local property access?
label | • All stockpiles shall be maintained in a neat, well shaped state capable of shedding water.
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
label | Shoalhaven City Council: Key - W
checkpoint | Works complete
text | Name:
text | Position:
text | Date Completed:
holdpoint | Sign ITP
checkpoint | Lot Conformance
select | Lot Status | Awaiting Hold Point Release,Awaiting NCR Closure,Awaiting Test Results,Awaiting Verification,Cancelled,Closed-out,Outstanding,Work In Progress
text | Lot opened date:
text | Lot opened by:
text | Date lot closed:
button | NCR raised? | Yes,No
text | NCR Raised Date:
button | NCR closed? | Yes,No
text | NCR Closed Date:
text | NCR Number:
text | Comments
holdpoint | Sign ITP
checklist | SYM-0388-ITP-002 Earthworks [C] | itp |  |  |  | Yes | SYM-0388-ITP-002 Earthworks [C] | 523ddfe3-645b-4df4-a621-2381e3e44085
section | 1.0 General & Extent Approval
checkpoint | 1.1 - Determine Site Size
label | Ref docs - IFC Drawings
label | Acceptance criteria -
text | Treatment Length: |  |  | m
text | Treatment Width: |  |  | m
button | Acceptance | Yes,No,N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - H
label | Shoalhaven City Council: Key - H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
boolean | Approved Earthworks Extent Markup
text | Doc No.
holdpoint | AUTHORITY HOLDPOINT
checkpoint-no-status | 1.1.1 - Lot Map
button | Lot map uploaded | Yes,No,N/A
checkpoint | 1.2 - Slope Treatment Type
label | Ref docs - IFC Drawings
text | Acceptance criteria -
text | Dated: _____/_____/_____
button | Acceptance | Yes,No,N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - H
label | Shoalhaven City Council: Key - H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
boolean | Approved Design Change Markup
text | Doc No.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Survey Set Out
label | Ref docs - TfNSW G71 CL3.2, IFC Drawing
label | Acceptance criteria - Set out and pegged to suit the approved design extent markup.
button | Acceptance | Yes,No,N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - H
label | Shoalhaven City Council: Key - H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
boolean | Photos of pegged out location
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - Slope Treatment Submission
label | Ref docs - IFC Drawings
label | Acceptance criteria - The following documents have been submitted by Symal to the Client for the slope treatment type approval:
label | • Survey report
label | • Notification of completion of clearing
label | • Details of tests, inspections, assessments and any recommended slope treatment proposed by the Geotechnical Engineer
button | Acceptance | Yes,No,N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - H
label | Shoalhaven City Council: Key - H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
boolean | Survey Report
text | Survey Report Doc No.
boolean | Notification of Clearing
text | Notification of Clearing Lot No.
boolean | Geotech Report
text | Geotech Report Doc No.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - Methodology
label | Ref docs - TfNSW R44 Cl 1.5, IFC Drawings
label | Acceptance criteria - Symal to submit methodology for excavation, shoring and filling works per IFC Drawings Note 191 (A).
button | Acceptance | Yes,No,N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - H
label | Shoalhaven City Council: Key - H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
boolean | Approved Earthworks Methodology
text | Doc No.
holdpoint | AUTHORITY HOLDPOINT
section | 2.0 Surface Excavation
checkpoint | 2.1 - Erosion and sediment control
label | Ref docs - IFC Drawings
label | Acceptance criteria - Installed as per Erosion and Sediment Control Plans in the approved Activity Method Statement document.
button | Acceptance | Yes,No,N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
checkpoint | 2.2 - Clearing and Grubbing
label | Ref docs - IFC Drawings
label | Acceptance criteria - Completed as per ITP-001 and signed off.
button | Acceptance | Yes,No,N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
boolean | Completed ITP-001
text | Lot No.
checkpoint | 2.3 - Working Platform & Temporary Batters
label | Ref docs - IFC Drawings
label | Acceptance criteria - Requirement for any working platform or temporary batter stabilisation assessed by Geotechnical Engineer and temporary work designed. Working platform or batter stabilisation then constructed in accordance with the temporary works design.
button | Acceptance | Yes,No,N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - W
label | Shoalhaven City Council: Key - W
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
boolean | Geotechnical Inspection Report
text | Geotechnical Inspection Report Doc No.
boolean | Temporary Works Design
text | Temporary Works Design Doc No.
checkpoint | 2.4 - Excavation Permit
label | Ref docs - IFC Drawings Note 191 (B) (i)
label | Acceptance criteria - Have all trees / native flora and fauna been protected including the establishment of no go zones as indicated in the construction documentation?
button | Acceptance | Yes,No,N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - H
label | Shoalhaven City Council: Key - H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
boolean | Excavation Permit
text | Doc No.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Sub Vertical Excavation
label | Ref docs - TfNSW R64 CL. 3.3, IFC Drawings Note 71
label | Acceptance criteria - Sub vertical excavation must not exceed a total depth of 1.5 m. Where this depth is required to be exceeded it shall be first inspected by a suitably qualified geotechnical engineer and either signed off or provide a temporary works design to facilitate the excavation.
button | Acceptance | Yes,No,N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - W
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
boolean | Written confirmation from Geotech
text | Written confirmation from Geotech Doc No.
boolean | Temporary Works Design
text | Temporary Works Design Doc No.
checkpoint | 2.6 - Proof rolling of subgrade
label | Ref docs - IFC Drawings Note 62
label | Acceptance criteria - The subgrade must be proof rolled with a 12 tonne static mass smooth drum roller. Any soft or yielding materials must be removed and replaced
button | Acceptance | Yes,No,N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - W
label | Shoalhaven City Council: Key - W
checkpoint | 2.7 - Foundation
label | Ref docs - IFC Drawings Note 61
label | Acceptance criteria - Foundation layer shall be dry, smooth, level and graded to the profile as shown in the detailed drawing. It shall be free of surface irregularities, loose or unsuitable material. Foundation level to be confirmed on site by a suitably qualified geotechnical engineer
button | Acceptance | Yes,No,N/A
checkpoint | 2.8 - Compaction
label | Ref docs - TfNSW R44
label | Acceptance criteria - Has the stabilised subgrade been adequately compacted achieving a mean value density ratio of 99% Standard?
button | Acceptance | Yes,No,N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - W
label | Shoalhaven City Council: Key - W
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
boolean | Compaction Test Report
text | No.
checkpoint | 2.9 - Stockpile
label | Ref docs - IFC Drawings Note 77
label | Acceptance criteria - Excavated material stockpiled in the nominated and approved location to a height not exceeding 2m. Ensure that different soil types are separated into different stockpiles
button | Acceptance | Yes,No,N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
checkpoint | 2.10 - Shape of Excavation
label | Ref docs - IFC Drawings
label | Acceptance criteria - Survey pickup of cut surface after completion of stripping and earthworks.
button | Acceptance | Yes,No,N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - W
label | Shoalhaven City Council: Key - W
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
boolean | Batter Survey Conformance
text | Doc No.
section | 3.0 Filling
checkpoint | 3.1 - Fill Material
label | Ref docs - IFC Drawings Note 54
label | Acceptance criteria - Import material shall be virgin excavated natural material only unless otherwise approved. Provide test data and documentation where non-virgin material is used on site.
button | Acceptance | Yes,No,N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - H
label | Shoalhaven City Council: Key - H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
boolean | Material Dockets
text | Material Dockets Doc No.
boolean | Material Test Data
text | Material Test Data Doc No.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Proof rolling of subgrade
label | Ref docs - IFC Drawings
label | Acceptance criteria - The subgrade must be proof rolled with a 12 tonne static mass smooth drum roller prior to any filling. Any soft or yielding materials must be removed and replaced.
button | Acceptance | Yes,No,N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - W
label | Shoalhaven City Council: Key - W
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
boolean | Photos
text | Doc No.
checkpoint | 3.3 - Fill Placement
label | Ref docs - IFC Drawings
label | Acceptance criteria - Fill material shall be spread in layers not exceeding 150mm and compacted at +- 2% of OMC. Density testing of each fill layer at a rate of 1 test per 100m2 (min. 2 tests per site).
button | Acceptance | Yes,No,N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - H
label | Shoalhaven City Council: Key - H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
boolean | Compaction Test Report
text | No.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 - Foundations
label | Ref docs - IFC Drawings Note 191 (C)
label | Acceptance criteria - Witness bearing capacity of excavations prior to pouring of any foundations by geotechnical engineer
button | Acceptance | Yes,No,N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - H
label | Shoalhaven City Council: Key - H
holdpoint | AUTHORITY HOLDPOINT
section | 4.0 Backfilling and Geotextile and Erosion Control Mat
checkpoint | 4.1 - Backfill Material
label | Ref docs - IFC Drawings
label | Acceptance criteria - Appropriate backfill material as per IFC Drawings.
button | Acceptance | Yes,No,N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - W
label | Shoalhaven City Council: Key - W
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
boolean | Material Test Data
text | No.
checkpoint | 4.2 - Backfill Depth
label | Ref docs - IFC Drawings
label | Acceptance criteria - Backfilled to the depth as per the IFC Drawings.
button | Acceptance | Yes,No,N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - W
checkpoint | 4.3 - Backfill Compaction
label | Ref docs - IFC Drawings
label | Acceptance criteria - Compaction tests are conducted to ensure the specified compaction level is achieved.
button | Acceptance | Yes,No,N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - H
label | Shoalhaven City Council: Key - H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
boolean | Compaction Test Report
text | No.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.4 - Erosion Control Mat Installation
label | Ref docs - IFC Drawings
label | Acceptance criteria - Erosion Control Mat Installed as per IFC Drawings.
button | Acceptance | Yes,No,N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - W
label | Shoalhaven City Council: Key - W
checkpoint | 4.5 - Geotextile
label | Ref docs - TfNSW R44 cl3.2.4
label | Acceptance criteria - Geotextile installed as per the IFC drawing or the direction from the principal.
button | Acceptance | Yes,No,N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - W
label | Shoalhaven City Council: Key - W
section | 5.0 Blinding Layer
checkpoint | 5.1 - Blinding layer
label | Ref docs - IFC Drawings Note 68
label | Acceptance criteria - Blinding may be required to infill voids, uneven ground and cavities at foundation level to create a stable working platform. Where required, blinding layer should be created using granular site won soils and rockfill, compacted to minimum relative density of 70%.
button | Acceptance | Yes,No,N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - W
label | Shoalhaven City Council: Key - W
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
boolean | Material Test Data
text | Material Test Data No.
boolean | Compaction Test Report
text | Compaction Test Report No.
section | 6.0 Post Process
checkpoint | 6.1 - Tolerances
label | Ref docs - IFC Drawings
label | Acceptance criteria - Tolerances of the slope conform to the IFC Drawings.
button | Acceptance | Yes,No,N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
checkpoint | 6.2 - Non-Conformity
label | Ref docs - TfNSW Q6 CL8.3
label | Acceptance criteria - Identified non-conformity captured and closed-out.
button | Acceptance | Yes,No,N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
text | NCR No.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Works complete
text | Name:
text | Position:
text | Date Completed:
holdpoint | Sign ITP
checkpoint | Lot Conformance
select | Lot Status | Awaiting Hold Point Release,Awaiting NCR Closure,Awaiting Test Results,Awaiting Verification,Cancelled,Closed-out,Outstanding,Work In Progress
text | Lot opened date:
text | Lot opened by:
text | Date lot closed:
button | NCR raised? | Yes,No
text | NCR Raised Date:
button | NCR closed? | Yes,No
text | NCR Closed Date:
text | NCR Number:
text | Comments
holdpoint | Sign ITP
checklist | SYM-0388-ITP-007 Structural Concrete Works [B] | itp |  |  |  | Yes | SYM-0388-ITP-007 Structural Concrete Works [B] | 697544c7-78aa-407a-a490-aba90c760b6e
section | 1.0 – PRELIMINARIES
checkpoint | 1.1 - Submit details of each concrete mix and proposed curing regime, together with a certificate stating that the nominated mix, its constituents and the proposed curing regime
label | Ref docs - TfNSW R53 Cl 2.4.3
label | Acceptance criteria - Submit at least 5 working days before the concrete mix is proposed to be used for the concrete mix.
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - H
label | Shoalhaven City Council: Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint-no-status | 1.1.1 - Lot Map
button | Lot map uploaded | Yes,No,N/A
checkpoint | 1.2 - Designate concrete truck washout area (s)
label | Acceptance criteria - Designate a washout bay for the cleaning of concrete trucks
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
section | 2.0 – CONCRETE WORKS
checkpoint | 2.1 - SWMS and Induction
label | Acceptance criteria - Ensure Symal SWMS in place for current works and all personal inducted to site
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
checkpoint | 2.2 - Submit formwork design documentation & certification
label | Ref docs - TfNSW R53 Cl 3.1 AS 3610.1
label | Acceptance criteria - Submission of Formwork design if required, Submit 5 working days before placing of reinforcement
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Determine Extent of the Site
label | Ref docs - IFC Drawings
label | Acceptance criteria - Survey work is performed by qualified surveyor using appropriate surveying equipment to determine extent of the site.
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - H
label | Shoalhaven City Council: Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Set out the structural element
label | Ref docs - IFC Drawings
label | Acceptance criteria - Centre and Invert of Pit or Stormwater Line set out by Survey
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
checkpoint | 2.5 - Weld Testing Results Prior to Delivery
label | Ref docs - IFC Drawings
label | Acceptance criteria - Weld testing results are sent to the client prior to delivery.
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Shoalhaven City Council: Key - W
checkpoint | 2.6 - Reinforcement
label | Ref docs - TfNSW R53 Cl3.2, IFC Drawings
label | Acceptance criteria - IFC Drawings
label | • Refer CC0388 Pre-Pour Checklist
label | 1. Lapped splices length as per drawings & Specs (400mm)
label | 2. Bar sizes correct
label | 3. Bar spacing correct
label | 4. Chairs adequate & correct type
label | 5. Reinforcement secure
label | • Cover to formwork faces is 50mm unless shown on the drawings
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
label | Shoalhaven City Council: Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.7 - Headed Anchor and Anchor Blocks
label | Ref docs - IFC Drawings, Manufacturer's Specifications
label | Acceptance criteria - The anchor is installed in the correct alignment.
label | • The lockshear bolts is tightened appropriately.
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
label | Shoalhaven City Council: Key - W
checkpoint | 2.8 - Concrete Joints
label | Ref docs - TfNSW R53 Cl3.3.9
label | Acceptance criteria - Joints constructed to prevent loss of mortar.
label | • If it’s an adjoining concrete, roughen the surface of constructions joints to expose coarse aggregate.
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
label | Shoalhaven City Council: Key - W
checkpoint | 2.9 - Formwork
label | Ref docs - TfNSW R53 Cl3.1 AS 3610.1
label | Acceptance criteria - IFC Drawings
label | – Formwork in the correct position and level
label | – Embedment in correct position and level
label | – Formwork is clean, oiled and free from grease, adequately supported in place with no movement.
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
label | Shoalhaven City Council: Key - W
section | 3.0 – CONCRETE PLACEMENT
checkpoint | 3.1 - Pre pour planning
label | Ref docs - TfNSW R53 Cl3.3.1 Cl3.3.2 Cl3.3.3
label | Acceptance criteria - Ensure the following:
label | 1. Areas free of water
label | 2. Construction debris removed
label | 3. Concrete temperature at the point of discharge is <32°C except for precast concrete members.
label | 4. Air temperature at the point of discharge is between 5°C and 35°C.
label | 5. Rain not forecasted
label | 6. NATA lab arranged
label | • Concrete pump or crane / kibble arranged (where required)
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
checkpoint | 3.2 - Intention to place concrete in the Works
label | Ref docs - TfNSW R53 Cl3.3.1
label | Acceptance criteria - Submit checklists for verifying conformity of the following:
label | – Nominated Concrete Mix
label | – Formwork
label | – Reinforcement
label | – Embedment’s and other relevant details
label | – Intention to place concrete in the Works.
label | • Submit ≥2 working days before commencement.
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Pour in Progress Inspections
label | Ref docs - TfNSW R53
label | Acceptance criteria - Ensure the following:
label | 1. Adequate resources are onsite for works
label | 2. Adequate vibrators are available as necessary
label | 3. Record Times
label | • Concrete is being compacted adequately
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
label | Shoalhaven City Council: Key - W
checkpoint | 3.4 - Concrete Slump/Strength Field Testing
label | Ref docs - TfNSW R53 Cl4.1, Annex B53/L
label | Acceptance criteria - Slump Test 1 per first 3 batches
label | • Strength test, Concrete Cylinder set of 7,28,28 days every 100m3
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
label | Shoalhaven City Council: Key - H
holdpoint | AUTHORITY HOLDPOINT
section | 4.0 – AFTER CONCRETE POUR
checkpoint | 4.1 - Curing
label | Ref docs - TfNSW R53 Cl2..6 Cl3.4
label | Acceptance criteria - Apply approved concrete curing compound in line with specification
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
checkpoint | 4.2 - Stripping of Formwork
label | Ref docs - TfNSW R53 Cl3.3.7
label | Acceptance criteria - Stripping of Concrete
label | • External surfaces – 2 days
label | • Permanently Hidden Surface – 1 day
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
checkpoint | 4.3 - Inspection of Concrete Surface Finish/Class
label | Ref docs - TfNSW R53 Cl4.2 Cl3.3.8
label | Acceptance criteria - Inspect for
label | 1. Compliance with specified surface finish;
label | 2. Check for extent of any cracking after 21 days (Cracks are less than 0.2 mm)
label | • are repairs required, specify repair methods
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
label | Shoalhaven City Council: Key - W
checkpoint | 4.4 - Tolerance
label | Ref docs - TfNSW R53 Cl4.3 AS3610.1
label | Acceptance criteria - Within tolerance set out in R53
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
checkpoint | 4.5 - Test Results
label | Ref docs - TfNSW R53
label | Acceptance criteria - Test certificates received, reviewed and conforming to requirements.
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
checkpoint | Works complete
text | Name:
text | Position:
text | Date Completed:
holdpoint | Sign ITP
checkpoint | Lot Conformance
select | Lot Status | Awaiting Hold Point Release,Awaiting NCR Closure,Awaiting Test Results,Awaiting Verification,Cancelled,Closed-out,Outstanding,Work In Progress
text | Lot opened date:
text | Lot opened by:
text | Date lot closed:
button | NCR raised? | Yes,No
text | NCR Raised Date:
button | NCR closed? | Yes,No
text | NCR Closed Date:
text | NCR Number:
text | Comments
holdpoint | Sign ITP
checklist | SYM-0388-ITP-006 Mass Block Retaining Wall [B] | itp |  |  |  | Yes | SYM-0388-ITP-006 Mass Block Retaining Wall [B] | 6e019156-61e8-42d8-8588-b4654894e488
section | 1.0 General
checkpoint | 1.1 - Block Material Type
label | Ref docs - IFC Drawings
label | Acceptance criteria - Blocks to be correct size and approved prior to placement.
label | • 1m (W) x 1m (H) x 1m (L)
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - H
label | Shoalhaven City Council: Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint-no-status | 1.1.1 - Lot Map
button | Lot map uploaded | Yes,No,N/A
checkpoint | 1.2 - Concrete Core Fill Mix
label | Ref docs - IFC Drawings
label | Acceptance criteria - Core fill material shall be minimum 25 MPa concrete
label | • Material properties meet project specification, AS 3600, AS 1379.
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - H
label | Shoalhaven City Council: Key - H
holdpoint | AUTHORITY HOLDPOINT
section | 2.0 Footing completion
checkpoint | 2.1 - Set out
label | Ref docs - IFC Drawings
label | Acceptance criteria - Extents and levels correct to relevant drawings
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - H
label | Shoalhaven City Council: Key - S
checkpoint | 2.2 - Footing complete and approved
label | Ref docs - IFC Drawings
label | Acceptance criteria - Retaining Wall Footing completed in line with Drawings and Specification
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - H
label | Shoalhaven City Council: Key - H
holdpoint | AUTHORITY HOLDPOINT
section | 3.0 Retaining wall construction
checkpoint | 3.1 - Steel reinforcement
label | Ref docs - IFC Drawings
label | Acceptance criteria - Steel reinforcement to be placed as per design drawings with the correct amount of cover.
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - H
label | Shoalhaven City Council: Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Setout and positioning correct
label | Ref docs - IFC Drawings
label | Acceptance criteria - Setout of block courses correct to line and level. Wall shall be generally straight and true.
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - H
label | Shoalhaven City Council: Key - S
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Blockwork jointing
label | Ref docs - IFC Drawings
label | Acceptance criteria - Expansion joints to be installed in accordance with Construction Drawings/ Manufacturer Spec using correct materials.
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - W
label | Shoalhaven City Council: Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
checkpoint | 3.4 - Blockwork installation
label | Ref docs - IFC Drawings
label | Acceptance criteria - Blocks shall be installed in accordance with the details of the Civil Drawings/ Manufacturer Spec.
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
label | Shoalhaven City Council: Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
checkpoint | 3.5 - Core filling
label | Ref docs - TfNSW R53 CL.3.3.4
label | Acceptance criteria - Concrete shall be transported, handled and placed to prevent segregation, loss or leakage of materials.
label | • Concrete to be tamped/vibrated to increase density and prevent voids, honeycombing or surface defects.
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
label | Shoalhaven City Council: Key - W
checkpoint | 3.6 - Strength testing
label | Ref docs - TfNSW R53 Annexure L AS 1379
label | Acceptance criteria - Samples to be taken from chute. Each sample shall consist of two cylinder specimens for 28 day testing.
label | – – – – – – – – – – – – – – – – – – –
label | No. of samples ¦¦ Volume of concrete (m3)
label | 2 ¦¦ <50
label | 3 ¦¦ 50-100
label | 4 ¦¦ 101-250
label | 5 ¦¦ >250
label | – – – – – – – – – – – – – – – – – – –
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
label | Shoalhaven City Council: Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Test report
checkpoint | 3.7 - Capping Block
label | Ref docs - IFC Drawings
label | Acceptance criteria - Capping Block is installed along top block of retaining Wall
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
label | Shoalhaven City Council: Key - S
section | 4.0 Backfill
checkpoint | 4.1 - Non-Woven Geotextile
label | Ref docs - IFC Drawings
label | Acceptance criteria - Install 1 layer of Bidim A34 (or equivalent) non-woven geotextile. Ensure geotextile is properly anchored
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - W
label | Shoalhaven City Council: Key - W
checkpoint | 4.2 - Backfill
label | Ref docs - IFC Drawings
label | Acceptance criteria - Install rock fill comprising max 200mm particle size well graded rock.
label | • Symal’s Geotechnical Engineer to detail the maximum installation slope of backfill material
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
label | Shoalhaven City Council: Key - S
section | 5.0 Subsoil
checkpoint | 5.1 - Subsoil Drainage Pipe
label | Ref docs - IFC Drawings
label | Acceptance criteria - DN100 Socked Subsoil Drainage Pipe installed at base of wall before backfill.
label | • Discharge through face of wall at 25m centres
label | ○ Provide clear out riser to surface
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - W
label | Shoalhaven City Council: Key - W
checkpoint | 5.2 - Subsoil Aggregate
label | Ref docs - IFC Drawings
label | Acceptance criteria - Install subsoil layer min. 200mm wide from rear face of wall before backfill.
label | • Aggregate to be nominal 20mm in dimension.
label | ○ Wrapped in approved Geotextile.
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
label | Shoalhaven City Council: Key - S
section | 5.0 Conformance check
checkpoint | 5.1 - Subsoil Drainage Pipe
label | Ref docs - Tolerances
label | Acceptance criteria - Surface Level: the top surface level must be as per design levels or as approved.
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
label | Shoalhaven City Council: Key - S
checkpoint | 5.2 - NCR Closeout
label | Ref docs - Contract Documents
label | Acceptance criteria - All defects have been rectified and NCR’s closed out and Site is accepted
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - H
label | Shoalhaven City Council: Key - S
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Works complete
text | Name:
text | Position:
text | Date Completed:
holdpoint | Sign ITP
checkpoint | Lot Conformance
select | Lot Status | Awaiting Hold Point Release,Awaiting NCR Closure,Awaiting Test Results,Awaiting Verification,Cancelled,Closed-out,Outstanding,Work In Progress
text | Lot opened date:
text | Lot opened by:
text | Date lot closed:
button | NCR raised? | Yes,No
text | NCR Raised Date:
button | NCR closed? | Yes,No
text | NCR Closed Date:
text | NCR Number:
text | Comments
holdpoint | Sign ITP
checklist | SYM-0388-ITP-011 Spray Seal [B] | itp |  |  |  | Yes | SYM-0388-ITP-011 Spray Seal [B] | 6f16f491-c9ce-4a15-adc7-5e59d7179f60
section | 1.0 Traffic
checkpoint | 1.1 - Traffic Management Plan Submitted
label | Ref docs - TfNSW G10 Cl. 2.2
label | Acceptance criteria - Submitted at least 20 working days prior to submission of ROL’s if required.
button | Acceptance | Yes,No,N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint-no-status | 1.1.1 - Lot Map
button | Lot map uploaded | Yes,No,N/A
checkpoint | 1.2 - Traffic Control Plan
label | Ref docs - TfNSW G10 Cl. 2.5
label | Acceptance criteria - If not previously submitted as part of the TMP or where a TMP is not required, submitted at least 3 working days prior to its proposed use.
button | Acceptance | Yes,No,N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - ROL’s
label | Ref docs - TfNSW G10 Cl. 2.1
label | Acceptance criteria - Submitted at least ten (10) days prior to commencement of works.
button | Acceptance | Yes,No,N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - Survey Extent of the Site
label | Ref docs - IFC Drawing
label | Acceptance criteria - Survey work is performed by qualified surveyor using appropriate surveying equipment to determine extent of the site.
button | Acceptance | Yes,No,N/A
section | 2.0 Material
section | 2.1 Bituminous Material
checkpoint | 2.1.1 - Binder
label | Ref docs - TfNSW R106/R107 Cl. 2.1.1
label | Acceptance criteria - Conformance of Characteristics as per tables 3252.1 and 3253.1
label | – – – – – – – – – – – – –
label | Property
label | – – – – – – – – – – – – –
label | Viscosity at 165°C (1) Pa.s
label | Torsional recovery at 25°C, 30 s %
label | Softening point °C
label | Viscosity at 60°C Pa.s
label | Penetration at 25°C 0.1 mm
label | – – – – – – – – – – – – –
label | • Sample to be taken for each load at delivery point
button | Acceptance | Yes,No,N/A
checkpoint | 2.1.2 - Storage and Handling
label | Ref docs - TfNSW R106/R107 Cl. 2.1.2
label | Acceptance criteria - Bitumen not to be heated above the manufacturer’s recommendations
button | Acceptance | Yes,No,N/A
section | 2.2 Aggregate Precoating Agent & Bitumen Adhesion Agent
checkpoint | 2.2.1 - Aggregate Precoating Agent
label | Ref docs - TfNSW R106/R107 Cl. 2.2
label | Acceptance criteria - Aggregate precoating agents must conform to Specification TfNSW 3268 for the grade of polymer modified binder specified in Annexure R107/A.
button | Acceptance | Yes,No,N/A
checkpoint | 2.2.2 - Bitumen Adhesion Agent
label | Ref docs - TfNSW R106/R107 Cl. 2.2
label | Acceptance criteria - Bitumen adhesion agents must conform to Specification TfNSW 3269 for the grade of polymer modified binder specified in Annexure R107/A.
button | Acceptance | Yes,No,N/A
section | 2.3 Oils for Reducing the Viscosity of Bitumen
checkpoint | 2.3.1 - Oils for Reducing the Viscosity of Bitumen
label | Ref docs - TfNSW R106/R107 Cl. 2.3
label | Acceptance criteria - The oils for reducing the viscosity of bitumen must conform to AS 3568.
button | Acceptance | Yes,No,N/A
section | 2.4 Aggregate
checkpoint | 2.4.1 - Properties
label | Ref docs - TfNSW R106/R107 Cl. 2.4.1
label | Acceptance criteria - The supply and delivery of aggregate must meet the requirements of Specification TfNSW 3151.
label | • Test results for each site of aggregate must be obtained before use in the Works.
label | • If requested, a sample from the same site must be provided to the Principal.
label | • The sample size must follow AS 1141.3.
button | Acceptance | Yes,No,N/A
checkpoint | 2.4.2 - Stockpiles
label | Ref docs - TfNSW R106/R107 Cl. 2.4.2
label | Acceptance criteria - Arrange and manage aggregate stockpiles in accordance with the following requirements:
label | • The maximum Site size for aggregate stockpiles is 250 m3.
label | • Stockpiles must be placed on firm level ground and separated from other stockpiles to prevent cross-contamination.
label | • The quantity and type of each stockpile must be clearly labeled.
label | • Recovery from stockpiles must minimize segregation and contamination.
button | Acceptance | Yes,No,N/A
section | 2.5 Geotextile
checkpoint | 2.5.1 - Properties
label | Ref docs - TfNSW R106/R107 Cl. 2.5
label | Acceptance criteria - Nonwoven needle punched fabric.
label | • Minimum melting point: 165°C.
label | • Minimum mass: 130 g/m2.
label | • Minimum bitumen saturation: 0.9 L/m2
button | Acceptance | Yes,No,N/A
section | 3.0 Nominated Materials and Design of Bituminous Surfacing
checkpoint | 3.1 - Surface texture
label | Ref docs - TfNSW R106/R107 Cl. 1.1
label | Acceptance criteria - Measure surface texture – Test Method T240
button | Acceptance | Yes,No,N/A
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Five (5) measurements every 250 metres and at changes in aggregate size or heavy patches (shoulder, wheel paths, between wheel paths and centre line) per lane of sprayed bituminous surfacing works)
checkpoint | 3.2 - Design
label | Ref docs - TfNSW R106/R107 Cl. 3.1
label | Acceptance criteria - Nominated application rates using T240 results and nominated materials.
button | Acceptance | Yes,No,N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Bitumen application rate in L/m², Aggregate spread rate in m²/m³
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Proportions of Constituents
label | Ref docs - TfNSW R106/R107 Cl. 3.2
label | Acceptance criteria -
label | – – – – – – – – – – – – –
label | Constituent ¦¦ Bituminous Surfacing ¦¦ Limit
label | – – – – – – – – – – – – –
label | Bitumen Adhesion Agent ¦¦ Prime/Primer seal ¦¦ 1 % maximum
label | Bitumen Adhesion Agent ¦¦ Seal/Reseal ¦¦ 0.5 - 1.0 % depending on the results of initial adhesion and stripping tests or anticipated weather
label
label | Cutter Oil ¦¦ Prime/Primer seal ¦¦ as per design
label | Cutter Oil ¦¦ Seal/Reseal ¦¦ as per TfNSW Form 382
label
label | Flux Oil ¦¦ Seal/Reseal ¦¦ Subject to the Principal's approval of your proposal, you may use up to 4%
label | – – – – – – – – – – – – –
button | Acceptance | Yes,No,N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 - Submission Materials and Spray Seal Design
label | Ref docs - TfNSW R106 CL. 3.3/R107 Cl. 3.2
label | Acceptance criteria - Submission of Nominated design, T240 surface texture recordings, nominated materials and conformance certificates
button | Acceptance | Yes,No,N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Constituent material:
label | • Aggregate
label | • Binder
label | • Precoat
label | • Adhesion agent
label | • Cutter oil (7 days prior to works being carried out)
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.5 - Design Review
label | Ref docs - TfNSW R106 CL. 3.4/R107 Cl. 3.3
label | Acceptance criteria - Review design at each location based on actual ALD test result for the actual aggregate to be used instead of the ALD of the nominated material.
button | Acceptance | Yes,No,N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - H
holdpoint | AUTHORITY HOLDPOINT
section | 4.0 Process Control
checkpoint | 4.1 - Sampling And Testing
label | Ref docs - TfNSW R106/R107 Cl. 4.1
label | Acceptance criteria - Materials are sampled and tested according to relevant specifications in Clause 2 and AS 2008. Testing complies with Annexure R107/L.
button | Acceptance | Yes,No,N/A
checkpoint | 4.2 - Application Of Sprayed Bituminous Surfacing
label | Ref docs - TfNSW R106/R107 Cl. 4.2
label | Acceptance criteria - provide a uniform application of binder with adequate adhesion to the underlying surface.
label | • provide a complete cover of interlocking aggregate particles.
label | • achieve effective bond between binder and aggregate.
button | Acceptance | Yes,No,N/A
checkpoint | 4.3 - Process Control Chart
label | Ref docs - TfNSW R106 Cl. 4.3
label | Acceptance criteria - Use process control chart for work where 10 or more sprayer runs greater than 1,000 litres are required per shift.
label | • Take corrective action where conformance criteria is not met.
button | Acceptance | Yes,No,N/A
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - ≥ 2% and ≤5% over 5 successive runs
section | 5.0 Condition for Commencement of Sprayed Bituminous Surfacing Works
checkpoint | 5.1 - Aggregate Delivery
label | Ref docs - TfNSW R106/R107 C.L. 5.1
label | Acceptance criteria - Aggregate supplied with a light, uniform coverage of all particles. Store to avoid contamination– Clean and dry.
label | • Stockpile the material at the site, the maximum site size must not exceed 250 cubic metres
label | • Adequately precoated
button | Acceptance | Yes,No,N/A
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Cover aggregate if rain is imminent
checkpoint | 5.2 - Transitions
label | Ref docs - IFC Drawing
label | Acceptance criteria - Loose or damaged material is removed.
label | • Transition areas are properly compacted.
label | • Neat edges on the transition area.
button | Acceptance | Yes,No,N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
boolean | Transition extent mark-up
checkpoint | 5.3 - Preparation Of Pavement Surface
label | Ref docs - TfNSW R106/R107 CL. 5.2
label | Acceptance criteria - Pavement surface to be swept by use of rotary road broom, suction broom and stiff bass hand broom (if needed).
button | Acceptance | Yes,No,N/A
label | Verify of acceptance by
label | Shoalhaven City Council: Key - W
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Sweeping must extend a least 300mm beyond each edge.
checkpoint | 5.4 - Pick Up Surface Level
label | Ref docs - IFC Drawing
label | Acceptance criteria - Surface Level picked up by qualified surveyor.
button | Acceptance | Yes,No,N/A
label | Verify of acceptance by
label | Shoalhaven City Council: Key - W
checkpoint | 5.5 - Pavement Temperature and Weather Conditions
label | Ref docs - TfNSW R106/R107 CL. 5.3
label | Acceptance criteria - Measure and record pavement temperatures at regular intervals during the course of work.
label | • Where spray sealing is delayed and significant rain events have since occurred, undertake moisture testing to ensure the base has achieved sufficient dry back.
button | Acceptance | Yes,No,N/A
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - If pavement is in shade and sun take both measurements.
label | • Do not spray wet pavement or when rain is imminent
label | • Do not spray during strong winds or dust storm.
checkpoint | 5.6 - Protection of services and road fixtures
label | Ref docs - TfNSW R106/R107 CL. 5.4
label | Acceptance criteria - Protect road fixtures, (gratings, hydrants, valve boxes, hydrants, manhole covers, bridge or culvert decks etc.
label | • Remove adherent patches of foreign material from the surface of the pavement. Mask or remove raised pavement markers.
button | Acceptance | Yes,No,N/A
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - TRPMs shall be the same colour as the colour of the RRPMs. For example, they should be:
label | • Supplement the lane line - white
label | • Dividing line - yellow
label | • TRPMs should simulate the normal RRPM pattern for the respective pavement markings
section | 6.0 Application of Sprayed Bituminous Surfacing
checkpoint | 6.1 - Plant
label | Ref docs - TfNSW R106/R107 C.L. 6.1
label | Acceptance criteria - Certification and operation of sprayer
label | • Sufficient loaded and measured trucks of dry aggregate to provide full cover for the area sprayed and a uniform finish.
label | • Rollers – dual axle smooth pneumatic tyred multi-wheel with mass greater than seven (7) tonnes without ballast and minimum tyre pressure of 550kPa.
button | Acceptance | Yes,No,N/A
checkpoint | 6.2 - Operation of the Sprayer
label | Ref docs - TfNSW R106/R107 C.L. 6.2
label | Acceptance criteria - Protect all fixtures using paper (or other appropriate barrier material)
label | • Check the quantity of binder sprayed against the area covered and make necessary adjustments.
label | • 50 mm overlap spray between adjacent longitudinal for special type end nozzles or intermediate nozzles set with a jig.
label | • normal manner for intermediate nozzles and the overlap must be at least 300 mm.
button | Acceptance | Yes,No,N/A
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Dip after each run
label | • Within ±5% of target design application rate for conventional and PMB bitumen’s
label | And
label | • ±10% for PMB containing scrap rubber
checkpoint | 6.3 - Bitumen Type and Temperature Requirements
label | Ref docs - TfNSW R106/R107 C.L. 6.3 & 6.6
label | Acceptance criteria -
label | – – – – – – – – – – – – –
label | Class ¦¦ Temperature Range (°C)
label | – – – – – – – – – – – – –
label | 170, Multigrade (600/170) ¦¦ 160-190
label | 240 ¦¦ 165-195
label | 320 ¦¦ 170-200
label | PMB ¦¦ Manufacturer recommended temperature
label | – – – – – – – – – – – – –
button | Acceptance | Yes,No,N/A
section | 7.0 Application of Binder
checkpoint | 7.1 - Spraying of Binder
label | Ref docs - TfNSW R106/R107 C.L. 7.1 & 7.2
label | Acceptance criteria - Application of binder over primer as per design application rate.
label | • Limit area to be sprayed to ensure coverage of aggregate at the target application rated and initially rolled within;
label | • Conventional Bitumen: 15mins
label | • PMB: 5mins
button | Acceptance | Yes,No,N/A
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Keep all traffic off primed surface
section | 8.0 Application and Incorporation of Aggregate
checkpoint | 8.1 - Application and Incorporation of Aggregate
label | Ref docs - TfNSW R106/R107 C.L. 8
label | Acceptance criteria - Only precoated aggregate should be used.
label | • The aggregate must be of the specified size and applied at the target rate. The actual spread rate must be determined using TfNSW T274 or an approved method and reported using TfNSW Form 500E.
label | • The aggregate must be spread uniformly using suitable equipment and any bare or insufficiently covered areas must be re-run or covered by hand to achieve uniform coverage at the target rate.
label | • Initial rolling must be carried out using two or more dual axle smooth pneumatic tyred multi-wheel rollers with a minimum load of one tonne per tyre and minimum tyre pressure of 550 kPa until aggregate is firmly embedded in the binder.
label | • Rolling must continue with at least eight passes within one hour of spraying at every point on the surface. Sufficient rollers must be on site to complete the specified minimum amount of rolling as a continuous operation with successive spray runs.
button | Acceptance | Yes,No,N/A
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Aggregate application must begin within five minutes of spraying the binder and be completed and initially rolled within that time.
label | • Aggregate containing surface moisture or free surface water should not be used.
label | • If the aggregate is not evenly distributed, a light drag broom may be used after initial rolling. If the broom dislodges aggregate particles, drag brooming should be deferred or eliminated.
section | 9.0 Sweeping and Loose Aggregate Removal (10mm and 14mm Seal / Reseals only)
checkpoint | 9.1 - Final sweeping and loose aggregate measurement prior to opening to traffic.
label | Ref docs - TfNSW R106/R107 C.L. 7.1 & 7.2
label | Acceptance criteria - All loose material removed.
label | • Measure loose aggregate particles – RMS Test method T277.
label | • Maximum allowable loose particles:
label | • Urban Areas: 20 particles / m²
label | • Other medium to high traffic (250 v/l/d): 30 particles / m²
label | • Low traffic (≤ 250 v/l/d): 40 particles / m²
button | Acceptance | Yes,No,N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - W
label | Shoalhaven City Council: Key - W
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Temporary 60 km/h speed zoning must be in place until the maximum allowable loose aggregate requirement is met.
checkpoint | Works complete
text | Name:
text | Position:
text | Date Completed:
holdpoint | Sign ITP
checkpoint | Lot Conformance
select | Lot Status | Awaiting Hold Point Release,Awaiting NCR Closure,Awaiting Test Results,Awaiting Verification,Cancelled, Closed-out,Outstanding,Work In Progress
text | Lot opened date:
text | Lot opened by:
text | Date lot closed:
button | NCR raised? | Yes,No
text | NCR Raised Date:
button | NCR closed? | Yes,No
text | NCR Closed Date:
text | NCR Number:
text | Comments
holdpoint | Sign ITP
checklist | SYM-0388-ITP-009 Pavement Construction [B] | itp |  |  |  | Yes | SYM-0388-ITP-009 Pavement Construction [B] | 87dcc060-545e-446e-acde-149f4ac1d7f4
section | 1.0 Preliminaries
checkpoint | 1.1 - Determine Site Size
label | Ref docs - IFC Drawings
label | Acceptance criteria - What is the site size.
text | Acceptance |  |  | m2
label | Verify of acceptance by
label | Symal Infrastructure: Key - W
label | Shoalhaven City Council: Key - W
checkpoint-no-status | 1.1.1 - Lot Map
button | Lot map uploaded | Yes,No,N/A
checkpoint | 1.2 - Survey Set Out
label | Ref docs - IFC Drawings
label | Acceptance criteria - Is the work area clearly pegged out for line and level?
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - W
label | Shoalhaven City Council: Key - W
checkpoint | 1.3 - Material Classification and Source
label | Ref docs - IFC Drawings
label | Acceptance criteria - Pavement Base and Subbase meets specification as per TfNSW Specification 3051 and construction drawings.
label | • Pavement Base and Subbase Material:
boolean | DGB20
boolean | DGB20
boolean | DGS40
boolean | Other
text | Other:
text | Source
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - H
label | Shoalhaven City Council: Key - H
holdpoint | AUTHORITY HOLDPOINT
section | 2.0 Conformance of Previous Layer
checkpoint | 2.1 - Conformance of Previous Layer
label | Ref docs - IFC Drawings
label | Acceptance criteria - Has the previous layer passed acceptance criteria?
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - W
section | 3.0 Pavement Construction
checkpoint | 3.1 - Placement
label | Ref docs - IFC Drawings
label | Acceptance criteria - Fill has been placed in compacted layers as per IFC Drawing.
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
checkpoint | 3.2 - Moisture
label | Ref docs - IFC Drawings
label | Acceptance criteria - Material must be maintained at optimum moisture content with additional water being added if required during compaction. Review and approve laboratory testing results
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
label | Shoalhaven City Council: Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Compaction
label | Ref docs - IFC Drawings
label | Acceptance criteria - Base / Subbase Layer has been adequately compacted achieving minimum either:
label | ○ Subbase
label | • 95%-100% SMDD (Refer to IFC Drawings)
label | ○ Base
label | • 100% SMDD
label | ○ Review and approve laboratory testing results
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - W
label | Shoalhaven City Council: Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 - Dry Back
label | Ref docs - TfNSW R71
label | Acceptance criteria - The field moisture content of base courses that are not being treated / stabilised and are to receive a bituminous seal must not exceed 70% of OMC.
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
checkpoint | 3.5 - Proof Roll Inspection
label | Ref docs - TfNSW R44
label | Acceptance criteria - Proof rolled surfaces must not exhibit visible deformation, rutting or yielding
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - W
label | Shoalhaven City Council: Key - H
holdpoint | AUTHORITY HOLDPOINT
section | 4.0 Conformance Check
checkpoint | 4.1 - Pavement Finish
label | Ref docs - IFC Drawings
label | Acceptance criteria - Has the pavement course been finished to a smooth and uniform surface?
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - W
label | Shoalhaven City Council: Key - W
checkpoint | 4.2 - Surface Level and pavement thickness of subbase / base.
label | Ref docs - IFC Drawings
label | Acceptance criteria - Surface Level and Pavement Thickness after compaction and surface trimming conform to the following requirements:
label | ○ Thickness:
label | • Base, - 0mm, + 20mm
label | • Subbase, ± 10mm
label | ○ Surface Level:
label | • Base, - 0mm, + 10mm
label | • Subbase, -10mm, +0mm
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
label | Shoalhaven City Council: Key - W
checkpoint | 4.3 - Surface Deviation
label | Ref docs - TfNSW T183
label | Acceptance criteria - Surface does not deviate more than 5mm from a 3 m straight edge when laid in any direction.
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - W
checkpoint | 4.4 - Width
label | Ref docs - IFC Drawings
label | Acceptance criteria - Width of pavement between outside edges is not less than the width specified on the drawings.
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - W
checkpoint | 4.5 - NCR
label | Acceptance criteria - Any NCRs have been closed out
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - H
label | Shoalhaven City Council: Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Works complete
text | Name:
text | Position:
text | Date Completed:
holdpoint | Sign ITP
checkpoint | Lot Conformance
select | Lot Status | Awaiting Hold Point Release,Awaiting NCR Closure,Awaiting Test Results,Awaiting Verification,Cancelled,Closed-out,Outstanding,Work In Progress
text | Lot opened date:
text | Lot opened by:
text | Date lot closed:
button | NCR raised? | Yes,No
text | NCR Raised Date:
button | NCR closed? | Yes,No
text | NCR Closed Date:
text | NCR Number:
text | Comments
holdpoint | Sign ITP
checklist | SYM-0388-ITP-012 Signage [B] | itp |  |  |  | Yes | SYM-0388-ITP-012 Signage [B] | 968e15d0-db89-460a-972a-a2a1f33a3adf
section | 1.0 Preliminaries
checkpoint | 1.1 - Survey set-out
label | Ref docs - TfNSW R143 Construction drawings
label | Acceptance criteria - Has the work area and all required signage been set out for correct positions?
button | Acceptance | Yes, No, N/A
label | • Has the set out been approved by Shoalhaven City Council?
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - H
label | Shoalhaven City Council: Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint-no-status | 1.1.1 - Lot Map
button | Lot map uploaded | Yes,No,N/A
section | 2.0 Signage install
checkpoint | 2.1 - Foundations
label | Ref docs - TfNSW R143 Construction drawings
label | Acceptance criteria - Have all post footings been set in concrete foundations to the depths show in the Sign & Post Schedule with the following diameters:
label | • <32mm Steel Posts: 225mm
label | • 80mm-150mm Steel Posts: 300mm
label | • 180mm x 100mm Frangible: 300mm
label | Is the finished
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
boolean | Subcontractors ITP
checkpoint | 2.2 - Installation of posts
label | Ref docs - TfNSW R143 Construction drawings
label | Acceptance criteria - Have all posts been installed in accordance with the following requirements:
label | – Posts shall be straight
label | – Posts shall be vertical with a maximum deviation of 1 in 100
label | – Post tops shall be 50mm (+/- 10mm) below the top edge of the sign
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
label | Shoalhaven City Council: Key - W
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
boolean | Subcontractors ITP
checkpoint | 2.3 - Installation of signs
label | Ref docs - TfNSW R143 Construction drawings
label | Acceptance criteria - Has all signage been installed as per the design drawings and sign & post schedule and in accordance with the following requirements:
label | – Signs shall be level with a maximum deviation of 1 in 100
label | – Symmetrically (where applicable)
label | – Sign surface shall present an even surface free from faults
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
label | Shoalhaven City Council: Key - W
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
boolean | Subcontractors ITP
checkpoint | 2.4 - Tolerances
label | Ref docs - TfNSW R143 Construction drawings
label | Acceptance criteria - Has the signage been installed in accordance with RMS standards, to following tolerances:
label | – Height: +/- 40 mm
label | – Location: +/- 100mm
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - W
checkpoint | 2.5 - Temporary masking
label | Ref docs - TfNSW R143 Construction drawings
label | Acceptance criteria - Have the required signs been masked to effectively and securely cover the signage prior to implementation?
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - S
label | Shoalhaven City Council: Key - W
checkpoint | Works complete
text | Name:
text | Position:
text | Date Completed:
holdpoint | Sign ITP
checkpoint | Lot Conformance
select | Lot Status | Awaiting Hold Point Release,Awaiting NCR Closure,Awaiting Test Results,Awaiting Verification,Cancelled,Closed-out,Outstanding,Work In Progress
text | Lot opened date:
text | Lot opened by:
text | Date lot closed:
button | NCR raised? | Yes,No
text | NCR Raised Date:
button | NCR closed? | Yes,No
text | NCR Closed Date:
text | NCR Number:
text | Comments
holdpoint | Sign ITP
checklist | SYM-0388-ITP-004 Ground Support [B] | itp |  |  |  | Yes | SYM-0388-ITP-004 Ground Support [B] | cb6ec89c-1959-43b7-a728-1808a0c14069
section | 1.0 Preliminaries
checkpoint | 1.1 - Construction Program and Method Statement
label | Ref docs - TfNSW R64
label | Acceptance criteria - Clause 3.1 - TfNSW R64
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - H
label | Shoalhaven City Council: Key - H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Submittals of Construction Program and Method Statement prior to start the activity.
holdpoint | AUTHORITY HOLDPOINT
checkpoint-no-status | 1.1.1 - Lot Map
button | Lot map uploaded | Yes,No,N/A
checkpoint | 1.2 - Mix Design: Soil Nails
label | Ref docs - TfNSW R64
label | Acceptance criteria - Clause .2.27 - TfNSW R64, As per relevant MAR
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - H
label | Shoalhaven City Council: Key - H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Cement Grout Mix Design for Soil Nails
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Mix Design: Shotcrete
label | Ref docs - TfNSW R64, TfNSW R68
label | Acceptance criteria - Clause 3.8.1 - TfNSW R68, As per relevant MAR
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - H
label | Shoalhaven City Council: Key - H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Exposure Classification B2 shotcrete mix design.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - Material: Soil Nail
label | Ref docs - TfNSW R64
label | Acceptance criteria - Clause 2.1 - TfNSW R64, As per IFC Drawing / MAR
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - H
label | Shoalhaven City Council: Key - H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Material Certificates for the structural components.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - Suitability Test: Soil Nail
label | Ref docs - TfNSW R64
label | Acceptance criteria - Clause 5.1 - TfNSW R64
label | • Clause 5.2.1 - TfNSW R64
label | • Clause 5.4 - TfNSW R64
label | ○ The number of test nails to be assessed by Suitability Test must be the greater of:
label | (i) the number specified on the Design Documentation drawings; or
label | (ii) 1% of the permanent nails but not less than 2.
label | ○ The Suitability test will be considered successful if all of the following are satisfied:
label | (i) A total creep movement of less than 2 mm between the 6 and 60 minutes readings is measured during Cycle 4; and
label | (ii) A total creep movement of less than 1mm between the 60 and 180 minutes readings is measured in Cycle 4; and
label | (iii) The creep rate is linear or decreasing, when plotted against the logarithm of time throughout Cycle 4.
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - H
label | Shoalhaven City Council: Key - H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Suitability Test Reports
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.6 - Test Equipment
label | Ref docs - TfNSW R64
label | Acceptance criteria - Clause 5.3 - TfNSW R64
label | • Submit NATA Calibration Certificate (issued within 12 month) accompanied by the related calibration curve and tabulated record of hydraulic pressure against jack load.
label | • The identification numbers on the field test equipment must match the identification numbers on the calibration data sheets.
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - W
label | Shoalhaven City Council: Key - W
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Calibration Certificates for hydraulic jack, pressure gauge and load cell as a set.
label | • Hydraulic jack with a minimum travel of 150 mm.
label | • Dial gauge with a minimum accuracy of 0.01 mm.
section | 2.0 Operations
checkpoint | 2.1 - Surface Preparation
label | Ref docs - TfNSW R64 Cl. 3.3
label | Acceptance criteria - Witness of exposed slope face after clearing of each section.
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - W
label | Shoalhaven City Council: Key - W
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Unless otherwise shown on the Drawings or directed by the Principal, construct soil nail slopes in an incremental, “top-down” manner.
checkpoint | 2.2 - Soil Nail Installation
label | Ref docs - TfNSW B64
label | Acceptance criteria - Clause 3.4 - TfNSW R64
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - W
label | Shoalhaven City Council: Key - H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Drill Record
label | • As-built Drawing
label | • Soil Nail Installation Checklist
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Soil Nail Grouting
label | Ref docs - TfNSW R64, ASTM C940, ASTM C939, TfNSW T375
label | Acceptance criteria - Clause 2.2.7 - TfNSW R64
label | • Clause 3.4.3 - TfNSW R64
label | • Final Bleeding <0.5%
label | • Fluidity <20s
label | • Compressive Strength (7 Days) > 32MPa
label | • Compressive Strength (28 Days) >40MPa @28Days
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - W
label | Shoalhaven City Council: Key - W
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Grout Record
label | • Compressive Strength Test Report
checkpoint | 2.4 - Soil Nail Acceptance Test
label | Ref docs - TfNSW R64
label | Acceptance criteria - Clause 5.1 - TfNSW R64
label | • Clause 5.2.2 - TfNSW R64
label | • Clause 5.4 - TfNSW R64
label | ○ A total of 3% of permanent nails must be subjected to Acceptance Test.
label | ○ The acceptance test will be considered successful if all of the following are satisfied:
label | (a) A total creep movement of less than 2 mm between the 6 and 60 minutes readings is measured in Creep Test hold period; and
label | (b) A total creep movement of less than 1 mm between the 60 and 180 minutes readings is measured in Creep Test hold period; and
label | (c) The creep rate is linear or decreasing, when plotted against the logarithm of time throughout Creep Test hold period.
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - H
label | Shoalhaven City Council: Key - H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Acceptance Test Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Slope Preparation
label | Ref docs - TfNSW R64 CL. 6.2, TfNSW R68 CL. 4.2
label | Acceptance criteria - Inspection and approval of surface preparation for mesh placement and shotcreting.
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - W
label | Shoalhaven City Council: Key - W
checkpoint | 2.6 - Horizontal Drains Installation
label | Ref docs - TfNSW R40
label | Acceptance criteria - Clause 3 - TfNSW R40
label | • Clause 4 - TfNSW R40
label | • As per IFC Drawing
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - W
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Horizontal Drains Installation Record
label | • Horizontal Drainage Installation Checklist
label | • As-built Drawing
checkpoint | 2.7 - Sl72 Galvanised Mesh
label | Ref docs - IFC Drawings
label | Acceptance criteria - Steel reinforcement SL72 2N12 1200mm long is centrally located in both direction at each soil nail.
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - W
label | Shoalhaven City Council: Key - W
checkpoint | 2.8 - Grassroot Mattress
label | Ref docs - IFC Drawings, Manufacturer's Specification
label | Acceptance criteria - Grass roots erosion control geotextile matting (or equivalent) is correctly installed.
label | • Mat reinforcement pins are corrected installed.
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - W
label | Shoalhaven City Council: Key - W
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Shall be installed as per IFC Drawings / Manufacturer's Specification.
checkpoint | 2.9 - Preparation for Shotcrete Placement
label | Ref docs - TfNSW R68
label | Acceptance criteria - Clause 4 - TfNSW R68
label | • Protect the drainage system against contamination to ensure proper functioning.
label | • Steel mesh support anchor bars are correctly installed.
label | • Firmly fix steel reinforcement to prevent movement and vibration while the shotcrete is being applied.
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - W
label | Shoalhaven City Council: Key - W
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Shotcrete Inspection Checklist
checkpoint | 2.10 - Shotcrete Application
label | Ref docs - TfNSW R68
label | Acceptance criteria - Clause 7 - TfNSW R68
label | • Apply shotcrete in two successive layers of 50mm (and not exceeding 75 mm) thickness for a total of 100mm and with adequate adhesion to the surface or previous layers of shotcrete to prevent slumping or sagging.
label | • Shotcrete must not cover or impair the function of slotted pipe drain or strip drain outlets which protrude through the shotcrete layer.
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - W
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Pouring Record
checkpoint | 2.11 - Shotcrete Test
label | Ref docs - TfNSW R68
label | Acceptance criteria - 6.4.4 TfNSW R64, In accordance with mix design
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - W
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Concrete Test Report
checkpoint | 2.12 - Steel Wire Mesh installation
label | Ref docs - IFC Drawing
label | Acceptance criteria - Steel wire mesh (TECCO® or other equivalent). Shall be installed as per IFC Drawings.
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - W
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Mesh Installation Checklist
checkpoint | 2.13 - Surface Excavation
label | Ref docs - TfNSW R64 – 3.3
label | Acceptance criteria - 3.3 – TfNSW R64, As per IFC Drawing
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - W
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Earthworks Record
section | 3.0 Post Operations
checkpoint | 3.1 - Review of the Site
label | Ref docs - IFC Drawing
label | Acceptance criteria - Completeness of the documentation
button | Acceptance | Yes, No, N/A
label | Verify of acceptance by
label | Symal Infrastructure: Key - W
checkpoint | Works complete
text | Name:
text | Position:
text | Date Completed:
holdpoint | Sign ITP
checkpoint | Lot Conformance
select | Lot Status | Awaiting Hold Point Release,Awaiting NCR Closure,Awaiting Test Results,Awaiting Verification,Cancelled,Closed-out,Outstanding,Work In Progress
text | Lot opened date:
text | Lot opened by:
text | Date lot closed:
button | NCR raised? | Yes,No
text | NCR Raised Date:
button | NCR closed? | Yes,No
text | NCR Closed Date:
text | NCR Number:
text | Comments
holdpoint | Sign ITP
checklist | SYM-0388-ITP-003 Bored Piles [C] | itp |  |  |  | Yes | SYM-0388-ITP-003 Bored Piles [C] | df77a3a6-5c85-4472-91de-599e5bb0eee2
section | 1.0 Preliminaries
checkpoint | 1.1 - Documentation
label | Ref docs - IFC Drawing
label | Acceptance criteria - Check that you have the latest site and engineering IFC drawings before starting each task/set of tasks.
button | Acceptance | Yes,No,N/A
label | Verification or test by
label | Symal Infrastructure: Key - S
checkpoint-no-status | 1.1.1 - Lot Map
button | Lot map uploaded | Yes,No,N/A
checkpoint | 1.2 - Safety measures and plans
label | Ref docs - Site Documents/ SWMS
label | Acceptance criteria - Traffic Control Plan, Safety Plan, Environmental Management Plan, Symal Infrastructure Site Documents, Subcontractor SWMS.
button | Acceptance | Yes,No,N/A
label | Verification or test by
label | Symal Infrastructure: Key - S
checkpoint | 1.3 - Excavation permit
label | Ref docs - Symal Infrastructure GPP
label | Acceptance criteria - Have services within the works area been identified and a group penetration permit covers the area, is current and signed onto by the works crew? Check underground and overheads services.
button | Acceptance | Yes,No,N/A
label | Verification or test by
label | Symal Infrastructure: Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - Piling Plant and Equipment
label | Ref docs - TfNSW B59 Cl 3.3
label | Acceptance criteria - Details of the proposed piling equipment and method are submitted with certification.
button | Acceptance | Yes,No,N/A
label | Verification or test by
label | Symal Infrastructure: Key - H
label | Shoalhaven City Council: Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - Steel Reinforcement Material
label | Ref docs - IFC Drawing, TfNSW B59 Cl 2.3
label | Acceptance criteria - Certification Authority for Reinforcing Steel (ACRS) Certificate Submitted. Material test certificate Submitted.
button | Acceptance | Yes,No,N/A
label | Verification or test by
label | Symal Infrastructure: Key - S
label | Shoalhaven City Council: Key - W
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Steel reinforcement for piles must conform to Specification TfNSW B80.
checkpoint | 1.6 - Concrete Mix Design
label | Ref docs - TfNSW B59 Cl 2.2, TfNSW B80 Annexure B80/G
label | Acceptance criteria - Mix designs have been reviewed by the Superintendent. Use only self-compacting concrete or high workability concrete conforming to Annexure B80/G of TfNSW B80, as approved by the Principal.
button | Acceptance | Yes,No,N/A
label | Verification or test by
label | Symal Infrastructure: Key - S
label | Shoalhaven City Council: Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.7 - Engineering Certification
label | Ref docs - TfNSW B59 Cl 3.4.1
label | Acceptance criteria - Drawings and calculations certified by a Chartered Professional Geotechnical Engineer, verifying that under the proposed set up and site conditions, the proposed piling equipment and working platforms or supports will operate safely.
button | Acceptance | Yes,No,N/A
label | Verification or test by
label | Symal Infrastructure: Key - S
section | 2.0 Bored Pile Excavation and Cleaning
checkpoint | 2.1 - Set out
label | Ref docs - IFC Drawings
label | Acceptance criteria - Set out the site with adequate recovery pegs and survey markers so that the drilling and/or piling rig can be set up accurately at the specified location and aligned correctly for each pile.
button | Acceptance | Yes,No,N/A
label | Verification or test by
label | Symal Infrastructure: Key - S
label | Shoalhaven City Council: Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Commencement of excavation of bored pile
label | Ref docs - TfNSW B59 Cl 4.1
label | Acceptance criteria - Bored pile Set out and any additional borehole required are completed. Borehole logs are submitted.
label | • If not previously submitted, details of the following:
label | (i) Extent of temporary casing or details of drilling fluids where proposed for each bored pile.
label | (ii) Method of placing concrete in the bored pile including size and number of any proposed tremie pipes (refer to Clause 6.5).
button | Acceptance | Yes,No,N/A
label | Verification or test by
label | Symal Infrastructure: Key - H
label | Shoalhaven City Council: Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Temporary Casings
label | Ref docs - TfNSW B59 Cl 4.2
label | Acceptance criteria - Drive or sink the temporary casing through any inferior materials, without damaging it, to seal its toe in the founding layer.
label | • Control the alignment of the casing with sufficient accuracy to ensure that the drilling head can be inserted and withdrawn without fouling against the casing.
button | Acceptance | Yes,No,N/A
label | Verification or test by
label | Symal Infrastructure: Key - S
checkpoint | 2.4 - Drilling Fluids
label | Ref docs - TfNSW B59 Cl 4.3
label | Acceptance criteria - The drilling fluid is appropriate for the ground conditions and the groundwater at the site and the method of bored pile excavation.
button | Acceptance | Yes,No,N/A
label | Verification or test by
label | Symal Infrastructure: Key - S
checkpoint | 2.5 - Bored Pile Excavation
label | Ref docs - TfNSW B59 Cl 4.4
label | Acceptance criteria - Record and measure the operating parameters of the drilling rig when excavating the bored pile.
button | Acceptance | Yes,No,N/A
label | Verification or test by
label | Symal Infrastructure: Key - S
checkpoint | 2.6 - Excavated Spoil
label | Ref docs - TfNSW B59 Cl 3.5
label | Acceptance criteria - Removal all spoil off site during excavation works. Submission of methodology for any spoil stockpile and proposed cartage route and drop-off.
button | Acceptance | Yes,No,N/A
label | Verification or test by
label | Symal Infrastructure: Key - S
checkpoint | 2.7 - Final Pile Toe Level
label | Ref docs - TfNSW B59 Cl 4.5.1
label | Acceptance criteria - Inspection of the footing material at pile toe level by Symal’s Geotechnical Engineer to ensure rock socket depth is achieved.
label | • Symal’s Geotechnical Engineer directs excavation of a bored pile to a level lower than shown on the Drawings?
label | • Principal accepted the level as the final pile toe level to satisfy design requirement?
button | Acceptance | Yes,No,N/A
text | Final Level:
label | Verification or test by
label | Symal Infrastructure: Key - S
label | Shoalhaven City Council: Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.8 - Roughening Sides and Cleaning Bored Pile
label | Ref docs - TfNSW B59 Cl 4.5.2
label | Acceptance criteria - Roughen the side of the rock socket as specified. Remove debris and surface smear and expose intact rock over the side and base of the rock socket.
button | Acceptance | Yes,No,N/A
label | Verification or test by
label | Symal Infrastructure: Key - S
checkpoint | 2.9 - Acceptance of Bored Pile
label | Ref docs - TfNSW B59 Cl 4.5.3
label | Acceptance criteria - Notification that the bored pile excavation is complete.
label | • Submitted verification documents, verifying that the bored pile has been excavated to the design position, size and level.
label | • De-sanded and re-circulated the drilling fluid before concrete placing, drilling fluid samples are tested to verify conformity from the bottom of the bored pile.
button | Acceptance | Yes,No,N/A
label | Verification or test by
label | Symal Infrastructure: Key - H
label | Shoalhaven City Council: Key - H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Following acceptance of bored pile, keep the bored pile side and base in a clean and stable condition without contamination or softening, until concrete is placed
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.10 - Indirect Examination of Bored Pile
label | Ref docs - TfNSW B59 Cl 4.6
label | Acceptance criteria - Verify conformity of the depth of each bored pile using a weighted tape at a minimum of three locations of the bored pile.
button | Acceptance | Yes,No,N/A
label | Verification or test by
label | Symal Infrastructure: Key - S
section | 3.0 Reinforcement Placing
checkpoint | 3.1 - Cage and Bored Pile Inspection
label | Ref docs - TfNSW B59 Cl 5.1
label | Acceptance criteria - Notify the Principal at least 24 hours prior to proposed time of placement of the reinforcement cage into bored pile.
button | Acceptance | Yes,No,N/A
label | Verification or test by
label | Symal Infrastructure: Key - W
label | Shoalhaven City Council: Key - W
checkpoint | 3.2 - Placing Steel Reinforcement Cage
label | Ref docs - TfNSW B59 Cl 5.2
label | Acceptance criteria - Certification that the bored pile is clean, and that all loose and adhering materials have been cleaned from the reinforcement cage.
button | Acceptance | Yes,No,N/A
label | Verification or test by
label | Symal Infrastructure: Key - H
label | Shoalhaven City Council: Key - H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Place the steel reinforcement and concrete within 24 hours of the excavation of the pile hole.
holdpoint | AUTHORITY HOLDPOINT
section | 4.0 Concrete Supply and Placing
checkpoint | 4.1 - Dewatering
label | Ref docs - TfNSW B59 Cl 6.3
label | Acceptance criteria - Approval from Principal if dewatering is required.
label | Acceptance - Before Backfill
label | Verification or test by
label | Symal Infrastructure: Key - S
checkpoint | 4.2 - Concrete Supply
label | Ref docs - TfNSW B59 Cl 6.4
label | Acceptance criteria - Provide a continuous supply of concrete so that each bored pile is concreted in one uninterrupted operation.
button | Acceptance | Yes,No,N/A
label | Verification or test by
label | Symal Infrastructure: Key - S
label | Shoalhaven City Council: Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3 - Concrete Placing
label | Ref docs - TfNSW B59 Cl 6.5, TfNSW B90 Cl 9.2
label | Acceptance criteria - Tremie pipe and hopper are used to place the concrete.
label | • Concrete is placed in a continuous process from the base to above the top of the pile.
label | • Concrete testing for compressive strength at 28 days
button | Acceptance | Yes,No,N/A
label | Verification or test by
label | Symal Infrastructure: Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Carry out placing of concrete on test members when there is uncertainty about the outcome of placing concrete in piles.
checkpoint | 4.4 - Tremie
label | Ref docs - TfNSW B59 Cl 6.6
label | Acceptance criteria - The tremie pipe is rigid and watertight throughout.
label | • Appropriate tremie pipe size.
label | • Appropriate tremie placement procedure as per B59 Cl 6.6.
button | Acceptance | Yes,No,N/A
label | Verification or test by
label | Symal Infrastructure: Key - S
label | Shoalhaven City Council: Key - W
checkpoint | 4.5 - Concreting Record
label | Ref docs - TfNSW B59 Cl 6.7
label | Acceptance criteria - The depth of the tremie pipe outlet.
label | • The level of the concrete in the bored pile.
label | • The corresponding volume of concrete placed.
button | Acceptance | Yes,No,N/A
label | Verification or test by
label | Symal Infrastructure: Key - S
checkpoint | 4.6 - Casing Extraction
label | Ref docs - TfNSW B59 Cl 6.8
label | Acceptance criteria - Withdraw any temporary casing slowly whilst the concrete is still fluid at close to the original slump.
label | • Maintain a sufficient head of concrete.
label | • Maintain the direction of pull on the temporary casing along the axis of the pile.
label | • Last section of casing not withdrawn until the concreting operation is completed.
button | Acceptance | Yes,No,N/A
label | Verification or test by
label | Symal Infrastructure: Key - S
checkpoint | 4.7 - Temporary Casings Left in Place
label | Ref docs - TfNSW B59 Cl 6.9
label | Acceptance criteria - Temporary casings may be left in place when approved by the Principal.
button | Acceptance | Yes,No,N/A
label | Verification or test by
label | Symal Infrastructure: Key - S
checkpoint | 4.8 - Cut-Off And Clean Up of Top of Pile
label | Ref docs - IFC Drawings, TfNSW B59 Cl 6.10
label | Acceptance criteria - Concrete and/or casing above the cut-off level is carefully removed without damaging the permanent work not earlier than 24 hours after completion of placement of concrete.
label | • The top of the pile to be embedded in the substructure is undamaged, sound, free of any laitance and loose material and have a surface roughness profile not less than 3 mm.
button | Acceptance | Yes,No,N/A
label | Verification or test by
label | Symal Infrastructure: Key - S
section | 5.0 Conformance Check
checkpoint | 5.1 - Tolerances
label | Ref docs - IFC Drawings
label | Acceptance criteria - Tolerances on pile installation must conform to Section 7 of AS 2159. Inclination tolerance for vertical piles must not exceed 1%.
button | Acceptance | Yes,No,N/A
label | Verification or test by
label | Symal Infrastructure: Key - S
checkpoint | Works complete
text | Name:
text | Position:
text | Date Completed:
holdpoint | Sign ITP
checkpoint | Lot Conformance
select | Lot Status | Awaiting Hold Point Release, Awaiting NCR Closure, Awaiting Test Results, Awaiting Verification, Cancelled, Closed-out, Outstanding, Work In Progress
text | Lot opened date:
text | Lot opened by:
text | Date lot closed:
button | NCR raised? | Yes, No
text | NCR Raised Date:
button | NCR closed? | Yes, No
text | NCR Closed Date:
text | NCR Number:
text | Comments
holdpoint | Sign ITP