## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | FHC-ITP-010 - StormTrap Construction v2 | itp |  |  |  |  | FHC-ITP-010 - StormTrap Construction v2 Rev1
section | Preliminary Works
checkpoint | 1.1 Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | — using the correct and complete set of drawings
label | — all drawings are the latest revision
label | REFERENCE DOCUMENTS: IFC Drawings, Approved Shop Drawings
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
label | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 1.3 Material approvals
label | FREQUENCY: Prior to Placement
label | ACCEPTANCE CRITERIA: Material intended for use is to be submitted to the client prior to placement to verify it conforms to required specifications.
label | REFERENCE DOCUMENTS: Material specification sheets
label | INSPECTION/TEST METHOD: Verfiy
label | RECORD OF CONFORMITY: Teambinder Acceptance
label | HP*
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 1.4 Precast Materials Inspection
label | FREQUENCY: Each Delivery
label | ACCEPTANCE CRITERIA: Precast materials have been inspected and fit for purpose and free of defects
label | REFERENCE DOCUMENTS: 619.08
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed Receival and Inspection Checklist
label | IP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 1.5 Precast Unit Compliance
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Precast Reinforced Concrete Box Culverts to comply with requirements of VicRoads Section 619.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.619, 701.04, 701.05
label | INSPECTION/TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: Receival & Inspection Checklist, Manufacturer cetificate or accreditation
label | IP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 1.6 Slab Bedding Material
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Stormtrap modules shall be placed on an insitu concrete base supported on a level, 150mm pad of compacted road sub-base material compacted to 95% relative MDD with a minimum allowable bearing capacity of 150kpa that extends 600mm past the outside of the system.
label | REFERENCE DOCUMENTS: IFC Drawings, Supplier Shop Drawings
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Test Reports from supplier
label | TP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 1.7 Backfill Material Classification
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Nominated material shall be free from perishable matter and conform with the requirements of Vicroads section 204. The placement and compaction methodology adjacent to the detention system shall not compromise the stability of the system and be placed in even layers no more than 600mm higher than the fill on the opposite side in accordance with AS1289
label | REFERENCE DOCUMENTS: FHC-ITP-021, 204.04, AS1289
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Test Reports from supplier / site
label | TP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 1.8 Grouting Material Classification
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Where required for general applications other than those specified elsewhere in this specification, cementitious mortars and grouts shall be shrinkage compensating proprietary products with a consistency appropriate for the required use, and able to be placed and compacted to achieve full encapsulation. Cementitious mortars and grouts shall have a minimum 28 day compressive strength of not less than 40 MPa.
label | ○ Cementitious grouts shall be as a minimum Type C Class dual shrinkage compensating.
label | ○ Only whole bags of material shall be used. Test certificates, material data sheets and health and safety data sheets shall be available for all materials. The mortar and grout applications shall be cured in accordance with the requirements of clause 610.23.
label | REFERENCE DOCUMENTS: 610.33
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Test Reports from supplier
label | TP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
section | Construction Works
checkpoint | 2.1 Excavation Permit
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
label | ○ Plant and equipment shall be appropriate for the task.
label | ○ Excavation operations shall not disturb areas outside the limit of excavation.
label | REFERENCE DOCUMENTS: Excavation Permit
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 2.2 Review
label | FREQUENCY: Prior to construction
label | ACCEPTANCE CRITERIA: Stormtrap construction shall not commence until the Contractor’s construction quality procedure and inspection and test plan(s) addressing all requirements of this section have been reviewed by the Superintendent. Stormtrap modules shall be manufactured according to shop drawings and approved by the installing contractor and engineer. The shop drawings shall indicate size and location of all roof openings and inlet/outlet pipe openings.
label | REFERENCE DOCUMENTS: Shop Drawings 626.02
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Site Engineer/ Superintendent
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 Diversion of Water
label | FREQUENCY: Prior to construction
label | ACCEPTANCE CRITERIA: Stormtrap construction shall not commence until water flow has been diverted to the satisfaction of the Superintendent.
label | REFERENCE DOCUMENTS: 626.04
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 2.4 Conformity with Drawings
label | FREQUENCY: Prior to excavation
label | ACCEPTANCE CRITERIA: Prior to commencement of excavation for the stormtrap the Contractor shall confirm the position of all stormtrap units with the Superintendent.
label | REFERENCE DOCUMENTS: 701.1
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Site Engineer/ Superintendent
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 Tolerances For Placement
label | FREQUENCY: Prior to Backfilling
label | ACCEPTANCE CRITERIA: The stormtrap shall be constructed in the location, to the alignment, cross sectional shape, dimensions and levels shown on the drawings.
label | REFERENCE DOCUMENTS: Shop Drawings
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Foreman
textbox | Date Completed:
checkpoint | 2.6 Foundation Inspection
label | FREQUENCY: Prior to Bedding
label | ACCEPTANCE CRITERIA: Bedding for the cast-in-place concrete base slab shall consist of a compacted layer of 20 mm Class 3 crushed rock, of not less than 150 mm compacted thickness or as specified by geotechnical engineer. No bedding material shall be placed until the foundation or foundation materials have been inspected and approved by the Superintendent. Per FHC-ITP-006 - Class 3 Crushed Rock
label | REFERENCE DOCUMENTS: IFC Drawings 812, 626.06, FHC-ITP-006
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | TP
label | RESPONSIBILITY: Site Engineer/ Superintendent
textbox | Date Completed:
checkpoint | 2.7 Cast in Place Blinding Concrete
label | FREQUENCY: Prior to construction of blinding slab
label | ACCEPTANCE CRITERIA: All cast‑in‑place concrete for stormtrap construction shall comply with the drawings and Section 610. Construction of the concrete blinding shall not commence until the bedding has been approved by the Superintendent.
label | REFERENCE DOCUMENTS: IFC Drawings 610, 611, 626.07
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Site Engineer/ Superintendent
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.8 Cast in Place Structural Concrete
label | FREQUENCY: Prior to construction of concrete base slab
label | ACCEPTANCE CRITERIA: All cast‑in‑place concrete for culvert construction shall comply with the drawings and Section 610. Steel reinforcement shall comply with the drawings and Section 611. Construction of the concrete base slab shall not commence until the pre-pour checklist and the reinforcement and form levels has been checked and approved by the Superintendent.
label | REFERENCE DOCUMENTS: FHC-ITP-025
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed, Completion of Pre-Pour Checklist & Load Batch Traceability Checklist
label | HP
label | RESPONSIBILITY: Site Engineer/ Superintendent
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.9 Placement of Precast Units
label | FREQUENCY: During Construction
label | ACCEPTANCE CRITERIA: The perimeter horizontal joint of the stormtrap modules, shall be sealed with preformed mastic joint sealer (stormmastic). The stormtrap modules shall be placed such that the maximum space between adjacent modules does not exceed 20mm. If the space exceeds 20mm, the modules shall be laid again with appropriate adjustment made to line and grade to bring the space into specification.
label | REFERENCE DOCUMENTS: Shop Drawings
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 2.10 Covering External Surface of Joints
label | FREQUENCY: During Construction
label | ACCEPTANCE CRITERIA: All exterior joints between adjacent stormtraps modules shall be sealed with 300mm preformed cold-applied, self-adhering elastometric resin bonded to woven highly punctured resistant polymer wrap and shall be 300mm integrated primer sealant as approved by humes (stormwrap). The adhesive exterior joint wraps shall be prepared/cleaned and installed according to the manufacturers installation instructions.
label | REFERENCE DOCUMENTS: Shop Drawings
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Site Engineer/ Superintendent
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | Testing & Completion
checkpoint | 3.1 Concrete Sampling and Testing
label | FREQUENCY: Each Strucutral Concrete Pour
label | ACCEPTANCE CRITERIA: Concrete sampled and tessted for strength and slump as per requirements outlined FHC-ITP-025 - Structural Concrete Construction
label | REFERENCE DOCUMENTS: FHC-ITP-025
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Test Reports
label | TP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 3.2 Final Inspection
label | FREQUENCY: Post Construction
label | ACCEPTANCE CRITERIA: Units which do not comply with the requirements of clause 619.14 prior to laying and backfilling shall be rejected and removed from the site.
label | ○ Where inspections after backfilling identify defects which do not comply with the requirements of clause 619.14, such culverts shall be removed and replaced, unless the Superintendent approves repairs to be undertaken in accordance with the requirements of Section 610, and Section 687 for crack repairs and Section 689 for conventional patch repairs
label | REFERENCE DOCUMENTS: 701.31 (d)
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 3.3 Lot Mapping
label | FREQUENCY: Post Construction
label | ACCEPTANCE CRITERIA: Stormtrap to have suitable lot map based on days production for traceability purposes.
label | REFERENCE DOCUMENTS: Shop Drawings
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Lot Maps
label | TP
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date: