## Project Structure
Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Name of ITP/Checklist Template Required
Kainga Ora - 18 Fowlds Ave
Level 2
Unit 2.3
|  |  | Floor Preparation |  | Floor Preparation Installation
|  |  | Damtec |  | Vinyl Installation
|  |  | Vinyl |  | Vinyl Installation
|  |  | Carpet - Conventional |  | Carpet Installation
|  |  | Carpet - Double Stick |  | Carpet Installation
Unit 2.4
|  |  | Floor Preparation |  | Floor Preparation Installation
|  |  | Damtec |  | Vinyl Installation
|  |  | Vinyl |  | Vinyl Installation
|  |  | Carpet - Conventional |  | Carpet Installation
|  |  | Carpet - Double Stick |  | Carpet Installation
Unit 2.5
|  |  | Floor Preparation |  | Floor Preparation Installation
|  |  | Damtec |  | Vinyl Installation
|  |  | Vinyl |  | Vinyl Installation
|  |  | Carpet - Conventional |  | Carpet Installation
|  |  | Carpet - Double Stick |  | Carpet Installation

## Checklist Templates
Type | Name | Values
checklist | Floor Preparation
checkpoint | Check area clear of all other trades and their materials
checkpoint | Grind Floor
checkpoint | Are there any cracks that require remediation? | Yes, No
checkpoint | Remediate cracks
checkpoint | Apply feather coat, Sanded, Edges
checkpoint | Screed to areas if applicable
signoff | SEND TO CLIENT FOR QUALITY APPROVAL
checklist | Vinyl Installation (Basic)
section | Preparation
checkpoint | Check area clear of all other trades and their materials
checkpoint | Check floor for U3 (3mm variance over 3m)
checkpoint | Check wall for smoothness where coving
checkpoint | Check if area requires damtec as require
checkpoint | If damtec is required check substrate is acceptable
checkpoint | Measure area
checkpoint | Acclimatise vinyl
section | Installation
checkpoint | Confirm damtec and install
checkpoint | Confirm vinyl layout direction
checkpoint | Confirm coving/capping location/type as applicable
checkpoint | Glue out floors
checkpoint | Install vinyl
checkpoint | Install coving & capping/sealant as applicable
section | Handover & Signoff
checkpoint | Remove all excess material
checkpoint | Clean any excess glue
checkpoint | Report for inspection
checkpoint | Quality Approval
signoff | SEND TO CLIENT FOR QUALITY APPROVAL
checklist | Carpet Installation
section | Preparation
checkpoint | Check area clear of all other trades and their materials
checkpoint | Check floor if prep is required
section | Installation
checkpoint | Install carpet including smoothedge and underlay as applicable
checkpoint | Check carpet direction
checkpoint | Check areas that are conventional install and/or double stick installation
checkpoint | Install trims as applicable
checkpoint | Smoothedge nails not protruding through carpet
checkpoint | All temporary nails removed
checkpoint | All areas are carpeted: bedrooms, wardrobes, living, stairs, hall etc
checkpoint | If installed double stick carpet - ensure any adhesive is clean
checkpoint | All strands cut off
section | Handover & Signoff
checkpoint | Remove all excess material
checkpoint | Report for inspection
checkpoint | Quality Approval
signoff | SEND TO CLIENT FOR QUALITY APPROVAL

## Template Guide
TEMPLATE GUIDE
Type | Name | Values
checklist | Template Guide (This is where you type the name/title of your checklist)
section | Section A - This is a section which helps you split your checklist
checkpoint | This is a checkpoint (all checkpoints have the options to PASS, FAIL, N/A by default)
checkpoint | This is a checkpoint with a dropdown (you can select only one option)
dropdown | Select: | Option 1, Option 2, Option 3
checkpoint | This is a checkpoint with a textbox
textbox | Description:
checkpoint | This is a checkpoint with buttons (you can select only one option)
button | Select: | Option 1, Option 2, Option 3
section | Section B - This is a section which helps you split your checklist
checkpoint | This is a checkpoint with a note
note | This is a note
checkpoint | This is a checkpoint with tickboxes (you can select more than one option)
tickbox | White
tickbox | Grey
tickbox | Black
checkpoint | This is a checkpoint with a signoff (you can send it to anyone within or outside of CONQA)
signoff | SIGN HERE OR REQUEST SIGNOFF
NOTE: You can customise ALL wordings under the 'Name' column and the options in the 'Values' column.
PLEASE SHARE YOUR CURRENT ITP/CHECKLIST PACKS FOR US TO DIGITISE OR CREATE YOUR OWN BELOW.