## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Floor Preparation
section | Details
checkpoint | Check area clear of all other trades and their materials
checkpoint | Grind Floor
checkpoint | Are there any cracks that require remediation?
checkpoint | Remediate cracks
checkpoint | Apply feather coat, Sanded, Edges
checkpoint | Screed to areas if applicable
signoff | SEND TO CLIENT FOR QUALITY APPROVAL
checklist | Vinyl Installation (Basic)
section | Preparation
checkpoint | Check area clear of all other trades and their materials
checkpoint | Check floor for U3 (3mm variance over 3m)
checkpoint | Check wall for smoothness where coving
checkpoint | Check if area requires damtec as require
checkpoint | If damtec is required check substrate is acceptable
checkpoint | Measure area
checkpoint | Acclimatise vinyl
section | Installation
checkpoint | Confirm damtec and install
checkpoint | Confirm vinyl layout direction
checkpoint | Confirm coving/capping location/type as applicable
checkpoint | Glue out floors
checkpoint | Install vinyl
checkpoint | Install coving & capping/sealant as applicable
section | Handover & Signoff
checkpoint | Remove all excess material
checkpoint | Clean any excess glue
checkpoint | Report for inspection
checkpoint | Quality Approval
signoff | SEND TO CLIENT FOR QUALITY APPROVAL
checklist | Carpet Installation
section | Preparation
checkpoint | Check area clear of all other trades and their materials
checkpoint | Check floor if prep is required
section | Installation
checkpoint | Install carpet including smoothedge and underlay as applicable
checkpoint | Check carpet direction
checkpoint | Check areas that are conventional install and/or double stick installation
checkpoint | Install trims as applicable
checkpoint | Smoothedge nails not protruding through carpet
checkpoint | All temporary nails removed
checkpoint | All areas are carpeted: bedrooms, wardrobes, living, stairs, hall etc
checkpoint | If installed double stick carpet - ensure any adhesive is clean
checkpoint | All strands cut off
section | Handover & Signoff
checkpoint | Remove all excess material
checkpoint | Report for inspection
checkpoint | Quality Approval
signoff | SEND TO CLIENT FOR QUALITY APPROVAL