## Project Structure
Folder Structure |  |  |  | Checklists
Site QA
Building A
|  | Ground Floor | Lobby | Plastering & Hebel | External Hebel Wall
|  |  | Common Room | Plastering & Hebel | External Hebel Wall
|  |  | UG01 | Plastering & Hebel | External Hebel Wall
|  |  | UG02 | Plastering & Hebel | External Hebel Wall
|  |  | UG03 | Plastering & Hebel | External Hebel Wall
|  |  | UG04 | Plastering & Hebel | External Hebel Wall
|  |  | UG13 | Plastering & Hebel | External Hebel Wall
|  | Level 1 | Corridor | Plastering & Hebel | External Hebel Wall
|  |  | U101 | Plastering & Hebel | External Hebel Wall
|  |  | U102 | Plastering & Hebel | External Hebel Wall
|  |  | U103 | Plastering & Hebel | External Hebel Wall
|  |  | U104 | Plastering & Hebel | External Hebel Wall
|  |  | U113 | Plastering & Hebel | External Hebel Wall
|  |  | U114 | Plastering & Hebel | External Hebel Wall
|  | Level 2 | Corridor | Plastering & Hebel | External Hebel Wall
|  |  | U201 | Plastering & Hebel | External Hebel Wall
|  |  | U202 | Plastering & Hebel | External Hebel Wall
|  |  | U203 | Plastering & Hebel | External Hebel Wall
|  |  | U204 | Plastering & Hebel | External Hebel Wall
|  |  | U213 | Plastering & Hebel | External Hebel Wall
|  |  | U214 | Plastering & Hebel | External Hebel Wall
|  | Level 3 | Corridor | Plastering & Hebel | External Hebel Wall
|  |  | U301 | Plastering & Hebel | External Hebel Wall
|  |  | U302 | Plastering & Hebel | External Hebel Wall
|  |  | U303 | Plastering & Hebel | External Hebel Wall
|  |  | U304 | Plastering & Hebel | External Hebel Wall
|  |  | U313 | Plastering & Hebel | External Hebel Wall
|  |  | U314 | Plastering & Hebel | External Hebel Wall
|  | Level 4 | Corridor | Plastering & Hebel | External Hebel Wall
|  |  | U401 | Plastering & Hebel | External Hebel Wall
|  |  | U402 | Plastering & Hebel | External Hebel Wall
|  |  | U403 | Plastering & Hebel | External Hebel Wall
|  |  | U404 | Plastering & Hebel | External Hebel Wall
|  |  | U413 | Plastering & Hebel | External Hebel Wall
|  |  | U414 | Plastering & Hebel | External Hebel Wall
|  | Level 5 | Corridor | Plastering & Hebel | External Hebel Wall
|  |  | U501 | Plastering & Hebel | External Hebel Wall
|  |  | U502 | Plastering & Hebel | External Hebel Wall
|  |  | U503 | Plastering & Hebel | External Hebel Wall
|  |  | U504 | Plastering & Hebel | External Hebel Wall
|  |  | U513 | Plastering & Hebel | External Hebel Wall
|  |  | U514 | Plastering & Hebel | External Hebel Wall
Building B
|  | Ground Floor | Lobby | Plastering & Hebel | External Hebel Wall
|  |  | UG05 | Plastering & Hebel | External Hebel Wall
|  |  | UG06 | Plastering & Hebel | External Hebel Wall
|  |  | UG07 | Plastering & Hebel | External Hebel Wall
|  |  | UG08 | Plastering & Hebel | External Hebel Wall
|  |  | UG09 | Plastering & Hebel | External Hebel Wall
|  |  | UG10 | Plastering & Hebel | External Hebel Wall
|  |  | UG11 | Plastering & Hebel | External Hebel Wall
|  |  | UG12 | Plastering & Hebel | External Hebel Wall
|  | Level 1 | Corridor | Plastering & Hebel | External Hebel Wall
|  |  | U105 | Plastering & Hebel | External Hebel Wall
|  |  | U106 | Plastering & Hebel | External Hebel Wall
|  |  | U107 | Plastering & Hebel | External Hebel Wall
|  |  | U108 | Plastering & Hebel | External Hebel Wall
|  |  | U109 | Plastering & Hebel | External Hebel Wall
|  |  | U110 | Plastering & Hebel | External Hebel Wall
|  |  | U111 | Plastering & Hebel | External Hebel Wall
|  |  | U112 | Plastering & Hebel | External Hebel Wall
|  | Level 2 | Corridor | Plastering & Hebel | External Hebel Wall
|  |  | U205 | Plastering & Hebel | External Hebel Wall
|  |  | U206 | Plastering & Hebel | External Hebel Wall
|  |  | U207 | Plastering & Hebel | External Hebel Wall
|  |  | U208 | Plastering & Hebel | External Hebel Wall
|  |  | U209 | Plastering & Hebel | External Hebel Wall
|  |  | U210 | Plastering & Hebel | External Hebel Wall
|  |  | U211 | Plastering & Hebel | External Hebel Wall
|  |  | U212 | Plastering & Hebel | External Hebel Wall
|  | Level 3 | Corridor | Plastering & Hebel | External Hebel Wall
|  |  | U305 | Plastering & Hebel | External Hebel Wall
|  |  | U306 | Plastering & Hebel | External Hebel Wall
|  |  | U307 | Plastering & Hebel | External Hebel Wall
|  |  | U308 | Plastering & Hebel | External Hebel Wall
|  |  | U309 | Plastering & Hebel | External Hebel Wall
|  |  | U310 | Plastering & Hebel | External Hebel Wall
|  |  | U311 | Plastering & Hebel | External Hebel Wall
|  |  | U312 | Plastering & Hebel | External Hebel Wall
|  | Level 4 | Corridor | Plastering & Hebel | External Hebel Wall
|  |  | U405 | Plastering & Hebel | External Hebel Wall
|  |  | U406 | Plastering & Hebel | External Hebel Wall
|  |  | U407 | Plastering & Hebel | External Hebel Wall
|  |  | U408 | Plastering & Hebel | External Hebel Wall
|  |  | U409 | Plastering & Hebel | External Hebel Wall
|  |  | U410 | Plastering & Hebel | External Hebel Wall
|  |  | U411 | Plastering & Hebel | External Hebel Wall
|  |  | U412 | Plastering & Hebel | External Hebel Wall
|  | Level 5 | Corridor | Plastering & Hebel | External Hebel Wall
|  |  | U505 | Plastering & Hebel | External Hebel Wall
|  |  | U506 | Plastering & Hebel | External Hebel Wall
|  |  | U507 | Plastering & Hebel | External Hebel Wall
|  |  | U508 | Plastering & Hebel | External Hebel Wall
|  |  | U509 | Plastering & Hebel | External Hebel Wall
|  |  | U510 | Plastering & Hebel | External Hebel Wall
|  |  | U511 | Plastering & Hebel | External Hebel Wall
|  |  | U512 | Plastering & Hebel | External Hebel Wall

## Checklists
Type | Name | Values
Checklist | Plastering & Internal Hebel
Section | Framing
Checkpoint | All frames/studs set out correctly
Checkpoint | All frames plumb and square
Checkpoint | Fix to structural members
Checkpoint | All window and sliding door openings are as per plan and line up with above elements.
Checkpoint | Nogging all installed correctly
Checkpoint | Door frames fixing
Checkpoint | Studco Supplier inspection (Provide report to builder)
Section | Internal Hebel wall
Checkpoint | Angle/sarking/top hats in place
Checkpoint | Hebel panel alignment
Checkpoint | Ensure hebel installed plumb and level with adjoining surfaces
Checkpoint | Ensure hebel panels are in full and not cracked
Checkpoint | Ensure control joints have been installed in accordance with manufacturers specifications and installation guide
Checkpoint | Panels finish (patches done)
Checkpoint | Fire-rated caulking and sealing
Checkpoint | Satisfaction and sign off from CSR inspection (Provide report to builder)
Section | Plasterboard for Walls
Checkpoint | Ply nogging
Checkpoint | Rough-in sign off
Checkpoint | Insulation installed as per AS/BCA
Checkpoint | Correct type of plasterboards and thickness installed as per wall details, project drawings and BCA requirements
Checkpoint | Villaboard/WR to wet areas ONLY
Checkpoint | Plasterboard Lining to be installed as wall set out plan
Section | Plasterboard for Ceiling
Checkpoint | Confirm ceiling height
Checkpoint | Confirm access panel location
Checkpoint | Ceiling frame work
Checkpoint | Ceiling bulkheads where required
Checkpoint | Pelmets
Checkpoint | Ceiling insulation as per AS/BCA
Checkpoint | Correct type of plasterboards and thickness installed as per wall details, project drawings and BCA requirements
Checkpoint | Ceiling plasterboard lining
Section | Setting & Sanding
Checkpoint | Angle/LB/P50 install
Checkpoint | First coat setting
Checkpoint | Second coat setting
Checkpoint | Final coat setting
Checkpoint | Sanding
Checkpoint | patching
Checkpoint | Defects
Checkpoint | Final Inspection
Checklist | External Hebel Wall
Checkpoint | Angle/Sarking or RAB Board/Top Hats in place
Checkpoint | Hebel panels alignment
Checkpoint | Ensure Hebel PowerPanel finish are as per the finishes shown on project drawings and elevations
Checkpoint | All Sarking/RAB Board has been installed as per manufacturer's recommendations
Checkpoint | Sarking overlap flashing by min. 150mm
Checkpoint | Flashing are installed correctly, are continuous and free of any imperfections
Checkpoint | Ensure Hebel installed plumb and level with adjoining surfaces
Checkpoint | Window seal cuts to be neat and consistent
Checkpoint | Hebel panel cut treatment reinforcement
Checkpoint | Ensure Hebel panels are in full and not cracked
Checkpoint | Ensure on site routing of panels to be perfectly straight and level
Checkpoint | Ensure control joints have been installed in accordance with manufacturer's specifications and installation guides
Checkpoint | Hebel expansion joins have been installed and are consistent, including slab junctions
Checkpoint | Weep holes have been installed correctly and at correct heights and spacing
Checkpoint | All Hebel walls to line up with elements above
Checkpoint | Panels finish (patches done)
Checkpoint | Fire-rated caulking and sealing (junctions should be treated with sealant and backing rod - for both top and bottom junctions)
Checkpoint | Satisfaction and sign off from CSR inspection (Provide report to builder)