## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Plastering & Internal Hebel
section | Framing
checkpoint | All frames/studs set out correctly
checkpoint | All frames plumb and square
checkpoint | Fix to structural members
checkpoint | All window and sliding door openings are as per plan and line up with above elements.
checkpoint | Nogging all installed correctly
checkpoint | Door frames fixing
checkpoint | Studco Supplier inspection (Provide report to builder)
section | Internal Hebel wall
checkpoint | Angle/sarking/top hats in place
checkpoint | Hebel panel alignment
checkpoint | Ensure hebel installed plumb and level with adjoining surfaces
checkpoint | Ensure hebel panels are in full and not cracked
checkpoint | Ensure control joints have been installed in accordance with manufacturers specifications and installation guide
checkpoint | Panels finish (patches done)
checkpoint | Fire-rated caulking and sealing
checkpoint | Satisfaction and sign off from CSR inspection (Provide report to builder)
section | Plasterboard for Walls
checkpoint | Ply nogging
checkpoint | Rough-in sign off
checkpoint | Insulation installed as per AS/BCA
checkpoint | Correct type of plasterboards and thickness installed as per wall details, project drawings and BCA requirements
checkpoint | Villaboard/WR to wet areas ONLY
checkpoint | Plasterboard Lining to be installed as wall set out plan
section | Plasterboard for Ceiling
checkpoint | Confirm ceiling height
checkpoint | Confirm access panel location
checkpoint | Ceiling frame work
checkpoint | Ceiling bulkheads where required
checkpoint | Pelmets
checkpoint | Ceiling insulation as per AS/BCA
checkpoint | Correct type of plasterboards and thickness installed as per wall details, project drawings and BCA requirements
checkpoint | Ceiling plasterboard lining
section | Setting & Sanding
checkpoint | Angle/LB/P50 install
checkpoint | First coat setting
checkpoint | Second coat setting
checkpoint | Final coat setting
checkpoint | Sanding
checkpoint | patching
checkpoint | Defects
checkpoint | Final Inspection
checklist | External Hebel Wall
checkpoint | Angle/Sarking or RAB Board/Top Hats in place
checkpoint | Hebel panels alignment
checkpoint | Ensure Hebel PowerPanel finish are as per the finishes shown on project drawings and elevations
checkpoint | All Sarking/RAB Board has been installed as per manufacturer's recommendations
checkpoint | Sarking overlap flashing by min. 150mm
checkpoint | Flashing are installed correctly, are continuous and free of any imperfections
checkpoint | Ensure Hebel installed plumb and level with adjoining surfaces
checkpoint | Window seal cuts to be neat and consistent
checkpoint | Hebel panel cut treatment reinforcement
checkpoint | Ensure Hebel panels are in full and not cracked
checkpoint | Ensure on site routing of panels to be perfectly straight and level
checkpoint | Ensure control joints have been installed in accordance with manufacturer's specifications and installation guides
checkpoint | Hebel expansion joins have been installed and are consistent, including slab junctions
checkpoint | Weep holes have been installed correctly and at correct heights and spacing
checkpoint | All Hebel walls to line up with elements above
checkpoint | Panels finish (patches done)
checkpoint | Fire-rated caulking and sealing (junctions should be treated with sealant and backing rod - for both top and bottom junctions)
checkpoint | Satisfaction and sign off from CSR inspection (Provide report to builder)