## Structure
Tier 1 | Tier 2 | Tier 3 | Tier 4 | Checklist to use
STAGE #2
| WE 04 Mod 1 | Factory Works |  | General Manufacturing Template
|  | Pre Install Checklist |  | Pre Install Checklist
|  | Installation |  | Flush Glaze - Install Checklist
|  | Glazing |  | Glazing Checklist
|  | Performance Tests |  | Performance Tests
|  | Handover Checklist |  | Handover Checklist
| WE 04 Mod 2 | Factory Works |  | General Manufacturing Template
|  | Pre Install Checklist |  | Pre Install Checklist
|  | Installation |  | Flush Glaze - Install Checklist
|  | Glazing |  | Glazing Checklist
|  | Performance Tests |  | Performance Tests
|  | Handover Checklist |  | Handover Checklist
| WE 04 Mod 3 | Factory Works |  | General Manufacturing Template
|  | Pre Install Checklist |  | Pre Install Checklist
|  | Installation |  | Flush Glaze - Install Checklist
|  | Glazing |  | Glazing Checklist
|  | Performance Tests |  | Performance Tests
|  | Handover Checklist |  | Handover Checklist
| WE 04 Mod 4 | Factory Works |  | General Manufacturing Template
|  | Pre Install Checklist |  | Pre Install Checklist
|  | Installation |  | Flush Glaze - Install Checklist
|  | Glazing |  | Glazing Checklist
|  | Performance Tests |  | Performance Tests
|  | Handover Checklist |  | Handover Checklist
| WE 04 Mod 5 | Factory Works |  | General Manufacturing Template
|  | Pre Install Checklist |  | Pre Install Checklist
|  | Installation |  | Flush Glaze - Install Checklist
|  | Glazing |  | Glazing Checklist
|  | Performance Tests |  | Performance Tests
|  | Handover Checklist |  | Handover Checklist
| WE 04 Mod 6 | Factory Works |  | General Manufacturing Template
|  | Pre Install Checklist |  | Pre Install Checklist
|  | Installation |  | Flush Glaze - Install Checklist
|  | Glazing |  | Glazing Checklist
|  | Performance Tests |  | Performance Tests
|  | Handover Checklist |  | Handover Checklist
| WE 04 Mod 7 | Factory Works |  | General Manufacturing Template
|  | Pre Install Checklist |  | Pre Install Checklist
|  | Installation |  | Flush Glaze - Install Checklist
|  | Glazing |  | Glazing Checklist
|  | Performance Tests |  | Performance Tests
|  | Handover Checklist |  | Handover Checklist
| WE 04 Mod 8 | Factory Works |  | General Manufacturing Template
|  | Pre Install Checklist |  | Pre Install Checklist
|  | Installation |  | Flush Glaze - Install Checklist
|  | Glazing |  | Glazing Checklist
|  | Performance Tests |  | Performance Tests
|  | Handover Checklist |  | Handover Checklist
| WE 04 Mod 9 | Factory Works |  | General Manufacturing Template
|  | Pre Install Checklist |  | Pre Install Checklist
|  | Installation |  | Flush Glaze - Install Checklist
|  | Glazing |  | Glazing Checklist
|  | Performance Tests |  | Performance Tests
|  | Handover Checklist |  | Handover Checklist
| WE 04 Mod 10 | Factory Works |  | General Manufacturing Template
|  | Pre Install Checklist |  | Pre Install Checklist
|  | Installation |  | Flush Glaze - Install Checklist
|  | Glazing |  | Glazing Checklist
|  | Performance Tests |  | Performance Tests
|  | Handover Checklist |  | Handover Checklist
| WE 04 Mod 11 | Factory Works |  | General Manufacturing Template
|  | Pre Install Checklist |  | Pre Install Checklist
|  | Installation |  | Flush Glaze - Install Checklist
|  | Glazing |  | Glazing Checklist
|  | Performance Tests |  | Performance Tests
|  | Handover Checklist |  | Handover Checklist
| WE 04 Mod 12 | Factory Works |  | General Manufacturing Template
|  | Pre Install Checklist |  | Pre Install Checklist
|  | Installation |  | Flush Glaze - Install Checklist
|  | Glazing |  | Glazing Checklist
|  | Performance Tests |  | Performance Tests
|  | Handover Checklist |  | Handover Checklist
| WE 03 Mod A | Factory Works |  | General Manufacturing Template
|  | Pre Install Checklist |  | Pre Install Checklist
|  | Installation |  | Flush Glaze - Install Checklist
|  | Glazing |  | Glazing Checklist
|  | Performance Tests |  | Performance Tests
|  | Handover Checklist |  | Handover Checklist
| WE 03 Mod B | Factory Works |  | General Manufacturing Template
|  | Pre Install Checklist |  | Pre Install Checklist
|  | Installation |  | Flush Glaze - Install Checklist
|  | Glazing |  | Glazing Checklist
|  | Performance Tests |  | Performance Tests
|  | Handover Checklist |  | Handover Checklist
| WE 03 Mod C | Factory Works |  | General Manufacturing Template
|  | Pre Install Checklist |  | Pre Install Checklist
|  | Installation |  | Flush Glaze - Install Checklist
|  | Glazing |  | Glazing Checklist
|  | Performance Tests |  | Performance Tests
|  | Handover Checklist |  | Handover Checklist
| WE 03 Mod D | Factory Works |  | General Manufacturing Template
|  | Pre Install Checklist |  | Pre Install Checklist
|  | Installation |  | Flush Glaze - Install Checklist
|  | Glazing |  | Glazing Checklist
|  | Performance Tests |  | Performance Tests
|  | Handover Checklist |  | Handover Checklist
| WE 03 Mod E | Factory Works |  | General Manufacturing Template
|  | Pre Install Checklist |  | Pre Install Checklist
|  | Installation |  | Flush Glaze - Install Checklist
|  | Glazing |  | Glazing Checklist
|  | Performance Tests |  | Performance Tests
|  | Handover Checklist |  | Handover Checklist
| WE 03 Mod F | Factory Works |  | General Manufacturing Template
|  | Pre Install Checklist |  | Pre Install Checklist
|  | Installation |  | Flush Glaze - Install Checklist
|  | Glazing |  | Glazing Checklist
|  | Performance Tests |  | Performance Tests
|  | Handover Checklist |  | Handover Checklist
| WE 03 Mod G | Factory Works |  | General Manufacturing Template
|  | Pre Install Checklist |  | Pre Install Checklist
|  | Installation |  | Flush Glaze - Install Checklist
|  | Glazing |  | Glazing Checklist
|  | Performance Tests |  | Performance Tests
|  | Handover Checklist |  | Handover Checklist
| WE 03 Mod H | Factory Works |  | General Manufacturing Template
|  | Pre Install Checklist |  | Pre Install Checklist
|  | Installation |  | Flush Glaze - Install Checklist
|  | Glazing |  | Glazing Checklist
|  | Performance Tests |  | Performance Tests
|  | Handover Checklist |  | Handover Checklist
| WE 03 Mod I | Factory Works |  | General Manufacturing Template
|  | Pre Install Checklist |  | Pre Install Checklist
|  | Installation |  | Flush Glaze - Install Checklist
|  | Glazing |  | Glazing Checklist
|  | Performance Tests |  | Performance Tests
|  | Handover Checklist |  | Handover Checklist
| WE 03 Mod J | Factory Works |  | General Manufacturing Template
|  | Pre Install Checklist |  | Pre Install Checklist
|  | Installation |  | Flush Glaze - Install Checklist
|  | Glazing |  | Glazing Checklist
|  | Performance Tests |  | Performance Tests
|  | Handover Checklist |  | Handover Checklist
| WE 03 Mod K | Factory Works |  | General Manufacturing Template
|  | Pre Install Checklist |  | Pre Install Checklist
|  | Installation |  | Flush Glaze - Install Checklist
|  | Glazing |  | Glazing Checklist
|  | Performance Tests |  | Performance Tests
|  | Handover Checklist |  | Handover Checklist
| WE 03 Mod L | Factory Works |  | General Manufacturing Template
|  | Pre Install Checklist |  | Pre Install Checklist
|  | Installation |  | Flush Glaze - Install Checklist
|  | Glazing |  | Glazing Checklist
|  | Performance Tests |  | Performance Tests
|  | Handover Checklist |  | Handover Checklist
| WE 03 Mod M | Factory Works |  | General Manufacturing Template
|  | Pre Install Checklist |  | Pre Install Checklist
|  | Installation |  | Flush Glaze - Install Checklist
|  | Glazing |  | Glazing Checklist
|  | Performance Tests |  | Performance Tests
|  | Handover Checklist |  | Handover Checklist
| WE 03 Mod N | Factory Works |  | General Manufacturing Template
|  | Pre Install Checklist |  | Pre Install Checklist
|  | Installation |  | Flush Glaze - Install Checklist
|  | Glazing |  | Glazing Checklist
|  | Performance Tests |  | Performance Tests
|  | Handover Checklist |  | Handover Checklist
| WE 03 Mod O | Factory Works |  | General Manufacturing Template
|  | Pre Install Checklist |  | Pre Install Checklist
|  | Installation |  | Flush Glaze - Install Checklist
|  | Glazing |  | Glazing Checklist
|  | Performance Tests |  | Performance Tests
|  | Handover Checklist |  | Handover Checklist
| WE 03 Mod P | Factory Works |  | General Manufacturing Template
|  | Pre Install Checklist |  | Pre Install Checklist
|  | Installation |  | Flush Glaze - Install Checklist
|  | Glazing |  | Glazing Checklist
|  | Performance Tests |  | Performance Tests
|  | Handover Checklist |  | Handover Checklist
| WE 03 Mod Q | Factory Works |  | General Manufacturing Template
|  | Pre Install Checklist |  | Pre Install Checklist
|  | Installation |  | Flush Glaze - Install Checklist
|  | Glazing |  | Glazing Checklist
|  | Performance Tests |  | Performance Tests
|  | Handover Checklist |  | Handover Checklist
| WE 0 Mod 1 | Factory Works |  | General Manufacturing Template
|  | Pre Install Checklist |  | Pre Install Checklist
|  | Installation |  | Flush Glaze - Install Checklist
|  | Glazing |  | Glazing Checklist
|  | Performance Tests |  | Performance Tests
|  | Handover Checklist |  | Handover Checklist
| WE 0 Mod 2 | Factory Works |  | General Manufacturing Template
|  | Pre Install Checklist |  | Pre Install Checklist
|  | Installation |  | Flush Glaze - Install Checklist
|  | Glazing |  | Glazing Checklist
|  | Performance Tests |  | Performance Tests
|  | Handover Checklist |  | Handover Checklist
| WE 0 Mod 3 | Factory Works |  | General Manufacturing Template
|  | Pre Install Checklist |  | Pre Install Checklist
|  | Installation |  | Flush Glaze - Install Checklist
|  | Glazing |  | Glazing Checklist
|  | Performance Tests |  | Performance Tests
|  | Handover Checklist |  | Handover Checklist
| WE 01 Mod 4 | Factory Works |  | General Manufacturing Template
|  | Pre Install Checklist |  | Pre Install Checklist
|  | Installation |  | Flush Glaze - Install Checklist
|  | Glazing |  | Glazing Checklist
|  | Performance Tests |  | Performance Tests
|  | Handover Checklist |  | Handover Checklist
| WE 01 Mod 5 | Factory Works |  | General Manufacturing Template
|  | Pre Install Checklist |  | Pre Install Checklist
|  | Installation |  | Flush Glaze - Install Checklist
|  | Glazing |  | Glazing Checklist
|  | Performance Tests |  | Performance Tests
|  | Handover Checklist |  | Handover Checklist
| WE 01 Mod 6 | Factory Works |  | General Manufacturing Template
|  | Pre Install Checklist |  | Pre Install Checklist
|  | Installation |  | Flush Glaze - Install Checklist
|  | Glazing |  | Glazing Checklist
|  | Performance Tests |  | Performance Tests
|  | Handover Checklist |  | Handover Checklist

## Universal Templates
Type | Name | Values
checklist | Pre-Install Checklist
Mandatory checkpoint | Openings are prepared and match the dimensions specified in the drawings
Mandatory checkpoint | Waterproofing are prepared
Mandatory checkpoint | Windows are free from any visible damage or defects
checklist | Glazing Checklist
checkpoint | Frame installed securely
checkpoint | Correct glass installed
checkpoint | Glass installed with correct face to the outside
checkpoint | Setting/location blocks correctly installed
checkpoint | Beads installed
checkpoint | Wedge rubber complete
checkpoint | Trade clean
checklist | Performance Tests
checkpoint | Water test (if applicable) performed and passed.
checkpoint | Sealant Peel Test (if applicable) performed and passed
checklist | Handover Checklist
checkpoint | All works completed as per specifications
date | Date:
checkpoint | Company Signoff
signoff | SIGN HERE
checkpoint | Client Signoff
signoff | SIGN HERE

## Install Templates (by type)
Type | Name | Values
checklist | Flush Glaze - Install Checklist
checkpoint | Has the window/door installation been completed?
checkpoint | Is interior sealants installation neat and continuous.
checkpoint | Is exterior sealants installation neat and continuous.
checkpoint | Is sill flashing installed per plans and as detailed in the shop drawings?
checkpoint | Is head flashing installed per plans and as detailed in the shop drawings?
checkpoint | Are all window and doors working?
checkpoint | All handles installed correctly?
checkpoint | Are all the hardware installed correctly?
checkpoint | Is the joinery free of scratches?
checkpoint | Is the joinery clean and tidy?
checkpoint | Hinge doors strikes adjusted and locking easily
checkpoint | Hinge doors 4 or 3 point lock operate easily
checkpoint | Hinge doors and sliding doors - Bungs are fitted (every hole)
checkpoint | Sliding doors - panels are adjusted and locking easily
checkpoint | Sliding doors - Strikes are adjusted
checkpoint | Sliding doors - Anti lift blocks and stops fitted properly
checkpoint | Proper spacing and clearances are maintained around the window units.
checkpoint | Fasteners used are correct in type, size, and spacing
checkpoint | End Caps Installed
checkpoint | Frames installed correctly?
checkpoint | Modules installed correctly?
checkpoint | Drains are not blocked
Mandatory checkpoint - no status | The correct consumables specified were used (Sealant) - Photo of Label Required
Mandatory checkpoint - no status | The correct consumables specified were used (Screws) - Photo of Label Required
checklist | Metro-Resi - Install Checklist
checkpoint | Has the window/door installation been completed?
checkpoint | Is interior sealants installation neat and continuous.
checkpoint | Is exterior sealants installation neat and continuous.
checkpoint | Is sill flashing installed per plans and as detailed in the shop drawings?
checkpoint | Is head flashing installed per plans and as detailed in the shop drawings?
checkpoint | Are all window and doors working?
checkpoint | All handles installed correctly?
checkpoint | Are all the hardware installed correctly?
checkpoint | Is the joinery free of scratches?
checkpoint | Is the joinery clean and tidy?
checkpoint | Are Restrictor Stays fitted(Fully Fixed off & Silent operation)
checkpoint | Hinge doors strikes adjusted and locking easily
checkpoint | Hinge doors 4 or 3 point lock operate easily
checkpoint | Hinge doors and sliding doors - Bungs are fitted (every hole)
checkpoint | Sliding doors - panels are adjusted and locking easily
checkpoint | Sliding doors - Strikes are adjusted
checkpoint | Sliding doors - Anti lift blocks and stops fitted properly
checkpoint | Windows open, close, and lock smoothly without excessive force.
checkpoint | All operable windows have functional hardware (locks, latches, etc.)
checkpoint | Proper spacing and clearances are maintained around the window units.
checkpoint | Fasteners used are correct in type, size, and spacing
checkpoint | End Caps Installed
checkpoint | Frames installed correctly?
checkpoint | Drains are not blocked
Mandatory checkpoint - no status | The correct consumables specified were used (Sealant) - Photo of Label Required
Mandatory checkpoint - no status | The correct consumables specified were used (Screws) - Photo of Label Required
checklist | Structural Glaze - Install Checklist
checkpoint | Has the window/door installation been completed?
checkpoint | Is interior sealants installation neat and continuous.
checkpoint | Is exterior sealants installation neat and continuous.
checkpoint | Is sill flashing installed per plans and as detailed in the shop drawings?
checkpoint | Is head flashing installed per plans and as detailed in the shop drawings?
checkpoint | Are all window and doors working?
checkpoint | All handles installed correctly?
checkpoint | Are all the hardware installed correctly?
checkpoint | Is the joinery free of scratches?
checkpoint | Is the joinery clean and tidy?
checkpoint | Hinge doors strikes adjusted and locking easily
checkpoint | Hinge doors 4 or 3 point lock operate easily
checkpoint | Hinge doors and sliding doors - Bungs are fitted (every hole)
checkpoint | Sliding doors - panels are adjusted and locking easily
checkpoint | Sliding doors - Strikes are adjusted
checkpoint | Sliding doors - Anti lift blocks and stops fitted properly
checkpoint | Proper spacing and clearances are maintained around the window units.
checkpoint | Fasteners used are correct in type, size, and spacing
checkpoint | End Caps Installed
checkpoint | Frames installed correctly?
checkpoint | Modules installed correctly?
checkpoint | Drains are not blocked
Mandatory checkpoint - no status | The correct consumables specified were used (Sealant) - Photo of Label Required
Mandatory checkpoint - no status | The correct consumables specified were used (Screws) - Photo of Label Required
checklist | Shopfront - Install Checklist
checkpoint | Has the window/door installation been completed?
checkpoint | Is interior sealants installation neat and continuous.
checkpoint | Is exterior sealants installation neat and continuous.
checkpoint | Is sill flashing installed per plans and as detailed in the shop drawings?
checkpoint | Is head flashing installed per plans and as detailed in the shop drawings?
checkpoint | Are all window and doors working?
checkpoint | All handles installed correctly?
checkpoint | Are all the hardware installed correctly?
checkpoint | Is the joinery free of scratches?
checkpoint | Is the joinery clean and tidy?
checkpoint | Hinge doors strikes adjusted and locking easily
checkpoint | Hinge doors 4 or 3 point lock operate easily
checkpoint | Hinge doors and sliding doors - Bungs are fitted (every hole)
checkpoint | Sliding doors - panels are adjusted and locking easily
checkpoint | Sliding doors - Strikes are adjusted
checkpoint | Sliding doors - Anti lift blocks and stops fitted properly
checkpoint | Proper spacing and clearances are maintained around the window units.
checkpoint | Fasteners used are correct in type, size, and spacing
checkpoint | End Caps Installed
checkpoint | Frames installed correctly?
checkpoint | Modules installed correctly?
checkpoint | Drains are not blocked
Mandatory checkpoint - no status | The correct consumables specified were used (Sealant) - Photo of Label Required
Mandatory checkpoint - no status | The correct consumables specified were used (Screws) - Photo of Label Required
checklist | Architectural - Install Checklist
checkpoint | Has the window/door installation been completed?
checkpoint | Is interior sealants installation neat and continuous.
checkpoint | Is exterior sealants installation neat and continuous.
checkpoint | Is sill flashing installed per plans and as detailed in the shop drawings?
checkpoint | Is head flashing installed per plans and as detailed in the shop drawings?
checkpoint | Are all window and doors working?
checkpoint | All handles installed correctly?
checkpoint | Are all the hardware installed correctly?
checkpoint | Is the joinery free of scratches?
checkpoint | Is the joinery clean and tidy?
checkpoint | Are Restrictor Stays fitted(Fully Fixed off & Silent operation)
checkpoint | Hinge doors strikes adjusted and locking easily
checkpoint | Hinge doors 4 or 3 point lock operate easily
checkpoint | Hinge doors and sliding doors - Bungs are fitted (every hole)
checkpoint | Sliding doors - panels are adjusted and locking easily
checkpoint | Sliding doors - Strikes are adjusted
checkpoint | Sliding doors - Anti lift blocks and stops fitted properly
checkpoint | Windows open, close, and lock smoothly without excessive force.
checkpoint | All operable windows have functional hardware (locks, latches, etc.)
checkpoint | Proper spacing and clearances are maintained around the window units.
checkpoint | Fasteners used are correct in type, size, and spacing
checkpoint | End Caps Installed
checkpoint | Frames installed correctly?
checkpoint | Modules installed correctly?
checkpoint | Drains are not blocked
Mandatory checkpoint - no status | The correct consumables specified were used (Sealant) - Photo of Label Required
Mandatory checkpoint - no status | The correct consumables specified were used (Screws) - Photo of Label Required
checklist | Centrafix - Install Checklist
checkpoint | Has the window/door installation been completed?
checkpoint | Is Foam Seal installation neat and continuous
checkpoint | Is sill flashing installed per plans and as detailed in the shop drawings?
checkpoint | Are all window and doors working?
checkpoint | All handles installed correctly?
checkpoint | Are all the hardware installed correctly?
checkpoint | Is the joinery free of scratches?
checkpoint | Is the joinery clean and tidy?
checkpoint | Are Restrictor Stays fitted(Fully Fixed off & Silent operation)
checkpoint | Hinge doors and sliding doors - Bungs are fitted (every hole)
checkpoint | Sliding doors - panels are adjusted and locking easily
checkpoint | Sliding doors - Strikes are adjusted
checkpoint | Sliding doors - Anti lift blocks and stops fitted properly
checkpoint | Windows open, close, and lock smoothly without excessive force.
checkpoint | All operable windows have functional hardware (locks, latches, etc.)
checkpoint | Proper spacing and clearances are maintained around the window units.
checkpoint | Fasteners used are correct in type, size, and spacing
checkpoint | Frames installed correctly?
checkpoint | Drains are not blocked
Mandatory checkpoint - no status | The correct consumables specified were used (Sealant) - Photo of Label Required
Mandatory checkpoint - no status | The correct consumables specified were used (Screws) - Photo of Label Required
checklist | Box Fins - Install Checklist
checkpoint | Has the window/door installation been completed?
checkpoint | Is interior sealants installation neat and continuous.
checkpoint | Is exterior sealants installation neat and continuous.
checkpoint | Is sill flashing installed per plans and as detailed in the shop drawings?
checkpoint | Are all window and doors working?
checkpoint | Is the joinery free of scratches?
checkpoint | Is the joinery clean and tidy?
checkpoint | Proper spacing and clearances are maintained around the window units.
checkpoint | Fasteners used are correct in type, size, and spacing
checkpoint | End Caps Installed
checkpoint | Brackets installed to modules as per Shop Drawings
checkpoint | Brackets installed to Box fins as per Shop Drawings
checkpoint | Box Fin Spacing as per Shop Drawings
checkpoint | Box Fin Alignment completed
checkpoint | Frames installed correctly?
checkpoint | Modules installed correctly?
checkpoint | Drains are not blocked
Mandatory checkpoint - no status | The correct consumables specified were used (Sealant) - Photo of Label Required
Mandatory checkpoint - no status | The correct consumables specified were used (Screws) - Photo of Label Required
checklist | Channel Glazing - Install Checklist
checkpoint | Has the window/door installation been completed?
checkpoint | Is interior sealants installation neat and continuous.
checkpoint | Is exterior sealants installation neat and continuous.
checkpoint | Is sill flashing installed per plans and as detailed in the shop drawings?
checkpoint | Are all window and doors working?
checkpoint | Is the joinery free of scratches?
checkpoint | Is the joinery clean and tidy?
checkpoint | Proper spacing and clearances are maintained around the window units.
checkpoint | Fasteners used are correct in type, size, and spacing
checkpoint | Frames installed correctly?
checkpoint | Drains are not blocked?
Mandatory checkpoint - no status | The correct consumables specified were used (Sealant) - Photo of Label Required
Mandatory checkpoint - no status | The correct consumables specified were used (Screws) - Photo of Label Required

## General Manufacturing Template
General Manufacturing Template | Type | Checklist Questions
| PASS / FAIL / N/A | Item free of defects and damages
| PASS / FAIL / N/A | Item is clean - No pencil marks / dirt / excessive sealant
| PASS / FAIL / N/A | Item is clearly labelled in accordance with fabrication sheets
| PASS / FAIL / N/A | Item is square - Frame / Sashes / Panels
| MANDATORY CHECKLIST | Sealant is correct colour
| MANDATORY CHECKLIST | Beads / Thresholds / Infills correct length
| MANDATORY CHECKLIST | Mitres flush
| MANDATORY CHECKLIST | Drainage correct as per APL manufacturing pack and aligned
| MANDATORY CHECKLIST | Liners - TWT Measured / Correct Liner / Liner Thickness 19mm or 25mm /Grooved or Non Groove /Staples every 150 - 200mm
| MANDATORY CHECKLIST | Rubbers continuous and free of damage - not pinched under glass / foam
| PASS / FAIL / N/A | Fin Mullions painted
| PASS / FAIL / N/A | Sealant tidy on frame where sash is present
| PASS / FAIL / N/A | Glass inspection done - Clean / Correct type / No defects
| PASS / FAIL / N/A | Glazing done correctly - No movement / correct glazing rubber
| PASS / FAIL / N/A | Bungs / Caps fitted
| PASS / FAIL / N/A | Support Blocks fitted
| PASS / FAIL / N/A | Transport Blocks between panel and frame
| PASS / FAIL / N/A | Protective tape on bottom sill
| PASS / FAIL / N/A | Overall item dimensions correct
| MANDATORY CHECKLIST | Correct Windzone sticker applied
| PASS / FAIL / N/A | Item match drawing
| PASS / FAIL / N/A | Comments on jobsheets followed
| PASS / FAIL / N/A | Machining done as per assembly sheet
| PASS / FAIL / N/A | Correct Hardware fitted as per jobsheet
| MANDATORY CHECKLIST | Soaker correctly fitted
| MANDATORY CHECKLIST | Sillsafe applied correctly
| PASS / FAIL / N/A | Soaker correctly fitted over sillsafe ends
| PASS / FAIL / N/A | Foam tape fitted to sill fixed leg
| MANDATORY CHECKLIST | Top & Bottom Screws sealed
| PASS / FAIL / N/A | Screws fitted to all hardware & components
| PASS / FAIL / N/A | Glazing Platform fitted (TH Frames)
| PASS / FAIL / N/A | Seal between liners - Correct application
| PASS / FAIL / N/A | Tracks / Stoppers fitted correctly
| PASS / FAIL / N/A | Sashes / Panels opening and closing correctly
| PASS / FAIL / N/A | Handles facing the right way and are not lose
| PASS / FAIL / N/A | Strikes fitted - Item locks / unlocks freely
| PASS / FAIL / N/A | All hardware operational
| MANDATORY CHECKLIST | Protective tape on handle - Key taped to inside of handle