## Master List Templates
Id | Type | Name | Values | Prompting Name
51a12ec0-5226-4c6b-8497-16296f16e1ad | checklist | 00. PRELIMINARY ACTIVITIES |  | 00. PRELIMINARY ACTIVITIES
48e4218e-45a8-4736-9db1-f8b473607d34 | section | PRODUCTION PLANNING REQUIREMENTS FOR EACH PRECAST UNIT TYPE
fbae4257-3740-4385-a73f-8baef1bc8ac2 | checkpoint | Contractor's Construction / Installation Programme
4c17f0ae-d635-5446-8102-f58b6683b1f6 | tickbox | Verify Production Lot System / Precast Unit identification accepted by Contractor
39e7973a-d4d2-5270-bff3-b96b27cf6358 | tickbox | Verify programme details are current
3b293d63-69b3-5897-8e58-99d0ac62365f | tickbox | Verify programme dates are achievable
af0e4698-f4e8-575d-b0dd-531cb7f19353 | tickbox | Verify Casting Programme finalised
fcffb182-07ca-4d38-ac4b-fc3a2badc1f2 | checkpoint | Production Area
579351f4-766c-5618-9663-a62334fe80b7 | tickbox | Verify work area identified including storage of raw materials
d9e1fa8e-c515-5d66-83f6-ec23d1f2ce06 | tickbox | Easy access for concrete agitator trucks / craneage / forklift
1b65f8f3-6bff-5386-82a8-e75c440afa89 | tickbox | Curing facilities available
971bebca-0818-4607-88f5-833b11a1ff81 | checkpoint | Storage Area
1fc7ebc9-c919-5b22-a0ed-8a9e125ab63a | tickbox | Adequate area for potential long term storage
fc866bd6-8c25-569e-ac5b-b71cc2ced7cf | tickbox | Bearing capacity of storage area will meet loading of precast units
7eafe01b-be85-55f6-a59d-059d0bb400b8 | tickbox | Unit Layout plan developed
d3819f18-3061-57e7-8810-34df0a946d29 | tickbox | Adequate area for craneage operation and access by heavy haulage
f3951a81-4113-419f-a8e1-8eef4d1bb7c0 | section | Plant / Equipment / Procurements
e169f410-7b38-401f-93cb-adb060d5ddfe | checkpoint | Verify moulding received and dimensions checked
3a486025-0db3-59e8-9ae7-0df173263807 | tickbox | Curing facility available as required
41a6c4f1-6434-5bc9-8f1a-bfcefc4ac8aa | tickbox | Jigs / working platform (rebar) available as required
b67ede46-479c-5cc6-bd81-49cba272a77d | tickbox | Verify Curing Methodology signed off
52df5fbb-24af-5d4d-90c5-5782461d43ee | tickbox | Verify Curing System functional
ec1c13d3-8420-4625-a4c8-4a39b44c1fed | checkpoint | Verify Stressing System / bed signed off by member of MIAustE as required
2e088c6d-9bd7-4b34-9955-a8b854b07bfd | checkpoint | Craneage available as required
14a0a9e4-7879-4248-998b-9839b49c6c8f | checkpoint | Procurements
e136e4b6-fa85-515f-a436-14de3ba3b053 | tickbox | Verify Reinforcement ordered and delivery commenced
15207860-3dec-56d2-b7db-001f13d4d521 | tickbox | Verify concrete order process agreed with concrete supplier
79defdea-c083-5305-a37d-e3d70738e1aa | tickbox | Verify Strand / Couplers ordered and delivery commenced
d343f4bb-0910-57b6-a625-13f85587cf93 | tickbox | Verify Contractor Supplied Product ordered and delivery commenced
729cc4e1-a30a-51a0-9bf8-2232340aeac6 | tickbox | Verify cast-in items ordered and delivery commenced
143c224f-600d-55a0-80e3-a75c38f4a4c1 | tickbox | Verify lifting systems in precast unit signed off
364457e4-a104-5e99-b2a3-c78a15712125 | tickbox | Verify lifting equipment available and signed off by Authority as required
95f55b2b-467e-511c-8bdd-244e9f956e5d | tickbox | Verify production consumables ordered and delivery commenced
d52d6a14-56ca-5dc7-ab1b-87056b157a7e | textbox | specify others
da870fe2-3e5c-4737-8241-32c9c13b46d0 | checklist | 01. MDR COMMON BOOK |  | [object Object]
934dad02-da98-46dd-8ffd-864f2d3f3039 | section | A - PERMACAST CERTIFICATE OF CONFORMANCE
1cd9ddf7-c0d3-495c-b20c-a06ea009be09 | checkpoint | A1 - Certificate of Conformance for all Precast Concrete Items
7486e8cc-d0c7-4cf7-ba79-f95b1f289a2f | checkpoint | A2 - Permacast ISO 9001 Certification
aecdf89a-57b4-4acf-9f10-dee9aa47df2c | section | B - PERMACAST'S DOCUMENTATION (approved and signed off)
1939f1a2-a93c-4c8a-9a84-a4894270867b | checkpoint | B1 - Register for Quality Plan, Inspection & Test Plans, Work Method Statements, Manufacturer's Data Reports
ae3cd83f-ad52-46e5-a5ff-3a78b9a1126b | checkpoint | B2 - Project Quality Management Plan and Work Method Statement
f0645899-b47f-4ced-bbac-b81fb2ca989b | checkpoint | B3 - Inspection & Test Plans (Approved copies)
b09883d2-112e-4df5-890d-381af8b54214 | section | C - DRAWINGS - IFC and SHOP
4e5d1a67-dfa8-4334-8f29-fd931d669523 | checkpoint | C1 - Register of IFC drawings
95ab4be0-a329-4732-8323-48bee05c8009 | checkpoint | C2 - Register of Shop Drawings
0154a1db-9324-45e7-aa5b-b17abb0c7661 | checkpoint | C3 - Register of Lifting Designs
65e74ac1-0239-4884-b786-3b82108a3d22 | section | D - CHANGE MANAGEMENT
deb166f2-ebf4-4542-bbf7-a5f6843ce599 | checkpoint | D1 - Technical Query Register
f3339897-f6cd-4c60-98dc-78aa61e60f42 | checkpoint | D2 - Completed Technical Queries
be7f5608-5f63-4fde-a3e2-3c5b4a64e9d2 | checkpoint | D3 - Non-Conformance Register
d6256022-d60b-4fab-8344-4e6a7acbf947 | checkpoint | D4 - Closed Out Non-Conformance Reports
3edb889d-66c9-46cd-9ed3-74a7634c9277 | checkpoint | D5 - Defects Register
ab5acc04-82c1-4ab7-9aef-51feed7a4f38 | checkpoint | D6 - Defects to be carried through to Defects Liability Period
63643224-b85a-4546-97d1-813685ea57c0 | section | E - CONCRETE
d01ec6b2-d7ac-470c-bb06-6d973597d88d | checkpoint | E1 - Concrete Supplier: ISO 9001 Certificate
1e7b8dda-7837-4369-a221-c2a34f7c8301 | checkpoint | E2 - Aggregate Supplier: ISO 9001 Certificate
334fe272-3536-4ae2-9234-80564cce9a93 | checkpoint | E3 - Concrete Mix Designs
065033bf-8bc0-46a6-a102-321f54027d41 | checkpoint | E4 - CMRS Cement Certificate
9c6677f3-f204-4f77-8635-cab895a044fe | checkpoint | E5 - Concrete Aggregate Reports
d688f6d9-7a44-4664-91ed-94a0ede3f258 | section | F - REINFORCEMENT
acc6d4fb-cdf9-4c97-9bf3-88c09f1471fd | checkpoint | F1 - Reinforcement Supplier: ISO 9001 Certificate
4de12951-d853-4a6a-a32b-816cd5c5c867 | checkpoint | F2 - ACRS Certificate
e1e83138-6fe3-49a0-8f80-cc4a237b8d55 | checkpoint | F3 - Register of Mill Certificates
bde164ea-f3f9-4f4a-a810-4053d05ad5e6 | checkpoint | F4 - Mill Certificates
8e2d2802-9e56-4236-90c0-3701f607d691 | section | G - STRESSING (if applicable)
7d6a8b30-3342-44e4-be7d-0c5dd3795cab | checkpoint | G1 - Strand Supplier: ISO 9001 Certificate
663e5a9e-7aa1-49b6-b979-ab05b0ec14ee | checkpoint | G2 - Register of Stressing Coils
e46221ed-ea9b-4ceb-ad1c-12c9265c69c0 | checkpoint | G3 - Mill Certificates
1ca73c81-c365-4049-ad5d-baca0e7655b6 | checkpoint | G4 - Stressing Calculations
fefd5974-4073-4697-ba01-3ae09e538658 | section | H - CAST IN ITEMS
f76fcc04-6a17-4de0-9b13-0a76c5441e86 | checkpoint | H1 - Cast-in Items Compliance Records
d5d195f9-af43-4b52-8aed-1657c2172af9 | section | I - REINFORCEMENT WELDING (if applicable)
9389d26e-5926-4ec5-8bcf-8fa89b0ace9d | checkpoint | I1 - Weld Procedure Specifications / WPQR
93ae595c-1149-4220-859e-8ce4710db1ab | checkpoint | I2 - Welder Qualification Register
964c06cf-b0de-475e-b103-5f86f3fdb73c | checkpoint | I3 - Welder Qualifications
7d60d22b-5dc1-4b96-a6dc-3a185bf55a1e | section | J - CALIBRATION OF INSPECTION, MEASURING AND TEST EQUIPMENT
a3dfe0fd-1621-4150-9d17-13dfa367178a | checkpoint | J1 - Register of NATA Laboratories Used for the Precast Project
beef67be-38e3-4987-bb60-42b9fe12f0f9 | checkpoint | J2 - In-house Concrete Crusher Calibration Certificate
cdee279b-9cf6-41fa-96b3-aa3f43de105d | checkpoint | J3 - Calibration of Jacks / Gauges (if applicable)
71c492dd-643d-4289-a0e5-5018eedc7642 | checkpoint | J4 - Other Calibration Records
28b3c1cb-d34b-4ad9-94aa-8c14a901fd64 | section | K - DELIVERY OF PRECAST UNITS
73e4b907-1ff3-4472-a9b7-7bf075bb7344 | checkpoint | K1 - Register of Permacast IRC Certificates
43a016c3-7341-49cc-bfa5-667ae9dca1da | checkpoint | K2 - Permacast IRC Certificates
de39c62b-5c45-45a8-80d9-271597623748 | checkpoint | K3 - Register of Permacast Conformance Certificates
5f3ba94d-89f4-4994-b4c5-463eb16426e1 | checkpoint | K4 - Permacast Conformance Certificates
bf4f0275-5511-4021-8c59-ec458ed4fbcf | checkpoint | K5 - Register of Deliveries
86a952ca-cdd0-4dfb-94a9-c65bcc39adb3 | checkpoint | K6 - Delivery Dockets
3487535a-3429-43c8-b8d5-848e3382ada4 | section | L - AUDITS
0cf5ecd8-0f78-43ef-9c1e-60d32f349ab7 | checkpoint | L1 - Register of Audits
83a5971f-c157-4508-956d-980884502f1f | checkpoint | L2 - Audit Reports
857251c3-b042-41c1-9cce-99a51f990358 | checklist | 02. PRE-POUR CHECKLIST-STAGE 1 |  | [object Object]
5f58bb04-0ac7-4b00-a701-325e40b364c7 | section | PRE-POUR CHECKLIST-STAGE 1
fa5d2c6e-e0b9-4ba7-86c0-7936532d767a | checkpoint-no-value | Details
6c69bb8a-7ab5-56ed-a847-b666b4850bc3 | textbox | Cast Number
46422424-bf21-58de-9874-cb2df9b9ba6d | textbox | Specify Precast ID (separating each with a comma):
935c300c-9a13-5ca7-8aef-1e5f920fa3a7 | textbox | Strand Arrangement Type (If Required)
e990782b-844c-492d-847b-f16207e79814 | checkpoint | Shop Drawings approved for Works
a8c386cc-951a-5ba1-b11f-a5bfb8d77f36 | date | IFC Date
60e0d779-8814-4f37-aa8f-aacef7996904 | checkpoint | Mould Dimensions are within Shop Drawings Tolerance
f040da53-f7d7-55f3-b80a-aa6fbdca7948 | tickbox | Mould set-out drawing provided
07885dd3-1a42-52ae-bc35-97beb1b132ff | tickbox | Length
d02da1eb-be22-55eb-9630-b25a131eb3f9 | tickbox | Width
d7e0e20c-3656-552e-a4c6-78972072af75 | tickbox | Height
5974fd95-a84d-5fed-b873-81afb9879349 | tickbox | Straightness
2a367b9e-511d-5800-85b3-b2d7c785ecb7 | tickbox | Cross-section
ff2fd0b8-f981-4abe-82f0-996a3cdf8601 | checkpoint | Mould Surface Checked
d4bbc9ac-2bf7-5014-ad78-62296dff2612 | tickbox | Cleaned
490f6c37-397f-5cf9-9fdd-e4e297b7dd77 | tickbox | Sealed
10d83b64-01f1-507b-8bb5-01fb2472e6fb | tickbox | Rubbers in Place
2337f462-4a65-5c16-a75d-2b4b7d83d1d5 | tickbox | Oiled
a79a299a-1e4c-5430-800b-9553b50f170d | tickbox | Chamfers / Drip Groove in Place
c58bea86-d9e9-5dee-a3e8-f762e31edcf0 | tickbox | shutters angle checked
abec3e4d-080e-55bc-ac72-e15f22632b2e | tickbox | Temporary props / Push-pull spreader in place and secured
ed251e5e-98a0-420f-94bc-d19c78fd467f | checkpoint | Reinforcement in Accordance with Drawings
b426138e-9aa6-5765-a728-8ad327d1c77e | tickbox | Reinforcement size
0d1a6046-cd1b-51de-a426-e2d9c0ea6f2b | tickbox | Reinforcement Quantity
487f0b14-07cd-5978-ae84-d178df01d443 | tickbox | Lap Length
54de0207-c2d5-5bb7-b313-981f9319bdec | tickbox | Splicing
3da43414-2467-5066-a5b2-9fdd22048f42 | tickbox | Blockout recess around lifting Hoops (If Required)
0449a9bb-e3bd-5a09-94f0-c62934b6becd | tickbox | Additional reinforcement around Lifters (If Required)
a1d72892-b351-5d50-ac18-782e0c5ce344 | tickbox | Bar Chairs / Deck rails
30e4bbaf-d007-5872-9624-4ee055830ec7 | tickbox | Cover maintained and within tolerance
8dc9d538-8239-4877-9079-286704b77fc5 | checkpoint | All Cast-in Items are installed in accordance with Drawings and Tolerances
a8ff62b4-04e8-501a-a868-27d5bd4c8abe | tickbox | All Ferrules are installed in accordance with Drawings and Tolerances
8c4b3916-3bf5-5e92-adef-4c15bdda9528 | textbox | Ferrules Type / Quantity
c161e4b5-afb0-5c8f-a92b-1a06aff072cd | tickbox | All Stainless Items are installed in accordance with Drawings and Tolerances
70eb8a43-b5c5-5182-9b84-90e9061894df | textbox | Items:
aca02a2a-422d-526f-9673-b28e5acccdd0 | tickbox | All Blockout Conduits / PT ducts / Stressbar are installed in accordance with Drawings and Tolerances
f58a8c00-ef17-5bcd-bbd6-3dc13b391469 | textbox | Temporary Works Conduits
a692e9ba-30e1-5544-ad3e-478c3bf1be06 | textbox | Transport Holes Conduits
5fbf1f91-95ef-5453-b79a-b9b6483752bf | textbox | Bearings
639a4f2f-bd59-5f46-99f3-fca3e74a462e | textbox | PT ducts
eabc0c6c-73cf-5473-a449-90996a5abbf1 | textbox | Stress Bars
b135e145-e40a-5b3b-892f-724869100639 | tickbox | All Lifting Inserts are installed in accordance with Drawings and Tolerances
16093bce-4b1a-5b5d-b6ec-35898095880f | dropdown | Lifting System | Lifting Loops, Lifting Anchors, Edge Lifters, VLGB Load Ring, VSL Bars (Stress Bars / Cors Nuts / Lock Nuts / Bearing Plate / Washer) Others (Specify)
8e4c7da7-6b2b-5a02-9676-81564ac32894 | textbox | Others (Specify)
967fd563-07ad-5be2-8012-49a453da59da | tickbox | Additional reinforcement around Lifters (If Required)
116cf655-268a-5c9c-91a1-1e37f57d5266 | tickbox | All Couplers are installed in accordance with Drawings
ef366132-7f72-5ad6-95fd-bfd7d6111826 | textbox | Couplers Type and Quantity
4ea6e68d-02dc-5bb7-b676-3b14a369e474 | tickbox | Other Casting Items are installed in accordance with Drawings
f5c8bd08-5465-57b9-8508-465c90a3f07e | textbox | Type and Quantity
9547df62-986a-4e52-accb-8a59772adcfc | checkpoint | Earthing and Bonding is installed in accordance with Drawings
ed45fa19-99ae-59cf-a478-bceb46e0275c | tickbox | Earthing Terminals Specify Type and Quantity
ce9862ca-e082-5fe9-abc7-de7b5a9bf0e0 | tickbox | Flexi cables
d6f6bdfb-5f6c-5570-bd8e-2e9e4a91c28f | tickbox | 100mm long 6mm fillet welds between bars/ 55mm long butt welds (not permitted within 75mm of a bend)
1133b98d-af6b-5703-9aca-5895e305f57c | tickbox | <20 mOhm across cage Length
245b40c2-f27e-576e-845e-e3299922a0b7 | tickbox | Checklist Completed (attach results)
55c26dff-cbe5-4e4e-8523-810fd641562c | signoff | Client Hold / Withness Point
3dbda0f9-7f7b-4799-bc17-acf9cf94d49b | checkpoint | Post-Tensioning Equipment is installed in accordance with Drawings and Tolerances
f954c845-688a-5c60-a86c-a803a51e186b | note | Verify
37277c50-acad-5a38-aa87-5f2196fe5fa5 | textbox | Tendon Types
b8fbbdf0-bf17-5330-adb3-32f41d275b27 | tickbox | Profile
2c72f38c-ab6d-5854-a792-c759b5e8346b | tickbox | Firmly secured to rebar
4571fd59-65d7-5040-9242-1b5c41d85987 | tickbox | Grout tubes, Breathing Tubes and Grout Vents secure / sealed
1081e767-207a-56a7-9657-2765cd5b1032 | textbox | Anchors installed / secured
ab7f8e63-688b-5b69-b02d-afb4de6f4d28 | tickbox | Temporary blockouts in Tendons
41a0ef04-8ef3-4ad0-91df-7b2b4dab704f | signoff | Client Hold / Withness Point
52932e12-afbb-4df7-8ea5-366b52bae6ab | checkpoint | Prestressing Strands
13f07c60-e3df-5c67-ac16-29c54908d2e0 | note | Verify
9246e222-6719-5e68-a31e-18e6e4575541 | textbox | No of strands
7cd9c758-8e97-5080-a9af-d84061d2e23a | textbox | Debonded strands encased to correct length
65770d88-de29-5393-a76e-e7e23f429744 | textbox | Enter Coil Number Used for this Cast
35f1d800-314b-5955-9b3c-848151464c9e | tickbox | Sag Load all Strand
dd2c4042-6eec-559e-9156-8bdb999028b9 | tickbox | Full Load: Multi-Stress as per Pre-stressing Procedures and Verify lock off with spacer plates
5cbd42f0-b25a-5026-b560-73fbd9746faf | tickbox | Full Load: Singel-Stress as per Pre-stressing Procedures and Verify lock off with spacer plates
2142f2db-356c-48a8-b907-f038b1139b87 | signoff | Prepare Stressing Records and Submit to Client for Review (HOLD POINT FOR CLIENT TO SIGN OFF)
dd2ebacf-e090-4ec6-9d40-bf5e9c484fa1 | checkpoint | QA Engineer Check Completed by
c0f50e47-c0cb-41b3-be25-bab6b2bb50c9 | signoff | Pre-lifting cage inspection (Client present)
5345fdd8-abda-4cb9-bdfa-6c69c539d550 | checkpoint | QA Engineer Check Completed by
2efb977f-0143-486c-8ae9-90b947c106aa | signoff | Pre-Pour Mould inspection (Client present)
176e9f20-232e-44a8-99f2-be1f56ad7ee6 | checklist | 03. EARTHING AND BONDING CHECKLIST |  | [object Object]
0715e136-f927-47f2-a563-a5fea94b1b58 | section | EARTHING AND BONDING DETAILS
07eaa810-4a99-4678-8525-e1f4a5abeaf1 | checkpoint | Earthing and Bonding is installed in accordance with Drawings
7ce6bb22-bf9e-5914-b87a-2a594210034f | tickbox | Earthing Terminals Specify Type and Quantity
7f7f3ba0-510d-59e7-aefb-af24f5afa28f | tickbox | Flexi cables
e75fef62-af8c-5614-9388-bd84d618e4a1 | tickbox | 100mm long 6mm fillet welds between bars/ 55mm long butt welds (not permitted within 75mm of a bend)
04453ed1-a5ea-53bd-bfe2-d037a5f57b76 | tickbox | <20 mOhm across cage Length
4d061799-868b-5177-b289-454dbafcb2ec | tickbox | Checklist Completed (attach results)
6b8cdffe-3264-44fc-b9a7-f846ce4f25a5 | signoff | Client Hold / Withness Point
be6b9dfb-2898-4d32-8cfc-289e29b1facd | checklist | 04. POST-TENSIONING CHECKLIST |  | [object Object]
87c1cd30-b9b3-4584-ad09-50b2c5fcfee9 | section | POST-TENSIONING DETAILS
8d1a4d5f-d182-4264-b89f-bd44787c940a | checkpoint | Post-Tensioning Equipment is installed in accordance with Drawings and Tolerances
5cf2e112-19e8-5390-bbb6-2c1621dc58be | note | Verify
d004acf0-bfd6-5647-a8c1-f7e2a777bb48 | textbox | Tendon Types
c2993635-7f3b-51ae-b517-deb254172790 | tickbox | Profile
360d42c1-d622-53e8-8288-01b30f0a94ef | tickbox | Firmly secured to rebar
86b67513-e84d-535e-8f48-ef26d18b3c8f | tickbox | Grout tubes, Breathing Tubes and Grout Vents secure / sealed
5101c99d-7222-5354-a421-806834d73e4b | textbox | Anchors installed / secured
d1f94899-66b4-5dc5-8f4b-0e8a745f8310 | tickbox | Temporary blockouts in Tendons
10eb2669-3e31-447e-8431-74c1a524c5a5 | signoff | Client Hold / Withness Point
006f6de8-d9b2-4e64-a454-e54323f20ef0 | checklist | 05. PRESTRESSING CHECKLIST |  | [object Object]
3ab59075-98bc-4ee0-ab42-b1976bc82fff | section | PRESTRESSING DETAILS
9dfe944f-57cf-4f31-9801-fd5c2138c751 | checkpoint | Prestressing Strands
b383005b-a4bb-5246-a1cb-17d65524007c | note | Verify
5af10872-30a2-5a74-991f-c56c2765e701 | textbox | No of strands
cdd425f9-6d57-5cc3-aeea-7e1afa1c5d9d | textbox | Debonded strands encased to correct length
77cded8e-d23d-5946-9e60-f56d43e59bff | textbox | Enter Coil Number Used for this Cast
3ee65468-9101-5a0a-a2b4-1ff10da8f137 | tickbox | Sag Load all Strand
9d971636-4f35-5036-bfa7-6a4e64755589 | tickbox | Full Load: Multi-Stress as per Pre-stressing Procedures and Verify lock off with spacer plates
183d5110-ac09-5c20-82f7-5ee3bb7b5cf3 | tickbox | Full Load: Singel-Stress as per Pre-stressing Procedures and Verify lock off with spacer plates
bc1f6702-78d8-4bbe-819e-d99895e17b90 | checklist | 06. TUBS / BOATS CHECKLIST |  | [object Object]
4b1b9663-c429-4f2a-a6a3-4040a8bb9c2c | section | INSTALLATION OF TUBS / BOATS
91455804-dad9-401f-9115-3d4ece07f07e | checkpoint | Installation Details
6c448aba-3496-50a3-bbdb-8059a3fec070 | tickbox | Tubs are tightened and positioned correctly
80ac8a49-8bef-571d-b322-20209aec7430 | tickbox | All Sliding arms are locked in position
537393e7-1a0e-583a-97f5-906a3f867561 | tickbox | All accrow props are locked in position
0121b5cb-e682-5e98-a1ab-59ac29c6ee50 | tickbox | Dimensions of Tub and Webb are correct
93354a7e-7c7f-569b-8725-e030b44e49df | tickbox | All feet for tubs resting on mould & bolted down
eae895ff-467b-5d68-8d3e-f6151814c530 | tickbox | Tubs have release agent
574b9862-382d-4eaa-8fdd-bf976b34c6a9 | checklist | 07. COOLING PIPES CHECKLIST |  | [object Object]
86a07b26-42e9-4de8-be0d-0383b2d2e023 | section | INSTALLATION OF COOLING PIPES
fabb973f-d8e1-440e-b069-1acafdb51ce7 | checkpoint | Water Cooling Pipes
0694bcfd-70fc-5c19-a505-5df4043858a2 | note | Verify
54d5ff3e-c012-5910-98f2-73acf2923db6 | textbox | Number, location and installation of water cooling pipes as per approved WMS
39f218aa-1f26-4b2f-9d21-3f826335b26f | checklist | 08. TEMPERATURE CONTROL (LOGGERS) CHECKLIST |  | [object Object]
d541ad92-28f9-4b80-a9ed-5ec35dcccdd9 | section | TEMPERATURE LOGGERS
ee0e7ef0-42ac-4694-9a7c-c06f5c535413 | checkpoint | All Temperature Loggers are installed as per Approved WMS
345d29a3-7dce-5a21-95f0-041581bafe22 | tickbox | Ensure All temperature Loggers are Working (Check Maturix)
4e2d5a97-ab14-5d01-9dcd-ed517be3bd3c | tickbox | Number, location and installation of loggers matches WMS
7178fff8-8193-5bc0-9b1c-e58968f2ff71 | tickbox | Every 25m
9ecdf5da-79f8-59b3-9c9e-49e2d1e39b5d | tickbox | 1 x Core (If Required)
32aff360-2f25-55b6-944f-80e56a11eb2b | tickbox | 1 x Within Cover Zone
cecc5a9f-2689-5e1f-9016-2413afe4ae57 | tickbox | 1 x Within Tent/Tarp Enclosure (Outside concrete)
3b51ddf6-8a88-5378-abc5-fb4897368f07 | tickbox | 1 x Outside Tent/Tarp Enclosure (Ambient Temperature)
5bc70331-17a3-5f85-b4d1-52003feffc49 | textbox | Specify Extra Loggers If Required
2b766f83-4c56-46c9-8785-9f73a8875728 | checklist | 09. SUPERVISOR / SUBCONTRACTOR CHECKLIST |  | [object Object]
0807ad3e-ef97-4033-a159-7ab4572e9daa | section | SUPERVISOR / SUBCONTRACTOR CHECK
e3677b1c-f2bb-4796-a65c-629bf5d9f609 | checkpoint | Supervisor Release to Engineering Team
def7d631-c8eb-5503-be8d-59f13fcdfcb7 | tickbox | Verify all concrete placement plant / equipment available
10d91e8f-4f74-5fb3-ad45-29acb6b4b5ec | tickbox | Concrete Supplier of pour Notified
b2c9e418-5fda-5945-9a24-87ba4a8a1c3c | tickbox | NATA Testing Laboratory of pour Notified
b73e67f0-fc6c-40fd-8764-b3ce9ad35ce7 | signoff | Supervisor Hold / Withness Point
84e2fe58-0c38-4703-8b02-7b5fe9934d30 | checklist | 10. CASTING AND STRIPPING CHECKLIST |  | [object Object]
cec76016-ca67-43f9-8ed1-a0d306ee9585 | section | CASTING DETAILS
f945c7be-511a-4394-afdf-4551ca56cf37 | checkpoint | Pour Detail
f42f7780-cecb-505f-a9d9-0904914fcb8b | date | Cast Date
84297fee-1cab-528d-a164-8a0626058e27 | textbox | Concrete Delivery Docket (list All And Attach Dockets)
d1835901-0807-5fb0-a244-473cd0b75b58 | textbox | Total Concrete Volume (m3)
379e9d6e-c195-550d-b86e-7d7cda28043f | textbox | Specify Mix Design Verified/Used
0ad8642c-fae0-5e82-a72f-24c8ea0f9b80 | textbox | Ambient Temperature within Limits (max 38°C)
c4e7582a-97a5-5017-bd2c-4e00a577c53b | textbox | Concrete Temperature within Limits (max 32°C)
e091bb48-f19b-599f-97ac-11c1bb472bef | tickbox | Slump within Allowable Tolerance (First truck and every 20m3)
9af4795b-92f8-5ee8-88ad-fe0a31f4a593 | textbox | Slump (list all)
d197ea09-2f8d-4681-8768-7189575ebd39 | checkpoint | Truck Tested for strength
4e2c3236-7a5f-5913-aab0-491c2778e9e2 | tickbox | If volume <=20m3, 2 sets min required
8b5e2328-1829-5c23-982c-e374b2939383 | tickbox | If volume >20m3 & <= 40m3, 2 sets min required (every 20m3 tested)
c09bea15-d8e4-5766-94e7-a4e73467a2a3 | tickbox | If volume >40m3, sample every 20m3
80f12246-e86c-5162-b0b2-90141850cb77 | tickbox | 1 * 7 Days and 3 * 28 Days per test (Total 4 Per Test)
4f3c23a5-2ae9-5454-9fdb-f5166efdb222 | tickbox | Cast 2-4 Cylinders for Destressing / Stripping / Lifting / Curing (PMC Internal)
00bb189e-acf0-5a94-9070-38062966fdc7 | textbox | Test Report Reference Number (list all)
9f3afe7f-220c-4cc8-821e-3b7476781e7b | checkpoint | Concreting
bc83adcf-547a-554a-8832-45b807b041ec | tickbox | Vibration adedquate
9c64e365-538f-502e-a7b3-821ab1e8026e | tickbox | Time Lag Between Trucks is not exceeded
7a49c5c2-2d7b-5c98-85a0-86aedeff3bf3 | tickbox | Concrete Placed within allowable time from Batching Plant
14f75ae6-6cd9-505d-a9f2-06da1be24fef | tickbox | No Free Fall During Pour
4423455f-c10f-54ca-aade-d779d4916c1a | tickbox | Required Finish Applied as per Drawings
8751d84b-eb61-44a3-80d4-5d8826dadf2b | checkpoint | Curing
840f74da-85f6-5e8f-b016-2a0f27dad9c0 | tickbox | Concrete Covered Overnight and Tent sealed
c07c8b01-b56e-52f3-8613-e884c05e57cd | tickbox | Cylinders Stored next to Bed and covered as per AS1012
b4a2cc7e-ec26-54a7-ab2e-63debb157e7b | tickbox | Verify (if used) Temperature loggers are connected and recording and set the temperature alarm to 65°C.
f53bd25b-bcc3-59fd-82d7-9dc70df7242f | tickbox | Verify (if used) Pipes connected, pump working, no leaks in mould
3bd63fbe-f8dd-5aaa-97b9-4e5d12462318 | tickbox | Verify (if used) Steam Temperature Monitors installed and connected
3fb63c2c-7e91-4521-8b5e-1b4a6c530da8 | section | STRIPPING DETAILS
2d067a9e-8e34-4caa-a710-7a063ed09526 | checkpoint | STRIPPING DETAILS
2b426fce-884c-5373-b9cf-47c8559ca8be | date | Date Stripped
e31b157a-cbe7-45f4-832f-f021f6044a4e | checkpoint | Minimum Required Strength for Stripping, Destressing, Lifting, and Curing Achieved
6a1cf701-a12c-5108-9fe0-c9470bdfe468 | dropdown | Strength Determined by | Crushing Cylinders, Maturity Report
1514a90a-c1ec-505a-9a60-8c09efcd74a3 | textbox | Specify Min Stripping Strength and Record Strength MPa (Mpa: Reading / 7.851)
af44740d-805c-543c-bd43-9f34aaab421f | textbox | Specify Min Destressing Strength and Record Strength MPa (Mpa: Reading / 7.851)
7ee9b0ed-e0ac-5f2d-82b2-8034a6668d8f | textbox | Specify Min Lifting Strength and Record Strength MPa (Mpa: Reading / 7.851)
21bfc05c-1dce-5685-a52f-e848f3c87255 | textbox | Specify Min Curing Strength and Record Strength MPa (Mpa: Reading / 7.851)
fea69f5d-8112-5376-bca3-9ce2140ab37d | textbox | Specify Strength by Maturity if available
260fc9ef-4f5a-574a-8fc5-55730350d256 | tickbox | Mould and Steam Cured until the curing strength achieved
6e73e6ab-9d97-5d52-a761-00872542d719 | tickbox | Curing Strength: 70% of fc (Characteristic design strength)
da07f8da-9bfe-45ca-a0c3-c5a13b11409f | signoff | Client Hold / Withness Point
862acedc-775f-4157-9cf4-d8c9783c90ff | checkpoint | Lifted and Handled as per Drawings
d5731aa0-1fc5-4e47-9d94-82d819d2ee68 | checkpoint | Product Clearly Labelled
95efa7b4-fdd7-5e1b-81cc-a7b3f19048a2 | tickbox | Product ID, Weight, Cast Date, Job Number
a5963a25-9d4f-4aa1-87a3-98c02346a508 | checkpoint | Storage as per Approved Temporary Works Drawings
2b2b9632-87c7-5002-adb2-02c42a3d0d89 | tickbox | Verify supports complies with approved storage drawings and Orientation and Location matches with delivery Orientation and Schedule
d4ac5dc6-a6b3-4c71-8aec-f90060adb38e | checkpoint | Secondary Curing as per Approved Methodology
37e89761-64ee-5bbb-a2f1-9c36d3341c98 | tickbox | Temperature 5 degrees past its peak
b8d2a475-78bb-5f4b-8e60-49c5a56db7ff | tickbox | Differential between Core and Ambient As Per Spec i.e., within 30 degrees
d66db876-4555-5f46-974b-8d89e0c1b678 | tickbox | Differential between Core and Cover As Per Spec i.e., within 25 degrees
c2984c9f-e25a-45f2-9eb6-2c11ac8cacdb | checkpoint | Product Dimensions Achieved and are within Specified Tolerance
f665a54f-fd95-5fb2-9ffd-0f0418fd4cf7 | tickbox | Length
babf1c7b-48d3-56a6-9902-1d6732f660b4 | tickbox | Width
c6b22bc3-96b6-5214-9138-4cb92addfada | tickbox | Height
b94f3e0e-2b64-505d-8fa1-75faa041a40f | tickbox | Straightness
3cc51bd9-f95b-51a9-b9a9-9be13f346d16 | tickbox | Cross-section
2073f460-9594-5d2a-9aa1-7767c72092a6 | tickbox | Check all critical dimensions comply (Bearing Location)
7b98a17b-46fe-4fe5-b911-86a639b0c203 | checkpoint | Specified Finish Achieved
0d6f9f0f-e060-47a2-86b9-7a17be6be21a | checkpoint | Cast-in Items are all in Place and within Specified Tolerance
3869c0e7-a6d6-55a6-9674-8e20fe67a67f | tickbox | Ferrules
bc4e476b-4afd-560e-ba01-16a42565cc6f | tickbox | Couplers
365ccd26-f2a6-5404-9bc9-9d4e6283c47e | tickbox | Stainless Items
4061d645-927d-511f-9bfc-3c65635f8f65 | tickbox | Lifters
e2ec123c-87d1-5650-beec-bff9bd436efa | tickbox | Blockouts
ace00dcf-5396-532b-9f2a-09337a431784 | tickbox | Earthing and Bonding
3d057abd-3dc3-5e0e-b5ef-ae56b1f3089b | tickbox | Post-Tensioning Equipment
7a7dcfcc-99d1-4e58-87e1-68895a5074cd | checkpoint | Post-Pour Works Completed (As Required)
f2b0c6c6-7a4c-5b7a-8c99-00d409c6a555 | tickbox | Strands have been cut flush and epoxied.
1021c974-3946-5b3b-925d-a22fc65d0d39 | tickbox | Strands are properly bulbed.
26016113-806c-5feb-b64f-1db620d9e687 | tickbox | Nailplates, recesses, and other obstructions have been removed.
029b8acc-73d8-5c12-b253-cf7d0a6e3922 | tickbox | Couplers and ferrules are cleaned and capped.
75da6244-4a9a-58f0-9113-ad94873cde83 | tickbox | Earthing and bonding terminals are cleaned, with bolts securely screwed.
85f9be96-7587-5bf3-9e2a-8a1f75d3e768 | tickbox | Chamfers are clean, neat, and present on all required edges.
b4d3651e-11c7-5d9d-8a09-a22afe562421 | tickbox | Cooling pipes are drained of water and filled with grout as per the Work Method Statement (WMS).
cf33d765-d640-5e3b-9969-813bd8e0dffc | tickbox | All drain holes, service ducts, and blockouts are cleaned and cut as required.
c9e76e87-9427-585e-9a1e-20490e4c863d | tickbox | Temperature logging wires are cut flush with the surface.
06625071-dc3a-551b-b8bf-005069d07f8d | tickbox | Starter bars are cleaned and bent as specified.
7b138042-6139-53e5-8b41-d8d628322836 | tickbox | Surfaces requiring roughening are greencut according to the drawings.
209e7e70-9889-59f0-9f85-00e0404ff213 | tickbox | The top concrete surface is free of loose concrete.
4d30da38-f5fd-5ecb-b920-41f54cb5232a | tickbox | Areas requiring U2/U3 finish do not have a roughened surface.
b2a45234-d63e-5f00-b7ad-ff7e4352c4f2 | tickbox | Bug holes and air bubbles have been identified, with sizes and distribution compared to AS Standards.
343f48b9-a3ab-5c0c-a8a3-60cc2a30ad3d | tickbox | All blemishes (dry concrete) have been removed and patched.
113cbaf3-63cc-58bc-88ce-e071636496a1 | tickbox | Any discoloration on external/visible surfaces has been removed by sanding.
2d5fd840-99f4-572b-a5fd-c10ee44951b5 | tickbox | All generic post-pour works are completed as required.
60e25e57-7414-4792-8334-d33a2d6b86c9 | checkpoint | Temperature Logging Completed and Conforming. Attach Results
dedae1e1-b22e-4d0d-bbb1-2791bf6b797f | checklist | 11. PRECAST SURVAY |  | [object Object]
bf4d87da-8b9d-406b-802b-462502d9a2ad | section | HOG/BOW DETAILS
80dbcdf6-71a7-4513-913a-bdc5180efa84 | checkpoint | Survey Hog of Beams
b9879238-98e1-59c9-8eb9-d0721a70b59f | textbox | First Reading (mm) (Once Stripped)
bd3d0d35-1e7d-5811-b3e1-a1741f54216d | date | First Reading date
1d0ae6d5-01ff-504a-84c0-3a51687c7cd0 | textbox | Second Reading (mm) (After casting stage 2 And / Or atleast 7days after stage 1 casting) (if required)
c66af43e-8afd-52f4-91bb-decd5925de63 | date | Second Reading date
9a37f45a-db9f-5aaf-b7eb-9fbe7ad959b7 | textbox | Third Reading (mm) (At 28 days after stage 1 casting)(if required)
b3acb8ea-e6c5-51bf-9866-7751b806f4cc | date | Third Reading date
b575fd8d-094c-59c7-9527-cce61dbecaa8 | textbox | Final Reading (mm) (7 days prior to scheduled delivery)
55172cb1-aa63-54f8-8f01-a505dde829f3 | date | Final Reading date
469de381-c4cc-4d53-8743-50d274408bbf | section | GENERAL SURVAY
c19e985f-6ab6-4e3a-b612-ef7594cc5f88 | checkpoint | Survey Details
bccfa221-0935-5d36-b913-87c8dee3dab3 | tickbox | Geometry Survay (Attach the files)
bcf5c231-1cd0-5ce4-8a95-117ed84e082e | tickbox | Stress bars
898fcd6f-cfea-5ca2-89b4-1f51483d04b5 | tickbox | Ferrules
c1286140-b823-5e93-a838-6d5bfd44da06 | tickbox | Bearings
a09b26c5-246b-54a5-a138-cb0071a33ed7 | textbox | Others (specify)
bcdb07bb-8c18-4bbc-aab7-fae190a87cb7 | checklist | 12.CHECKLIST-STAGE 2 |  | [object Object]
b361a97f-c9e5-49cc-9645-8ff4e4cff1f0 | section | PRE-POUR CHECKLIST
03e4f3ad-7feb-48ad-a948-8827de32d122 | checkpoint-no-value | Details
9f0e9e99-8316-52f5-936e-51bf7dd937fe | textbox | Cast Number
8b0d3764-fe36-5981-a0ba-e7f0e3d398c7 | textbox | Specify Precast ID:
92f5b112-4694-4f79-909b-25a6e0e5698d | checkpoint | Shop Drawings approved for Works
0b3d1c82-1fbc-5a0a-a117-139318274443 | date | IFC Date
cb95c90d-f69b-44db-9cb9-9b770cd5d878 | checkpoint | Mould Dimensions are within Shop Drawings Tolerance
11c9cd97-9673-5cdb-ab28-ae1d0d107c56 | tickbox | Length
5b784ac6-cd11-52a3-9742-1d9717fd6977 | tickbox | Width
e35cdf7d-b875-59a9-85d5-c7bbde139622 | tickbox | Height
f5f750e5-bb29-5543-ab21-507648dc91dd | tickbox | Straightness
949ca7a8-2d4f-5fe7-912e-c821831e4d10 | tickbox | Cross-section
35ba85b8-13f1-4432-9f7d-459614c5f8bc | checkpoint | Mould Surface Checked
a43d38bc-ad2e-5009-98fd-4f9f45c87747 | tickbox | Cleaned
c24d869f-057a-5a18-8d38-2cd58e3d45c4 | tickbox | Sealed
3b0dfa1d-65f2-5b43-be4f-ff04d2d30afc | tickbox | Rubbers in Place
63c74c30-42a9-50cf-a4e4-ed9032223a18 | tickbox | Oiled
5e619914-8f6c-576b-a15d-b3f7b5ec61a0 | tickbox | Chamfers in Place
a109d478-0955-5fb5-b48a-b12c5ab98beb | tickbox | shutters angle checked
0e8bf17c-ed37-56bb-865a-9b9d167da934 | tickbox | Temporary props / Push-pull spreader in place and secured
bd81d7c1-5e25-4345-a9b3-afe91c0a1f90 | checkpoint | Reinforcement in Accordance with Drawings
fa9b856b-f8b8-5135-a97d-6c363b31c2c9 | tickbox | Reinforcement size
2f4f5f92-e197-5f2f-9b43-08fa109b6fe3 | tickbox | Reinforcement Quantity
81ac48f3-1d65-5231-a203-2426ac83937b | tickbox | Lap Length
8bf19184-4341-572f-9899-ef0b444912b5 | tickbox | Splicing
a9e3d935-31e3-52be-a0c5-f7adb8cca5fd | tickbox | Stitch pour reinforcement lapping bars spacing maintained (If Required)
3023a652-75ad-53dd-97da-132cc3572d8a | tickbox | Blockout recess around lifting Hoops (If Required)
b472b02c-8e5f-594b-baaa-213f1a835bf6 | tickbox | Reinforcement bars with couplers (If Required)
dc734b34-3508-5d40-9a74-5fdd4d7d7d36 | tickbox | Additional reinforcement around Lifters (If Required)
85ab804b-132d-5f9e-8ede-39f23a50476b | tickbox | Bar Chairs / Deck rails
59028b56-b5a7-525a-95c0-a923955ecd1e | tickbox | Cover maintained and within tolerance
8a9951db-2f19-4f4d-a033-2ddb23a02a85 | checkpoint | All Cast-in Items are installed in accordance with Drawings and Tolerances
991aa870-e527-55df-b9e7-a42f6faa9d81 | tickbox | All Ferrules are installed in accordance with Drawings and Tolerances
8597c8f4-9aef-5bc5-bd55-253997dbd9fb | textbox | Specify Ferrules Type and Quantity
ac3f3621-bd8c-5589-8ec5-11dc459eb09a | tickbox | All Stainless Items are installed in accordance with Drawings and Tolerances
239a5f0c-9766-56de-bf7f-0066f2826009 | textbox | Items:
b7cce523-056d-5f84-9b89-8fd83dc27b9f | tickbox | All Blockout Conduits / PT ducts / Stressbar are installed in accordance with Drawings and Tolerances
73e196c5-2926-5096-88e6-358d9365d4ad | textbox | Temporary Works Conduits
c10be822-9e34-55a0-8a7a-73c8ff6596f1 | textbox | Transport Holes Conduits
826c2734-7de8-55f4-8f29-d7389855cf59 | textbox | Bearings
f2d1e711-8e14-566b-8b94-922ece29e4ea | textbox | PT ducts
29ab7959-5da1-57ca-84af-87c75a4f00d6 | textbox | Stress Bars
636b59cb-9a89-5d97-983b-26b30b01b776 | textbox | Other type, specify
0a43c230-2c5a-5d7a-9ef6-eca5a2f5ef08 | tickbox | All Lifting Inserts are installed in accordance with Drawings and Tolerances
50785aec-164e-51d0-a1c0-241b2f416c2e | dropdown | Lifting System | Lifting Loops, Lifting Anchors, Edge Lifters, VLGB Load Ring, VSL Bars (Stress Bars / Cors Nuts / Lock Nuts / Bearing Plate / Washer) Others (Specify)
9732f007-5fd4-5465-a8d1-3c7b6f0f9739 | textbox | Items:
32244b35-e09f-5ad0-9d71-6e67adc4669b | tickbox | Additional reinforcement around Lifters (If Required)
a3f811c4-2fdf-5e36-86f7-cefd9ac5baca | tickbox | All Couplers are installed in accordance with Drawings
1ef4a3e1-d09e-53e1-851c-edbe4bf7b0ac | textbox | Specify Couplers Type and Quantity
fd76aa09-a5cc-5305-a1a0-99c79cc50d2f | tickbox | Other Casting Items are installed in accordance with Drawings
8840f70c-ec8a-58fb-93f2-c840a901cf73 | textbox | Specify Type and Quantity
3789be93-0381-4f79-9042-3496883cd6c7 | checkpoint | Earthing and Bonding is installed in accordance with Drawings
c9a4c704-b5bd-5cd4-976f-9b954e48a932 | textbox | Earthing Terminals Specify Type and Quantity
29efb438-30ec-53f5-b88c-3833f8007079 | textbox | Flexi cables
56b527d5-0f18-5e57-86bd-6f2ba5fbda59 | textbox | 100mm long 6mm fillet welds between bars/ 55mm long butt welds (not permitted within 75mm of a bend)
af6658b3-eb20-5a60-afd2-510b2beb6fa6 | textbox | <20 mOhm across cage Length
fc97ab05-8225-5b01-b91d-96f9b93cd3e1 | tickbox | Checklist Completed (attach results)
9ed9b5bf-15b6-4399-8c6f-0d568326e90c | signoff | Client Hold / Withness Point
30f0df5c-f99a-4264-9480-93bef48d3c6f | checkpoint | Pre-lifting cage inspection (Client present)
c7e697bb-8136-43d0-8218-e186f3f5316c | checkpoint | Installation of tubs
2a1e6230-920b-572e-bc5e-1cc6ce2bc216 | tickbox | Tubs are tightened and positioned correctly
ce438532-e8fa-57a1-8af1-566e1da999e2 | tickbox | All Sliding arms are locked in position
f8c910d5-f218-5a93-bdce-868d7f099823 | tickbox | All accrow props are locked in position
630032af-f723-579c-a9c5-26db16776e10 | tickbox | Dimensions of Tub and Webb are correct
dd937ce0-e738-57e7-8b45-1c94e45d0d70 | tickbox | All feet for tubs resting on mould & bolted down
6ebb0a68-8ed9-5ef8-b46a-4a89d0006b59 | tickbox | Tubs have release agent
0f73d548-d15d-4ae1-8283-3921cb20d22d | checkpoint | Water Cooling Pipes
c32b4e6e-4f92-5e8d-a112-ce89e473730b | note | Verify (if used):
fb4bb7f5-93d9-5e19-957e-53e2c25f59f3 | tickbox | Number, location and installation of water cooling pipes as per approved WMS
294bf859-7873-421a-8bbc-e63125213e18 | checkpoint | All Temperature Loggers are installed as per Approved WMS
fef5712b-3eca-5503-930a-56655851c238 | tickbox | Ensure All temperature Loggers are Working (Check Maturix)
c7d1ca00-2d4e-58cf-8718-49edc7b3db2e | tickbox | Number, location and installation of loggers matches WMS
3a4e41a6-17b9-5137-9d6b-53c5d9f3d4ee | tickbox | Every 25m
b212e29f-0b18-57bb-8e30-f667a90c5086 | tickbox | 1 x Core (If Required)
b3c6a265-a0e9-5d98-acc6-1a678156758c | tickbox | 1 x Within Cover Zone
b7133d39-d382-58cf-929a-80428d4671ac | tickbox | 1 x Within Tent/Tarp Enclosure (Outside concrete)
3a5a675a-1ee0-5610-a553-17ce654e4c7a | tickbox | 1 x Outside Tent/Tarp Enclosure (Ambient Temperature)
ea517cc6-bfc9-573d-80ee-1417cdb2e8d7 | textbox | Specify Extra Loggers If Required
8d2970f9-dd4d-45ea-bd2b-5f338d119c40 | checkpoint | QA Engineer Check Completed by
8b4f97ef-da94-4c76-90d5-7f7763a91b85 | checkpoint | Pre-Pour Mould inspection (Client present)
791d630d-839f-42de-8c59-f5f4410480aa | signoff | Client Hold / Withness Point
783ecc72-0e74-4593-a7a4-cb6575393065 | section | SUPERVISOR / SUBCONTRACTOR CHECK COMPLETED OF MOULD & CAGE FOR CONCRETE PLACEMENT
4b289063-ebb4-4e96-8b63-2bdad2003617 | checkpoint | Supervisor Release to Engineering Team
89ed2bc8-2d61-542e-bafd-dcead03c4ccd | tickbox | Verify all concrete placement plant / equipment available
0ce09959-b389-5b6f-9bf2-dc3ba886d92d | tickbox | Concrete Supplier of pour Notified
cd9cd1dc-f2b2-5dfe-a5d1-ff738102bfbd | tickbox | NATA Testing Laboratory of pour Notified
13f00c57-3e63-4818-8641-270d5498d7bf | signoff | Supervisor Hold / Withness Point
004e8efb-66fb-4a7d-aa6f-45bb448b75ba | section | CASTING DETAILS
f301287c-29b8-4254-b02e-d9f6e8619f9d | checkpoint | Pour Detail
f82790ea-a706-5212-aaad-df456c58d233 | date | Cast Date
fcfa5678-e7ea-5af9-be8a-1c02c68f9aec | textbox | Concrete Delivery Docket (list All And Attach Dockets)
38ba7fb7-0c35-5502-9632-75f9a09a512d | textbox | Total Concrete Volume (m3)
8b4fec13-a024-5e5f-96d4-8f8bf5bc2d71 | textbox | Specify Mix Design Verified/Used
02bef180-0c2a-5a5d-9479-391cd7bc4f98 | textbox | Ambient Temperature within Limits (max 38°C)
1c9faa4d-75de-5426-9ee2-58a9aec5208f | textbox | Concrete Temperature within Limits (max 32°C)
a6660e46-679f-5558-99d8-4380ce0a5157 | tickbox | Slump within Allowable Tolerance (First truck and every 20m3)
ce064523-54d8-5bbb-857c-4c44d66d8d0e | textbox | Slump (list all)
d8e9f653-d4fa-474e-92e9-7f6c5269e6ab | checkpoint | Truck Tested for strength
397613b8-36b1-56ec-9802-64e277b1b6b0 | tickbox | If volume <=20m3, 2 sets min required
d31a5548-b7d7-5452-bd55-12cb12eb0ddc | tickbox | If volume >20m3 & <= 40m3, 2 sets min required (every 20m3 tested)
37082075-ee2b-5ef2-a529-89bc0ddcc922 | tickbox | If volume >40m3, sample every 20m3
09fb05a7-dd66-5edf-b3b5-75da50e05ba2 | tickbox | 1 * 7 Days and 3 * 28 Days per test (Total 4 Per Test)
7b54b34d-3117-517e-94b2-79ddf46dbf3f | tickbox | Cast 2-4 Cylinders for Destressing / Stripping / Lifting / Curing (PMC Internal)
1a7e0072-3fac-5bae-9380-7a3970ac9812 | textbox | Test Report Reference Number (list all)
67b8e22b-915c-4dc2-9366-6d7636f73425 | checkpoint | Concreting
70326ab8-389b-5f2b-a259-e10c695c6384 | tickbox | Vibration adedquate
a5ba3335-18d5-511b-aad2-2d032c653863 | tickbox | Time Lag Between Trucks is not exceeded
8bab3df6-c029-541c-ad93-b31b69fa9fe1 | tickbox | Concrete Placed within allowable time from Batching Plant
88f36ed6-ccf0-593c-b2fd-98c4507060ac | tickbox | No Free Fall During Pour
d5b861c9-7ba2-59dc-a61c-0c51512c6bce | tickbox | Required Finish Applied as per Drawings
1147d21a-0a58-41cb-aa9b-911caa27e100 | checkpoint | Curing
7211db0f-370c-599b-ab01-4a04afa13393 | tickbox | Concrete Covered Overnight and Tent sealed
7a12766d-dfad-5140-b9dd-2480e57103cf | tickbox | Cylinders Stored next to Bed and covered as per AS1012
a19b2af1-4c45-5337-bc9b-b8b3fd286cf3 | tickbox | Verify (if used) Temperature loggers are connected and recording and set the temperature alarm to 65°C.
9c688c35-4b37-5ee3-b27a-717fc8ee091c | tickbox | Verify (if used) Pipes connected, pump working, no leaks in mould
56fefcf0-97c0-5953-8484-398720880360 | tickbox | Verify (if used) Steam Temperature Monitors installed and connected
43e4ab73-8291-4b8f-a95f-6c466ccfcec2 | section | STRIPPING CHECKLIST
de1007bb-6477-4b54-8a22-661a576085c0 | checkpoint | Date Stripped
898525b0-4443-5363-a028-8f012eb3984a | date | Date Stripped
d6dd3896-ff7b-4bbd-ba6a-093c3b9a88f6 | checkpoint | Minimum Required Strength for Stripping, Lifting, and Curing Achieved
d8cc68ac-4a1f-5b3b-9482-ec30f693514f | dropdown | Strength Determined by | Crushing Cylinders, Maturity Report
afaf5c6e-9925-5aab-b050-89bb0bc798e6 | textbox | Specify Min Stripping Strength and Record Strength MPa (Mpa: Reading / 7.851)
caeff3eb-2f71-5599-aeec-707aec63d32a | textbox | Specify Min Lifting Strength and Record Strength MPa (Mpa: Reading / 7.851)
27ce5e77-31a9-5bdd-bb52-14be8e4e1ba2 | textbox | Specify Min Curing Strength and Record Strength MPa (Mpa: Reading / 7.851)
0ab03ce7-24d7-51af-b179-023e66a3786d | textbox | Specify Strength by Maturity if available
d5cbcca8-6274-5b3c-bc36-0071fbee62c6 | tickbox | Mould and Steam Cured until the curing strength achieved
29287b31-80b6-5e17-83d7-503f874d096d | tickbox | Curing Strength: 70% of fc (Characteristic design strength)
457250a4-696f-4b54-9e5d-fd055eee81c8 | signoff | Client Hold / Withness Point
aa228f29-8d57-4716-87a0-1c1a09dd3f2a | checkpoint | Lifted and Handled as per Drawings
49992e6c-564a-4d88-b6ca-8452809526ce | checkpoint | Product Clearly Labelled
d2eec5c5-ba35-5f82-8804-7a029fa980f9 | tickbox | Product ID, Weight, Cast Date, Job Number
0060417b-7c5e-4226-a51f-e29e396e89a8 | checkpoint | Storage as per Approved Temporary Works Drawings
93d6551e-6ab7-5303-89b2-63d8a47364a6 | tickbox | Verify supports comply and Orientation and Location match with delivery Orientation and Schedule
a433d982-c1e0-49fb-8386-f9a0d020441a | checkpoint | Secondary Curing as per Approved Methodology
cf01856d-5492-5cb5-a63d-cc6481f0e5a0 | tickbox | Temperature 5 degrees past its peak
e146da65-d4ff-5f16-9191-73e3c2708a40 | tickbox | Differential between Core and Ambient As Per Spec i.e., within 30 degrees
7e02f5e8-3257-575d-b400-758caf13f35b | tickbox | Differential between Core and Cover As Per Spec i.e., within 25 degrees
d708de6b-7d3d-44e5-bb45-efd2a3026883 | checkpoint | Product Dimensions Achieved and are within Specified Tolerance
9f7c1361-be3b-5f9f-867e-7b79c09ab2e3 | tickbox | Length
1c1ac710-f857-591d-81b2-60c5fed53a69 | tickbox | Width
5db5d58a-3bbe-513a-80b4-9a7fab794bb1 | tickbox | Height
361c9ca4-bfce-5ac8-b53f-404f345c7990 | tickbox | Straightness
f3d6c00c-db18-5f2e-bf94-8d10c2d1c359 | tickbox | Cross-section
1784cc08-ce2f-4e78-b380-a8f1e7c79f39 | checkpoint | Cast-in Items are all in Place and within Specified Tolerance
2a463640-33b8-501a-ae63-75fdc3e573c0 | tickbox | Ferrules
8d785afc-d25d-5e08-845b-1ec9b069a28b | tickbox | Couplers
66aa1112-2149-5eb8-8425-5ebf90024f15 | tickbox | Stainless Items
a920c776-6975-5b7d-aeff-3fd113eb7b3f | tickbox | Lifters
f18007b5-d903-579e-91b0-294255d91113 | tickbox | Blockouts
592c2eb8-f26b-5dde-bb9e-23c8d4f154e0 | tickbox | Earthing and Bonding
d227688a-0ecb-56aa-9559-8e4e305c91ac | tickbox | Post-Tensioning Equipment
a102d273-9f73-4f1c-a3c8-6b24249616a4 | checkpoint | Post-Pour Works Completed (As Required)
a0145470-6116-5443-bf7a-9baecaaa68af | tickbox | Strands have been cut flush and epoxied.
25d4927c-1ace-5e25-b786-455382ad9343 | tickbox | Strands are properly bulbed.
faa8d30f-a635-5b86-8087-708652765047 | tickbox | Nailplates, recesses, and other obstructions have been removed.
38cf029a-f542-5ef5-82d1-a716d4d47a92 | tickbox | Couplers and ferrules are cleaned and capped.
6a2fda68-8ee2-5cf1-adcc-4b58f97c341c | tickbox | Earthing and bonding terminals are cleaned, with bolts securely screwed.
3cc9a579-4c9d-5cef-870c-3da85c06ea2e | tickbox | Chamfers are clean, neat, and present on all required edges.
79e57536-fdde-5494-a45c-82ad320ea77c | tickbox | Cooling pipes are drained of water and filled with grout as per the Work Method Statement (WMS).
cd60d997-d35e-57cc-8a7c-3679aab138cb | tickbox | All drain holes, service ducts, and blockouts are cleaned and cut as required.
e48d6c5b-dda2-5095-9d65-6660bdbf9135 | tickbox | Temperature logging wires are cut flush with the surface.
20174a5d-2654-5567-b6e5-ff23fb30de8a | tickbox | Starter bars are cleaned and bent as specified.
87906db0-d9d7-5d50-95eb-6164f5540326 | tickbox | Surfaces requiring roughening are greencut according to the drawings.
43dec4db-8567-5b51-b2de-954b84c9599a | tickbox | The top concrete surface is free of loose concrete.
c7d80fdd-585b-5848-b4f3-0c45e3118024 | tickbox | Areas requiring U2/U3 finish do not have a roughened surface.
a5c9d536-bd94-5fd9-83fc-9061d00d9afe | tickbox | Bug holes and air bubbles have been identified, with sizes and distribution compared to AS Standards.
448931be-ce30-53d0-9372-dd31c2905ddd | tickbox | All blemishes (dry concrete) have been removed and patched.
fd058ab6-44be-5446-adbe-aa17c299f5c6 | tickbox | Any discoloration on external/visible surfaces has been removed by sanding.
2eea5460-7aee-51c4-a941-366a9fbe3f4e | tickbox | All generic post-pour works are completed as required.
74a7325b-16f4-5dad-baf4-1fe870f1b029 | tickbox | Specified Finish Achieved
46f0980d-ddd5-4827-91d5-a0f03f3ea3f0 | checkpoint | Temperature Logging Completed and Conforming. Attach Results
499e506b-0f2c-410e-b768-a26ad6700ca4 | section | CONCRETE STRENGTH TEST REPORT
51d31563-fc81-4bf2-bef0-f79da921ae15 | checkpoint | Concrete Strength Test Report Received
350b401e-bbc0-57fc-afdb-abbaf76c95ec | textbox | Concrete Test Report Number
8cbfabad-6b98-5bfe-9f98-23e4bf3f0d72 | textbox | 7 Day Strength (List all) (separating each with a comma)
4eaa9841-c12d-5f25-91f0-3e5eee656bfc | textbox | 28 Day Strength (List all) (separating each with a comma)
85ace93f-b44f-4524-9154-57f28d77770e | checklist | 13. POST POUR CHECK LIST |  | [object Object]
f456a1ad-1387-4707-ac3d-de66909efdcb | section | ANY DEFECT IDENTIFIED
bf7c6075-cee9-4575-8d4d-90b13c134150 | checkpoint | Punchlisting Completed for all Units / Attached
5edad631-ae83-5a93-a19d-94b30ff02723 | textbox | Precast IDs (More Than One Unit)
07d7c9a1-3c6d-494b-ade4-66f5e938b8e7 | checkpoint | Crack Map Completed (If Applicable) / Attached
d510870a-eea5-5405-a354-70911d350397 | textbox | Precast IDs (More Than One Unit)
cd914ff4-a76c-4a3b-ac96-9dea4679e884 | checkpoint | NCR Approved by Client and Repairs Completed (If Applicable)
97ee1a33-7f46-58fa-8ec9-29480adca045 | textbox | Precast IDs (More Than One Unit)
68d81d52-de51-446d-8be4-e8db95b2df1d | checkpoint | Client Inspected Precast and Accepted Visual Condition
68ee04bf-9da3-58b4-bb1d-c376f5b26f10 | textbox | Specify Precast ID (separating each with a comma)
5edce80f-793f-469b-9664-00115ebaf00b | signoff | Client Hold / Withness Point
91a870ac-9022-4c19-abaa-160a456188ff | checkpoint | Precasts are free of Defects and QC Stamp Placed
4c26b251-3cf1-58ec-8821-831476c135e5 | textbox | Precast IDs (More Than One Unit)
053ceda5-6c7f-4ab5-81b6-a09ff7d4260e | section | AS-BUILT DRAWINGS
0829f354-be80-4c04-b84a-36fd2841a5bf | checkpoint | As-Built Drawings Completed, Stamped and Attached
c3d19c94-6fd5-4ca8-8e36-b29fcb8b3fd3 | section | CONCRETE STRENGTH TEST REPORT
c68970de-edf4-497a-8f84-f1d41e4ceef5 | checkpoint | Concrete Strength Test Report Received
d0ee4965-9db5-5ecf-8c05-3c4ced47ef3c | textbox | Concrete Test Report Number
5e2feb95-44a5-5b94-aae5-50905a19da21 | textbox | 7 Day Strength (List all) (separating each with a comma)
4d9df370-5376-55d1-8e57-53f771e848a6 | textbox | 28 Day Strength (List all) (separating each with a comma)
3f87a390-0239-440c-9de1-9a653939ac15 | section | TRANSPORTATION REQUIREMENTS
6ac09494-dff9-447a-8d81-6d885bf12c73 | checkpoint | Transport Strength / Age
d2df4cf2-93df-5764-b5ab-fe0b381ab5d5 | tickbox | Verify unit(s) have achieved 28 day concrete strength
6d32f000-5138-59f7-9c70-19e1ce46d661 | tickbox | Verify unit(s) is at least 7 days old
1ca005ab-e2f0-49cd-be1d-ce4386cbc634 | signoff | If 28-day strength is not achieved by the delivery time, obtain client approval for a minimum of 95% of the 28-day strength before delivery.
27af60bc-636f-4e60-886c-cfb73669ce5e | checkpoint | Certificate of Conformance
611188dc-6617-4148-a376-edea189a3071 | checkpoint | Inspection Release Certificate
79ebb25c-5e93-4d7d-b099-9b7889e44f15 | checkpoint | Delivery Notes
f71171ff-d506-4e7f-9a52-92cd6c75d552 | checkpoint | Delivery Docket
b3b03f3b-fe01-53a6-8dfa-0dbb0a5eb66a | tickbox | Lashing, chains, frames, bolts, supports, and orientation of precast elements as per approved drawings.
f7061603-79af-5a2a-929f-28c616221c80 | tickbox | Attach Final photos prior to delivery (on Truck)
708a2e8e-5275-4ce6-9ba1-7e3273fa0a2e | section | FINAL ACCEPTANCE
0003d44b-8ea2-4203-813b-f61e53e2de77 | checkpoint | Completed by
55688a03-ecb3-40d6-bdce-e8ef08325868 | checkpoint | Reviewed by
77fa9a17-5069-4126-86ef-3e7fbe86d8f4 | checkpoint | Client Representative (if applicable)
876ba526-3084-4c5b-9793-98e303309318 | signoff | Client Hold / Withness Point
1a50bb77-c632-45a5-b5e1-fe10dca5de73 | checklist | 14. PRECAST UNIT CHECKLIST- COMBINED |  | 14. PRECAST UNIT CHECKLIST- COMBINED
0713e52b-b29d-4e0b-b43c-b3c33b37f7f6 | section | PRE-POUR CHECKLIST
5c57768d-af6c-4aa8-a4d9-977828634fe7 | checkpoint-no-value | Details
b24b80db-0096-50f2-882d-4dd53f6c6690 | textbox | Cast Number
53e1297d-4d94-551a-9abe-83a2d95b4331 | textbox | Specify Precast ID (separating each with a comma):
f030d3b5-9c23-5aa0-bcf0-acb15f0b3228 | textbox | Strand Arrangement Type (If Required)
20316608-58f0-4f09-9558-03545ad75783 | checkpoint | Shop Drawings approved for Works
825d3e4f-3777-53ae-940b-3216aea31088 | date | Shop Drawings approved for Works
7e6bf3fc-443c-4aa5-9996-4f9e06815903 | checkpoint | Mould Dimensions are within Shop Drawings Tolerance
fc2decf0-a8e1-50ba-8be0-1deeb72ef8ff | tickbox | Mould set-out drawing provided
3a4d61ee-5ade-5142-80af-4fd4bb575e50 | tickbox | Length
65cfe034-e345-5d92-9012-e7ae5f0e594d | tickbox | Width
2ab6a27d-e34f-51a2-82e0-698765858a05 | tickbox | Height
9a122bd7-5173-5969-ae12-c718da6480ec | tickbox | Straightness
77b2e8be-ad10-5370-88a2-fef4a4da8110 | tickbox | Cross-section
06bf0f00-f13f-45b3-9a67-ebacd9a7ec37 | checkpoint | Mould Surface Checked
938246b8-b070-59e9-a261-7340e973e084 | tickbox | Cleaned
e91c4b91-d47f-5a9c-8d38-b7e864857eae | tickbox | Sealed
f04408d5-0f1e-5029-97fa-b917df1362e0 | tickbox | Rubbers in Place
013ba197-acf3-5328-80f1-dfa558fec0ee | tickbox | Oiled
ac4af697-1e62-5b70-9a15-abc12325922d | tickbox | Chamfers / Drip Groove in Place
5b9f0eb2-837d-5544-aa59-deeba05c4030 | tickbox | shutters angle checked
0fdcd2a5-d46d-5f3e-a55b-6691311b4e85 | tickbox | Temporary props / Push-pull spreader in place and secured
8349a6b8-dfdb-4b5f-a7e2-f743a3a24cfc | checkpoint | Reinforcement in Accordance with Drawings
fc707278-ede0-517a-9313-5ef04db9765d | tickbox | Reinforcement size
b2aa4d32-2aee-5a2e-bab8-83684ae528a8 | tickbox | Reinforcement Quantity
0c8554b1-b145-5dff-897a-2d07d5ddde0d | tickbox | Lap Length
7db7c5a8-e683-5c1c-8c2b-8f4128db8234 | tickbox | Splicing
73d18704-8603-5588-bf13-6c5281dab456 | tickbox | Blockout recess around lifting Hoops (If Required)
3b45e2c0-ff4f-5750-bb16-0c37665219a9 | tickbox | Additional reinforcement around Lifters (If Required)
45b51328-70a5-5cb5-9549-55e3eeee6eef | tickbox | Bar Chairs / Deck rails
09d66f4e-3103-5d82-bb0c-a1232897e04f | tickbox | Cover maintained and within tolerance
20c8d3c1-8119-4a10-bd82-2915660cb15a | checkpoint | All Cast-in Items are installed in accordance with Drawings and Tolerances
3c750ff9-2881-56f7-bca9-ca59ce15fc27 | tickbox | All Ferrules are installed in accordance with Drawings and Tolerances
7ea80980-986d-5145-847d-2789bf523982 | textbox | Specify Ferrules Type and Quantity
d1ee5ccc-6566-5773-bb89-328ca282ded1 | tickbox | All Stainless Items are installed in accordance with Drawings and Tolerances
fc25bd79-e712-5b90-a67d-73ec3c3f4fbc | textbox | Items:
924b225c-013c-577a-977a-cec7b5fb61dc | tickbox | All Blockout Conduits / PT ducts / Stressbar are installed in accordance with Drawings and Tolerances
6607d171-f2f9-51b0-91b3-892691b27c36 | textbox | Temporary Works Conduits
3edf30b4-2845-58ad-b870-63f41150c222 | textbox | Transport Holes Conduits
5ec7c023-2570-5d69-95ce-893dd0347bc4 | textbox | Bearings
4ffa91f2-4f8a-567d-a06e-342426d0c1b6 | textbox | PT ducts
82672e2a-321f-599f-ae59-6eabfec010aa | textbox | Stress Bars
5ca07be5-0233-5fa7-87c1-747a8bb91576 | tickbox | All Lifting Inserts are installed in accordance with Drawings and Tolerances
b3d72cb1-7df3-53dd-bb0e-8c2a6d017896 | dropdown | Lifting System | Lifting Loops, Lifting Anchors, Edge Lifters, VLGB Load Ring, VSL Bars (Stress Bars / Cors Nuts / Lock Nuts / Bearing Plate / Washer) Others (Specify)
0068bc02-3ef1-5cea-a46a-3bf2888de499 | textbox | Others (Specify)
a0331e37-992d-581b-9e95-559a8b7b86a9 | tickbox | Additional reinforcement around Lifters (If Required)
8c123e31-399b-56ac-afe4-3f30c934eed6 | tickbox | All Couplers are installed in accordance with Drawings
d1925633-c1b3-5495-be1a-b8d6948e92f7 | textbox | Couplers Type and Quantity
91df6178-6925-5dec-996f-f9567a58e3fa | tickbox | Other Casting Items are installed in accordance with Drawings
67d23308-442b-5dcc-8eb1-a08247aa9f14 | textbox | Type and Quantity
af1fb13b-9d09-414f-b2af-4b07477e2c40 | checkpoint | Earthing and Bonding is installed in accordance with Drawings
c4388b32-982c-51e7-bd4b-6c7e815d5734 | tickbox | Earthing Terminals Specify Type and Quantity
d66b5a91-cb7b-54f8-a09e-7b26c2fee27d | tickbox | Flexi cables
fb271d30-31bd-5306-a84d-b13e5f803b56 | tickbox | 100mm long 6mm fillet welds between bars/ 55mm long butt welds (not permitted within 75mm of a bend)
ad9e5151-48ad-5846-b750-e4f16b9f9da7 | tickbox | <20 mOhm across cage Length
b0c82d2f-67dd-5c94-b7c6-67276010a12d | tickbox | Checklist Completed (attach results)
0b293ad8-7653-4072-b3a3-e9f5840c0858 | signoff | Client Hold / Withness Point (If Required)
3ef854cc-bf36-4e46-bb00-875e76117fa8 | checkpoint | Post-Tensioning Equipment is installed in accordance with Drawings and Tolerances
4a8da3fc-81ab-5327-a5c4-bd01e89ecef9 | note | Verify:
123c4cf3-814c-5ac7-9fef-d40928c24f6b | textbox | Tendon Types
70b6a9d0-2585-55a2-be86-83a3519f2a2c | tickbox | Profile
cab4a874-16d2-5ef1-81bb-c4ff4afc269f | tickbox | Firmly secured to rebar
88ee8892-bd08-503a-a057-d77d56e90036 | tickbox | Grout tubes, Breathing Tubes and Grout Vents secure / sealed
a3477fb2-1654-5256-a861-2fe70ac004bb | textbox | Anchors installed / secured
bd40fb7a-c32f-511f-bbc5-65e1629a3c86 | tickbox | Temporary blockouts in Tendons
e48eec06-2579-40a1-986e-80bd44902abd | signoff | Client Hold / Withness Point
37d0a13f-928b-4276-b1c0-f17baeebca91 | checkpoint | Prestressing Strands
d511bdb5-9991-5c9b-817e-f8dd70f82b9a | note | Verify
c8b8557c-00a3-5813-80c5-1c28fbd1e3d1 | textbox | No of strands
70c34e83-a8cb-5e84-9ad6-f8b4d3e8cd6e | textbox | Debonded strands encased to correct length
4b396c84-939e-596b-9a76-47b453a2e4d1 | textbox | Enter Coil Number Used for this Cast
660f76db-2f15-5e8c-8b5f-b75d56ed1ed7 | tickbox | Sag Load all Strand
3a228dc1-68fc-5294-b72b-2f52f12494c9 | tickbox | Full Load: Multi-Stress as per Pre-stressing Procedures and Verify lock off with spacer plates
fdd712d1-6244-5039-8c4b-2630d31a8510 | tickbox | Full Load: Singel-Stress as per Pre-stressing Procedures and Verify lock off with spacer plates
a56f60e5-b092-4431-9a18-1885d48b55d8 | signoff | Prepare Stressing Records and Submit to Client for Review (HOLD POINT FOR CLIENT TO SIGN OFF)
555529a9-cbeb-46d9-85f4-b15cbe78cbf3 | checkpoint | Pre-lifting cage inspection (Client present)
2ddd9b6d-5b75-470c-be52-2954597ae0d2 | checkpoint | Installation of tubs
5426041a-f9ca-57b7-9298-cf3204d368c3 | tickbox | Tubs are tightened and positioned correctly
3b793e3c-afa5-544b-ace8-91fc567b554d | tickbox | All Sliding arms are locked in position
47ac13ed-6b13-57e2-af1b-a018a9a88f72 | tickbox | All accrow props are locked in position
d5756507-d4f2-514c-8bfa-e74f8341c1ec | tickbox | Dimensions of Tub and Webb are correct
7b31496a-0aa4-5429-ad34-9462b0b28df6 | tickbox | All feet for tubs resting on mould & bolted down
1a103c27-9baa-54c0-bd8a-89fee9922de4 | tickbox | Tubs have release agent
0b38d9c4-4fd1-42ac-8ca7-56b6ccb6fb92 | checkpoint | Water Cooling Pipes
28227867-35d8-5cb0-ad16-f69b4f96d81a | note | Verify (if used):
bd566169-8122-5f2e-9a47-1ba74440263c | tickbox | Number, location and installation of water cooling pipes as per approved WMS
60301485-1833-423a-a79b-211656979e41 | checkpoint | All Temperature Loggers are installed as per Approved WMS
6c2e861f-a6e1-5805-a378-b61274b7b9fc | tickbox | Ensure All temperature Loggers are Working (Check Maturix)
394bccf1-b6c3-5646-9fc4-6b33bd40ccde | tickbox | Number, location and installation of loggers matches WMS
2c2ea927-36ac-52ba-8af5-3801ea04b21b | tickbox | Every 25m
72fb952c-00cd-56ed-be29-fc5ad150cd7a | tickbox | 1 x Core (If Required)
8a0889bf-2b44-5b4a-9331-25581f80db75 | tickbox | 1 x Within Cover Zone
8058adf5-d427-5544-9351-80f77849f61e | tickbox | 1 x Within Tent/Tarp Enclosure (Outside concrete)
acbb3a12-df03-5cde-bebc-3ad503eb1c42 | tickbox | 1 x Outside Tent/Tarp Enclosure (Ambient Temperature)
ec5f579a-18b0-5ca0-be3b-7ea91b4eba63 | textbox | Specify Extra Loggers If Required
d2f0ccb0-bcca-4a08-bb8d-0780115f29c7 | checkpoint | QA Engineer Check Completed by
2725f722-f1b3-48ca-b1b1-4811f05feb9e | checkpoint | Pre-Pour Mould inspection (Client present)
9140d14d-1ebd-460d-a2cb-e73af706b0d9 | signoff | Client Hold / Withness Point
67e1f4ea-9a09-4909-b1e9-65cdbda8d4e3 | section | SUPERVISOR / SUBCONTRACTOR CHECK COMPLETED OF MOULD & CAGE FOR CONCRETE PLACEMENT
57e74153-1ba7-4070-8e1f-30a208a70c29 | checkpoint | Supervisor Release to Engineering Team
2458dc2f-5244-54b6-a091-3df03148bba3 | tickbox | Verify all concrete placement plant / equipment available
cc8d6641-7ded-51dd-8af8-584be2cadd62 | tickbox | Concrete Supplier of pour Notified
5536b3c0-6804-5d7e-b670-07ed5ff4cdc3 | tickbox | NATA Testing Laboratory of pour Notified
47383fc6-fc09-446c-a7b8-b90257afff22 | signoff | Supervisor Hold / Withness Point
28ce6b4f-0bb3-448b-a87a-08ea10aceb50 | section | CASTING DETAILS
14603eb8-d885-42ab-b27e-2c888153977f | checkpoint | Pour Detail
b8cae436-8596-59ad-8a3d-ca4817d9dca4 | date | Cast Date
1f5384ba-ae49-584a-bdcd-586d3989aa50 | textbox | Concrete Delivery Docket (list All And Attach Dockets)
5f383b8b-03ee-5b68-b7b9-a5299938f7b9 | textbox | Total Concrete Volume (m3)
60b5a2b4-a546-575f-a532-3b411e05543b | textbox | Specify Mix Design Verified/Used
bfe989df-839b-5dc7-bc41-c7cc46940555 | textbox | Ambient Temperature within Limits (max 38°C)
c1f0718c-f108-5bf6-9bd4-3caec6b700cf | textbox | Concrete Temperature within Limits (max 32°C)
b6230f87-7fde-550c-9595-5d421424f007 | tickbox | Slump within Allowable Tolerance (First truck and every 20m3)
806c4ab1-43de-5d73-ba53-90a8144e5f06 | textbox | Slump (list all)
833a35a2-c2f7-49bf-93d8-802c3b9459e5 | checkpoint | Truck Tested for strength
e109839c-938c-54fe-9eab-50cb8b8fb6d6 | tickbox | If volume <=20m3, 2 sets min required
d0a7531f-4ab4-5d62-9e70-18057b439b44 | tickbox | If volume >20m3 & <= 40m3, 2 sets min required (every 20m3 tested)
49c43334-fdc6-5b14-b82e-97c7c090f89b | tickbox | If volume >40m3, sample every 20m3
aafe37fe-c097-5ce1-8579-a48f016e353f | tickbox | 1 * 7 Days and 3 * 28 Days per test (Total 4 Per Test)
65080bce-f204-5e84-a502-df0172c5a4f5 | tickbox | Cast 2-4 Cylinders for Destressing / Stripping / Lifting / Curing (PMC Internal)
401161a7-deee-52bb-80ee-0922ae52fcfd | textbox | Test Report Reference Number (list all)
356f5f95-928a-4876-8902-7c5f3e11e434 | checkpoint | Concreting
db717803-4179-5036-b5cc-70de97135bb2 | tickbox | Vibration adedquate
45b530f3-bc8a-5fd6-95e2-e8488af82fe0 | tickbox | Time Lag Between Trucks is not exceeded
855b7cfa-e076-5ed6-8398-d5467d9f8652 | tickbox | Concrete Placed within allowable time from Batching Plant
2ac9e16f-5da8-559b-8aca-0bce84ad0982 | tickbox | No Free Fall During Pour
792d6004-aab8-5178-8c5f-20c1091d2786 | tickbox | Required Finish Applied as per Drawings
c83c3955-6e77-42f1-afb7-6259deb54ddb | checkpoint | Curing
fd6af66f-db96-596d-908a-d366958eb11a | tickbox | Concrete Covered Overnight and Tent sealed
0d34e3e2-d59c-5716-9aab-79bfaa7b44fd | tickbox | Cylinders Stored next to Bed and covered as per AS1012
4d188ee6-48f0-5c5a-8a62-940db65d2785 | tickbox | Verify (if used) Temperature loggers are connected and recording and set the temperature alarm to 65°C.
1a66798b-8576-5a41-bb02-06b50c7d813d | tickbox | Verify (if used) Pipes connected, pump working, no leaks in mould
0945bdc8-0336-50c0-be52-3142a8bee080 | tickbox | Verify (if used) Steam Temperature Monitors installed and connected
5c71b37d-1d7b-4ed4-a25a-7a5500006fff | section | STRIPPING CHECKLIST
685e4b14-935a-4c38-b0fa-c3c8c7c51c34 | checkpoint | Date Stripped
07fb3ab0-3d5a-564d-b728-bb91806685ec | date | Date Stripped
1ddeb403-46cb-4efa-9cd5-445e1abd2365 | checkpoint | Minimum Required Strength for Stripping, Destressing, Lifting, and Curing Achieved
9333de2c-f623-5335-81d1-6c9fddf5bf22 | dropdown | Strength Determined by | Crushing Cylinders, Maturity Report
de20fb02-b2bf-5f50-9643-752abf99b763 | textbox | Specify Min Stripping Strength and Record Strength MPa (Mpa: Reading / 7.851)
79c09c47-031b-5673-b28e-13527fe4396f | textbox | Specify Min Destressing Strength and Record Strength MPa (Mpa: Reading / 7.851)
012e076c-52f2-5baa-893c-57dc423c59fd | textbox | Specify Min Lifting Strength and Record Strength MPa (Mpa: Reading / 7.851)
a246371a-68f1-52bf-a51b-372545193ee0 | textbox | Specify Min Curing Strength and Record Strength MPa (Mpa: Reading / 7.851)
34a46fe5-8818-5848-acdf-89bfa32a5c49 | textbox | Specify Strength by Maturity if available
ef413462-02e0-5dc5-ad1f-738fdc36795e | tickbox | Mould and Steam Cured until the curing strength achieved
ab33fdad-d4b2-5a94-8d2b-2bd7679c97bc | tickbox | Curing Strength: 70% of fc (Characteristic design strength)
08eb7d49-c0f8-4e4b-b319-eb92756a2090 | signoff | Client Hold / Withness Point
d7f2ece2-3553-4ed2-965d-8ae6da45c8dd | checkpoint | Lifted and Handled as per Drawings
5d436d90-815a-4962-9ccb-a294d5baa710 | checkpoint | Product Clearly Labelled
0b8dee5b-1277-58b2-ab30-e3dcf8b75ec7 | tickbox | Product ID, Weight, Cast Date, Job Number
9dcb8d55-a661-4bca-a0d8-a5bf663d8e8c | checkpoint | Storage as per Approved Temporary Works Drawings
a7ca56d0-36e9-54f3-b16d-035e440a980a | tickbox | Verify supports complies with approved storage drawings and Orientation and Location matches with delivery Orientation and Schedule
dd7ba9a3-970f-4d06-a0f3-4dbb56ad8fbc | checkpoint | Secondary Curing as per Approved Methodology
0787e3e1-4432-5b5e-8f53-cfbe769b30f1 | tickbox | Temperature 5 degrees past its peak
f9ade2b5-a1da-5f3f-9378-5607c04e50a6 | tickbox | Differential between Core and Ambient As Per Spec i.e., within 30 degrees
5b09f76e-dfee-5e5d-aec5-d86b1ff7a0a2 | tickbox | Differential between Core and Cover As Per Spec i.e., within 25 degrees
08ca23ac-f1e0-49ae-bbed-65e0de59fd26 | checkpoint | Product Dimensions Achieved and are within Specified Tolerance
c03a112e-242d-5a18-b513-d1b2c890cda6 | tickbox | Length
f2a6b042-02ae-5d39-b774-9b6991d4db3e | tickbox | Width
cbe1e5e6-ef46-5435-ab3f-c5d2ec244b71 | tickbox | Height
eb28d0ce-6016-5f23-a69c-2b2c447dcb36 | tickbox | Straightness
1725355b-acad-572c-83b2-f00518779179 | tickbox | Cross-section
bc33de54-75d4-4648-8692-8662c5476f51 | checkpoint | Specified Finish Achieved
72b412d9-f32f-44d0-b38b-91e56e47972f | checkpoint | Cast-in Items are all in Place and within Specified Tolerance
37d1df15-071d-5cd7-b81c-ad357c2f82f5 | tickbox | Ferrules
6a64b94f-6a6b-5328-8955-57cd60869a39 | tickbox | Couplers
c42e3db1-3448-598a-afe3-26eb016afef4 | tickbox | Stainless Items
48822101-fd73-5ffc-9378-33fb819336e6 | tickbox | Lifters
9f13321c-33dc-5b4c-94ab-835a3d20b72a | tickbox | Blockouts
028dc839-1da6-5c4a-820e-cce29f0411af | tickbox | Earthing and Bonding
4c33cbf4-0bd7-5fe2-b552-13b47760f448 | tickbox | Post-Tensioning Equipment
1c91f69a-c5cc-49fd-a86b-5e158683177a | checkpoint | Post-Pour Works Completed (As Required)
a57e1c3d-c47c-5ca4-ac0c-b61a82827265 | tickbox | Strands have been cut flush and epoxied.
f2b1cfa2-fd90-5275-ab7d-7dd625c3424a | tickbox | Strands are properly bulbed.
63ae0adf-eb83-5232-8c53-f4dfc945ebaf | tickbox | Nailplates, recesses, and other obstructions have been removed.
05f54b4d-1130-5d40-9111-3cfaa0aa9879 | tickbox | Couplers and ferrules are cleaned and capped.
84035b4c-f598-53f8-b663-13a247248df7 | tickbox | Earthing and bonding terminals are cleaned, with bolts securely screwed.
74d41e6a-f0e9-5a22-8819-7d503119f75b | tickbox | Chamfers are clean, neat, and present on all required edges.
afd65c28-a4b0-5918-b4bd-820553e26711 | tickbox | Cooling pipes are drained of water and filled with grout as per the Work Method Statement (WMS).
a465e7c8-bdb1-5375-bf85-47159625a5a4 | tickbox | All drain holes, service ducts, and blockouts are cleaned and cut as required.
7b555a36-daa2-5c1c-85ce-d68575577593 | tickbox | Temperature logging wires are cut flush with the surface.
4ee848cd-8cb1-5ed2-bbc1-5b5042f9e04d | tickbox | Starter bars are cleaned and bent as specified.
018a0610-821f-5631-adf9-f0b9022ef890 | tickbox | Surfaces requiring roughening are greencut according to the drawings.
1df82490-6752-5a91-bda5-660a6b511716 | tickbox | The top concrete surface is free of loose concrete.
40eec08a-9c43-575a-8df1-501546e772b3 | tickbox | Areas requiring U2/U3 finish do not have a roughened surface.
5e9757b5-6c55-5ba9-947b-b5ba915ea200 | tickbox | Bug holes and air bubbles have been identified, with sizes and distribution compared to AS Standards.
9ecb1e8f-8aec-5d3b-87ad-ffbc535c4569 | tickbox | All blemishes (dry concrete) have been removed and patched.
218f471f-974d-5e42-9218-04b459f1f5fd | tickbox | Any discoloration on external/visible surfaces has been removed by sanding.
2bc7f389-ba2b-56a4-9b21-e1afa19ab3e0 | tickbox | All generic post-pour works are completed as required.
bfe90614-e869-4ce8-baa6-33ffb321a902 | checkpoint | Temperature Logging Completed and Conforming. Attach Results
a0eb8a3d-ecec-4705-a2d4-096b17a29954 | checkpoint | Survey Hog of Beams
b0827207-6cf3-584b-b183-37edc415c6ab | textbox | First Reading (mm) (Once Stripped)
d3dc6789-c26d-57ce-868b-ecaa4a01525a | date | First Reading date
8fb1843f-87b9-5559-aa26-e8383fc9f463 | textbox | Second Reading (mm) (After casting stage 2 And / Or atleast 7days after stage 1 casting) (if required)
df5c980e-fb62-5e4d-a1aa-e997aed27fb8 | date | Second Reading date
ed6cf66d-7deb-5a96-99f7-765671236bc1 | textbox | Third Reading (mm) (At 28 days after stage 1 casting)(if required)
b3306e61-f717-5755-8900-a5597c5cacfb | date | Third Reading date
957e4f47-1335-5d98-8bba-322723d554af | textbox | Final Reading (mm) (7 days prior to scheduled delivery)
1daa3f80-ae1e-51d9-aaae-79951f522d91 | date | Final Reading date
ba80ef08-5c1f-4a04-aa8f-a049df1fa8ef | section | ANY DEFECT IDENTIFIED
81c0b640-4e1a-40d1-858e-fde7e77b61db | checkpoint | Punchlisting Completed for all Units / Attached
2172f117-10ab-5072-a74f-7aa40fc48887 | textbox | Precast IDs (More Than One Unit)
ea14f02b-8657-4470-980f-273b72fa435b | checkpoint | Crack Map Completed (If Applicable) / Attached
c2ba4d38-ac16-5133-b801-78f2dea01821 | textbox | Precast IDs (More Than One Unit)
6fe07d2b-f651-484c-ac73-110a52821c38 | checkpoint | NCR Approved by Client and Repairs Completed (If Applicable)
b5c9f7c4-97e0-52de-8b9e-f332cddfbabf | textbox | Precast IDs (More Than One Unit)
e571e159-b4a7-4a97-a7a8-6067597ff8cd | checkpoint | Client Inspected Precast and Accepted Visual Condition
8f0ced2d-1688-5bbb-8c74-4b3e8b9f7431 | textbox | Specify Precast ID (separating each with a comma)
5c6fd29c-c477-4d47-9c18-5b3e23d312c0 | signoff | Client Hold / Withness Point
e6ee8aae-4d82-4324-b419-177a93039f4a | checkpoint | Precasts are free of Defects and QC Stamp Placed
b6cc5b21-f884-5b9b-aedd-e496b911727d | textbox | Precast IDs (More Than One Unit)
313518fd-5b87-4605-b4a2-155a60592c2b | section | AS-BUILT DRAWINGS
bb61108b-3ec3-42f1-abbe-164320e1f027 | checkpoint | As-Built Drawings Completed, Stamped and Attached
642a71ca-e473-4acc-bd73-074afd8444e3 | section | CONCRETE STRENGTH TEST REPORT
cb578869-19e1-469b-b75f-9102880f962b | checkpoint | Concrete Strength Test Report Received
9145f656-ab47-585d-9a92-f9344cf6548e | textbox | Concrete Test Report Number
ab5e8bf6-190d-5d77-939c-77250b02bfcd | textbox | 7 Day Strength (List all) (separating each with a comma)
55369a9a-faa2-5cd3-86c2-87173ef70193 | textbox | 28 Day Strength (List all) (separating each with a comma)
ceffccf0-6950-40e4-8803-3906f3807107 | section | TRANSPORTATION REQUIREMENTS
3084df4f-d8d4-4fc5-a00b-c628bc07ef93 | checkpoint | Transport Strength / Age
21e9bf21-9449-55aa-86fa-15ea83206611 | tickbox | Verify unit(s) have achieved 28 day concrete strength
5030083c-d1c3-58d9-9372-608b1bcba1b9 | tickbox | Verify unit(s) is at least 7 days old
8f37bcfb-4357-44c5-ba98-3c4c99fe45c8 | signoff | If 28-day strength is not achieved by the delivery time, obtain client approval for a minimum of 95% of the 28-day strength before delivery.
786cb5fc-bc32-4715-a2a3-c349b4166740 | checkpoint | Certificate of Conformance
89e75904-08f9-4c26-87c1-75d82a07737d | checkpoint | Inspection Release Certificate
4b11af3d-e3c6-49de-9c2e-c87ff8845d91 | checkpoint | Delivery Notes
a5d1ffc2-0b70-4df0-a9a1-5e575f4196c5 | checkpoint | Delivery Docket
90fe47dd-f1e0-57df-b22d-7985623d647d | tickbox | Lashing, chains, frames, bolts, supports, and orientation of precast elements as per approved drawings.
66314b2a-b882-5db8-b952-3b9eb8f6129e | tickbox | Attach Final photos prior to delivery (on Truck)
f3ce2e3f-8068-40a0-8638-931c2652afce | section | FINAL ACCEPTANCE
68907f6e-7e4d-4f77-a3de-c412af2870b3 | checkpoint | Completed by
17997d9b-76ad-47e9-af57-bccd801b9714 | checkpoint | Reviewed by
48e802e1-c468-4bc1-b2a7-bbbd18f6057f | checkpoint | Client Representative (if applicable)
6cfe3816-b28f-4b8f-b627-55041d953833 | signoff | Client Hold / Withness Point
ff718cdd-ae63-5e10-a1ff-017bc4b24c44 | checklist | Precast Piers |  | Precast Piers
f08fa224-1de2-518e-aa1c-5f58f28bd147 | section | Pre-Pour Checklist
bf2183c3-5dea-51a2-b588-7dc474f28b0e | checkpoint | Pre-Pour Checklist completed
4e7afe8a-b8d9-5737-beb2-8f0c651cc3db | textbox | Cast Number
6382421e-9011-5979-a5cf-caa01c812d0b | textbox | Bridge Name
1b405b9f-fce4-5f29-9ad7-cf8b7830b312 | textbox | Precast Pier 1
803beb40-e5e5-5a44-bf24-76a5a1c5a84f | textbox | Precast Pier 2
fb3f9880-435f-58dc-ba52-1d45aa4273ff | textbox | Precast Pier 3
b5911e03-de0e-5993-a1e9-93e08c119355 | textbox | Mould Beam 1
a4f9d4ba-07f4-5b06-bca4-80ad1be63b42 | textbox | Mould Beam 2
6a1dce4b-d24c-541b-97b7-7306d8f795a6 | textbox | Mould Beam 3
72f04931-bd50-5612-b377-f8c5f7a4bbb9 | checkpoint | Shop Drawings approved for Works
ab6ca2fa-a309-5329-8358-c167957d493d | checkpoint | Mould Dimensions are within Shop Drawings Tolerance
4a541877-249f-545d-bc97-6617f72a285b | note | Length
997dfb26-56c3-59ac-bb51-ddf4f1c6b76c | note | Width
d2ed374d-ed18-5380-b9ea-baf4de7a17d0 | note | Height
b89e4592-7c2a-5ccb-b943-59e89ff86ee1 | note | Straightness
abf4fef2-0533-577c-838c-14a84beb59a0 | note | Cross-section
d3d6f84f-ef56-5e96-94e2-afc9fbaa7275 | checkpoint | Mould Surface Checked
7c8696d3-1934-566d-bed6-c8e865fa0df7 | note | Cleaned
51dd88d9-c039-5d77-af83-fd32c458ca8e | note | Sealed
0f80e1ae-97a8-5e62-b15c-65be62b256df | note | Rubbers in Place
91d250fa-0054-5fce-84be-f611ddba06ba | note | Oiled
068cb4c4-bbc1-5e41-a1bf-1edcf1214016 | note | Chamfers in Place
92d17aa5-00ed-5c40-8f19-33f23c57d515 | checkpoint | Reinforcement in Accordance with Drawings
c64a314c-7abf-54af-8075-0933650c8688 | note | Reinforcement size
4c6c8d01-7687-5eaa-8cf5-773557da8666 | note | Lap Length
7846081a-7480-5750-9e9c-3fbc6005a7b8 | note | Splicing
93650da2-93fd-5101-bc8a-21fc7d2d7bf5 | note | Bar Chairs
7a6650dd-f242-52b2-b3ea-a830935b1fdd | checkpoint | Earthing and Bonding
aafa5a88-24c1-54e2-9789-9d78c0e4c8b1 | note | Weld Locations
a9dc0e15-fc25-5f74-af3a-340bb7c4acf2 | note | Rebar Ties
a96b0f67-c42e-5bfb-862f-145daaab421b | note | Continuity. E&B requirements ≤ 20 mΩ per continuous reinforcing section
f0138e2d-b5be-5588-b158-e78acfe85484 | checkpoint | Cover maintained and within tolerance
b0e3a157-c3a4-5224-8cf4-be7a450178dd | checkpoint | All Cast-in Items are installed in accordance with Drawings
1686e113-f8aa-5180-980b-7889804e3fc3 | note | Cast-in Items
3a3203fa-dac2-55b5-b13d-2e768acad43c | note | Fittings
e8a3a7a6-1145-558f-b368-2d6d053245e6 | note | Cooling pipes
ea81cea0-825c-5685-af89-cfb43cfc41ba | note | Lifters Position and Type
1b4db2c8-9d4f-5d84-9daa-c79f1aeddef7 | checkpoint | All Temperature Loggers are installed as per Approved WMS
1e08fcf4-f01f-5281-8fd2-a8f0e3753065 | note | Every 25m
00584b31-b35b-5a86-a5c5-dcde4a1a6961 | note | 1 x Core
a9b9cb9b-ff4b-57a1-a886-7c653cc08f62 | note | 1 x Within Cover Zone
a91d09e6-62d0-5753-9e47-7a7fa831ae1b | note | 1 x Within Tent/Tarp Enclosure (Outside concrete)
266be85a-b264-5821-89b4-d15bbab95090 | note | 1 x Outside Tent/Tarp Enclosure (Ambient Temperature)
fb5ad20f-1f4e-5b63-aa56-86c023529dad | checkpoint | Ensure All temperature Loggers are Working (Check App)
2cd8fd8f-3d52-583c-8630-e75ad3a4112f | checkpoint | QA Engineer Check Completed by
7f7d7a42-0803-51f2-829f-57c51aea3319 | checkpoint | Client Inspector (if present)
cd3f8d7b-3f3d-5688-8e51-f8b3b938b035 | signoff | (HOLD POINT FOR CLIENT TO SIGN OFF)
789084cb-7fc5-5794-8638-4848859d2b58 | section | Casting Checklist
3fcbe0b6-efc2-57cf-bdec-e437c3479934 | checkpoint | Casting Information
d5bc242e-198a-5fe4-89fd-aa2d862704e9 | textbox | Cast Date
28115d49-b84a-56ca-ad9f-64b24d12d36e | checkpoint | Concrete Delivery Dockets
65e7e5bf-5179-5b28-89b1-0b98256daecf | textbox | Concrete Delivery Docket 1
ddb485d9-b658-5895-b8a2-c7ce65ba2b36 | textbox | Concrete Delivery Docket 2
629f4247-61b3-5292-92e7-074a48c0a627 | textbox | Concrete Delivery Docket 3
09a3b841-f0e5-58b1-af50-05de919ebfbc | textbox | Concrete Delivery Docket 4
1f8d1a26-941a-51df-82b4-8e65c1b2c071 | textbox | Concrete Delivery Docket 5
68937190-4236-54c8-8ed6-7072e952a1cb | textbox | Concrete Delivery Docket 6
32e9f5a8-ebef-541f-ac31-01140b4bff1b | textbox | Concrete Delivery Docket 7
691a9416-704e-5968-837f-2d85385773d8 | textbox | Concrete Delivery Docket 8
377de638-7a81-55a5-93ee-6c65110a4f5d | textbox | Concrete Delivery Docket 9
704a746b-6be5-50b9-ac5a-8a5dfa283a41 | checkpoint | Total Concrete Volume
5f884b4f-d4df-535c-a7df-874fbbe13a6f | textbox | Volume (m3)
c46f06a2-f512-54ca-9e47-5b4590e437d4 | checkpoint | Mix Design Verified ( WS654TC04 - S65/14/200)
bbf79f64-bafd-56de-b60c-09b53bfa0b36 | note | Concrete Mix Strength (Mpa)
a4371627-db94-5bbb-8d71-b1816bae2be4 | checkpoint | Ambient Temperature within Limits
00c2756c-e7f7-52b7-8376-ed06d275c47e | note | 5 - 38°C
bed93563-c38c-51c7-91b6-8e768e5ba876 | checkpoint | Concrete Temperature
c81d5fc7-1908-54b3-b531-5fd513c02e60 | note | max 32°C
716d3605-e943-5339-a185-d09ccf8ebce3 | checkpoint | Slump within Allowable Tolerance
d77627c2-1a93-508d-a8f7-66a60991ad9b | textbox | Slump 1
f621aee8-a0db-501a-bd0f-d90736924785 | textbox | Slump 2
b8649bc6-16a1-5fc3-9af1-716c304209b7 | note | 200 ± 40mm
737e55bc-7b31-5f86-a6d6-4b8fe303e86c | checkpoint | Truck Tested for strength
eaf5ea38-9e36-5b8e-9828-e841190d89a5 | textbox | Test Report Reference Number 1
f17b016a-c178-5519-b874-596dee6cc6e9 | textbox | Test Report Reference Number 2
3844376e-24fc-5afb-a6c4-94e9efe892ac | checkpoint | Time Lag Between Trucks (< 20min)
2704b6e9-dbf4-5827-ad5c-b307ec87cb39 | checkpoint | Concrete Placed within 90min from Batching Plant
3908f2fd-1b62-54d9-95b8-ca884c8a108e | checkpoint | No Free Fall During Pour (< 2m)
66e85e9f-0988-51ff-bd77-6972a786f31b | checkpoint | Required Finish Applied as per Drawings
14807022-93ea-5920-ae91-d2dbbfb0454f | checkpoint | Concrete Covered Overnight
01b1e6a4-17fa-5294-acd1-913dc9ad34db | checkpoint | Cylinders Stored next to Bed
d864682e-90c5-53e0-a4e3-b1ab8a731815 | section | Stripping Checklist
5e8be59e-c74e-5b8c-907d-822ceae41037 | checkpoint | Date Stripped
76e496ab-cc01-58cb-b7a8-6fe48d30343f | textbox | Enter Date
67290ce3-a714-5fcd-80e1-fafab39cab6e | checkpoint | Soffit check
c2c476a9-971d-5866-b594-e79473f21315 | checkpoint | Concrete Cylinders Crushed and Submitted to Client
ffe4cd27-3fac-5353-9ac6-adcd7c1af936 | textbox | Stripping Strength
acbdc093-9fc6-5e09-a7a9-322ed791b373 | note | Strength = Reading / 7.851
49e1cea0-f53a-55f6-88e2-a239ee63a3fa | signoff | (HOLD POINT FOR CLIENT TO SIGN OFF)
7fe48a8e-007a-51ad-b586-e696bbae63dc | checkpoint | Lifting Strength Achieved
3c9399df-179b-543e-ac40-9aa01aff10e0 | checkpoint | Product Clearly Labelled
bd9288b9-c7e1-5c29-a7ab-4d7621176a6d | checkpoint | Product Dimensions Achieved and are within Specified Tolerance
598b7281-145b-5cef-928b-da6eee1456b1 | note | Length
a528a2c1-6f71-5737-949b-627ecda0c70d | note | Width
cebe45d3-0319-59b4-8e5f-f91f07439a39 | note | Height
89df516c-6291-5cbe-8928-91cab3f42587 | note | Straightness
edd83b4a-d83d-5071-aa61-3f429d8d56f8 | note | Cross-section
7987d2d5-7d74-5305-bb64-793887f70b48 | checkpoint | Specified Finish Achieved
443e754e-890c-5de3-8260-2e5a910ab541 | checkpoint | Cast-in Items are all in Place and within Specified Tolerance
95009e70-111f-533e-8f19-6dab1c33a033 | note | Cast-in Items
441b4cf2-f5bf-506d-b0bd-79e5d4da46c5 | note | Fittings
f2fff155-ec67-5455-98f4-b4573bab5a49 | note | Lifters Position and Type
67650e13-4700-5cf3-991a-15370fae4f0f | checkpoint | Lifted and Handled as per Drawings
9b26f369-5398-5688-b0bf-a8ec6cead294 | checkpoint | Storage/Stacking as per Approved Plan
aadb9bc6-1041-56df-9b90-51ef1cdaac91 | checkpoint | Curing as per Approved Methodology
0e05ae6b-6054-562f-bfd7-6545d2468273 | checkpoint | Electrical Conductivity verified post Cast
edc16acb-3c65-5a12-8acd-5e564f9217aa | checkpoint | Temperature Logging Completed and Conforming. Attach Results
82714ed1-ad56-54f6-bb8f-c35c2f5fb2cb | section | Any Defect Identified
08b88b51-fc04-54c7-9e12-2ff172b737bb | checkpoint | Punchlisting Completed
a7ca8529-4c46-5ba4-8209-9ec90323b715 | checkpoint | Repairs Required (if applicable)
c47e73e2-f5da-5762-9b1d-d16cae40e3af | checkpoint | Repairs Completed as per approved WMS (if applicable)
0485a51e-9c30-5bb1-a737-796165be473d | checkpoint | Any NCR Required (if applicable)
3c21c9ed-8a83-591a-b46a-0be92087eb7c | checkpoint | NCR Approved by Client and Repairs Completed (if applicable)
6dee7a22-2dbc-5a4e-bf8b-7ed31a3e39dc | section | As-Built Drawings
d2c74ef1-6e3c-5989-8443-f576a5207186 | checkpoint | As-Built Drawings Completed, Stamped and Attached
8b80f22f-30cd-5652-ae3d-f97e2ba75fc3 | section | Concrete Strength Test Report
2c0327a6-df91-52e1-b234-788128f14e1e | checkpoint | Concrete Strength Test Report Received
4c8de007-e0fd-5370-94a1-259aa65ff214 | textbox | Concrete Test Report Number 1
6812011e-8001-5584-b364-e347458b80e7 | textbox | 7 Day Strength (1)
83d550c1-017c-51de-80ef-48626a8fed9d | textbox | 7 Day Strength (2)
f49a74cf-7835-5696-86da-9256a7335bf0 | textbox | 7 Day Strength (3)
7b0b9d48-e6b1-5213-b367-715d105ed1d2 | textbox | 7 Day Strength (4)
09871642-037f-5de5-8fda-0aba8e2c0551 | textbox | 28 Day Strength (5)
c62c9f34-b494-5c15-bf09-d9f741297d64 | textbox | 28 Day Strength (6)
67c3dfad-b4e1-51a8-ba83-51aac88e6b04 | textbox | 28 Day Strength (7)
9727d4c4-a7e8-569d-bcd9-cf99a1d164f7 | textbox | 28 Day Strength (8)
41f8a009-e1df-5fd1-899f-1a137fbcbc92 | textbox | 28 Day Strength (9)
5097f656-7700-50d6-8114-6800f4cf107e | textbox | 28 Day Strength (10)
fb33e640-5364-5534-b04e-92641c7a75dd | section | Final Acceptance (Conforming to all Requirements and is Ready for Transport)
2064c690-894d-5cab-8947-40a9df86e443 | checkpoint | Completed by
87159759-0253-5729-9bcb-b99c5329aeea | checkpoint | Reviewed by
9f0f461c-4bdf-5c10-a62e-b13f283313de | signoff | (INTERNAL HOLD POINT)
bcf6540b-010f-5869-8258-1f3dec323faa | checkpoint | Client Representative
8950e037-f699-55e7-accc-30cbc93b52eb | signoff | (HOLD POINT FOR CLIENT TO SIGN OFF)
7605bf30-c1f9-5482-a376-3b826a959448 | checklist | Preliminary Activities and Materials Approval |  | Preliminary Activities and Materials Approval
c39cc750-2dae-5eca-ac76-904b1e18ab2d | section | Preliminary Activities (Approved by Client)
af3354c0-11d8-509c-8b7e-f565abab0194 | checkpoint | Compliance to AS/NZ ISO 9001:2015
f0711b14-4d8c-5482-9d56-a347b560a95d | checkpoint | HSE Management Plan
5c56c4bf-684f-54e8-a9a9-616e649f150e | checkpoint | Permacast Project Quality Management Plan
a08fce35-3cc7-541a-b85e-3a4ae145cd7b | checkpoint | Inspection & Test Plan
61eca204-30f9-5e04-a5ef-deb81a8a4354 | checkpoint | MDR Index
752c1167-27a5-5a35-8c0e-aceeee8e6800 | checkpoint | Work Method Statement (WMS) - Prestress
0b48a948-f4e4-520c-b926-a99897667ec1 | checkpoint | Work Method Statement (WMS) - Curing
7a5a3207-0c1f-573f-a9c8-42b6879ccd9e | checkpoint | Concrete Repair Methodology
18a683b7-0dcd-56aa-8ef4-a1c42559600c | checkpoint | Shop Drawings
74083d7b-a35b-5008-9433-d14d6c221d04 | checkpoint | All Technical Query Forms (TQs) Reviewed and Approved for Works
5c66b280-0e24-5bf6-a8f9-047d28ee4c5a | section | Concrete
a14cab8a-60b7-59dc-af3c-d9a60d9aba5f | checkpoint | S65 Concrete Mix Design Approved by Client
33b6cdb2-b160-5f7e-9ac9-6d02d7f9d343 | note | Supplier : Holcim
8223150c-f306-5fa2-b141-18eb98bd804e | note | Mix Code: WS654TC04 (S65/14/200)
5bd07ac6-dc5e-5c3b-9565-d52a7f942343 | note | Slump : 200 ± 40
fcf20326-3e5c-5304-83b6-e1e055f5168d | section | Steel Reinforcement
46d8448d-f392-5a6a-a603-26176c7d2521 | checkpoint | Inspection of Delivery to Confirm Compliance with Order and Drawings
d4df882a-1bbc-55f1-a23b-dd8167daf9b5 | checkpoint | Cut Bar Length Tolerance +0mm -10mm, Bends in Plane, Correct Cog Lengths etc.
8a7d129a-ad41-59ca-9e57-de47223b0ec4 | section | Prestressing Tendons
8ff4487c-8551-4de6-8066-04562c0223d9 | checkpoint | Inspection of Delivery to Confirm Compliance with Order and Drawings
199f0aca-27b8-5aa5-820c-8124d88e5269 | checkpoint | Ensure that all Coil Numbers are recorded
9c7ee5d6-0ee5-5f86-8a6f-e02fcd835262 | checkpoint | Stressing Calculations Submitted and Approved by Client for Works
e2316708-226c-546e-87f1-c7a585de0093 | checkpoint | Stressing Jack Calibration Certificates
2ee852bc-adf3-5a76-94f5-30dd3f09b292 | section | Lifting Anchors
8324c69c-ff0d-5cd5-8035-88869b535a39 | checkpoint | Lifting Design Approved by Client
a1a28c54-a471-5f49-9868-84a6962e56cc | checkpoint | Lifting Devices Approved by Client
54a80bb7-7c99-5bd5-8734-52bc0c6c04e5 | checkpoint | Inspection of Delivery for Completeness and Quality
8bf8d05d-0455-59dd-be4f-0e6604fe6194 | section | Cast-in Items and Ferrules
57b8025e-33d7-5f39-bf03-3ce49887f05c | checkpoint | All Cast in Materials Approved
16b238a4-f7ed-48d3-9a33-9af2be76b4b7 | checkpoint | Inspection of Delivery for Completeness and Quality

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
1897eaa8-9b45-4683-869b-ac604269df48/1 | checklist | Austral Bump Stops |  | Austral Bump Stops
5bbc3e62-b282-4f0b-911b-25ad6e403f69 | section | Pre-Pour Checklist
4358938e-61ef-48db-ba3d-7a50544c256c | checkpoint | Structure
9dd0dda3-ff3a-565a-bc4c-5a592700f239 | textbox | Enter Name
cbbd6400-749e-4b71-bb43-2394cce5de64 | checkpoint | Shop Drawings approved for Works
c68cadc5-7b7a-514f-b0e2-7aaab27bcf49 | textbox | Cast Number
68792eb5-dcb8-5647-b7e5-4c59f3977375 | textbox | Approval date
69618a00-566b-469f-9498-9c1d2ed03e14 | checkpoint | Mould Dimensions are within Shop Drawings Tolerance
cdbf1afb-df9a-5818-b106-85eb4ff2c1cc | note | Length
9e1efb53-a575-58ee-b7cc-cf063839f553 | note | Width
07e178d6-6640-511e-adab-842dcdc4551e | note | Height
443a697b-0d1c-5806-9ffa-84af80338b31 | note | Straightness
59b02657-e5d9-5aa0-804d-734a51ebfbc3 | note | Cross-section
3fee8999-4412-4390-8167-9a8999471dd7 | checkpoint | Mould Surface Checked
f888c592-ce72-5632-9379-de8db6be4744 | note | Cleaned
9a758e11-0e33-5227-b5dd-cd7d1d2f716a | note | Sealed
b9a1fc82-44e0-56ea-b30b-d5a9d39b36cd | note | Oiled - for retaining walls only
91fff3b7-6639-5552-b0f6-7bbd3e3b9222 | note | Chamfers in Place - for retaining walls only
87780297-122e-4e86-ba6d-8ad47795d1ea | checkpoint | Reinforcement in Accordance with Drawings
2cc3bc35-91f9-5831-82d3-0c4aa7a94d9c | note | Reinforcement size
e6cf41cf-a55b-5c51-b85f-f80ada58a0f3 | note | Lap Length
c1f6613d-1ecf-50fc-a99c-5a03a5aefd2b | note | Bar Chairs
7bbf9c71-6d64-5046-aaf1-39098365bb3f | note | Spacings and positioning
de0b7440-c2ba-4158-b989-b619068fcb52 | checkpoint | Detailed welding inspection
fead0e01-e6f5-5d39-9fad-7bb174b72ff9 | note | Welding done in the correct position
7e1b69a1-8cc1-5c03-b2be-90b35d4a657e | note | Distance between weld and reo bend higher than 75mm
ed0786b8-7cec-4737-9385-d9444fe89bc4 | checkpoint | Pipes and openings - Bump Stops only
84b68f74-44a6-59ea-8820-b06558125583 | textbox | 219mm diameter conduit installed in correct position
ba253f17-c5f9-54a7-9a05-c2d637eed018 | textbox | 250mm diameter concrete holes in correct position
190a8cdd-6c22-5189-995a-413c37a762ed | textbox | 44mm diameter holes in correct position
67b510c2-1071-4d01-8547-f78bbf497923 | checkpoint | Detailed inspection of Mould and cage
f7eafdd4-007f-4054-948b-b964e3255d90 | checkpoint | Reinforcement installed in accordance with Drawings
727ddb95-27d7-42fd-b2ee-616e2aaed6de | checkpoint | Cover maintained and within tolerance
01c0afa2-093c-4ec5-bde5-9b78afd6876c | checkpoint | All Lifting Inserts are installed in accordance with Drawings
6f1bc27e-d0b7-5aac-a259-674043486344 | textbox | Lifters
010aaa02-8b97-40aa-9346-b8cd5c652704 | checkpoint | QA Engineer Check Completed by
8013351e-de7f-45b7-a675-82ba5114fa07 | checkpoint | Pre-pour cage/mould inspection (Client Present)
805f1b00-64a5-4418-80d3-563e9e58e868 | section | Supervisor Release
654e5a90-1b0c-4cc3-8fcf-3b36097d67e2 | checkpoint | Supervisor Release to Engineering Team
4d7ab054-e233-4a61-bc1f-311015ebc0df | section | Casting Checklist
777799a2-462f-405a-b767-b2dfbbea1d36 | checkpoint | Casting Information
81fe5018-1367-5e12-8f0a-55fa06b71e90 | textbox | Cast Date
a156a577-734b-486a-acfb-f0d63f4d41c9 | checkpoint | Concrete Delivery Dockets
40d33721-4624-52df-a2cf-5d268fe67e41 | textbox | Concrete Delivery Dockets (list all)
91a5d890-684f-4e06-9af8-7c885d86056e | checkpoint | Total Concrete Volume
dfed2669-f5d5-5129-8b1d-5e92de695122 | textbox | Volume (m3)
d6104c44-340a-44fe-926a-7f22a54e5327 | checkpoint | Mix Design Verified
efcd51ea-cf75-51aa-b4d0-9ae81cd3da49 | textbox | Specify mix used
81f98795-10dd-48cd-8947-0255596561bb | checkpoint | Ambient Temperature within Limits
3c98cacf-5eee-52ec-8d05-b2fea184c938 | note | max 45°C
03f1e579-8931-4ff5-a92e-ea9b75e195b4 | checkpoint | Concrete Temperature
06f1ef00-9998-5173-9013-58de9825ee01 | note | max 35°C
e1934445-cb07-4c22-aa5d-f3058c68733c | checkpoint | Slump within Allowable Tolerance (S50 mix 180+/-40, S65 mix 600+/-50) (Tested 1st truck, 10m3 and 25m3)
0d0628a7-8e9c-53f2-a4cf-5ad87020fbc5 | textbox | Slump (list all)
e2a34489-8588-4949-8c9e-6e1563307f4f | checkpoint | Trucks Tested for strength
3d1a3860-e8e6-52f3-aec4-b9f2035999a1 | textbox | Test Report Reference Number (list all)
9d375d5b-f820-4345-87a5-158f18a6b5ba | checkpoint | Time Lag Between Trucks not exceeded 20 minutes
0832c0f9-3460-4838-81bc-5b5fee2a668a | checkpoint | Travel time less than 45 min
a20c46ff-f423-4a46-9ddc-12fc7f20879a | checkpoint | Concrete Placed within allowable time from Batching Plant, not exceeding 90 minutes
405c9d61-079c-4117-8edf-c0038ffe88c2 | checkpoint | No Free Fall During Pour (not more than 2 metres from ground)
8b4b0614-8b77-44fb-a857-12343b9a4cf3 | checkpoint | Required Finish Applied as per Drawings
dc9fea58-18ce-429d-a674-dcbb575ccfdd | checkpoint | Retarders applied on Green Cut areas as shown in drawings
e5524fae-fc16-4099-a4af-c22b88f9f42a | checkpoint | Concrete Covered Overnight
6ceffd24-2418-4d83-9e1a-5845ca15dbd5 | checkpoint | Cylinders Stored next to Bed
a3756556-0e9b-4c87-8b3e-1068be10e8b8 | section | Stripping Checklist
2ca0462b-8ff5-458f-a8c8-dee5d3baa246 | checkpoint | Structure
39c22176-98a4-57d5-bf8d-ab9da6898a91 | textbox | Enter Name
0fe08fb7-fc7d-4e87-8051-28648d263a95 | checkpoint | Date Stripped
e60e705f-d589-52ee-86e5-ef8c6dc94cbc | textbox | Enter Date
a921f8b4-8953-411d-b45a-2fdaebb67563 | checkpoint | Concrete Cylinders Crushed and Checked for stripping/lifting strength
1334a9e4-b2d0-5e92-83d6-a6fcc00b0ab9 | note | Conversion KN to MPa = Reading / 7.851
71c67487-113f-5fd7-97fd-451aa0fcc13d | note | Stripping strength 35 MPa for Bump Stops and 25MPa for Retaining Walls
767fa409-193b-5430-9bc0-1f7454c8dde7 | textbox | Stripping Strength
487ee720-a475-4b84-925e-9adf8ae54123 | signoff | HOLD POINT FOR CLIENT TO SIGN OFF
d95b923b-5c19-418c-8203-f35a44a4b73c | checkpoint | Lifting Strength Achieved
99d2d753-1059-576e-8f39-788aca0e35d2 | note | Lifting strength required - 35 MPa/25MPa
24d8e10c-3caa-53f1-a6e1-808703bf5d88 | textbox | Specify strength at time of lifting
fd9efe30-58c7-4462-b790-935bdb711bff | checkpoint | Lifted and Handled as per Drawings
c521cb64-2cb0-4f75-967a-564f4cc867c5 | checkpoint | Product Clearly Labelled
947496a3-41bb-4476-80f6-fef1f0caef57 | checkpoint | Storage as per Approved Temporary Works Drawings
e79fe80c-b931-4274-8958-8e4388671dba | checkpoint | Product Dimensions Achieved and are within Specified Tolerance
1172497c-666d-584e-b7a2-cf1a02af1f0d | note | Length
288ecde9-0eec-5f02-986e-b1732ae59381 | note | Width
027ec65c-7742-551d-acf4-1c8cba005747 | note | Height
713cbc60-fddd-550b-8d06-f85fac5ded69 | note | Straightness
81470ab0-b23a-5875-bd3b-36910b03d162 | note | Cross-section
16e98570-6374-4da2-aea0-9f57e28d2776 | checkpoint | Specified Finish Achieved
1c26e6f1-ce7a-4b82-8395-d8046eead094 | checkpoint | Cast-in Items are all in Place and within Specified Tolerance
60ea849a-2e18-58d2-aee4-cafbf2f79b79 | textbox | Lifters
8f38901f-4b5c-4af6-95a7-5ddfb72b7ed6 | checkpoint | Post-Pour Works Completed (As Required)
80950c06-11b4-5f82-a9ec-2b689a19d468 | textbox | Lifters are cleaned
1bd7566a-d56f-5dde-9e5c-b5134f6dc41e | textbox | All Miscellaneous Items are Completed
8186e90a-4a4a-5242-b281-00b8f3145c18 | textbox | Bottom surface clear from tie wire (Attach Pictures)
421ad859-4c96-446e-adea-78ef66540679 | section | Any Defect Identified
b4ed0067-727b-4808-8386-ba4d66b114c1 | checkpoint | Punchlist Completed
f4332887-bcb0-4256-b838-baa7d95f6805 | checkpoint | Repairs Required (if applicable)
a7dbeab4-302b-4e96-bdaa-a781a6e28456 | checkpoint | Repairs Completed as per approved WMS (if applicable)
0e63be85-01aa-478f-bedc-894cb0463c33 | checkpoint | Crack Map Completed (if applicable)
952669f6-b369-460e-84e3-67c044d1f2b4 | checkpoint | Any NCR Required (if applicable)
fa3ab0cd-6dff-494b-8fbf-51cdc31cbb50 | checkpoint | NCR Approved by Client and Repairs Completed (if applicable)
3fffdd15-d42d-414f-b676-f4cd44074e4f | section | As-Built Drawings
f48b2989-532f-4a5a-a5db-d8df9459a067 | checkpoint | As-Built Drawings Completed, Stamped and Attached
63609869-242e-42cd-87cd-95114c627780 | section | Concrete Strength Test Report
ab7d0b11-afb8-49fd-8671-55e7df5fcc66 | checkpoint | Concrete Strength Test Report Received
67cc64ff-ab3b-51d9-9d6f-a5b15630ad6d | textbox | Concrete Test Report
e8600b39-fc7e-5ba4-8b30-3c6533b7c3ee | textbox | 7 Day Strength (List all)
65ae9979-dd90-5347-a77a-c653c093cd7c | textbox | 28 Day Strength (List all)
ee12f895-4168-5b34-9219-b686e60416b1 | textbox | 56 Day Strength (List all)
f3778e2c-b6df-47ba-80ed-ade7913793ee | section | Transportation Requirements
543ea2c8-f7aa-4308-96a9-4e2dd689ac3a | checkpoint | Certificate of Conformance
8eea461d-7471-4be3-a5ef-e633c8283704 | checkpoint | Inspection Release Certificate
dad25ae2-2861-4a96-833c-2d26428291d3 | checkpoint | Punchlist signed copy
c5ce1629-7b0f-4250-b51a-31e66be048f2 | checkpoint | Delivery Notes
21887243-0fc5-4122-97de-188a96e00d01 | checkpoint | Delivery Docket
2826ed4c-ebfd-4689-8d25-5a1fea84e0b4 | section | Final Acceptance
8acf39de-2341-49d0-8392-9250ba1b48fb | checkpoint | Completed by
e7e996c7-9123-40de-bc8a-3df502c8af04 | checkpoint | Reviewed by
18744f5a-4ecc-4a4e-b65a-5353b507875a | checkpoint | Client Representative (if applicable)
7b787f41-d160-4a84-a0c1-4903f49a6b99/1 | checklist | Preliminary Activities and Materials Approval Checklist |  | Preliminary Activities and Materials Approval Checklist
46261ba6-fb27-44d2-923b-4f82ce92b05a | section | Preliminary Activities (Approved by Client)
07beb446-3d0f-4557-82d8-8125e4c1a42c | checkpoint | Compliance to AS/NZ ISO 9001:2015
2274b50f-2604-44bb-8e88-2a24d1ca16d9 | checkpoint | Permacast Project Quality Management Plan
083befa8-089f-45e7-8e68-005efcfd9098 | checkpoint | Inspection & Test Plan
065e43af-5aef-4b3b-a67f-f76d03faec64 | checkpoint | MDR Index
51a0fc2d-0e3f-452b-a6f9-27a1f974c9fd | checkpoint | Shop Drawings
b6c489ad-c20c-4b49-a220-117920eed204 | checkpoint | All Technical Query Forms (TQs) Reviewed and Approved for Works
3ddb7f1f-6b79-4970-b005-85b6715558ea | section | Concrete
c8ce3a29-e52b-4d08-882a-bafb0f1a3c9e | checkpoint | S50 Concrete Mix Design Approved by Client
41285a65-242d-4360-a953-8262a3014803 | checkpoint | S65 Concrete Mix Design Approved by Client
55ff1836-570b-46d1-b43b-4647003d73f6 | section | Steel Reinforcement
4f584bc1-8e60-4d09-b4d8-057064eb4949 | checkpoint | Inspection of Delivery to Confirm Compliance with Order and Drawings
33b27923-0c37-4a19-ab2a-5dc64c99b52e | checkpoint | Cut Bar Length Tolerance +0mm -10mm, Bends in Plane, Correct Cog Lengths etc.
f994acd4-b827-4534-aff3-f415cf07fbf6 | section | Lifting Anchors
83194203-d87b-4719-b3c4-8024baec6ad4 | checkpoint | Lifting Design Approved by Client
c5e75125-765c-4e2a-9ba2-a74a8f20b983 | checkpoint | Lifting Devices Approved by Client
853c21a9-7a5b-4e37-9c3e-b5ce5edfe331 | checkpoint | Inspection of Delivery for Completeness and Quality
1f0f015f-0d83-4ac0-965e-8c41844fb33b | section | Cast-in Items
55d1b49a-249f-448d-8a6e-f333bce736d7 | checkpoint | All Cast in Materials Approved
e5d2e4e7-e03f-4894-b39a-e27710a07970 | checkpoint | Inspection of Delivery for Completeness and Quality