## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | 1cb5c546-65cc-44a2-9004-2f18a4db08c2 |  | checklist | Swelltite - Area: |  |  |  |  | Yes | SYS - Tanking Swelltite (V1) | 082c757f-1a6a-4429-95f2-c7ed9d81468f
checkpoint-status | 8381211b-a454-49f8-a6ba-6ad8cc52ae5e |  | checkpoint | Substrate to manufacturer's specifications (are there any voids that need filling, clean, etc.)
checkpoint-status | 7d206261-fa47-49b6-a420-e041ef0cd454 |  | checkpoint | Check and clean the voltex flap for the Swelltite
checkpoint-status | 334e4000-838c-4ae2-bb68-9dc0deb066a4 |  | checkpoint | Apply glue to the wall ready for the Swelltite
checkpoint-status | 68540012-2c0e-47b7-a3e6-f86cdc340b72 |  | checkpoint | Place water stoppage granules along the wall floor junction
checkpoint-status | 6b9f0a4f-f43c-4e9b-afd3-69b4c8e37d82 |  | checkpoint | Complete penetrations
checkpoint-status | 03b61bdc-aa62-4b8b-aed5-cda3bd87a988 |  | checkpoint | Tape the laps
checkpoint-status | fe87485f-87f2-4ab4-8b09-4abf73cf2897 |  | checkpoint | Place the termination bar
checkpoint-status | 59031ed7-affd-436f-8c61-0d0034b97812 |  | checkpoint | Apply Cetcoat
checkpoint-status | 51466e4e-c5f1-4a05-a6a1-1f529927cd0e |  | checkpoint | Hang protection layer
checkpoint-status | ba76be61-2ae3-4af3-9ef1-d806e3d83472 |  | checkpoint | Photo of highlighted drawing showing locations of work
checklist-flat | 98d16c9c-6a53-4e53-9b6f-da072c8951e9 |  | checklist | Centrguard Installation Checklist |  |  |  |  | Yes | Centrguard Installation Checklist | 1cf75469-8d6c-424e-8a96-c67447d141c0
checkpoint-status | 7c16a95f-c0b9-41c4-9f54-c2ad6da4b2d6 |  | checkpoint | 1. Is the Centeguard Installed in vertical or horizontal construction joint?
boolean | 3b7784e8-a7ec-5dd7-9aa3-2d4e344f7eb3 |  | tickbox | Vertical
boolean | d596e87c-32d7-5e0c-bd15-20fb198a8a89 |  | tickbox | Horizontal
text | 53011458-67c4-5af4-949b-1dc3a1abb5da |  | textbox | 2. What is the wall reference.
button | fb586a90-b06e-5530-866d-a1a8787e86ba |  | button | 3. Is the work area clear and safe to install Centreguard? | Yes,No,NA
button | a93863be-a2a3-5423-beb2-52cc6fd71feb |  | button | 4. Have Link Alliance provided height references for Centreguard | Yes,No,NA
button | a14be1a4-db19-5831-9ed1-875c7f216eb8 |  | button | 5. Centreguard installed as per drawings and specification within construction joint. | Yes,No,NA
button | 1dc67caf-c6d7-5dff-917e-2737778c5c12 |  | button | 6. Centreguard supported with ties, formwork and the like | Yes,No,NA
checklist-flat | 34ab7cb7-d10c-4acc-ba41-8a0128750286 |  | checklist | MC20 / MC30 Tunnel Reference |  |  |  |  | Yes | SYS - MC20 / MC30 Tunnel Reference | 21fde8d1-1b8a-4c7b-91a3-507204cee3a6
checkpoint-no-status | ac0e90cb-1c8d-4f5c-a475-0f6f765470d7 |  | checkpoint | MC20 / MC30 Tunnel Reference
checklist-flat | 47bcab2d-5f5c-4464-b84d-cfd8089957ef |  | checklist | Detail Drawing(s) |  |  |  |  | Yes | SYS - Detail Drawing Checklist | 5edd8cda-8e88-4fd4-b599-d37b3c1e5a6f
checkpoint-status | 05c3bc06-c4f5-4670-83b5-026d9a60f8ba |  | checkpoint | Detail drawing attached
checklist-flat | 745c9619-2aee-494e-9f3e-1789d0af8904 |  | checklist | Mt Eden - MC50 Capping Beam Checklist |  |  |  |  | Yes | Mt Eden - MC50 Capping Beam Checklist | 62013edd-f78b-48cb-b684-2f5f55fb5c23
checkpoint-status | 54734940-a736-4d5a-bd72-09303d7923d8 |  | checkpoint | 1. Photo of Work area
checkpoint-status | 3a63dca4-00fb-4853-ae42-8e9d2b9964bf |  | checkpoint | 2 Is the substrate acceptable for application of Volclay DS
checkpoint-status | 6e3aad99-cab8-48c3-beca-cbdc8e8a209f |  | checkpoint | 2 Is the boxing installaed and acceptable for installation of Volclay DS
checkpoint-status | 171fdd8d-fa2f-491c-9392-9c04e7e59979 |  | checkpoint | 3. Number of piles to be detailed?
checkpoint-status | 49b7086b-a59b-4aa3-b49b-4eb087c28c41 |  | checkpoint | 3. Volclay trimmed and detailed around piles
checkpoint-status | 151f1582-abc1-44de-b356-e8538a8d8520 |  | checkpoint | 4. Volclay Laps left for connection to roof & downturns into skin wall
checkpoint-status | 8a6414e1-c083-45df-a5aa-4ea0d330d4c0 |  | checkpoint | 5.. Bentoseal detailed & dressed around pile
checkpoint-status | fc52089c-dd26-4a92-814a-a521666fc0fd |  | checkpoint | 6. RX101detailed and dressed around pile
checkpoint-status | b8b6a8a4-9cae-4683-9403-1364d774025b |  | checkpoint | 7. RX101 "tail"left for connection to wall detail
checkpoint-status | 12fef046-1bb5-4562-a631-51067e281bb1 |  | checkpoint | 8. Is the boxing and site concrete acceptable for installation of Centreguard
checkpoint-status | 23547906-fdfc-4c5b-aaf3-9e8aa0a81c84 |  | checkpoint | 9. Centreguard installed as per specification
checkpoint-status | 6b147438-fa49-48f9-a4ad-601bdb0f7971 |  | checkpoint | 10. Centreguard laps left for connection onto next stage of capping beam
checklist-flat | c00d7060-0e60-49ef-98ff-93348cafae1c |  | checklist | Tanking Underfloor - Area: |  |  |  |  | Yes | QA - Tanking Underfloor (V1) | 657b1ad9-c347-4469-8e2d-96c2676f5902
checkpoint-status | 920fda5f-7859-4db4-8132-b84e2feddbe1 |  | checkpoint | Substrate to manufacturer's specifications (are there any voids that need filling, clean, etc.)
checkpoint-status | 1087fe27-86ff-4009-94dc-41379a090ce6 |  | checkpoint | Membrane installed to manufacturer's specifications
checkpoint-status | a0e625ed-a2c3-498d-974c-b3b000ffbb59 |  | checkpoint | Reo installed (by others) checked for damage to membrane and repaired (if necessary)
checkpoint-status | ee815d16-cf0c-49c4-8c96-ea9445e342bd |  | checkpoint | Final inspection before concrete
checkpoint-status | c3e32441-2cf7-4049-bd8b-e6757fcd5a6d |  | checkpoint | Waterbar installed to all cold joints
checkpoint-status | 2a22cc15-e2d5-4f34-999e-6a6ec64b4ad1 |  | checkpoint | Photo of highlighted drawing showing locations of work
checklist-flat | 37eab288-0b71-4994-ba9c-b01e78a44545 |  | checklist | Voltex - Area: |  |  |  |  | Yes | QA - Tanking Voltex (V1) | 6e0cef30-95af-46d2-a0cf-af2a717dc006
checkpoint-status | a9b6c130-c614-413a-9f71-4af9dec7bad8 |  | checkpoint | Substrate to manufacturer's specifications (are there any voids that need filling, clean, etc.)
checkpoint-status | 5c231a70-fdb6-48a3-aef4-f5704fab10bf |  | checkpoint | Form work acceptable
checkpoint-status | 506cbb52-11cc-4b93-b913-15c20dd05f83 |  | checkpoint | Voltex installed to wall as per specification
checkpoint-status | 8dd8a8cd-0743-4769-802a-7c959e6195ad |  | checkpoint | Penetration(s) detailed and photo(s) taken of each
checkpoint-status | e1f99b17-da1b-438b-b686-e95c5dd1dcf9 |  | checkpoint | Photo of highlighted drawing showing locations of work
checklist-flat | 28870a68-7168-4dac-9048-55952abb19ae |  | checklist | Mt Eden - Penetration Detailing Checklist |  |  |  |  | Yes | QA - Penetration Detailing Checklist | 77763228-cccf-45b0-a73a-0cb590797494
checkpoint-status | 828258b6-edb2-4aa2-9c65-9142e9cf74c4 |  | checkpoint | 1. Photo of Work Area
checkpoint-status | 587e6b0c-989a-4669-996e-cc0ff0d01b0b |  | checkpoint | 2. Is the penetration clear of material/debris for application of waterproofing
checkpoint-status | 506d1cdf-c158-4d65-bb18-478b110fe9d7 |  | checkpoint | 3. Installation of waterproofing material
checkpoint-status | a2067a65-a51f-4573-be13-cebc175f8fc0 |  | checkpoint | 4. Photo of Completed Works
checklist-flat | b3ad68c8-b1b8-492e-9a37-eedcc8679722 |  | checklist | QA - Slab Wall Remedial |  |  |  |  | Yes | QA - Slab Wall Remedial | 7c440d9a-bb4d-42cc-958d-d52b7f1958dc
checkpoint-status | d9ee65c6-e7d2-4963-94dc-cc95bce5a041 |  | checkpoint | Substrate and boxing acceptable for application of waterproofing materials
boolean | c81fed79-edfd-5c19-8734-401302088aae |  | tickbox | Substrate Handover completed and attached.
checkpoint-status | 00037cdc-3c1c-45d4-93cd-4cda8211a919 |  | checkpoint | Existing Volclay DS removed and acceptable lap left for lapping new membrane onto
checkpoint-status | 290c8cb2-e111-4928-bbf4-538b1d198855 |  | checkpoint | Volclay DS lapped to extended slab wall section
checkpoint-status | 139f8a6d-ca52-4dd6-bce4-c4c30a6b2f72 |  | checkpoint | RX101 Installed to Face of Concrete
checkpoint-status | 83c96a43-cb0d-4c25-a9c8-f9418364bf9e |  | checkpoint | RX101 Installed to the base of 309 Wall
checkpoint-status | 1a9ece90-ad59-4a77-b6ff-8dcc4537e300 |  | checkpoint | Existing Rearguard prepped for application of 90-degree rearguard to extended wall
checkpoint-status | 4ed50c80-1414-491c-83e9-28d4214eb4a2 |  | checkpoint | 90-degree Rearguard welded to existing rearguard
checkpoint-status | cc360d20-995d-4011-b7be-40d62f8719ec |  | checkpoint | No of welded joints
checkpoint-status | 8f0381d2-5781-467b-a49f-12cb9b473592 |  | checkpoint | Rearguard installed to formwork
checkpoint-status | 7d03c78f-106f-414a-bec7-a2261cbeb2b6 |  | checkpoint | Injection Tubes Installed
boolean | c7a1283b-f328-5b42-a447-4e55e68ad92d |  | tickbox | Photo of Injection port & feeder tubes
boolean | 0daebd25-d0a6-5c24-987c-247f7291e818 |  | tickbox | Stand back photo of injector tube system installed
boolean | 571bf612-b316-5c1c-90b2-ba6059559f6f |  | tickbox | Photos of injection line fixed and installed to concrete substrate.
checklist-flat | 797a8a69-06ac-44ae-8668-f3ee6a068dde |  | checklist | Tanking Beam / Capping Beam - Area: |  |  |  |  | Yes | QA - Tanking Beam and Capping Beam (V1) | 84655b25-001b-45e4-9a01-42144442a733
checkpoint-status | 59bc31f3-fd07-43f8-a1b5-395be8c01688 |  | checkpoint | Substrate to manufacturer's specifications (are there any voids that need filling, clean, etc.)
checkpoint-status | 0283cba5-3753-4bd8-a263-2d6783aa2923 |  | checkpoint | Protection core flute installed
checkpoint-status | 33cbc87e-2740-4e5e-a1ac-748edeaf341b |  | checkpoint | Preprufe installation and all laps and lap tapes done as per manufacturers requirements
checkpoint-status | ba737cb0-e860-4c04-9aa2-f671fb77cf53 |  | checkpoint | All water stops installed
checkpoint-status | 5d17c191-48c6-4dd4-b87d-28795d5eb3f1 |  | checkpoint | Check membrane for any damage and do repairs to manufacturers requirements. Take photos.
checkpoint-status | e2d68e3d-ec3c-4b58-933f-1d56024ec629 |  | checkpoint | Preform work and pour final inspection once other trades are finished. Do any required repairs. Take photos.
checkpoint-status | cf9e4bb5-d226-4503-a6a8-d3f54dec5ce5 |  | checkpoint | Photo of highlighted drawing showing locations of work
checklist-flat | 4b7b42fb-37cc-4194-b36f-8cb98e44be0b |  | checklist | Swelltite |  |  |  |  | Yes | SYS - Swelltite | 88bba55c-c9ad-429e-a561-7fcf4b3f89c7
checkpoint-status | a595fab3-a091-476b-a334-e562eece77c0 |  | checkpoint | 1. Substrate to manufacturer's specifications (are there any voids that need filling, clean, etc.)
checkpoint-status | 024fdf2c-ede9-4424-ac1f-35e4f55e8405 |  | checkpoint | 2. Check and clean the Voltex/Swelltite flap for the Swelltite
checkpoint-status | 098f236d-75cf-441f-862c-466e18af5294 |  | checkpoint | 3. Apply glue to the wall ready for the Swelltite
checkpoint-status | 8f012aee-913d-471b-870a-f179a4fb5c39 |  | checkpoint | 4. Are there any penetrations ?
checkpoint-status | 92d8ae53-de2f-4c23-b534-376a2f8649e8 |  | checkpoint | 5. Swelltite laps taped as per specification
checkpoint-status | f109d9be-5b0b-410d-90b3-4ca248388f87 |  | checkpoint | 7. Termination bar installed as per specification
checkpoint-status | c87454e7-132e-4312-8d51-7be1512656a1 |  | checkpoint | 8. Protection Layer Installed
boolean | 5b5d4f43-e36a-5b58-9360-a5c160d0df90 |  | tickbox | Corflute Installed
boolean | 94a4272a-7903-576c-897e-fe9866abffd8 |  | tickbox | Aquadrain 150 Installedon 8
boolean | 6b46e9eb-433b-58fb-8848-6263d1474855 |  | tickbox | 9mm Compressed Sheet Installed
checklist-sectioned | cb62e271-130f-4ce5-bdcb-271e5a6206ff |  | checklist | Tanking - Underfloor Checklist |  |  |  |  | Yes | Tanking - Underfloor Checklist | 8918cfc9-feb2-45c3-98d6-543017f30030
checkpoint-group | b9ce013e-9856-496c-bc77-c52ac8b2dd46 |  | section | Pre-installation QA
checkpoint-status | 821ae35f-7d05-4114-9548-507402a0b751 |  | checkpoint | Latest consented drawings available, checked and referenced
text | 4dd61b41-1e18-406c-822b-88ba53a0d930 |  | textbox | Relevant drawings & revisions for reference:
holdpoint | f66621f8-b11a-4138-a51b-54f3825901c5 |  | signoff | Raise Remedial / Request Review
checkpoint-status | 9a09b567-fb72-4824-8969-586686233b0a |  | checkpoint | Work area/substrate acceptable & approval given to start work
holdpoint | 1f84f184-9ae9-445f-bc34-02d0bafda0aa |  | signoff | Raise Remedial / Request Signoff
checkpoint-group | 0331ab43-1f61-479e-9504-4b68e50bc0f7 |  | section | Installation QA
checkpoint-status | cee35304-f2e5-427f-b517-3d6324bd7900 |  | checkpoint | Product being used input
select | 4560de98-7339-4444-b33c-227cb409044c |  | dropdown | Product name | Other, Preprufe 300, Voltex, Voltex DS, Voltex WSR,Preprufe 160
checkpoint-status | 32621b49-3afe-4a75-910f-a6f832f03f12 |  | checkpoint | Location where being applied input.
text | 20d893f0-1c05-40c7-8e2e-f8e3ff9da96a |  | textbox | Area:
checkpoint-status | def1e5ea-86e7-4b60-bad9-d98a1cb76cf0 |  | checkpoint | Geotextile in place if required
checkpoint-status | 43cb797b-a1ca-44c0-a307-0da7881ec0be |  | checkpoint | All laps to manufacturer's specifications.
checkpoint-status | ebc98c8c-8806-4df8-aa6e-ac4551d01b9b |  | checkpoint | (Voltex DS only) DPC must be removed 100mm minimum for lapping
checkpoint-status | ba68dce5-b199-4771-b84f-a8ae834abbb7 |  | checkpoint | Penetrations are detailed as to manufacturer's specification
checkpoint-status | 31369b2e-14ab-49aa-8e5b-ff1677df640b |  | checkpoint | All water stops installed
checkpoint-status | 5590fb7a-45ea-48b5-b961-be7510f2d6f1 |  | checkpoint | Check membrane for any damage and do repairs to manufacturers requirements. Take photos.
checkpoint-status | 0caff75b-c9e3-48ac-a07b-54dcd222d8e7 |  | checkpoint | Preform work and pour final inspection once other trades are finished. Do any required repairs. Take photos.
checkpoint-group | d7f36ff3-866c-4499-8061-27ecd400b505 |  | section | Completion / Handover
checkpoint-status | b0142291-77a7-47bd-bd72-a908e1d69db4 |  | checkpoint | Product installed correctly, checked & reviewed - as per specification
holdpoint | f9c2d0db-a7b7-4561-8eb0-4321768618aa |  | signoff | Raise Remedial / Request Review
checkpoint-status | f1654044-5476-4064-bedd-6c295451d035 |  | checkpoint | Area left clean & tidy
holdpoint | e7483eaf-d27c-489c-a849-f336d51079c8 |  | signoff | Raise Remedial / Request Review
checklist-flat | f0c5310b-f9c7-4932-bd6d-029391933f00 |  | checklist | MC30 Cut and Cover Set Out Plan |  |  |  |  | Yes | SYS - MC30 Cut and Cover Set Out Plan | a2e7331c-9d1c-458b-b296-436b65aaa410
checkpoint-no-status | a756f42c-8d95-49ac-84c5-a04808fa9e53 |  | checkpoint | MC30 Cut and Cover Set Out Plan
checklist-flat | b72f3061-1475-4f38-a74c-3eea1a8471a1 |  | checklist | Isolation Joint QA |  |  |  |  | Yes | Isolation Joint QA | acb0e478-653a-44f2-b927-e7beabd9ff9b
checkpoint-status | 4fdc372c-5611-4db3-a1e8-61de5016fcc4 |  | checkpoint | Concrete Substrate acceptable for installation/connection of Volclay & AllSheet
boolean | ecc7144c-f9c1-5083-80dd-3dbc35b99d69 |  | tickbox | Existing Rearguard in acceptable condition
boolean | e279ea4b-5bb5-556a-9420-bbd286de7f22 |  | tickbox | Existing Volclay/ AllSheet Lap in acceptable condition for lapping onto
checkpoint-status | bae769a4-14c8-4d06-859d-a465908f9245 |  | checkpoint | Concrete Substrate acceptable for installation of Injection Port
checkpoint-status | 4eadc4d8-bed3-4b52-8fad-b0eb70d34f9c |  | checkpoint | Injection Hose Installed as per specification
checkpoint-status | 0ae474bd-c9e0-42f0-a9a0-b6f28db7b02e |  | checkpoint | Injection Hose/Clear Hoses connected as per specification
checkpoint-status | b66e2f0c-19c4-4f3f-871a-826679a0b954 |  | checkpoint | Injection Hoses/Clear Hoses clear & accessible for install of Injection Ports post pour
checkpoint-status | 195b00a0-79e3-4986-99f6-511b2c6e2e07 |  | checkpoint | Injection Ports Installed as per specification
checklist-flat | a89ea8ab-d63c-4227-b0c8-fb0ce5e545f8 |  | checklist | Document: |  |  |  |  | Yes | Document Attach | c39919bb-10c5-4331-8c93-b5c199198c9a
checkpoint-status | 700d5cd3-d75b-4707-b6f5-7eb22e64b1b2 |  | checkpoint | Document Attached
checklist-flat | 8066889d-02de-4931-a0da-7f1dda648121 |  | checklist | Bluey URG Seal Detail |  |  |  |  | Yes | SYS - Bluey Urg Seal Detail | c5f92b4c-0124-4573-ac60-8dd4cc18e19e
checkpoint-no-status | 0657d69d-af0f-47b7-96ce-5f85fb2d2edc |  | checkpoint | Bluey URG Seal Detail
checklist-flat | 483d3a5c-07f3-4c84-9dc2-c8e57ecea1fa |  | checklist | Waterstop RX - Area: |  |  |  |  | Yes | QA - Tanking Waterstop RX (V1) | dc3a6ace-92c9-4b5a-a912-71c5cf91cf38
checkpoint-status | 86508ef1-95a2-4893-8bce-e91833e80f0c |  | checkpoint | Substrate to manufacturer's specifications (are there any voids that need filling, clean, etc.)
checkpoint-status | 2486fef7-8684-423e-ae68-b7d53a1f8693 |  | checkpoint | Concrete clearance above manufacturer's specifications
checkpoint-status | f7997b4f-46a3-45ea-81f4-90ef7be4d9c8 |  | checkpoint | Applied with sealant or mechanically fastened
checkpoint-status | 5914320c-a6a9-4a60-b03f-d5904257b6b0 |  | checkpoint | Photo of highlighted drawing showing locations of work
checklist-flat | ddec6858-f3ed-4d94-9e63-890ad95558a7 |  | checklist | AllSheets - Area: |  |  |  |  | Yes | QA - Tanking AllSheet (V1) | e4504568-4bf5-46cb-8c96-4141324d9ef1
checkpoint-status | 2f207cf5-465d-46f5-a34e-ea3740db9d43 |  | checkpoint | Specified area handed over to Sansom
checkpoint-status | 3ba342b9-1995-4acb-a159-4c60e4a43be9 |  | checkpoint | Substrate (Blinding Concrete) Acceptable - upturns and flat areas acceptable for Allproof DPM
boolean | 7f0e006c-8a91-5a86-a6dd-3b0e03a3fc83 |  | tickbox | Photo taken of Upturns
boolean | 2ac5f746-eb3e-5341-b7e6-b38ed3f30276 |  | tickbox | Photo taken of Flat Area ('stand back photo')
checkpoint-status | 0c722209-6167-4e89-a270-b6e4b0f184f8 |  | checkpoint | Specified DPM Supplied
boolean | 285821e5-6018-5624-a008-9813cd0ffd15 |  | tickbox | Photo of DPM roll sticker attached
checkpoint-status | 6efdc01b-79ec-41ac-aba3-fd9e0011ffb2 |  | checkpoint | AllSheet lapped & taped as per specification ( "100" c/c)
boolean | bcb39443-6caf-5cff-a949-8bced79a19f3 |  | tickbox | Photo taken of Lap
boolean | 53105f6b-e887-5e02-bd9e-26e6091ff9ce |  | tickbox | Photo taken of Taped Joint ('stand back photo')
checkpoint-status | 632e496a-0cd5-4ee9-b78d-b9dfb4f6b8ab |  | checkpoint | Allproof termination installed as per project & product specification
boolean | 5ac49482-b8fd-525d-a94f-43d95edbb496 |  | tickbox | Photo taken of Termination
checkpoint-status | 6c199081-721f-4362-8308-868d73867237 |  | checkpoint | Photo of highlighted drawing showing locations of work
checklist-flat | 1741d0ed-e96c-481d-bdd6-cd90c2bd1296 |  | checklist | Mt Eden - MC50 Capping Beam Checklist |  |  |  |  | Yes | SYS - Mt Eden - MC50 Capping Beam Checklist | e4b1d5c3-574c-4b12-b7bc-4df38811b6db
checkpoint-status | f0c01683-ebab-4973-bc5b-84690e290b31 |  | checkpoint | 1. Photo of Work area
checkpoint-status | 01f36d6f-1ebf-4f59-9223-2f51f427abe3 |  | checkpoint | 2 Is the substrate acceptable for application of Volclay DS
checkpoint-status | aaf504fe-0dc7-4761-b845-c1489ead7fe2 |  | checkpoint | 2 Is the boxing installaed and acceptable for installation of Volclay DS
checkpoint-status | 0cf7f627-0490-4886-8d95-d5cf28257ac8 |  | checkpoint | 3. Number of piles to be detailed? (Can we make this a number selection?
checkpoint-status | dfa86d14-de0c-4056-9601-287704d9566d |  | checkpoint | 3. Volclay trimmed and detailed around piles
checkpoint-status | c87f6d03-570f-462a-a32a-70cec8b263e7 |  | checkpoint | 4. Volclay Laps left for connection to roof & downturns into skin wall
checkpoint-status | 8adcb3b6-5e94-4129-86ad-7d595407b663 |  | checkpoint | 5.. Bentoseal detailed & dressed around pile
checkpoint-status | 09fd9a8a-ee12-4f2d-984c-02003c19dc60 |  | checkpoint | 6. RX101detailed and dressed around pile
checkpoint-status | df42f901-1f1f-42a8-8c8d-3d731ecf5008 |  | checkpoint | 7. RX101 "tail"left for connection to wall detail
checkpoint-status | face6fd1-24a0-42e9-a376-6df734565e56 |  | checkpoint | 8. Is the boxing and site concrete acceptable for installation of Centreguard
checkpoint-status | b2dd9480-b22e-4140-9ec2-d7a848042c3b |  | checkpoint | 9. Centreguard installed as per specification
checkpoint-status | 8290f07f-e9c7-41d1-b189-3c70bfd4ff82 |  | checkpoint | 10. Centreguard laps left for connection onto next stage of capping beam
checklist-flat | f9a4d234-713c-484d-8ac8-26a1cfc873b8 |  | checklist | Mt Eden - Swelltite QA |  |  |  |  | Yes | Mt Eden - Swelltite QA | e733ca29-8e98-4281-ac69-dd368369f3c1
checkpoint-status | e434df52-8ee7-4f94-bf78-21bfcebed75d |  | checkpoint | 1. Substrate to manufacturer's specifications (are there any voids that need filling, clean, etc.)
checkpoint-status | c02790e3-2a87-4955-8f71-048124c0403d |  | checkpoint | 2. Check and clean the Voltex/Swelltite flap for the Swelltite
checkpoint-status | 546f9357-3ae8-454a-b206-9bb1a84a6208 |  | checkpoint | 3. Apply glue to the wall ready for the Swelltite
checkpoint-status | 651a1f07-b1ff-42d3-8136-52150770d8e5 |  | checkpoint | 4. Are there any penetrations ?
checkpoint-status | dd42de53-820a-40bd-bfa4-85a93b1304be |  | checkpoint | 5. Swelltite laps taped as per specification
checkpoint-status | b740eabd-aecf-46d3-ba51-293dddd35f38 |  | checkpoint | 7. Termination bar installed as per specification
checkpoint-status | 88844533-201c-4646-80c2-b6ebe2ec79d8 |  | checkpoint | 8. Protection Layer Installed
boolean | bea6a54b-c2a0-5435-a67f-04cf2dbd6a08 |  | tickbox | Corflute Installed
boolean | e12047b3-7916-5f28-8a95-ac80a78056dc |  | tickbox | Aquadrain 150 Installedon
boolean | a4e22857-40aa-56bb-bd43-a36a43063117 |  | tickbox | 9mm Compressed Sheet Installed
checklist-flat | 3f9020cd-2d0c-4092-8bd6-37f03eaf5e08 |  | checklist | Mt Eden - AllSheet QA |  |  |  |  | Yes | QA - Tanking AllSheet (V2) | ed676aec-fe31-4dae-b48f-4aec39ead264
checkpoint-status | abf3bd67-1d5d-4cf2-a193-4c1b4d8fdeea |  | checkpoint | 1. Specified Area Handed over to Sansom
checkpoint-status | d94e0cef-fc6a-4e7c-bf20-84dc0caa9d89 |  | checkpoint | Tick Box - Substrate Handover Completed
checkpoint-status | 27b87ba2-38be-4bbe-80a9-c6d7524cedb8 |  | checkpoint | 2. Is the concrete substrate acceptable ?
checkpoint-status | 9600f8d0-9d2a-446f-b68a-b6874b307637 |  | checkpoint | 3. Photo of Work Area
checkpoint-status | ac87b83b-65f4-4e23-8c38-4bb7e90a6a2d |  | checkpoint | 4. Specified AllSheet 500 supplied
checkpoint-status | a2161d90-110a-4044-8535-23a5073a374e |  | checkpoint | Tick Box - Photo of DPM roll Sticker attached?
checkpoint-status | ae0362f5-6f1f-4236-8b8d-e47cde268958 |  | checkpoint | 5. Allsheet lapped & taped as per specification (100 c/c)
checklist-flat | 9357c7f0-9b5d-4b28-a040-099e74b53201 |  | checklist | 307 Wall Remedial Checklist |  |  |  |  | Yes | 307 Wall Remedial Checklist | f0a37b74-1365-4be6-bcf8-63a889a04796
checkpoint-status | c9ee4330-d81d-47b8-b900-8332d8744479 |  | checkpoint | Rearguard bonded to concrete as per remedial detail
checkpoint-status | 2f1f848f-1401-4d25-9ec9-476d4c05b59f |  | checkpoint | Substrate to manufacturer's specifications (are there any voids that need filling, clean, etc.)
checkpoint-status | 49324334-49d2-4631-9762-f79432fca12b |  | checkpoint | Check and clean the voltex flap for the Swelltite
checkpoint-status | 47d2d35c-c0b8-4e4a-a916-1a6bf6f8ed2a |  | checkpoint | Apply glue to the wall ready for the Swelltite
checkpoint-status | a200980f-b1a2-4687-bc98-6510b05e252c |  | checkpoint | Are there any penetrations in the wall section ?
checkpoint-status | b59d3eac-e9c4-4d96-bfca-d191f041fda3 |  | checkpoint | Tape the laps
checkpoint-status | 109b428b-ab07-4f52-ab38-eba86c1f9b7f |  | checkpoint | Termination between Voclay DS flap & Swelltite
checkpoint-status | fd0830d0-8377-4746-8ca3-12aa53eccbf9 |  | checkpoint | Hang protection layer
checkpoint-status | ea436edd-d37e-4498-bb89-98c91ba417a4 |  | checkpoint | Area Photo of completed works
checklist-flat | 1804ccf3-c934-4d6e-93c0-a53f761c9e95 |  | checklist | Tanking Insitu Walls - Area: |  |  |  |  | Yes | QA - Tanking Insitu Walls (V1) | f99811e4-02ca-4bc1-93c6-b4a628686efe
checkpoint-status | aee647cd-3c62-4a2d-b364-6f2bfe110971 |  | checkpoint | Substrate to manufacturer's specifications (are there any voids that need filling, clean, etc.)
checkpoint-status | 0f60b52c-1095-4418-871d-24e5e5c7ad61 |  | checkpoint | Check and clean flap.
checkpoint-status | 6189cf6c-52e9-49a1-aa1c-371ce1817f0c |  | checkpoint | Material installed as per manufacturer's specification.
checkpoint-status | d8535b25-9fc6-486c-9c50-4f4c456b0a56 |  | checkpoint | Check membrane for any damage and do repairs to manufacturers requirements. Take photos.
checkpoint-status | 4d27d747-388a-4df3-8fe5-62e815924fae |  | checkpoint | Complete penetrations
checkpoint-status | 597550ff-4464-4e78-bbe0-76f6ef89415a |  | checkpoint | Tape the laps
checkpoint-status | 69604550-6c6a-485b-9bdd-66d37a65dc9b |  | checkpoint | Place the termination bar
checkpoint-status | 51a64e24-98a6-4623-b3b8-11d624b25f52 |  | checkpoint | Cetcoat applied
checkpoint-status | aad91b58-9680-4d1b-bb01-91d8b1c8d28c |  | checkpoint | Protection layer installed
checkpoint-status | eb9dac93-517e-4165-9ea9-2b558d3f885e |  | checkpoint | Drainage installed and 100mm away from wall
checkpoint-status | adf4e0dc-1f8d-4136-8d43-9a93200ccf23 |  | checkpoint | Photo of highlighted drawing showing locations of work
checklist-flat | 68fe82bf-11c9-4d16-98b6-cb71b9fd1615 |  | checklist | MC20 Cut and Cover Set Out Plan |  |  |  |  | Yes | SYS - MC20 Cut and Cover Set Out Plan | fdb7fd22-9953-4a24-b521-d398916ba265
checkpoint-no-status | 57970eee-fb34-476b-8c10-45252f902aeb |  | checkpoint | MC20 Cut and Cover Set Out Plan
checklist-flat | d2ea48da-0e67-4ecc-8771-4d5c9fce2cb9 |  | checklist | Bluey Rearguard - Area: |  |  |  |  | Yes | QA - Bluey Rearguard (V1) | ff2d3900-c454-45b3-8f57-e0809373e17a
checkpoint-no-status | 1141efa7-a1ad-4fe2-a89c-ad4fa5420b22 |  | checkpoint | Work Area Details
text | 7fdcb233-69ac-5d99-ad1c-a6dc85a0f1e1 |  | textbox | Number of joints in area
boolean | 6f0724e9-1c76-5c7c-ad33-0cec6ad1d855 |  | tickbox | Photo taken of Rearguard in work area ('stand back photo')
checkpoint-status | 912410af-163a-44b5-b22b-2aa978b043b0 |  | checkpoint | Preprufe tape applied to underside of Rearguard
boolean | 65c3aa69-a458-546d-8242-5fed77f6024d |  | tickbox | Photo taken of tape applied to underside of Rearguard
checkpoint-status | 2747ee17-cda2-4dbb-b6a1-253fa73a0374 |  | checkpoint | Rearguard bedded into Volclay DS with Cetseal controlled sealant
boolean | 655b78be-fbbb-50bd-9dd9-d9fd4331dd88 |  | tickbox | Photo taken of sealant applied to underside of Rearguard
boolean | 2111b1dc-d5a4-5376-8ebe-edb8d504485d |  | tickbox | Photo taken of Rearguard installed
checkpoint-status | 5f77b359-39a6-497f-9e4a-90ee780eb79c |  | checkpoint | Rearguard welded connections as per production specification
boolean | 955e8ab1-3c2f-533e-ab8a-a8caf7b78c81 |  | tickbox | Photo taken of finished welded work
checkpoint-status | dc8cfa2e-5f6b-46dc-b402-94a1aa1a421b |  | checkpoint | Photo of highlighted drawing showing locations of work