## Membranes 2 Layer
Work Area |  | Checklist | Questions | Check type | photo prompt
Wall Sections | Section 1 West | Substrate Inspection | Substrate handover from LINK allaince | Pass/ Fail/ NA | YES
| Section 1 North |  | Substrate preparation as per manufacturers specification | Pass/ Fail/ NA | YES
| Section 2 North |  | Signature | Pass/ Fail/ NA | YES
| Section 3 South | Torch on checklist | Substrate ready /acceptable for application | Pass/ Fail/ NA | YES
| Section 4 West |  | Poly Primer Application as per manufacturers specification | Pass/ Fail/ NA | YES
|  |  | EVOlight 1st Layer installed as per manufacturers specification | Pass/ Fail/ NA | YES
|  |  | EVOlight 2nd Layer installed as per manufacturers specification | Pass/ Fail/ NA | YES
|  |  | Protection Layer as per Manufacturers specification | Pass/ Fail/ NA | YES
|  |  | Terminations Detailing- with Polydetail MS and termination bar | Pass/ Fail/ NA | YES
|  |  | ILD Test | Pass/ Fail/ NA | YES
|  | Substrate Completion HandOver | Substrate visual inspection- Area Clean Clear and Tidy | Pass/ Fail/ NA | YES
|  |  | Substrate handover to Link allaince signed off | Pass/ Fail/ NA | YES
Podium | Flats | Substrate Inspection | Substrate handover from LINK allaince | Pass/ Fail/ NA | YES
| Upstands |  | Substrate preparation as per manufacturers specification | Pass/ Fail/ NA | YES
|  |  | Signature | Pass/ Fail/ NA | YES
|  | Torch on checklist | Substrate ready /acceptable for application | Pass/ Fail/ NA | YES
|  |  | Poly Primer Application as per manufacturers specification | Pass/ Fail/ NA | YES
|  |  | EVOlight 1st Layer installed as per manufacturers specification | Pass/ Fail/ NA | YES
|  |  | EVOlight 2nd Layer installed as per manufacturers specification | Pass/ Fail/ NA | YES
|  |  | Protection Layer as per Manufacturers specification | Pass/ Fail/ NA | YES
|  |  | Terminations Detailing- with Polydetail MS and termination bar | Pass/ Fail/ NA | YES
|  |  | ILD Test | Pass/ Fail/ NA | YES
|  | Substrate Completion HandOver | Substrate visual inspection- Area Clean Clear and Tidy | Pass/ Fail/ NA | YES
|  |  | Substrate handover to Link allaince signed off | Pass/ Fail/ NA | YES