## Breakdown
|  | PROJECT BREAKDOWN |  |  |  | CHECKLIST
Adhesion Sealing - Riccarton Park
Project Build QA
Stage 8 - B04 Apartment
Basement
|  |  |  | Precast Panels (Yard) | Ability to add | QA - Precast Panels (Yard)
|  |  |  | Post applied - Stitch joints | Ability to add | QA - In-situ joints Bentonite
|  |  |  | Top Detail & Penetrations | Ability to add | QA - Detail Penetration(s)
|  |  |  | Base Detail |  | TBC
Compliance Documents
|  | Stage 8 - B04 |  |  | Ability to add | Compliance / Completion Documentation Checklist

## Checklist
checklist | QA - Precast Panels (Yard)
checkpoint | Installed as per spec and work complete
text | Date:
text | Panel ID(s):
text | Product(s):
text | Length:
text | Batch #:
holdpoint | Request Signoff
checklist | QA - In-situ joints Bentonite
checkpoint | Surface preparation if required
checkpoint | Precast wall panel bentonite sheet to lap 300mm minimum onto Block Wall
checkpoint | Bentonite to be applied to 600mm wide in-situ concrete stitch joints lapping 300mm beyond stitch joint Bentonite sheet
checkpoint | Installed as per spec and work complete
holdpoint | Request Signoff
checklist | QA - Sikalastic 152
checkpoint | Substrate clean and dry
checkpoint | Product applied within ambient parameters
checkpoint | 1st Coat Installed as per spec and work complete
checkpoint | 2nd Coat Installed as per spec and work complete
holdpoint | Request Signoff
checklist | QA - Detail Penetration(s)
checkpoint | Penetration Details complete
text | Area of Installation / Panel Location
bool | Photo taken
holdpoint | Request Signoff
checklist | QA - Overall Final Checks
checkpoint | All laps completed
checkpoint | Termination bar installed
checkpoint | Membrane completed as per specification
holdpoint | Request Signoff
type | name | values
checklist | Compliance / Completion Documentation Checklist
checkpoint | All Compliance / Completion Documentation - Completed & Attached
button | PS3 - Completed and Attached | Yes, N/A
button | Any Additional Compliance Documentation - Completed and Attached | Yes, N/A
label | Do not select "Pass" HERE until all above requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint | Request Signoff