## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | QA - Sikalastic 152 |  |  |  |  | Yes | QA - Sikalastic 152 | 1fdfc7b5-dd57-433b-9166-c7571f576062
checkpoint-status |  |  | checkpoint | Substrate clean and dry
checkpoint-status |  |  | checkpoint | Product applied within ambient parameters
checkpoint-status |  |  | checkpoint | 1st Coat Installed as per spec and work complete
checkpoint-status |  |  | checkpoint | 2nd Coat Installed as per spec and work complete
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | QA - Overall Final Checks |  |  |  |  | Yes | QA - Overall Final Checks | 21230d14-3c1a-4cde-a3b0-867c1e7d0077
checkpoint-status |  |  | checkpoint | All laps completed
checkpoint-status |  |  | checkpoint | Termination bar installed
checkpoint-status |  |  | checkpoint | Membrane completed as per specification
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | Compliance / Completion Documentation Checklist |  |  |  |  | Yes | SYS - Compliance / Completion Documentation Checklist | 6b5d400e-07d6-4b03-9dff-fca677648244
checkpoint-status |  |  | checkpoint | All Compliance / Completion Documentation - Completed & Attached
button | 632d7e55-58bc-5827-9a83-13ac1e5897ba |  | button | PS3 - Completed and Attached | Yes, N/A
button | 1edd9f2f-e53b-5500-bf0d-efc39ac19870 |  | button | Any Additional Compliance Documentation - Completed and Attached | Yes, N/A
label | 1aeb1178-3f42-5de6-a08c-502d326a6b6b |  | note | Do not select "Pass" HERE until all above requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | QA - Block Wall Bentonite |  |  |  |  | Yes | QA - Block Wall Bentonite | 8cb6b384-fba7-4a8f-baae-900c5d6084d7
checkpoint-status |  |  | checkpoint | Substrate clean dry
checkpoint-status |  |  | checkpoint | Bentonite sheet to lap with DPM approx 700mm down the face of the block formwork with a mechanical fixed termination bar
checkpoint-status |  |  | checkpoint | Installed as per spec and work complete
holdpoint |  |  | signoff | Request Signoff
checkpoint-status |  |  | checkpoint | Protection sheet installed
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | QA - Detail Penetration(s) |  |  |  |  | Yes | QA - Detail Penetration(s) | a0e7befa-885e-45e6-baef-541f20543c91
checkpoint-status |  |  | checkpoint | Penetration Details complete
text | d83248d8-628c-5376-af58-e3ae430ea409 |  | textbox | Area of Installation / Panel Location
boolean | 1e4ccb64-4185-5a70-8b82-480c9cf430aa |  | tickbox | Photo taken
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | QA - Precast Panels (Yard) |  |  |  |  | Yes | QA - Precast Panels (Yard) | a3345c43-85cd-4813-99af-9890efae6d74
checkpoint-status |  |  | checkpoint | Installed as per spec and work complete
text | 618bcea0-f84a-5531-aaf2-18615c286365 |  | textbox | Date:
text | bd6d7258-8b42-55fd-a434-ac6d4ecd6a66 |  | textbox | Panel ID(s):
text | 9ac0579b-0dd4-5668-8b01-127a82fb6b6f |  | textbox | Product(s):
text | aa715872-0aa5-59da-ae5f-afc0b7976975 |  | textbox | Length:
text | fcb37c78-ba88-5ace-ae42-bebd5656d659 |  | textbox | Batch #:
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | QA - In-situ joints Bentonite |  |  |  |  | Yes | QA - In-situ joints Bentonite | ca56e574-7b25-409b-8d51-ecebb3287b28
checkpoint-status |  |  | checkpoint | Surface preparation if required
checkpoint-status |  |  | checkpoint | Precast wall panel bentonite sheet to lap 300mm minimum onto Block Wall
checkpoint-status |  |  | checkpoint | Bentonite to be applied to 600mm wide in-situ concrete stitch joints lapping 300mm beyond stitch joint Bentonite sheet
checkpoint-status |  |  | checkpoint | Installed as per spec and work complete
holdpoint |  |  | signoff | Request Signoff