## ITP007 - Unbound Pavements
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP 016 - AGL Removal of Luminaires and Install of foundations | [5 empty] | ITP 016 - AGL Removal of Luminaires and Install of foundations
section | 1.0 Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | Frequency: Prior to commencing any activity
label | Acceptance Criteria:
label | • Ensure that all employees and subcontractors are using the latest and complete set of drawings
label | Reference Documents:
label | • IFC Drawings
label | • Appendix K- AGL Specification
label | Inspection/ Test Method: Verify
label | Record of conformity: Drawings
label | IP
label | Responsibility: Subcontractor Representative
text | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | Frequency: Prior to commencing any activities
label | Acceptance Criteria:
label | • All necessary measures and controls are being implemented, that is PSP, EMP, TMP, SWMS & WP.
label | Reference Documents:
label | • PSP
label | • EMP
label | • TMP
label | • JSEA
label | • SWMS
label | • WP
label | Inspection/ Test Method: Verify
label | Record of conformity: Site and Office Inspection
label | HP*
label | Responsibility: Site Engineer / Site Supervisor
text | Date Completed:
checkpoint | 1.3 - Material/Equipment Approvals and Certification
label | Frequency: Prior to Start
label | Acceptance Criteria:
label | • All materials shall be proven to meet contractual requirements prior to acceptance.
label | Reference Documents:
label | • Appendix K- AGL Specification Section 2.3.3
label | Inspection/ Test Method: Verify
label | Record of conformity: Datasheet / Material Submission
label | HP*
label | Responsibility: Site Engineer
text | Date Completed:
checkpoint | 1.4 - As-built location
label | Frequency: Prior to commencing any activity
label | Acceptance Criteria:
label | • Surveyor to pick up existing location of all AGL Luminaires and position of foundations are prescribed based on design RL.
label | Reference Documents: Survey Documentation
label | Inspection/ Test Method: Verify
label | Record of conformity: Survey as Built
label | SCP
label | Responsibility: Site Engineer
text | Date Completed:
section | 2.0 Removal of AGL Luminaires and installation of Foundation
checkpoint | 2.1 - Confirmation of pre-works
label | Frequency: Each Light
label | Acceptance Criteria:
label | • Ensure that the light to be removed corresponds to project drawings and documentation.
label | Reference Documents:
label | • IFC Drawings
label | • 12554937-E031 to 12554937-E037
label | Inspection/ Test Method: Verify
label | Record of conformity: This ITP Signed & Sub-contractor ITP
label | IP
label | Responsibility: Site Engineer / Site Supervisor
text | Date Completed:
checkpoint | 2.3 - Isolation of lights
label | Frequency: Each Light
label | Acceptance Criteria:
label | • Prior to commencement of removal, the subcontractor shall ensure that the light has been isolated from power.
label | Reference Documents: APAM Electrical Isolation Standards
label | Inspection/ Test Method: Verify
label | Record of conformity: This ITP Signed & Sub-contractor ITP
label | IP
label | Responsibility: Site Engineer / Site Supervisor
text | Date Completed:
checkpoint | 2.4 - Light removal
label | Frequency: Each Light
label | Acceptance Criteria:
label | • Remove light as per Subcontractor checklist for the different methods.
label | Reference Documents:
label | • IFC Drawings
label | • 12554937-E031 to 12554937-E037
label | Inspection/ Test Method: Verify
label | Record of conformity: This ITP Signed & Sub-contractor ITP
label | IP
label | Responsibility: Site Engineer / Site Supervisor
text | Date Completed:
checkpoint | 2.5 - Light storage
label | Frequency: Each Light
label | Acceptance Criteria:
label | • After removal of the light, the subcontractor must ensure that the light number and position is recorded and stored accordingly for re-installation.
label | Reference Documents:
label | • IFC Drawings
label | • 12554937-E031 to 12554937-E037
label | Inspection/ Test Method: Verify
label | Record of conformity: This ITP Signed & Sub-contractor ITP
label | IP
label | Responsibility: Site Engineer / Site Supervisor
text | Date Completed:
section | 3.0 Installation of Light Foundation
checkpoint | 3.1 - Coring
label | Frequency: Each Light
label | Acceptance Criteria:
label | • Core pavement to required depth as per subcontractor ITC for relevant Method.
label | • Remove base and clean void.
label | Reference Documents:
label | • IFC Drawings
label | • 12554937-E031 to 12554937-E037
label | Inspection/ Test Method: Verify
label | Record of conformity: This ITP Signed & Sub-contractor ITP
label | IP
label | Responsibility: Site Engineer / Site Supervisor
text | Date Completed:
checkpoint | 3.2 - Installation of foundation
label | Frequency: Each Light
label | Acceptance Criteria:
label | • Position bung/spacer in 150mm diameter hole of foundation. Ensure cables and conduits are clear and clean.
label | • Surveyor to provide final design surface level.
label | • Mix and position quick set concrete onto the top of the existing foundation and let cure.
label | Reference Documents:
label | • IFC Drawings
label | • 12554937-E031 to 12554937-E037
label | Inspection/ Test Method: Verify
label | Record of conformity: This ITP Signed & Sub-contractor ITP
label | IP
label | Responsibility: Site Engineer / Site Supervisor
text | Date Completed:
checkpoint | 3.3 - Blanking Plate
label | Frequency: Each Light
label | Acceptance Criteria:
label | • As required, luminaire fittings to be safeguarded to allow for placement of asphalt with a Blanking plate.
label | Reference Documents:
label | • IFC Drawings
label | • 12554937-E031 to 12554937-E037
label | Inspection/ Test Method: Verify
label | Record of conformity: This Signed ITP & Sub-contractor ITP
label | IP
label | Responsibility: Site Engineer / Site Supervisor
text | Date Completed:
checkpoint | 3.4 - Asphalt Backfill
label | Frequency: Each Light
label | Acceptance Criteria:
label | • Place hotmix asphalt in void above new foundation and compact using hand tools.
label | • Ensure asphalt is finished flush with surrounding surface.
label | Reference Documents:
label | • IFC Drawings
label | • 12554937-E031 to 12554937-E037
label | Inspection/ Test Method: Verify
label | Record of conformity: This ITP Signed & Sub-contractor ITP
label | IP
label | Responsibility: Site Engineer / Site Supervisor
text | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date: