## matrix
Matrix Name | Dimension | Name | Type / Data Field | Tag 1 | Tag 2
Hydraulic Services - Penetrations (includes Cast In)
| Scope |  |  | Penetrations (includes Cast In)
Rows
|  | Penetrations (includes Cast In) | dynamic | Penetrations (includes Cast In) | Hydraulic Services
Columns
|  | Peno - Floor |  | Peno - Floor
|  | Peno - Syphonic |  | Peno - Syphonic
|  | Peno - Wall |  | Peno - Wall
|  | Peno - Cast In |  | Peno - Cast In
Hydraulic Services - Drains, Stacks & Vents
| Scope |  |  | Drains, Stacks & Vents
Rows
|  | Level 1 | dynamic | Level 1 | Drains, Stacks & Vents | Hydraulic Services
|  | Level 2 | dynamic | Level 2 | Drains, Stacks & Vents | Hydraulic Services
|  | Level 3 | dynamic | Level 3 | Drains, Stacks & Vents | Hydraulic Services
|  | Level 4 | dynamic | Level 4 | Drains, Stacks & Vents | Hydraulic Services
|  | Level 5 | dynamic | Level 5 | Drains, Stacks & Vents | Hydraulic Services
|  | Level 6 | dynamic | Level 6 | Drains, Stacks & Vents | Hydraulic Services
Columns
|  | UQ Drains: Sewer, Stormwater & Vent - Underslung |  | UQ Drains: Sewer, Stormwater & Vent - Underslung
|  | UQ Stack Riser: Sewer, Vent, Trade Waste Vent & Stormwater |  | UQ Stack Riser: Sewer, Vent, Trade Waste Vent & Stormwater
|  | UQ Drains: Trade Waste - Underslung |  | UQ Drains: Trade Waste - Underslung
Hydraulic Services - Syphonic
| Scope |  |  | Syphonic
Rows
|  | Syphonic | dynamic | Syphonic | Hydraulic Services
Columns
|  | UQ Drains: Syphonic - Underslung |  | UQ Drains: Syphonic - Underslung
|  | UQ Stack Riser: Syphonic |  | UQ Stack Riser: Syphonic
Hydraulic Services - Corridor Rough In
| Scope |  |  | Corridor Rough In
Rows
|  | Level 2 | dynamic | Level 2 | Corridor Rough In | Hydraulic Services
|  | Level 3 | dynamic | Level 3 | Corridor Rough In | Hydraulic Services
|  | Level 4 | dynamic | Level 4 | Corridor Rough In | Hydraulic Services
|  | Level 5 | dynamic | Level 5 | Corridor Rough In | Hydraulic Services
|  | Level 6 | dynamic | Level 6 | Corridor Rough In | Hydraulic Services
Columns
|  | UQ Corridor Rough In (Cold Water) |  | UQ Corridor Rough In (Cold Water)
|  | UQ Corridor Rough In (Hot Water) |  | UQ Corridor Rough In (Hot Water)
|  | UQ Corridor Rough In (Gas) |  | UQ Corridor Rough In (Gas)
|  | UQ Corridor Rough In (Non Potable/Rainwater) |  | UQ Corridor Rough In (Non Potable/Rainwater)
|  | UQ Corridor - Meter Manifold Install |  | UQ Corridor - Meter Manifold Install
Hydraulic Services - Risers
| Scope |  |  | Risers
Rows
|  | Level 1 | dynamic | Level 1 | Risers | Hydraulic Services
|  | Level 2 | dynamic | Level 2 | Risers | Hydraulic Services
|  | Level 3 | dynamic | Level 3 | Risers | Hydraulic Services
|  | Level 4 | dynamic | Level 4 | Risers | Hydraulic Services
|  | Level 5 | dynamic | Level 5 | Risers | Hydraulic Services
Columns
|  | Is there existing work by previous plumbing contractor within workfront? |  | Is there existing work by previous plumbing contractor within workfront? (Pass = Yes)
|  | Photos of prior works BEFORE RSG commencement | Photos of prior works BEFORE RSG commencement must be included here | Is there existing work by previous plumbing contractor within workfront? (Pass = Yes)
|  | Installation complies with current IFC shop drawings, schematics |  | Installation complies with current IFC shop drawings, schematics & AS/NZS 3500 (2021)
|  | Expansion loop position & length comply with IFC schematics |  | Expansion loop position and length comply with IFC schematics & AS/NZS 3500 (2021)
|  | Clips, fixings & anchor points are correct |  | Clips, fixings & anchor points are correct (etc - fixed anchor, slide guide clamp, spring clip)
|  | Clips used are not dissimilar metals & will not corrode an element |  | Clips used are not dissimilar metals and will not corrode an element
|  | All pipework is clear of debris & any open ends sealed |  | All pipework is clear of debris and any open ends sealed (with duct tape if temporary measure required)
|  | Torque rates of all roll-groove joints are correct |  | Torque rates of all roll-groove joints are correct
|  | Flange connection gasket is fibre and not rubber |  | Flange connection gasket is fibre and not rubber
|  | Flange connection bolts are to the required torque rates |  | Flange connection bolts are to the required torque rates
|  | Branch junctions & off-set levels are correct |  | Branch junctions & off-set levels are correct
|  | Pipe joints & witness marks are correct |  | Pipe joints & witness marks are correct
|  | Check for damage or leaks |  | Check for damage or leaks
|  | Valve flow direction & disconnection unions are correct |  | Valve flow direction & disconnection unions are correct
|  | Extension points have sacrificial valves |  | Extension points have sacrificial valves
|  | Labels have been applied |  | Labels have been applied
|  | Pipes requiring lagging have been temporarily labelled |  | Pipes requiring lagging have been temporarily labelled
|  | Penos have been caulked & meet fire rating requirements |  | Penos have been caulked and meet fire rating requirements (top and underside of slab)
|  | RSG demarcation sticker has been applied to work zone |  | RSG demarcation sticker has been applied to work zone (if connecting to previous contractor works)
Hydraulic Services - High Level Rough In
| Scope |  |  | High Level Rough In
Rows
|  | Level 1 | dynamic | Level 1 | High Level Rough In | Hydraulic Services
|  | Level 2 | dynamic | Level 2 | High Level Rough In | Hydraulic Services
|  | Level 3 | dynamic | Level 3 | High Level Rough In | Hydraulic Services
|  | Level 4 | dynamic | Level 4 | High Level Rough In | Hydraulic Services
|  | Level 5 | dynamic | Level 5 | High Level Rough In | Hydraulic Services
|  | Level 6 | dynamic | Level 6 | High Level Rough In | Hydraulic Services
Columns
|  | Is there existing work by previous plumbing contractor within workfront? |  | Is there existing work by previous plumbing contractor within workfront? (Pass = Yes)
|  | Photos of prior works BEFORE RSG commencement | Photos of prior works BEFORE RSG commencement must be included here | Is there existing work by previous plumbing contractor within workfront? (Pass = Yes)
|  | Installation complies with current IFC shop drawings |  | Installation complies with current IFC shop drawings & AS/NZS 3500 (2021)
|  | Installation materials used in accordance with manufacturer reqs. |  | Installation materials used in accordance with manufacturer requirements
|  | Pipe joints & witness marks are correct |  | Pipe joints & witness marks are correct
|  | Clips & fixings are correct |  | Clips and fixings are correct
|  | All pipework is clear of debris & any open ends sealed |  | All pipework is clear of debris and any open ends sealed (with duct tape if temporary measure required)
|  | Check pipe clear spacing |  | Check pipe clear spacing (service separation min 25mm has been achieved)
|  | Valve flow direction & disconnection unions are correct |  | Valve flow direction & disconnection unions are correct
|  | TMV/TV have been installed correctly |  | TMV/TV have been installed correctly and in the location for future access
|  | Sharp edge pipe protection is secure |  | Sharp edge pipe protection is secure and will not lead to pipe abrasion in future
|  | Couta fittings visually inspected to ensure pex is in correct location |  | Couta fittings have been visually inspected to ensure pex is in correct location and crimped correctly
|  | Final check for cross connections has been undertaken |  | Final check for cross connections has been undertaken
|  | RSG demarcation sticker has been applied to work zone |  | RSG demarcation sticker has been applied to work zone (if connecting to previous contractor works)
Hydraulic Services - Low Level Rough In
| Scope |  |  | Low Level Rough In
Rows
|  | Level 1 | dynamic | Level 1 | Low Level Rough In | Hydraulic Services
|  | Level 2 | dynamic | Level 2 | Low Level Rough In | Hydraulic Services
|  | Level 3 | dynamic | Level 3 | Low Level Rough In | Hydraulic Services
|  | Level 4 | dynamic | Level 4 | Low Level Rough In | Hydraulic Services
|  | Level 5 | dynamic | Level 5 | Low Level Rough In | Hydraulic Services
|  | Level 6 | dynamic | Level 6 | Low Level Rough In | Hydraulic Services
Columns
|  | Is there existing work by previous plumbing contractor within workfront? |  | Is there existing work by previous plumbing contractor within workfront? (Pass = Yes)
|  | Photos of prior works BEFORE RSG commencement | Photos of prior works BEFORE RSG commencement must be included here | Is there existing work by previous plumbing contractor within workfront? (Pass = Yes)
|  | Installation complies with current IFC shop drawings |  | Installation complies with current IFC shop drawings & AS/NZS 3500 (2021)
|  | Installation materials used in accordance with manufacturer reqs. |  | Installation materials used in accordance with manufacturer requirements
|  | Pipe joints & witness marks are correct |  | Pipe joints & witness marks are correct
|  | Clips & fixings are correct |  | Clips and fixings are correct
|  | All pipework is clear of debris & any open ends sealed |  | All pipework is clear of debris and any open ends sealed (with duct tape if temporary measure required)
|  | Check pipe clear spacing |  | Check pipe clear spacing (service separation min 25mm has been achieved)
|  | Valve flow direction & disconnection unions are correct |  | Valve flow direction & disconnection unions are correct
|  | TMV/TV have been installed correctly |  | TMV/TV have been installed correctly and in the location for future access
|  | Mixer bodies & lugged are installed at the correct height |  | Mixer bodies & lugged are installed at the correct height and on a nog
|  | In-wall pan & cistern brackets are correct |  | In-wall pan & cistern brackets are correct and there is reinforcement behind flush pipe
|  | Sharp edge pipe protection is secure |  | Sharp edge pipe protection is secure and will not lead to pipe abrasion in future
|  | Couta fittings visually inspected to ensure pex in correct location |  | Couta fittings have been visually inspected to ensure pex is in correct location and crimped correctly
|  | Final check for cross connections has been undertaken |  | Final check for cross connections has been undertaken
|  | RSG demarcation sticker has been applied to work zone |  | RSG demarcation sticker has been applied to work zone (if connecting to previous contractor works)
Hydraulic Services - Fit Off/ Install
| Scope |  |  | Fit Off/ Install
Rows
|  | Level 1 | dynamic | Level 1 | Fit Off/ Install | Hydraulic Services
|  | Level 2 | dynamic | Level 2 | Fit Off/ Install | Hydraulic Services
|  | Level 3 | dynamic | Level 3 | Fit Off/ Install | Hydraulic Services
|  | Level 4 | dynamic | Level 4 | Fit Off/ Install | Hydraulic Services
|  | Level 5 | dynamic | Level 5 | Fit Off/ Install | Hydraulic Services
|  | Level 6 | dynamic | Level 6 | Fit Off/ Install | Hydraulic Services
Columns
|  | UQ Fit Off/ Fixture Install Toilets & Cisterns |  | UQ Fit Off/ Fixture Install Toilets & Cisterns
|  | UQ Fit Off/ Fixture Install - Showers & Tapware |  | UQ Fit Off/ Fixture Install - Showers & Tapware
|  | UQ Fit Off/ Fixture Install - Vanity Basin/s & Tapware |  | UQ Fit Off/ Fixture Install - Vanity Basin/s & Tapware
|  | UQ Fit Off/ Fixture Install - Kitchen sink & Tapware |  | UQ Fit Off/ Fixture Install - Kitchen sink & Tapware
|  | UQ Fit Off/ Fixture Install - Laundry trough & Tapware |  | UQ Fit Off/ Fixture Install - Laundry trough & Tapware
|  | UQ Fit Off/ Fixture Install - Bath & Tapware |  | UQ Fit Off/ Fixture Install - Bath & Tapware
|  | UQ Fit Off/ Fixture Install - Dishwasher |  | UQ Fit Off/ Fixture Install - Dishwasher
|  | UQ Fit Off/ Fixture Install - Wall Tundish |  | UQ Fit Off/ Fixture Install - Wall Tundish
|  | UQ Fit Off/ Fixture Install - Hose Taps |  | UQ Fit Off/ Fixture Install - Hose Taps
|  | UQ Fit Off/ Fixture Install - TMV |  | UQ Fit Off/ Fixture Install - TMV
|  | UQ Fit Off/ Fixture Install - Tempering Valve |  | UQ Fit Off/ Fixture Install - Tempering Valve
|  | UQ Fit Off/ Fixture Install - Gas Cooktop |  | UQ Fit Off/ Fixture Install - Gas Cooktop
|  | UQ Fit Off/ Fixture Install - RPZD |  | UQ Fit Off/ Fixture Install - RPZD
Testing - Corridor & Apts
| Scope |  |  | Testing
Rows
|  | Level 1 | grouping | Level 1
|  | Corridor & Apts - McLister St | expanded | Corridor & Apts - McLister St | Level 1 | Testing
|  | Corridor & Apts - Melbourne Rd | expanded | Corridor & Apts - Melbourne Rd | Level 1 | Testing
|  | Corridor & Apts - Macindoe St | expanded | Corridor & Apts - Macindoe St | Level 1 | Testing
|  | Level 2 | grouping | Level 2
|  | Corridor & Apts - McLister St | expanded | Corridor & Apts - McLister St | Level 2 | Testing
|  | Corridor & Apts - Melbourne Rd | expanded | Corridor & Apts - Melbourne Rd | Level 2 | Testing
|  | Corridor & Apts - Macindoe St | expanded | Corridor & Apts - Macindoe St | Level 2 | Testing
|  | Level 3 | grouping | Level 3
|  | Corridor & Apts - McLister St | expanded | Corridor & Apts - McLister St | Level 3 | Testing
|  | Corridor & Apts - Melbourne Rd | expanded | Corridor & Apts - Melbourne Rd | Level 3 | Testing
|  | Corridor & Apts - Macindoe St | expanded | Corridor & Apts - Macindoe St | Level 3 | Testing
|  | Level 4 | grouping | Level 4
|  | Corridor & Apts - McLister St | expanded | Corridor & Apts - McLister St | Level 4 | Testing
|  | Corridor & Apts - Melbourne Rd | expanded | Corridor & Apts - Melbourne Rd | Level 4 | Testing
|  | Corridor & Apts - Macindoe St | expanded | Corridor & Apts - Macindoe St | Level 4 | Testing
|  | Level 5 | grouping | Level 5
|  | Corridor & Apts - McLister St | expanded | Corridor & Apts - McLister St | Level 5 | Testing
|  | Corridor & Apts - Melbourne Rd | expanded | Corridor & Apts - Melbourne Rd | Level 5 | Testing
|  | Corridor & Apts - Macindoe St | expanded | Corridor & Apts - Macindoe St | Level 5 | Testing
|  | Level 6 | grouping | Level 6
|  | Corridor & Apts - McLister St | expanded | Corridor & Apts - McLister St | Level 6 | Testing
|  | Corridor & Apts - Melbourne Rd | expanded | Corridor & Apts - Melbourne Rd | Level 6 | Testing
|  | Corridor & Apts - Macindoe St | expanded | Corridor & Apts - Macindoe St | Level 6 | Testing
Columns
|  | UQ Testing - Potable Water - 1500kpa water test (not an air test) |  | UQ Testing - Potable Water - 1500kpa water test (not an air test)
|  | UQ Testing - Potable Water - 900kpa water test pressure sensitive valves (not an air test) |  | UQ Testing - Potable Water - 900kpa water test pressure sensitive valves (not an air test)
|  | UQ Testing - Natural Gas |  | UQ Testing - Natural Gas
Testing - Apartments
| Scope |  |  | Testing
Rows
|  | Level 1 | grouping | Level 1
|  | 101 | expanded | 101 | Level 1 | Testing
|  | 102 | expanded | 102 | Level 1 | Testing
|  | 103 | expanded | 103 | Level 1 | Testing
|  | 104 | expanded | 104 | Level 1 | Testing
|  | 105 | expanded | 105 | Level 1 | Testing
|  | 106 | expanded | 106 | Level 1 | Testing
|  | 107 | expanded | 107 | Level 1 | Testing
|  | 108 | expanded | 108 | Level 1 | Testing
|  | Level 2 | grouping | Level 2
|  | 201 | expanded | 201 | Level 2 | Testing
|  | 202 | expanded | 202 | Level 2 | Testing
|  | 203 | expanded | 203 | Level 2 | Testing
|  | 204 | expanded | 204 | Level 2 | Testing
|  | 205 | expanded | 205 | Level 2 | Testing
|  | 206 | expanded | 206 | Level 2 | Testing
|  | 207 | expanded | 207 | Level 2 | Testing
|  | 208 | expanded | 208 | Level 2 | Testing
|  | 209 | expanded | 209 | Level 2 | Testing
|  | 210 | expanded | 210 | Level 2 | Testing
|  | 211 | expanded | 211 | Level 2 | Testing
|  | 212 | expanded | 212 | Level 2 | Testing
|  | 213 | expanded | 213 | Level 2 | Testing
|  | 214 | expanded | 214 | Level 2 | Testing
|  | 215 | expanded | 215 | Level 2 | Testing
|  | 216 | expanded | 216 | Level 2 | Testing
|  | 217 | expanded | 217 | Level 2 | Testing
|  | 218 | expanded | 218 | Level 2 | Testing
|  | 219 | expanded | 219 | Level 2 | Testing
|  | 220 | expanded | 220 | Level 2 | Testing
|  | 221 | expanded | 221 | Level 2 | Testing
|  | 222 | expanded | 222 | Level 2 | Testing
|  | 223 | expanded | 223 | Level 2 | Testing
|  | 224 | expanded | 224 | Level 2 | Testing
|  | 225 | expanded | 225 | Level 2 | Testing
|  | Level 3 | grouping | Level 3
|  | 301 | expanded | 301 | Level 3 | Testing
|  | 302 | expanded | 302 | Level 3 | Testing
|  | 303 | expanded | 303 | Level 3 | Testing
|  | 304 | expanded | 304 | Level 3 | Testing
|  | 305 | expanded | 305 | Level 3 | Testing
|  | 306 | expanded | 306 | Level 3 | Testing
|  | 307 | expanded | 307 | Level 3 | Testing
|  | 308 | expanded | 308 | Level 3 | Testing
|  | 309 | expanded | 309 | Level 3 | Testing
|  | 310 | expanded | 310 | Level 3 | Testing
|  | 311 | expanded | 311 | Level 3 | Testing
|  | 312 | expanded | 312 | Level 3 | Testing
|  | 313 | expanded | 313 | Level 3 | Testing
|  | 314 | expanded | 314 | Level 3 | Testing
|  | 315 | expanded | 315 | Level 3 | Testing
|  | 316 | expanded | 316 | Level 3 | Testing
|  | 317 | expanded | 317 | Level 3 | Testing
|  | 318 | expanded | 318 | Level 3 | Testing
|  | 319 | expanded | 319 | Level 3 | Testing
|  | 320 | expanded | 320 | Level 3 | Testing
|  | 321 | expanded | 321 | Level 3 | Testing
|  | 322 | expanded | 322 | Level 3 | Testing
|  | 323 | expanded | 323 | Level 3 | Testing
|  | 324 | expanded | 324 | Level 3 | Testing
|  | Level 4 | grouping | Level 4
|  | 401 | expanded | 401 | Level 4 | Testing
|  | 402 | expanded | 402 | Level 4 | Testing
|  | 403 | expanded | 403 | Level 4 | Testing
|  | 404 | expanded | 404 | Level 4 | Testing
|  | 405 | expanded | 405 | Level 4 | Testing
|  | 406 | expanded | 406 | Level 4 | Testing
|  | 407 | expanded | 407 | Level 4 | Testing
|  | 408 | expanded | 408 | Level 4 | Testing
|  | 409 | expanded | 409 | Level 4 | Testing
|  | 410 | expanded | 410 | Level 4 | Testing
|  | 411 | expanded | 411 | Level 4 | Testing
|  | 412 | expanded | 412 | Level 4 | Testing
|  | 413 | expanded | 413 | Level 4 | Testing
|  | 414 | expanded | 414 | Level 4 | Testing
|  | 415 | expanded | 415 | Level 4 | Testing
|  | 416 | expanded | 416 | Level 4 | Testing
|  | 417 | expanded | 417 | Level 4 | Testing
|  | 418 | expanded | 418 | Level 4 | Testing
|  | 419 | expanded | 419 | Level 4 | Testing
|  | 420 | expanded | 420 | Level 4 | Testing
|  | 421 | expanded | 421 | Level 4 | Testing
|  | 422 | expanded | 422 | Level 4 | Testing
|  | 423 | expanded | 423 | Level 4 | Testing
|  | 424 | expanded | 424 | Level 4 | Testing
|  | 425 | expanded | 425 | Level 4 | Testing
|  | 426 | expanded | 426 | Level 4 | Testing
|  | 427 | expanded | 427 | Level 4 | Testing
|  | 428 | expanded | 428 | Level 4 | Testing
|  | 429 | expanded | 429 | Level 4 | Testing
|  | Level 5 | grouping | Level 5
|  | 501 | expanded | 501 | Level 5 | Testing
|  | 502 | expanded | 502 | Level 5 | Testing
|  | 503 | expanded | 503 | Level 5 | Testing
|  | 504 | expanded | 504 | Level 5 | Testing
|  | 505 | expanded | 505 | Level 5 | Testing
|  | 506 | expanded | 506 | Level 5 | Testing
|  | 507 | expanded | 507 | Level 5 | Testing
|  | 508 | expanded | 508 | Level 5 | Testing
|  | 509 | expanded | 509 | Level 5 | Testing
|  | 510 | expanded | 510 | Level 5 | Testing
|  | 511 | expanded | 511 | Level 5 | Testing
|  | 512 | expanded | 512 | Level 5 | Testing
|  | 513 | expanded | 513 | Level 5 | Testing
|  | 514 | expanded | 514 | Level 5 | Testing
|  | 515 | expanded | 515 | Level 5 | Testing
|  | 516 | expanded | 516 | Level 5 | Testing
|  | 517 | expanded | 517 | Level 5 | Testing
|  | 518 | expanded | 518 | Level 5 | Testing
|  | 519 | expanded | 519 | Level 5 | Testing
|  | 520 | expanded | 520 | Level 5 | Testing
|  | 521 | expanded | 521 | Level 5 | Testing
|  | 522 | expanded | 522 | Level 5 | Testing
|  | 523 | expanded | 523 | Level 5 | Testing
|  | 524 | expanded | 524 | Level 5 | Testing
|  | 525 | expanded | 525 | Level 5 | Testing
|  | 526 | expanded | 526 | Level 5 | Testing
|  | 527 | expanded | 527 | Level 5 | Testing
|  | 528 | expanded | 528 | Level 5 | Testing
|  | 529 | expanded | 529 | Level 5 | Testing
|  | Level 6 | grouping | Level 6
|  | 601 | expanded | 601 | Level 6 | Testing
|  | 602 | expanded | 602 | Level 6 | Testing
|  | 603 | expanded | 603 | Level 6 | Testing
|  | 604 | expanded | 604 | Level 6 | Testing
|  | 605 | expanded | 605 | Level 6 | Testing
Columns
|  | UQ Testing - Water Hold - Sewer & Stormwater Underslung |  | UQ Testing - Water Hold - Sewer & Stormwater Underslung
|  | UQ Testing - Water Hold - Sewer, Stormwater & Down Pipe Stacks |  | UQ Testing - Water Hold - Sewer, Stormwater & Down Pipe Stacks
|  | UQ Testing - Air Test - Sewer & Stormwater Underslung |  | UQ Testing - Air Test - Sewer & Stormwater Underslung
|  | UQ Testing - Air Test - Sewer, Stormwater & Down Pipe Stacks |  | UQ Testing - Air Test - Sewer, Stormwater & Down Pipe Stacks
|  | UQ Testing - TMV |  | UQ Testing - TMV
|  | UQ Testing - Tempering Valve |  | UQ Testing - Tempering Valve