## Resources
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | Panel/Frame Completion Checklist |  | Panel / Frame Completion | 671fb288-b9bc-4d9f-8d6b-b0a54e378f4c
| section | Panel/Frame Completion
| checkpoint | Panel/Frame has been installed correctly and is free from defects
a49d9cc4-7762-5231-b819-56b0c1cf1430 | note | If variation/modification required, click FAIL and add Variation/Modification checklist
| checklist | Variation/Modification Checklist |  | Variation / Modification | 82e490e4-d412-42e5-9f2d-ea78f4fb728f
| section | Details
| checkpoint | Add in comments variation/modification details. Attach relevant photos
| checklist | Bay Completion / Inspection Checklist |  | Bay Completion / Inspection | a6753e19-d389-4eb2-913a-aa0a2d45aace
| section | Bay Completion/Inspection
| checkpoint | Stick Walls
d34e464c-3036-5bfd-8110-32f53f853c1b | note | Grids and RL's in place (By Multiplex)
72fdcaf8-a151-5569-bde2-286dff5faffb | note | Structural Tolerance Check
bece4a92-6177-5ddf-9fc9-66006c407d55 | note | Mullion Position and Alignment
6c64ecfb-f5ee-53ff-9db3-8964cc7dd5f9 | note | Transom Position and Alignment
8aae2125-241a-58c1-96ec-6a9e696d6f25 | note | Gaskets and Silicone (Where Apllicable) Check
64937eaa-f966-5719-badc-6bc2f2932e92 | note | Panel Position and Alignment
d5fea45b-d7ac-5c3d-8cd6-9e9a5a8e74d3 | note | Side Bead Check
a030fa61-24cf-5f6f-a96b-21b73c60e448 | note | Internal Cladding Check
2adda5c2-5547-5c40-a41b-b3bbcbdd1c57 | note | Weather Seal (where Applicable) Check
cc2ca9dd-d867-51df-9cdc-1ded10e9ad38 | note | Stick wall installed to grid and RL achieved
| checkpoint | Bay has been completed & inspected
| signoff | Multiplex Signoff