## res
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | Fit-off Gas Appliance |  | Fit-off Gas Appliance | 57090dbd-5038-4ba3-b79e-6d3882264324
| section | Details:
| checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation or additional work. If not, mark as 'N/A'. You must still action all remaining checkpoints
| checkpoint | Installation complies with latest revision of AS/NZS 5601.1 (2022) (Note: Fit-off photos to be taken only within this Checkpoint)
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Check for damage or leaks
| checkpoint | Check fixing points are secure
| checkpoint | Check level & alignment is correct
| checkpoint | Check surrounding wall material is fire rated
| checkpoint | Check distance from cook-top to range hood complies with manufacturer specification
| checkpoint | Check surrounding walls to closest burner distance complies with manufacturer specification
| checkpoint | Check flexible connections are not twisted or kinked
| checkpoint | Check gas isolation valve
| checkpoint | Check gas pressure regulator
| checkpoint | Check all functions & controls for correct operation
| checklist | Testing Gas Pipework (Above 7kPa) |  | Testing Gas Pipework (Above 7kPa) | 59546074-f202-493e-85e9-341380b25565
| section | Details:
| checkpoint | Installation complies with latest revision of AS/NZS 5601.1 (2022)
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Testing kit & equipment have current certification
| checkpoint | Apply test as per latest revision of AS/NZS 5601.1 (2022) (Note: Start & Finish testing photos to be taken only within this Checkpoint)
| checklist | Commission Fixture Group |  | Commission Fixture Group | 6332ce8b-1db6-404d-b9a5-afa1401c91bf
| section | Details:
| checkpoint | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 &/or AS/NZS 5601.1 (2022) (Note: Commissioning photos to be taken only within this Checkpoint)
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Check for any damage, leaks or missing components
| checkpoint | Check level & alignment of all fixtures
| checkpoint | Check all fixtures, seats & covers are securely fastened
| checkpoint | Check all valves are fully open
| checkpoint | Check all flexible connections are not twisted or kinked
| checkpoint | Check for water for cross connections
| checkpoint | Check fixture wastes & connections
| checkpoint | Check pipework & all traps are clear of debris
| checkpoint | Check AAV is installed to correct height
| checkpoint | Check future connection water valves are securely capped
| checkpoint | Check TV do not exceed 50°C
| checkpoint | Check TMV do not exceed 45°C
| checkpoint | Check dishwasher function
| checkpoint | Check gas valves & regulators
| checkpoint | Check all gas burner functions
| checkpoint | Check balcony hose tap
| checkpoint | Check balcony floor grate & downpipe
| checkpoint | Check all fixtures & tapware are operating as specified
| checkpoint | Confirm area has been left clean
| checklist | Commission Hot Water Generating Plant |  | Commission Hot Water Generating Plant | 7589f21d-d177-4b19-a3b2-f707cbe90945
| section | Details:
| checkpoint | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 &/or AS/NZS 5601.1 (2022) (Note: Commissioning photos to be taken only within this Checkpoint)
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Check valves are fully open
| checkpoint | Check water filters are clean
| checkpoint | Check gas supply
| checkpoint | Check circulating pumps
| checkpoint | Check flue operation
| checkpoint | Check system auto start
| checkpoint | Check flow & return temperatures
| checkpoint | Check control panel display & set points
| checkpoint | Check BMS connection (if specified)
| checkpoint | Provide the suppliers commissioning report & all plant documentation to this checkpoint
| checklist | Testing Gas Pipework (7kPa or Less) |  | Testing Gas Pipework (7kPa or Less) | aaf66933-4ded-44d4-b87a-f448db361fff
| section | Details:
| checkpoint | Installation complies with latest revision of AS/NZS 5601.1 (2022)
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Testing kit & equipment have current certification
| checkpoint | Apply test as per latest revision of AS/NZS 5601.1 (2022) (Note: Start & Finish testing photos to be taken only within this Checkpoint)
| checklist | Installation Gas Service (Mains/Risers) |  | Installation Gas Service (Mains/Risers) | b5f42dd4-5919-4cdc-a1d4-6cc9457f8305
| section | Details:
| checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation or additional work. If not, mark as 'N/A'. You must still action all remaining checkpoints
| checkpoint | Installation complies with latest revision of AS/NZS 5601.1 (2022) (Note: Installation photos to be taken only within this Checkpoint)
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Check for damage & leaks
| checkpoint | Check materials & joining methods
| checkpoint | Check crimp fittings
| checkpoint | Check alignments & levels
| checkpoint | Check pipe clips, hangers & fixings (correct size, spacing & separation)
| checkpoint | Check valves & meter assemblies
| checkpoint | Check valves & meter assemblies fixings & brackets
| checkpoint | Check pipework is clear of debris
| checkpoint | Check for cross connections
| checkpoint | Check open ends are sealed
| checkpoint | Check pipe colour coding
| checkpoint | Check pipe labelling
| checkpoint | Check floor/wall penetration fire proofing
| checklist | Installation Gas Service (In-ground) |  | Installation Gas Service (In-ground) | c94227e8-5d1f-42c7-aed4-c069c77f5cba
| section | Details:
| checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation or additional work. If not, mark as 'N/A'. You must still action all remaining checkpoints
| checkpoint | Installation complies with latest revision of AS/NZS 5601.1 (2022) (Note: Installation photos to be taken only within this Checkpoint)
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Check for damage & leaks
| checkpoint | Check materials & joining methods
| checkpoint | Check alignments & levels
| checkpoint | Check bedding & clearances
| checkpoint | Check valve connections
| checkpoint | Check pipework is clear of debris
| checkpoint | Check open ends are sealed
| checkpoint | Check pipe colour coding
| checkpoint | Check pipe trench marking tape (if specified)
| checkpoint | Check trench backfill & compaction
| checklist | Installation Hot Water Plant/Unit |  | Installation Hot Water Plant/Unit | ed552afd-b058-48fe-be33-40ebdf0e30fd
| section | Details:
| checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation or additional work. If not, mark as 'N/A'. You must still action all remaining checkpoints
| checkpoint | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4, &/or AS/NZS 5601.1 (2022) (Note: Installation photos to be taken only within this Checkpoint)
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Check for damage or leaks
| checkpoint | Check level & alignment
| checkpoint | Check safe tray (if specified)
| checkpoint | Check isolation valves & non-return valves
| checkpoint | Check pressure reduction valve (if specified)
| checkpoint | Check flexible connections are not twisted or kinked
| checkpoint | Check waste & water connections
| checkpoint | Check all functions & controls for correct operation
| checkpoint | Check water temperatures are as specified
| checkpoint | Check electrical power is available
| checkpoint | Check solar panels & mounting brackets
| checkpoint | Check solar connecting pipework & fittings
| checkpoint | Check solar pump operation
| checklist | Installation Gas Service (Rough-ins) |  | Installation Gas Service (Rough-ins) | fb63f3da-fa4c-4c82-bffa-4ed803b5e237
| section | Details:
| checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation or additional work. If not, mark as 'N/A'. You must still action all remaining checkpoints
| checkpoint | Installation complies with latest revision of AS/NZS 5601.1 (2022) (Note: Installation photos to be taken only within this Checkpoint)
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Check for damage & leaks
| checkpoint | Check pipework can not be holed by plaster screws
| checkpoint | Check crimp fittings
| checkpoint | Check for cross connections
| checkpoint | Check alignment & levels
| checkpoint | Check materials & joining methods
| checkpoint | Check pipe clips, hangers & fixings (correct size, spacing & separation)
| checkpoint | Check lugged elbows
| checkpoint | Check noggings for future fixture
| checkpoint | Check sharp edge pipe protection
| checkpoint | Check pipe colour coding
| checkpoint | Check floor/wall penetration fire proofing