## Resources
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | Add New Task |  | Add New Task | 03ec6984-b366-47c9-9ce5-ca3d8d12dabb
| section | Details:
| checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation or additional work. If not, mark as 'N/A'. You must still action all remaining checkpoints
| checkpoint | New task checked off (Add brief description of this task and take photos)
| checklist | Commission Thermostatic Mixing Valves |  | Commission Thermostatic Mixing Valves | 0f4571eb-1834-4362-b7ba-180753f5f04d
| section | Details:
| checkpoint | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 (Note: Commissioning photos to be taken only within this Checkpoint)
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Check water temperature does not exceed 45°C
| checklist | Installation Gas Service (Rough-ins) |  | Installation Gas Service (Rough-ins) | 0fd3e2c1-4e3c-416d-8a42-41819ff68e04
| section | Details:
| checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation or additional work. If not, mark as 'N/A'. You must still action all remaining checkpoints
| checkpoint | Installation complies with latest revision of AS/NZS-5601 (Note: Installation photos to be taken only within this Checkpoint)
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Check for damage & leaks
| checkpoint | Check pipework can not be holed by plaster screws
| checkpoint | Check crimp fittings
| checkpoint | Check for cross connections
| checkpoint | Check alignment & levels
| checkpoint | Check materials & joining methods
| checkpoint | Check pipe clips, hangers & fixings (correct size, spacing & separation)
| checkpoint | Check lugged elbows
| checkpoint | Check noggings for future fixture
| checkpoint | Check sharp edge pipe protection
| checkpoint | Check pipe colour coding
| checkpoint | Check floor/wall penetration fire proofing
| checklist | Installation Waste & Vent |  | Installation Waste & Vent | 16bdb7fa-a79f-4cc4-bb28-4677c4bd2c7a
| section | Details:
| checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation or additional work. If not, mark as 'N/A'. You must still action all remaining checkpoints
| checkpoint | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 (Note: Installation photos to be taken only within this Checkpoint)
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Check for damage & leaks
| checkpoint | Check materials & joining methods
| checkpoint | Check alignments & levels
| checkpoint | Check pipe clips, hangers & fixings (correct size, spacing & separation)
| checkpoint | Check expansion joints and anchor points
| checkpoint | Check in-wall fixture mounting brackets & concealed cisterns (if specified)
| checkpoint | Check in-wall waste pipes & vents
| checkpoint | Check inspection openings
| checkpoint | Check pipework & traps are clear of debris
| checkpoint | Check open ends are sealed
| checkpoint | Check acoustic insulation (if specified)
| checkpoint | Check pipe labelling
| checkpoint | Check floor/wall penetration fire proofing
| checkpoint | Check vents are run to atmosphere and weather proofing is complete
| checklist | Testing Recycled Water Pipework |  | Testing Recycled Water Pipework | 1bd3b380-506e-4e5b-bb35-723458d15367
| section | Details:
| checkpoint | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Check installation is clean and ready for testing
| checkpoint | Are all valves, meters, etc , rated for the test pressure required
| checkpoint | Testing kit & equipment have current certification
| checkpoint | Apply test as per latest revision of AS/NZS-3500 Part 1 (Note: Start & Finish testing photos to be taken only within this Checkpoint)
| checkpoint | R3 certification has taken place (Provide photo of or attach PDF copy of the Authority acceptance report)
| checklist | Testing Drainage Pipework (Water Test) |  | Testing Drainage Pipework (Water Test) | 1c176709-2e15-48b2-bfe0-4a272e5ca1e1
| section | Details:
| checkpoint | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Testing kit & equipment have current certification
| checkpoint | Apply test as per latest revision of AS/NZS-3500 Part 2 (Note: Start & Finish testing photos to be taken only within this Checkpoint)
| checklist | Testing Gas Service |  | Testing Gas Service | 1f57dbda-916d-4384-867b-1f84a8889cd0
| checkpoint | Installation complies with current AS/NZS-5600
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | Installation & materials were used, comply with manufacturer requirements
| checkpoint | Check installation is clean and ready for testing
| checkpoint | Apply air test as per AS/NZS-5600 (Provide test process photos)
| checklist | Fit-off Washing Machine Stops |  | Fit-off Washing Machine Stops | 240d3bfd-0e03-4035-bf8c-c903c64e80af
| section | Details:
| checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation or additional work. If not, mark as 'N/A'. You must still action all remaining checkpoints
| checkpoint | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 (Note: Fit-off photos to be taken only within this Checkpoint)
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Check for damage or leaks
| checkpoint | Check level & alignment
| checkpoint | Check stops hose connections are capped off
| checklist | Installation Authority Main to Meter |  | Installation Authority Main to Meter | 2555f665-d784-4c7c-905d-9fccbcd5d16a
| section | Details:
| checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation or additional work. If not, mark as 'N/A'. You must still action all remaining checkpoints
| checkpoint | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 (Note: Installation photos to be taken only within this Checkpoint)
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Check for damage & leaks
| checkpoint | Check materials & joining methods
| checkpoint | Check alignments & levels
| checkpoint | Check bedding & clearances
| checkpoint | Check valve connections
| checkpoint | Check pipework is clear of debris
| checkpoint | Check pipe trench marking tape (if specified)
| checkpoint | Check trench backfill & compaction
| checkpoint | Check water meter assemblies
| checkpoint | Check RPZD assemblies (if specified)
| checkpoint | Check pipe labelling
| checklist | Fit-off Urinal & Cistern |  | Fit-off Urinal & Cistern | 319d3960-4a7a-421c-95c2-47b1281febef
| section | Details:
| checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation or additional work. If not, mark as 'N/A'. You must still action all remaining checkpoints
| checkpoint | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 (Note: Fit-off photos to be taken only within this Checkpoint)
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Check for damage or leaks
| checkpoint | Check fixing points are secure
| checkpoint | Check level & alignment
| checkpoint | Check mini stops
| checkpoint | Check flexible connections are not twisted or kinked
| checkpoint | Check button assembly
| checkpoint | Check all functions, controls & remote sensors for correct operation
| checkpoint | Check trap is clear of debris
| checkpoint | Check caulking is correct
| checklist | Installation Suction Line |  | Installation Suction Line | 37a8026e-fadd-431a-840b-cd8930b340ee
| section | Details:
| checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation or additional work. If not, mark as 'N/A'. You must still action all remaining checkpoints
| checkpoint | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 (Note: Installation photos to be taken only within this Checkpoint)
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Check for damage & leaks
| checkpoint | Check materials & joining methods
| checkpoint | Check alignments & levels
| checkpoint | Check pipe clips, hangers & fixings (correct size, spacing & separation)
| checkpoint | Check pipework is clear of debris
| checkpoint | Check open ends are sealed
| checkpoint | Check pipe labelling
| checkpoint | Check floor/wall penetration fire proofing
| checklist | Installation Drainage (In-ground) |  | Installation Drainage (In-ground) | 47852058-0ce2-43e7-8e85-9c31a795c751
| section | Details:
| checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation or additional work. If not, mark as 'N/A'. You must still action all remaining checkpoints
| checkpoint | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 (Note: Installation photos to be taken only within this Checkpoint)
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Check for damage & leaks
| checkpoint | Check materials & joining methods
| checkpoint | Check alignments & levels
| checkpoint | Check bedding & clearances
| checkpoint | Check connections to pits, tanks, & pump stations, etc
| checkpoint | Check covers, venting, & electrical conduits, etc
| checkpoint | Check pipework & traps are clear of debris
| checkpoint | Check inspection openings
| checkpoint | Check open ends are sealed
| checkpoint | Check pipe trench marking tape (if specified)
| checkpoint | Check trench backfill & compaction
| checklist | Installation Water Storage Tank |  | Installation Water Storage Tank | 48ae6775-d581-46a5-8cc6-600b1b6055fb
| section | Details:
| checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation or additional work. If not, mark as 'N/A'. You must still action all remaining checkpoints
| checkpoint | Tank Details:
d4db202b-c5da-5bd9-bc38-0c989d145786 | dropdown | Tank Type: | Potable Water Above Ground,Rain Water Above Ground,Potable Water In-ground,Rain Water In-ground,Fire Water Above Ground,Other
| checkpoint | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 (Note: Installation photos to be taken only within this Checkpoint)
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Check for damage & leaks
| checkpoint | Check materials & joining methods
| checkpoint | Check alignments & levels
| checkpoint | Check bedding & clearances
| checkpoint | Check inlet/outlet connections & vents
| checkpoint | Check covers, venting, & electrical conduits, etc
| checkpoint | Check pipework & traps are clear of debris
| checkpoint | Check inspection openings
| checkpoint | Check open ends are sealed
| checkpoint | Check trench backfill & compaction
| checklist | Installation Plant & Equipment |  | Installation Plant & Equipment | 4af52ce8-7734-4b29-bfcf-aff7885fd876
| section | Details:
| checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation or additional work. If not, mark as 'N/A'. You must still action all remaining checkpoints
| checkpoint | Plant & Equipment Installation checked off as below
| checkpoint | Installation complies with current AS/NZS-3500 & AS/NZS-5600
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Check for damage & leaks
| checkpoint | Check tundishes are correct
| checkpoint | Check electrical power is available
| checkpoint | Check BMS is available
| checkpoint | Must provide photo
| checklist | Installation Gas Service (In-ground) |  | Installation Gas Service (In-ground) | 4c14ab3b-2d01-4a8c-b46f-28350884c837
| section | Details:
| checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation or additional work. If not, mark as 'N/A'. You must still action all remaining checkpoints
| checkpoint | Installation complies with latest revision of AS/NZS-5601 (Note: Installation photos to be taken only within this Checkpoint)
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Check for damage & leaks
| checkpoint | Check materials & joining methods
| checkpoint | Check alignments & levels
| checkpoint | Check bedding & clearances
| checkpoint | Check valve connections
| checkpoint | Check pipework is clear of debris
| checkpoint | Check open ends are sealed
| checkpoint | Check pipe colour coding
| checkpoint | Check pipe trench marking tape (if specified)
| checkpoint | Check trench backfill & compaction
| checklist | Installation Water Meter |  | Installation Water Meter | 4e9a85f0-e17a-467f-a3f6-782cdad44b6a
| section | Details:
| checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation or additional work. If not, mark as 'N/A'. You must still action all remaining checkpoints
| checkpoint | Water Meter Details:
cfe26dbb-19c5-556b-aff5-d5a049ba0725 | textbox | Meter Type:
cd821c70-f9f9-5dd8-984b-06bb99a8bfa9 | textbox | Meter Number:
346bc941-5b73-5396-9c8e-a63e4c192e6f | textbox | Meter Location:
673eb70f-07f6-5222-9121-c139d0d97f22 | dropdown | Meter Size: | 20mm,25mm,32mm,40mm,50mm,65mm,80mm,100mm,150mm,225mm,300mm
| checkpoint | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 (Note: Installation photos to be taken only within this Checkpoint)
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Check for damage & leaks
| checkpoint | Check materials & joining methods
| checkpoint | Check alignments & levels
| checklist | Fit-off Cleaners Sink & Tapware |  | Fit-off Cleaners Sink & Tapware | 524943b1-643a-45a1-8f06-267e0e7719e7
| section | Details:
| checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation or additional work. If not, mark as 'N/A'. You must still action all remaining checkpoints
| checkpoint | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 (Note: Fit-off photos to be taken only within this Checkpoint)
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Check for damage or leaks
| checkpoint | Check fixing points are secure
| checkpoint | Check level & alignment
| checkpoint | Check tapware for fit & function
| checkpoint | Check wall brackets & fixings
| checkpoint | Check bucket grate
| checkpoint | Check waste & trap connections
| checkpoint | Check all functions & controls for correct operation
| checkpoint | Check trap is clear of debris
| checkpoint | Check caulking
| checklist | Installation Water Service (Rough-ins) |  | Installation Water Service (Rough-ins) | 53df7716-1ae8-4060-9fa0-48418ccf8c10
| section | Details:
| checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation or additional work. If not, mark as 'N/A'. You must still action all remaining checkpoints
| checkpoint | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 (Note: Installation photos to be taken only within this Checkpoint)
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Check for damage & leaks
| checkpoint | Check pipework can not be holed by plaster screws
| checkpoint | Check crimp fittings
| checkpoint | Check for cross connections
| checkpoint | Check alignment & levels
| checkpoint | Check materials & joining methods
| checkpoint | Check pipe clips, hangers & fixings (correct size, spacing & separation)
| checkpoint | Check TMV/TV
| checkpoint | Check in-wall mixer bodies & lugged elbows
| checkpoint | Check in-wall fixture mounting brackets & concealed cisterns (if specified)
| checkpoint | Check noggins for future fixture
| checkpoint | Check sharp edge pipe protection
| checkpoint | Check heat trace (if specified)
| checkpoint | Check hot water pipe clips & thermal insulation (if specified)
| checkpoint | Check pipe colour coding
| checkpoint | Check floor/wall penetration fire proofing
| checklist | Testing Gas Pipework (Above 7kPa) |  | Testing Gas Pipework (Above 7kPa) | 59546074-f202-493e-85e9-341380b25565
| section | Details:
| checkpoint | Installation complies with latest revision of AS/NZS-5601
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Testing kit & equipment have current certification
| checkpoint | Apply test as per latest revision of AS/NZS-5601 (Note: Start & Finish testing photos to be taken only within this Checkpoint)
| checklist | Installation Backflow Prevention Device |  | Installation Backflow Prevention Device | 5aa5aa3e-d273-4e2b-9c3c-4bd98e5d1403
| section | Details:
| checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation or additional work. If not, mark as 'N/A'. You must still action all remaining checkpoints
| checkpoint | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 (Note: Installation photos to be taken only within this Checkpoint)
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | RPZD Details:
211bbd3d-a453-517c-8b72-dce8c005cf44 | textbox | RPZD Serial Number:
ab345092-20ae-55f4-a0de-df8856b63a41 | textbox | RPZD Location:
178f0064-1eea-5f8d-8353-1713fbe6487a | dropdown | RPZD Size: | 20mm,25mm,32mm,40mm,50mm,65mm,80mm,100mm,150mm,225mm,300mm
| checkpoint | Check for damage & leaks
| checkpoint | Check materials & joining methods
| checkpoint | Check alignments & levels
| checkpoint | Check pipe clips, hangers & fixings (correct size, spacing & separation)
| checkpoint | Check pressure relief pipe to tundish
| checklist | Installation Water Pressure Pump Set |  | Installation Water Pressure Pump Set | 5e688d30-78b8-4380-bbe1-9cb9719d7b0e
| section | Details:
| checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation or additional work. If not, mark as 'N/A'. You must still action all remaining checkpoints
| checkpoint | Pump Set Details:
dbb13c7b-78da-5575-b79c-e2ba3c1332f6 | dropdown | Pump Set Type: | Potable Cold Water,Potable Hot Water,Recycled Rain Water,Non-Potable Water,Other
| checkpoint | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 (Note: Installation photos to be taken only within this Checkpoint)
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Check for damage or leaks
| checkpoint | Check fixing points are secure
| checkpoint | Check level & alignment
| checkpoint | Check isolation valves & non-return valves
| checkpoint | Check feed & delivery pipe connections
| checkpoint | Check back-up water supply by-pass (if specified)
| checkpoint | Check Control Panel
| checkpoint | Check all functions & controls for correct operation
| checkpoint | Check electrical power is available
| checkpoint | Check BMS is available
| checklist | Commission Water Storage Tank |  | Commission Water Storage Tank | 7c66d866-d5b8-490e-8934-d2ac60859f99
| section | Details:
| checkpoint | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 (Note: Commissioning photos to be taken only within this Checkpoint)
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Check valves are fully open
| checkpoint | Check water level sensor set points
| checkpoint | Check tank fill valve
| checkpoint | Check low level fault
| checkpoint | Check high level fault
| checkpoint | Check passive over-flow
| checkpoint | Check statutory warning signage
| checkpoint | Check control panel display & set points
| checkpoint | Check BMS connection as specified
| checkpoint | Provide the suppliers commissioning report & all plant documentation to this checkpoint
| checklist | Installation Hot Water Unit |  | Installation Hot Water Unit | 848ee66f-37db-41eb-9935-74c9d1378ec7
| section | Details:
| checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation or additional work. If not, mark as 'N/A'. You must still action all remaining checkpoints
| checkpoint | Installation complies with current AS/NZS-3500
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Check for damage or leaks
| checkpoint | Check level & alignment
| checkpoint | Check safe tray (if specified)
| checkpoint | Check isolation valves & non-return valves
| checkpoint | Check pressure reduction valve (if specified)
| checkpoint | Check flexible connections are not twisted or kinked
| checkpoint | Check waste & water connections
| checkpoint | Check operation & controls
| checkpoint | Check water temperatures are as specified
| checkpoint | Check electrical power is available
| checkpoint | Check solar connecting pipework & fittings
| checkpoint | Check solar pump operation
| checkpoint | Check solar panels & mounting brackets
| checkpoint | Must provide photo
| checklist | Installation Gas Service (Mains/Risers) |  | Installation Gas Service (Mains/Risers) | 84f043b1-b4c9-407b-af3a-045c44f37110
| section | Details:
| checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation or additional work. If not, mark as 'N/A'. You must still action all remaining checkpoints
| checkpoint | Installation complies with latest revision of AS/NZS-5601 (Note: Installation photos to be taken only within this Checkpoint)
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Check for damage & leaks
| checkpoint | Check materials & joining methods
| checkpoint | Check crimp fittings
| checkpoint | Check alignments & levels
| checkpoint | Check pipe clips, hangers & fixings (correct size, spacing & separation)
| checkpoint | Check valves & meter assemblies
| checkpoint | Check valves & meter assemblies fixings & brackets
| checkpoint | Check pipework is clear of debris
| checkpoint | Check for cross connections
| checkpoint | Check open ends are sealed
| checkpoint | Check pipe colour coding
| checkpoint | Check pipe labelling
| checkpoint | Check floor/wall penetration fire proofing
| checklist | Fit-off Wash Basin & Tapware |  | Fit-off Wash Basin & Tapware | 8922c316-5668-47ba-8af1-c3d32f49e630
| section | Details:
| checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation or additional work. If not, mark as 'N/A'. You must still action all remaining checkpoints
| checkpoint | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 (Note: Fit-off photos to be taken only within this Checkpoint)
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Check for damage or leaks
| checkpoint | Check fixing points are secure
| checkpoint | Check level & alignment
| checkpoint | Check mini stops
| checkpoint | Check flexible connections are not twisted or kinked
| checkpoint | Check special DDA accessories (if applicable)
| checkpoint | Check waste & trap connections
| checkpoint | Check all functions, controls & remote sensors for correct operation
| checkpoint | Check trap is clear of debris
| checkpoint | Check caulking
| checklist | Fit-off Tundish |  | Fit-off Tundish | 8eb92d2e-e57b-4f1e-a2fc-0968a0dbbdee
| section | Details:
| checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation or additional work. If not, mark as 'N/A'. You must still action all remaining checkpoints
| checkpoint | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 (Note: Fit-off photos to be taken only within this Checkpoint)
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Check for damage or leaks
| checkpoint | Check fixing points are secure
| checkpoint | Check level & alignment
| checkpoint | Check waste & trap connections
| checkpoint | Check trap is clear of debris
| checklist | Commission Rain Water Pressure Pump Set |  | Commission Rain Water Pressure Pump Set | 9a845d3b-4dfa-4f67-b03d-05cf0cd80aa9
| section | Details:
| checkpoint | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 (Note: Commissioning photos to be taken only within this Checkpoint)
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Check water supply fault
| checkpoint | Check pump motor rotation
| checkpoint | Check dry pump fault
| checkpoint | Check auto pump roll-over
| checkpoint | Check ultra violet lamps
| checkpoint | Check filters & backwash
| checkpoint | Check back-up water supply
| checkpoint | Check pump package operational set points
| checkpoint | Check control panel display & set points
| checkpoint | Check fault warning alarms
| checkpoint | Check BMS connection as specified
| checkpoint | Provide the suppliers commissioning report & all plant documentation to this checkpoint
| checklist | Installation Stack & Vent |  | Installation Stack & Vent | 9fda02f2-bfe5-4c3e-8c5b-df1f275f0a8b
| section | Details:
| checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation or additional work. If not, mark as 'N/A'. You must still action all remaining checkpoints
| checkpoint | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 (Note: Installation photos to be taken only within this Checkpoint)
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Check for damage & leaks
| checkpoint | Check materials & joining methods
| checkpoint | Check alignments & levels
| checkpoint | Check pipe clips, hangers & fixings (correct size, spacing & separation)
| checkpoint | Check expansion joints and anchor points
| checkpoint | Check inspection openings
| checkpoint | Check pipework is clear of debris
| checkpoint | Check open ends are sealed
| checkpoint | Check acoustic insulation (if specified)
| checkpoint | Check pipe labelling
| checkpoint | Check floor/wall penetration fire proofing
| checkpoint | Check vents are run to atmosphere and weather proofing is complete
| checklist | Fit-off Bath & Tapware |  | Fit-off Bath & Tapware | a046225a-db24-4507-adc0-eb47efbc2ef9
| section | Details:
| checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation or additional work. If not, mark as 'N/A'. You must still action all remaining checkpoints
| checkpoint | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 (Note: Fit-off photos to be taken only within this Checkpoint)
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Check for damage or leaks
| checkpoint | Check fixing points are secure
| checkpoint | Check level & alignment
| checkpoint | Check wall plates, mixers & diversion valves
| checkpoint | Check outlets, wall rails & hand showers
| checkpoint | Check special DDA accessories (if applicable)
| checkpoint | Check waste & trap connections
| checkpoint | Check all functions & controls for correct operation
| checkpoint | Check floor grate level & alignment
| checkpoint | Check trap is clear of debris
| checkpoint | Check caulking
| checklist | Commission Water Pressure Pump Set |  | Commission Water Pressure Pump Set | a63989ca-3594-4287-ae7f-9b31e9df3efa
| section | Details:
| checkpoint | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 (Note: Commissioning photos to be taken only within this Checkpoint)
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Check water supply fault
| checkpoint | Check pump motor rotation
| checkpoint | Check dry pump fault
| checkpoint | Check auto pump roll-over
| checkpoint | Check pump package operational set points
| checkpoint | Check control panel display & set points
| checkpoint | Check fault warning alarms
| checkpoint | Check BMS connection as specified
| checkpoint | Provide the suppliers commissioning report & all plant documentation to this checkpoint
| checklist | Testing Gas Pipework (7kPa or Less) |  | Testing Gas Pipework (7kPa or Less) | aaf66933-4ded-44d4-b87a-f448db361fff
| section | Details:
| checkpoint | Installation complies with latest revision of AS/NZS-5601
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Testing kit & equipment have current certification
| checkpoint | Apply test as per latest revision of AS/NZS-5601 (Note: Start & Finish testing photos to be taken only within this Checkpoint)
| checklist | Commission Drainage Pump Station |  | Commission Drainage Pump Station | ae822425-e27a-4d75-9ef1-8996bafa5686
| section | Details:
| checkpoint | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 (Note: Commissioning photos to be taken only within this Checkpoint)
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Check lifting rails & chains
| checkpoint | Check water level sensor set points
| checkpoint | Check pump motor rotation
| checkpoint | Check dry pump fault
| checkpoint | Check low water level fault
| checkpoint | Check high water level fault
| checkpoint | Check auto pump roll-over
| checkpoint | Check pump package operational set points
| checkpoint | Check control panel display & set points
| checkpoint | Check fault warning alarms
| checkpoint | Check BMS connection as specified
| checkpoint | Provide the suppliers commissioning report & all plant documentation to this checkpoint
| checklist | Installation Pump Station or Tank (In-ground) |  | Installation Pump Station or Tank (In-ground) | b20f6f43-1fc3-421d-98ea-b79e2301b0fe
| section | Details:
| checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation or additional work. If not, mark as 'N/A'. You must still action all remaining checkpoints
| checkpoint | Plant & Equipment Installation checked off as below
| checkpoint | Installation complies with current AS/NZS-3500
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Check for damage & leaks
| checkpoint | Check materials & joining methods
| checkpoint | Check alignments & levels
| checkpoint | Check bedding & clearances
| checkpoint | Check connections to pits, tanks, & pump stations, etc
| checkpoint | Check covers, venting, & electrical conduits, etc
| checkpoint | Check pipework & traps are clear of debris
| checkpoint | Check inspection openings
| checkpoint | Check open ends are sealed
| checkpoint | If trench is to be left open, make ensure pipe can not float
| checkpoint | Check trench backfill & compaction
| checkpoint | Must provide photo
| checklist | Fit-off Hose Tap |  | Fit-off Hose Tap | b3dae27a-8647-47d9-a3a0-caba4c310e87
| section | Details:
| checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation or additional work. If not, mark as 'N/A'. You must still action all remaining checkpoints
| checkpoint | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 (Note: Fit-off photos to be taken only within this Checkpoint)
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Check for damage or leaks
| checkpoint | Vacuum breaker fitted
| checkpoint | Check pipe colour coding
| checklist | Fit-off Dishwasher |  | Fit-off Dishwasher | b6153fd2-620c-42d3-819c-222904941673
| section | Details:
| checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation or additional work. If not, mark as 'N/A'. You must still action all remaining checkpoints
| checkpoint | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 (Note: Fit-off photos to be taken only within this Checkpoint)
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Check for damage or leaks
| checkpoint | Check fixing points are secure
| checkpoint | Check level & alignment
| checkpoint | Check isolation valves & non-return valves
| checkpoint | Check pressure reduction valve (if specified)
| checkpoint | Check flexible waste & water hoses are not twisted or kinked
| checkpoint | Check flexible waste hose height under cabinet
| checkpoint | Check waste connection to trap
| checkpoint | Check all functions & controls for correct operation
| checklist | Fit-off Gas Appliance |  | Fit-off Gas Appliance | b6c66481-b555-4898-90a0-ea4d082da158
| section | Details:
| checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation or additional work. If not, mark as 'N/A'. You must still action all remaining checkpoints
| checkpoint | Installation complies with latest revision of AS/NZS-5601 (Note: Fit-off photos to be taken only within this Checkpoint)
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Check for damage or leaks
| checkpoint | Check fixing points are secure
| checkpoint | Check level & alignment is correct
| checkpoint | Check surrounding wall material is fire rated
| checkpoint | Check distance from cook-top to range hood complies with manufacturer specification
| checkpoint | Check surrounding walls to closest burner distance complies with manufacturer specification
| checkpoint | Check flexible connections are not twisted or kinked
| checkpoint | Check gas isolation valve
| checkpoint | Check gas pressure regulator
| checkpoint | Check all functions & controls for correct operation
| checklist | Installation Downpipe & Overflow |  | Installation Downpipe & Overflow | b9273607-1758-4cd4-8876-9c87ba4a9d80
| section | Details:
| checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation or additional work. If not, mark as 'N/A'. You must still action all remaining checkpoints
| checkpoint | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 (Note: Installation photos to be taken only within this Checkpoint)
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Check for damage & leaks
| checkpoint | Check materials & joining methods
| checkpoint | Check alignments & levels
| checkpoint | Check pipe clips, hangers & fixings (correct size, spacing & separation)
| checkpoint | Check expansion joints and anchor points
| checkpoint | Check connection to roof & floor outlets
| checkpoint | Check inspection openings
| checkpoint | Check pipework is clear of debris
| checkpoint | Check open ends are sealed
| checkpoint | Check acoustic insulation (if specified)
| checkpoint | Check pipe labelling
| checkpoint | Check floor/wall penetration fire proofing
| checklist | Commission Fixture Group |  | Commission Fixture Group | c7bf1dc4-adf2-4f26-aa81-5a98e46c834c
| section | Details:
| checkpoint | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 &/or AS/NZS-5601 (Note: Commissioning photos to be taken only within this Checkpoint)
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Check for any damage, leaks or missing components
| checkpoint | Check level & alignment of all fixtures
| checkpoint | Check all fixtures, seats & covers are securely fastened
| checkpoint | Check all valves are fully open
| checkpoint | Check all flexible connections are not twisted or kinked
| checkpoint | Check for water for cross connections
| checkpoint | Check fixture wastes & connections
| checkpoint | Check pipework & all traps are clear of debris
| checkpoint | Check AAV is installed to correct height
| checkpoint | Check future connection water valves are securely capped
| checkpoint | Check TV do not exceed 50°C
| checkpoint | Check TMV do not exceed 45°C
| checkpoint | Check dishwasher function
| checkpoint | Check gas valves & regulators
| checkpoint | Check all gas burner functions
| checkpoint | Check balcony hose tap
| checkpoint | Check balcony floor grate & downpipe
| checkpoint | Check all fixtures & tapware are operating as specified
| checkpoint | Confirm area has been left clean
| checklist | Installation Pump Station |  | Installation Pump Station | c9b5c128-9d56-46e1-9ef2-417860afc502
| section | Details:
| checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation or additional work. If not, mark as 'N/A'. You must still action all remaining checkpoints
| checkpoint | Pump Station Details:
21fbf836-4d5d-5ba4-aad0-386cb8f69d1a | dropdown | Pump Station Type: | Sewer Above Ground,Stormwater Above Ground,Sewer In-ground,Stormwater In-ground,Other
| checkpoint | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 (Note: Installation photos to be taken only within this Checkpoint)
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Check for damage & leaks
| checkpoint | Check materials & joining methods
| checkpoint | Check alignments & levels
| checkpoint | Check bedding & clearances
| checkpoint | Check inlet/outlet connections & vents
| checkpoint | Check covers, venting, & electrical conduits, etc
| checkpoint | Check pipework & traps are clear of debris
| checkpoint | Check inspection openings
| checkpoint | Check open ends are sealed
| checkpoint | Check trench backfill & compaction
| checklist | Fit-off Toilet & Cistern |  | Fit-off Toilet & Cistern | cc3d97de-4fb4-42f3-8bc6-805b3d4362f8
| section | Details:
| checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation or additional work. If not, mark as 'N/A'. You must still action all remaining checkpoints
| checkpoint | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 (Note: Fit-off photos to be taken only within this Checkpoint)
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Check for damage or leaks
| checkpoint | Check fixing points are secure
| checkpoint | Check level & alignment
| checkpoint | Check mini stops
| checkpoint | Check flexible connections are not twisted or kinked
| checkpoint | Check special DDA accessories (if applicable)
| checkpoint | Check all functions, controls & remote sensors for correct operation
| checkpoint | Check trap is clear of debris
| checkpoint | Check caulking
| checklist | Installation Pump Line |  | Installation Pump Line | cc45c0d0-7895-42cb-91f1-461373479105
| section | Details:
| checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation or additional work. If not, mark as 'N/A'. You must still action all remaining checkpoints
| checkpoint | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 (Note: Installation photos to be taken only within this Checkpoint)
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Check for damage & leaks
| checkpoint | Check materials & joining methods
| checkpoint | Check alignments & levels
| checkpoint | Check pipe clips, hangers & fixings (correct size, spacing & separation)
| checkpoint | Check pipework is clear of debris
| checkpoint | Check open ends are sealed
| checkpoint | Check pipe labelling
| checkpoint | Check floor/wall penetration fire proofing
| checklist | Testing Potable Water Pipework |  | Testing Potable Water Pipework | cf1501ba-8925-4a18-b825-103f619430e2
| section | Details:
| checkpoint | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Check installation is clean and ready for testing
| checkpoint | Check all valves, mixers, meters, etc , in the test zone are rated for the test pressure required
| checkpoint | Testing kit & equipment have current certification
| checkpoint | Apply test as per latest revision of AS/NZS-3500 Part 1 (Note: Start & Finish testing photos to be taken only within this Checkpoint)
| checklist | Fit-off Laundry Trough & Tapware |  | Fit-off Laundry Trough & Tapware | d018fd7b-20fa-4762-b43e-31e8728fba8f
| section | Details:
| checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation or additional work. If not, mark as 'N/A'. You must still action all remaining checkpoints
| checkpoint | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 (Note: Fit-off photos to be taken only within this Checkpoint)
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Check for damage or leaks
| checkpoint | Check fixing points are secure
| checkpoint | Check level & alignment
| checkpoint | Check mini stops
| checkpoint | Check flexible connections are not twisted or kinked
| checkpoint | Check waste & water connections
| checkpoint | Check stop valves for future connections are capped
| checkpoint | Check all functions & controls for correct operation
| checkpoint | Check trap is clear of debris
| checkpoint | Check caulking
| checklist | Installation Penetration |  | Installation Penetration | d6de911b-41bd-4bc5-b296-330c5ed25230
| section | Details:
| checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation or additional work. If not, mark as 'N/A'. You must still action all remaining checkpoints
| checkpoint | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 (Note: Installation photos to be taken only within this Checkpoint)
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Check for damage & missing penos
| checkpoint | Check penetration sizes, locations & finished levels are correct
| checkpoint | Check fire collars types & ratings are correct
| checkpoint | Check blank sleeves are correct
| checkpoint | Check cast-in outlets location & finished levels are correct
| checkpoint | Check open ends are sealed
| checklist | Installation Water Service (Mains/Risers) |  | Installation Water Service (Mains/Risers) | d8784ba7-66f0-4777-8136-e22959cf8456
| section | Details:
| checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation or additional work. If not, mark as 'N/A'. You must still action all remaining checkpoints
| checkpoint | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 (Note: Installation photos to be taken only within this Checkpoint)
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Check for damage & leaks
| checkpoint | Check crimp fittings
| checkpoint | Check materials & joining methods
| checkpoint | Check alignments & levels
| checkpoint | Check pipe clips, hangers & fixings (correct size, spacing & separation)
| checkpoint | Check expansion joints and anchor points
| checkpoint | Check isolation & pressure reduction valves & meter assemblies
| checkpoint | Check hot water pipe clips & thermal insulation (if specified)
| checkpoint | Check pipework is clear of debris
| checkpoint | Check for cross connections
| checkpoint | Check open ends are sealed
| checkpoint | Check pipe labelling
| checkpoint | Check pipe colour coding
| checkpoint | Check floor/wall penetration fire proofing
| checklist | Fit-off Shower & Tapware |  | Fit-off Shower & Tapware | dbd721fd-cacb-4ea4-ad56-8d68f4fca749
| section | Details:
| checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation or additional work. If not, mark as 'N/A'. You must still action all remaining checkpoints
| checkpoint | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 (Note: Fit-off photos to be taken only within this Checkpoint)
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Check for damage or leaks
| checkpoint | Check fixing points are secure
| checkpoint | Check level & alignment
| checkpoint | Check wall plates, mixers & diversion valves
| checkpoint | Check outlets, wall rails & hand showers
| checkpoint | Check special DDA accessories (if applicable)
| checkpoint | Check waste & trap connections
| checkpoint | Check all functions & controls for correct operation
| checkpoint | Check floor grate level & alignment
| checkpoint | Check trap is clear of debris
| checkpoint | Check caulking
| checklist | Commission Rain Water Diversion Valve |  | Commission Rain Water Diversion Valve | e1112d12-614d-44e9-bd85-3ca0d17c7b0a
| section | Details:
| checkpoint | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 (Note: Commissioning photos to be taken only within this Checkpoint)
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Check valve operation
| checkpoint | Check valve defaults to storm-water if no power or tank full
| checkpoint | Check control panel display & set points
| checkpoint | Check BMS connection as specified
| checkpoint | Provide the suppliers commissioning report & all plant documentation to this checkpoint
| checklist | Testing Drainage Pipework (Air Test) |  | Testing Drainage Pipework (Air Test) | e167cbe3-2f78-4149-9957-420b502b75bc
| section | Details:
| checkpoint | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Testing kit & equipment have current certification
| checkpoint | Apply test as per latest revision of AS/NZS-3500 Part 2 (Note: Start & Finish testing photos to be taken only within this Checkpoint)
| checklist | Installation Waste Water Tank |  | Installation Waste Water Tank | e30ba22e-2191-498e-abe6-417a0c2bd545
| section | Details:
| checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation or additional work. If not, mark as 'N/A'. You must still action all remaining checkpoints
| checkpoint | Tank Details:
a3e2d56c-ba15-58b5-8c8e-8177203a7cf3 | dropdown | Tank Type: | Grease Interceptor,Neutralizing Pit,POI Interceptor,SW Detention Tank,SW Filtration Pit,Other
| checkpoint | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 (Note: Installation photos to be taken only within this Checkpoint)
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Check for damage & leaks
| checkpoint | Check materials & joining methods
| checkpoint | Check alignments & levels
| checkpoint | Check bedding & clearances
| checkpoint | Check inlet/outlet connections & vents
| checkpoint | Check covers, venting, & electrical conduits, etc
| checkpoint | Check pipework & traps are clear of debris
| checkpoint | Check inspection openings
| checkpoint | Check open ends are sealed
| checkpoint | Check trench backfill & compaction
| checkpoint | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Check installation is clean and ready for testing
| checkpoint | Apply test as per latest revision of AS/NZS-3500 Part 2 (Note: Start & Finish testing photos to be taken only within this Checkpoint)
| checklist | Cast-in Waste & Vent |  | Cast-in Waste & Vent | e7b8ad8d-224c-4864-9ac8-de44af55622e
| section | Details:
| checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation or additional work. If not, mark as 'N/A'. You must still action all remaining checkpoints
| checkpoint | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 (Note: Installation photos to be taken only within this Checkpoint)
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Check for damage & leaks
| checkpoint | Check materials & joining methods
| checkpoint | Check alignments & levels
| checkpoint | Check pipe clips, hangers & fixings (correct size, spacing & separation)
| checkpoint | Check pipework & traps are clear of debris
| checkpoint | Check pipe expansion lagging
| checkpoint | Check open ends are sealed
| checklist | Installation Hot Water Plant/Unit |  | Installation Hot Water Plant/Unit | ed552afd-b058-48fe-be33-40ebdf0e30fd
| section | Details:
| checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation or additional work. If not, mark as 'N/A'. You must still action all remaining checkpoints
| checkpoint | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4, &/or AS/NZS-5601 (Note: Installation photos to be taken only within this Checkpoint)
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Check for damage or leaks
| checkpoint | Check level & alignment
| checkpoint | Check safe tray (if specified)
| checkpoint | Check isolation valves & non-return valves
| checkpoint | Check pressure reduction valve (if specified)
| checkpoint | Check flexible connections are not twisted or kinked
| checkpoint | Check waste & water connections
| checkpoint | Check all functions & controls for correct operation
| checkpoint | Check water temperatures are as specified
| checkpoint | Check electrical power is available
| checkpoint | Check solar panels & mounting brackets
| checkpoint | Check solar connecting pipework & fittings
| checkpoint | Check solar pump operation
| checklist | Fit-off Kitchen Sink & Tapware |  | Fit-off Kitchen Sink & Tapware | efc54511-c355-4602-8535-1bfa42bad3c8
| section | Details:
| checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation or additional work. If not, mark as 'N/A'. You must still action all remaining checkpoints
| checkpoint | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 (Note: Fit-off photos to be taken only within this Checkpoint)
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Check for damage or leaks
| checkpoint | Check fixing points are secure
| checkpoint | Check level & alignment
| checkpoint | Check mini stops
| checkpoint | Check flexible connections are not twisted or kinked
| checkpoint | Check waste & trap connections
| checkpoint | Check dishwasher waste & water connections
| checkpoint | Check stop valves for future connections are capped
| checkpoint | Check all functions & controls for correct operation
| checkpoint | Check trap is clear of debris
| checkpoint | Check caulking
| checklist | Testing Drainage Pipework (Hydrostatic Test) |  | Testing Drainage Pipework (Hydrostatic Test) | f3156ad0-2f49-458a-88e3-a6710b0b17a6
| section | Details:
| checkpoint | Installation complies with current AS/NZS-3500
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Check installation is clean and ready for testing
| checkpoint | Apply water pressure test as per AS/NZS-3500
| checkpoint | Must provide test start & finish photos
| checklist | Commission Reduced Pressure Zone Device |  | Commission Reduced Pressure Zone Device | f6d51b4e-29c9-44c2-8c13-3766a80c9f8e
| section | Details:
| checkpoint | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 (Note: Commissioning photos to be taken only within this Checkpoint)
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | RPZD Details:
d7ca90c7-008e-5369-a1a7-7c4540d72953 | textbox | RPZD Serial Number:
4b7cc0ea-c1b3-53c6-b662-3a63abc77882 | textbox | RPZD Location:
35e4ceff-f4cb-5455-8f15-31464e541550 | dropdown | RPZD Size: | 20mm,25mm,32mm,40mm,50mm,65mm,80mm,100mm,150mm,225mm,300mm
| checkpoint | Check valves are fully open
| checkpoint | Check inlet water pressure does not exceed manufacturer specification
| checkpoint | Check outlet water pressure is as per manufacturer specification
| checkpoint | Check exhaust tundish drain sized to accept a full flush
| checkpoint | Provide the commissioning report & all plant documentation to this checkpoint
| checklist | Installation Water Service (In-ground) |  | Installation Water Service (In-ground) | f9a49558-0c5e-4511-81ff-522eb1bd5cf4
| section | Details:
| checkpoint | Mark this checkpoint as 'FAIL' if you think this task should be a variation or additional work. If not, mark as 'N/A'. You must still action all remaining checkpoints
| checkpoint | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 (Note: Installation photos to be taken only within this Checkpoint)
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Check for damage & leaks
| checkpoint | Check materials & joining methods
| checkpoint | Check alignments & levels
| checkpoint | Check bedding & clearances
| checkpoint | Check valve connections
| checkpoint | Check pipework is clear of debris
| checkpoint | Check open ends are sealed
| checkpoint | Check pipe colour coding
| checkpoint | Check pipe trench marking tape (if specified)
| checkpoint | Check trench backfill & compaction
| checklist | Commission Hot Water Generating Plant |  | Commission Hot Water Generating Plant | fc397b60-fd8d-4880-924e-6d4959b69e93
| section | Details:
| checkpoint | Installation complies with latest revision of AS/NZS-3500 Parts 1 - 4 &/or AS/NZS-5601 (Note: Commissioning photos to be taken only within this Checkpoint)
| checkpoint | Installation complies with current drawings & specifications
| checkpoint | All pipes, fittings, materials & associated systems were used in accordance to manufacturer instructions
| checkpoint | Check valves are fully open
| checkpoint | Check water filters are clean
| checkpoint | Check gas supply
| checkpoint | Check circulating pumps
| checkpoint | Check flue operation
| checkpoint | Check system auto start
| checkpoint | Check flow & return temperatures
| checkpoint | Check control panel display & set points
| checkpoint | Check BMS connection (if specified)
| checkpoint | Provide the suppliers commissioning report & all plant documentation to this checkpoint