## Master List Templates
Id | Type | Name | Values | Prompting Name
9b1b0614-c027-54d0-bc89-019256d340d5 | checklist | Add Drainage checks |  | Drainage
f339f425-bcec-5e00-916a-b230da94676b | section | Storm Water
b519a3d6-528e-56ad-9cbe-1d5aa50e8c4c | checkpoint | Plans correct issue and construction set
5d802f8a-4408-5081-8d90-e7297e2d8141 | checkpoint | Check set out from builders
1c35e006-e055-56c0-8759-1a389e6072e2 | checkpoint | Check Plans for correct sizing and pipe material
82018cb6-2f71-5667-bb4d-d3de9a34628e | checkpoint | All Falls achieved as per plans
f4cbcd85-de33-5d5a-9021-8783ca5a393f | checkpoint | All Manholes hauched as per code
5c466659-68a6-5586-9936-3b8d53c51a11 | checkpoint | All Cesspits, Manholes installed to correct heights
9c6eda90-de39-562e-b6aa-41edacf4e03e | checkpoint | All Trenches compacted with compactor
cbda2a42-9dd8-5a20-baa5-477be756ed81 | checkpoint | Subgrade Scala test ever 10m - 3 Blows per 100mm
4ad2e5a9-6125-526c-89d9-fa7bb2201af9 | checkpoint | Backfill in layers of 300mm and test every 10m - 3 Blows per 100mm
03d19b84-64a3-504c-9a0e-0dd7b9ab7639 | checkpoint | Pipes tested for inspection
caf0ab4f-382f-5f2e-a615-01e18f361472 | checkpoint | Rainwater Tank installed as per engineers report
484e0585-569a-57ba-acaa-547731a10b02 | checkpoint | Photos Taken
6dd94540-b727-577f-a50a-65cdd18ab664 | checkpoint | Inspection passed
0df12610-e59e-5413-a836-bddeb60ce91b | checkpoint | Engineer Inspected
031ca681-bc70-5712-ab0f-edb8818a4f08 | checkpoint | Mark up drawings Done
3d4d185c-07ae-54b0-be6d-8bfc78a811bf | section | Sewer
698e34ba-edf9-4f20-8ac2-c8509e9163ce | checkpoint | Plans correct issue and construction set
4e982c04-0a64-4e95-8d9b-9440912b7eb9 | checkpoint | Check Plans for correct sizing and pipe material
235ab823-5dad-4186-bdf2-3d001cfd1ab6 | checkpoint | All Falls achieved as per plans
f9253ff0-759f-4090-8c06-f1df926299c1 | checkpoint | All Manholes hauched as per code
415bfd0f-ce08-553c-8553-52583790a790 | checkpoint | All Manholes installed to correct heights
c9923cfb-dc72-4901-918b-92070b0d3ebc | checkpoint | All Trenches compacted with compactor
d672d884-43c1-4b42-a434-efe2a24ea227 | checkpoint | Subgrade Scala test ever 10m - 3 Blows per 100mm
65099e60-5d0a-4ed9-9e9f-d3483ce32fef | checkpoint | Backfill in layers of 300mm and test every 10m - 3 Blows per 100mm
a8f1670d-5e2f-5591-8e2d-d85e5d0aa20f | checkpoint | All ORG and RE installed as per plan
07bc8982-ff21-4aec-9ef8-2650b94303fb | checkpoint | Pipes tested for inspection
e0ef6ab6-6327-45fc-b64d-5572d6597a31 | checkpoint | Inspection passed
e3e6f59c-128b-475f-abf9-b59907a26be8 | checkpoint | Mark up drawings Done
2c07aa1c-17ef-4666-a8a2-a61ce3864ac2 | checkpoint | Photos Taken
5907f8f9-ea3e-5c11-963b-cab22210e551 | section | Water Mains and Infrastructure
b0dfeb94-9514-4621-9740-78b1dfbb4f04 | checkpoint | Plans correct issue and construction set
4be3874d-4db8-4ff6-b0b7-b69076223aab | checkpoint | Check Plans for correct sizing and pipe material
a349c3a7-160f-5434-832e-1837ac52629a | checkpoint | EF welding completed by a certified welder
3addc341-b291-42cc-8d75-2e393fbf5a13 | checkpoint | Subgrade Scala test ever 10m - 3 Blows per 100mm
3ed2200d-5e56-404f-a555-8f8c88f7392b | checkpoint | Backfill in layers of 300mm and test every 10m - 3 Blows per 100mm
003e33ad-2dfe-5495-ba85-654ce35af18a | checkpoint | Water Main flushed ready for connection - Fire Main 1600L/Min at 250KPA
76eef447-2c8f-450b-8f9e-0745216e83bd | checkpoint | Pipes tested for inspection
89a7df22-a89f-5112-b51f-ceff98bce047 | checkpoint | Chlorination of Pipe work completed as per TCC IDC Code
c40cf8c6-446a-5830-8033-8785200332f5 | checkpoint | E Coli Test done and Passed
8bafab90-62cc-5737-9cfc-e5761dd4c7a7 | checkpoint | Warning tape installed
d669af90-dbd6-45b7-a481-9e73bc51a2a8 | checkpoint | All Trenches compacted with compactor
c02670d9-ddba-499f-b0b8-ee21f0d6b763 | checkpoint | Inspection passed
a1161da3-c3ef-45d8-a6e6-7c4ed18aa0da | checkpoint | Mark up drawings Done
e4370a67-8b40-4200-a106-c6231c13d615 | checkpoint | Photos Taken
5b84a8b0-d5ba-56cc-b499-4286ca5f6a9c | section | Dewatering
1b3dba13-1e08-597c-beec-8f42b851d310 | checkpoint | Pumps supplied able to do flow rates required
cfcb7907-0ac8-5bb8-8afd-91e9d4a22632 | checkpoint | Wells installed to heights slightly lower than cut
1eacd13a-65fb-5d2a-baf9-1d5c8d2a97bc | checkpoint | Storage tanks install and linked dup to prevent overflow to street
7fff73ab-f219-5ca1-acf4-63c0a99c979e | checkpoint | Valves installed on tanks for Sludge removal
6ae7f704-de62-53c4-8671-eaab68f7e4f3 | checkpoint | Water Quanilty Monitored and checked daily
0ed9bbc2-d6fa-5dad-87fb-a77c424b308f | checkpoint | Balance pipes installed between tanks
9bb5a2c2-a79f-530d-b0f4-e42471b14282 | checkpoint | Water Flow rate checked daily
22832c03-201d-5456-b8a3-c7517f7ffd70 | checkpoint | Power supply checked for reliability
4e6aeccd-9b01-5d9e-8187-6a6c32fc69ad | checklist | Add First Fix checks |  | First Fix
67403ceb-410e-557f-a639-fbbb164673fe | section | Preinstall QA
7ebf3446-7d4c-542e-b6e3-d260b59f5278 | checkpoint | Substrate acceptable
d3924e5c-10b8-5f96-aac2-04ae27fdf756 | checkpoint | Area accessible and ok to begin work
b519a3d6-528e-56ad-9cbe-1d5aa50e8c4c | checkpoint | Plans correct issue and construction set
1c35e006-e055-56c0-8759-1a389e6072e2 | checkpoint | Check Plans for correct sizing and pipe material
9c4a0849-006b-5c54-b3f5-93291e700cff | section | First fix checks
f88c98b4-2897-5da9-bf01-a34faf15e01c | checkpoint | Sanitary fixtures and fittings specifications received for set out
8b6e4c2d-5c17-59ff-9861-a6d2cba1ad29 | checkpoint | All Pipes silicone though noggs
e2fac646-aa13-593e-93da-25a074c06498 | checkpoint | Vents install though roof
8499b1f7-f600-5d6a-b36a-27edc628331a | checkpoint | All stud stiffeners installed
8737215a-f411-55d7-856f-b73d4217a172 | checkpoint | Marshall flashings installed
19f03afc-47da-5063-97de-84b22ec80351 | checkpoint | All pipes pressure tested to 1500KPA (fusiotherm refer to test procedures)
a9c61512-3262-5000-87bb-9bb03e8abed6 | checkpoint | Gas sized and install as per NZS 5061
243b44cd-4da6-53d1-94f2-13579e0035b7 | checkpoint | Gas tested to 7KPA or Greater
0f81be15-6234-5b18-a9d4-f5b11ffc6998 | checkpoint | Gas piping material correct for installation
bf827ca5-4528-5458-9e02-0b9829b8eece | checkpoint | Noggs installed for fixing of sanitary fixtures and fittings
7ff22ae7-5c2a-5825-834e-b7c3580f4166 | section | Handover checks
295b6a1e-b413-5288-bb93-ddbb9aa5860c | checkpoint | Photos Taken & attached
6dd94540-b727-577f-a50a-65cdd18ab664 | checkpoint | Inspection passed
e0940c56-aadf-54ce-872c-c28e08319f7e | checkpoint | Work completed as per spec and tidied up
29d0cb0e-4fd0-56b2-b1df-99473810bbd4 | checklist | Add Penetrations |  | Fire Penetration
66f923c7-d47c-5017-826e-45f829e9012b | checkpoint | Wraps/ Collars/ Cast in installed
8199f420-03f7-59bf-a525-998854f39b02 | checkpoint | Seal approved for the wall / floor type
ad882e83-9312-53bc-8a65-eae23d71c61d | checkpoint | Seal approved for the penetration & its application
3c489df3-5484-5afe-9bb1-509da158ef57 | checkpoint | Are pipes supported as specified by the manufacturer
d79b1047-20af-5b41-a0a4-119172f4a4ea | checkpoint | Sealed is installed as per specification
b967e783-e213-53da-99c7-1ac3df1ea6c0 | checkpoint | Penetration Label includes
7fd27c99-1143-56a8-80bd-2f36076072ed | checklist | Add Second Fix checks |  | Second Fix
67403ceb-410e-557f-a639-fbbb164673fe | section | Preinstall QA
7ebf3446-7d4c-542e-b6e3-d260b59f5278 | checkpoint | Substrate acceptable
d3924e5c-10b8-5f96-aac2-04ae27fdf756 | checkpoint | Area accessible and ok to begin work
7f5ba437-9c5f-52c7-8692-7ed0683aa6c9 | section | Second fix checks
9ba3cff7-806a-53a3-8918-34e3714daac4 | checkpoint | Fixtures and fittings checked for damage
716ccc93-a571-58ab-adaf-dd4830188de6 | checkpoint | Flanges installed on all penetrations
c823b7dd-47ba-5b7b-9f9a-0b3071f1b3b5 | checkpoint | All fixtures sealed with silicone as required
0a3f255d-b717-565e-b114-caea5f3c57e8 | checkpoint | All fittings checked for leaks
0b3792ac-b878-5789-904d-0d36c3dd6cbf | checkpoint | Hot Water system commissioned
4387f256-0c97-519e-b1f9-68b04374ae38 | checkpoint | System commissioned
7ff22ae7-5c2a-5825-834e-b7c3580f4166 | section | Handover checks
295b6a1e-b413-5288-bb93-ddbb9aa5860c | checkpoint | Photos Taken & attached
e0940c56-aadf-54ce-872c-c28e08319f7e | checkpoint | Work completed as per spec and tidied up
e2d2c064-0b94-5e82-afdd-45f47851eecf | checklist | Add Underfloor checks |  | Underfloor
67403ceb-410e-557f-a639-fbbb164673fe | section | Preinstall QA
7ebf3446-7d4c-542e-b6e3-d260b59f5278 | checkpoint | Substrate acceptable
d3924e5c-10b8-5f96-aac2-04ae27fdf756 | checkpoint | Area accessible and ok to begin work
b519a3d6-528e-56ad-9cbe-1d5aa50e8c4c | checkpoint | Plans correct issue and construction set
5d802f8a-4408-5081-8d90-e7297e2d8141 | checkpoint | Check set out from builders
f1ec9d1b-37b5-5052-baa2-7df190e0912f | checkpoint | Subgrade and bedding detail as per Plans - Gap 20/ Sand
5661861a-3ac3-5aca-aa39-b57fb36ddb3a | checkpoint | Testing of subgrade required
4715d590-8542-52a8-a3a0-26b9d7fa887c | checkpoint | Wrapped all pipe work with a min of 25mm though concrete areas
cae74d21-640e-5bd6-b2b9-ebcf1bc316b1 | section | Install QA
6e40e479-5191-5707-bd1d-8e54b2cdadde | checkpoint | Hot Water System (relief drain)
00ee43a7-73f6-55fa-ac4f-6d78704d6cc4 | checkpoint | Drains laid to correct falls
732c6cc9-e7d1-596d-a906-9abb5c05c856 | checkpoint | Pipes wrapped though floor
03d19b84-64a3-504c-9a0e-0dd7b9ab7639 | checkpoint | Pipes tested for inspection
7ff22ae7-5c2a-5825-834e-b7c3580f4166 | section | Handover checks
295b6a1e-b413-5288-bb93-ddbb9aa5860c | checkpoint | Photos Taken & attached
6dd94540-b727-577f-a50a-65cdd18ab664 | checkpoint | Inspection passed
f795b8c7-7fd4-5714-8dfb-4a005a6538b9 | checkpoint | Water needed in floor for 1st fix
e0940c56-aadf-54ce-872c-c28e08319f7e | checkpoint | Work completed as per spec and tidied up
82b2c970-304b-5a20-a04a-16fd9f5eb3ae | checklist | Add Variation |  | Variation Details -
af43077e-903d-5d88-8da8-e50a24463098 | checkpoint | Variation Details Approved
1d219079-d951-5e85-8d55-3db63943c050 | textbox | Reference/Drawing/Instruction Number
dd08d29f-e2d7-502d-b954-98262563c270 | textbox | Variation Area
35251c75-59d5-5066-bc14-5e905bb08899 | textbox | Materials & labour breakdown
822653e1-1a8d-5c1e-9229-bee00e9e7e9a | signoff | Request Variation Acknowledgement
8d20db40-ceeb-512f-b832-5bd4676ee2c5 | checkpoint | Variation Completed
d302c95c-762e-5e5c-a32b-f0e8b483eb06 | signoff | Request Variation Signoff
0fb3504c-8658-53c3-9433-34f0c1a031f7 | checklist | H&S Toolbox Talks |  | Toolbox Checklist
8111ace1-1386-5c1f-8290-3df28e3c8d3f | section | Details
3a0365f7-d8cf-5281-8449-db2471d5f49b | checkpoint | Details Complete
09020810-29af-59cb-8738-ed3c206406fa | textbox | Office location:
22438a23-102d-5a40-9f75-a5112c4f34c4 | textbox | Who is running this meeting:
84e17b0b-b543-51f0-a6ff-0ddf7666f6f3 | textbox | Company
a4e2c638-2e08-5854-93c5-fa6f6d3da816 | textbox | Agenda items:
4a37a44d-e7dc-53e7-af99-a075e4607111 | textbox | Theme of the week (topic for focus):
8f43e25f-65e6-5225-921d-ab35dc0c24b7 | section | Health and safety issues
a0b01591-964f-5515-85c6-7f96b57877d7 | checkpoint | 1
159ba9d8-dafe-561e-91a5-2fb4a6f40812 | textbox | Issues raised from site safety inspection:
14c27c0b-2226-5434-9e78-f75e190ba8f6 | textbox | Actions:
8f3a5c2e-e3f5-503d-ab85-9c42870f768f | textbox | By who and when:
80eb3b16-184b-5f92-932d-71403b994572 | checkpoint | 2
3bb0df4d-5496-5a54-9242-25d4989edd43 | textbox | Issues outstanding from previous briefings:
eacd8cef-901d-5ac0-9da6-f4e2cdbe9b07 | textbox | Actions:
11ff0792-1f5a-5290-ba6c-61eddc0a518a | textbox | By who and when:
7a173f6c-500c-553d-b74a-85afb565eb50 | checkpoint | 3
6b604528-3642-5d95-8405-0bd6a4296afc | textbox | Employee-raised issues:
39861733-b210-585c-bb9a-2230d5f813a7 | textbox | Actions:
a74b34ec-f244-59df-8f9a-a687c130c680 | textbox | By who and when:
b911b1b9-6725-5360-8e28-f6a01e7ce249 | checkpoint | 4
2c490cd2-0a6f-5c5b-aac8-54a874720dbf | textbox | Positive safe-action observations:
ccd2a70e-350d-5092-a54d-b2d401e73f89 | textbox | Actions:
8ec86626-e486-5bc2-b22f-aca37c7d7b49 | textbox | By who and when:
24dce8d0-3e3b-5c3c-b560-2a93082053b4 | checkpoint | 5
f86da1f9-2286-5b05-ab4c-9edea3cfcdcc | textbox | Incidents or injuries:
98cac4be-9db4-5c20-9648-0af36717e94b | textbox | Actions:
34abfd1a-e08b-5c05-8747-f34e53c99b6e | textbox | By who and when:
65cf4cdb-858a-5a48-a1f8-60f558ae2c46 | section | Job plans reviewed
a8280800-1226-53e5-9c73-a7a52d5684e8 | checkpoint | Job/Task & Action/Outcome
4a91354d-f959-5d7d-b0dd-96a83061d23c | textbox | 1
1a014b15-25c7-571d-b186-e1ae30bb1438 | textbox | 2
4256dbdb-804a-563c-8e45-281d580fc06d | textbox | 3
76775c53-3903-5e27-9d33-11c9897b44a4 | textbox | 4
0f815e2c-ddba-5f14-94c0-d163ebb0b4cf | textbox | 5
0738b909-5034-52d9-acbf-e110260384c9 | textbox | 6
8d693926-2ea9-518f-87a9-fe6c0a53f6f9 | section | Operational issues
4f65d119-f79f-5ea2-8563-cefb57fc5845 | checkpoint | Issue & Action
e8a4616c-147b-560c-87e6-28e19c37c713 | textbox | 1
e108f108-e763-58c1-af6a-939e1104e89f | textbox | 2
af8f69ab-3326-548f-9084-201b968e9b0a | textbox | 3
e5c29fb7-501b-5efb-8885-69a4bdedea67 | textbox | 4
3e654e50-dfd1-5746-832a-11bf8f8838e9 | textbox | 5
74ccec0f-4832-5df4-a4f8-8c95739b8863 | textbox | 6
87859890-e1e4-5aaa-9e3c-6d48193f428b | section | Other business
807d9d40-3b89-5a55-a7d9-c9eed3e5ecf2 | checkpoint | Item & Action
6c0f4fe2-f9e8-5c25-ab0c-381203cf5f3b | textbox | 1
51dbd5bc-d440-58dc-84ec-581fd1ae8935 | textbox | 2
44f584c0-17ff-522a-a902-77cb68a7d7d7 | textbox | 3
129f0ed8-fae2-5475-ba5d-daf5fa086a90 | textbox | 4
271ce954-e33e-500f-a03e-c05358c15d2d | section | Attendees
401b3010-2947-5c78-bb98-db387017efe7 | checkpoint | Add name and Photo of attendees
fb78e717-0c25-50ab-a6fe-ad82138ef4f2 | section | Review by management
eb84de72-6352-54c4-acdc-96870fa0bf85 | checkpoint | Reviewed and signed off
ed8044f2-9314-58e9-9593-c47d5c920671 | textbox | 1
8fc8a6ca-10ec-5144-86da-4b9c74916fa9 | textbox | 2
f9698c46-93f5-42f0-b7dd-4914d2d4743c | checklist | TCC IDC Waste water/ Stormwater works |  | TCC IDC Waste water/ Stormwater works
3bc15162-6119-4f94-818f-71b3a7836e2f | section | Lot Connections Procedures:
f3099f79-e782-4093-ac26-7536ae2a8148 | checkpoint | Make Sure SCA is approved and you have paperwork onsite
b757cdc5-d229-4ef7-be67-3159b8493bfa | checkpoint | If working in roadway make sure CAR is applied for including TMP if required
e7219f06-b521-447a-8f23-4e06fd27f884 | checkpoint | Organise Service Locate Including B4 you DIG
137b196a-6e14-45bc-83f1-560b48e7215c | checkpoint | Hydro exvacate Service if required
f5928cc4-3fbb-4ec8-86d6-f7ddc85a5fb1 | checkpoint | If work over 1.5m Deep orginse notificable work form with Worksafe
be57011a-285c-4578-80d5-8871455c5dd1 | checkpoint | Complete Paperwork including – SWMS, Toolbox Talk, Digger Pre starts, Chain cerfication/ sling inspection and current
08c1f296-b445-4a6a-a879-620e6dd309df | checkpoint | If working in a live manhole – Complete Confied space HS forms including Rescue plan. Make sure you have confined space gear – Gas Detector, Triodposd, Harness – (Check Harness is current)
9a7d3367-dc1c-4643-82b2-934860cc694e | checkpoint | Book inspection with the TCC Asset inspector for the area and explain what we are doing. (photos taken)
72246d87-143b-48cd-be89-227ba5df50cf | checkpoint | Work Complete – Before backfilling – make sure inspection has been undertaken and get inspecto to sign off SCA – if there are a few inspecitons required make sure they sign the form attached to state what they have witnessed,
d41e9b90-765e-44ee-9a25-c67cfc9fd436 | checkpoint | Complete asbuilts on SCA form
a7866ae4-3e83-4e87-85e6-77411555abf1 | checkpoint | Backfill and compact (photos taken) – Scala and Test results checked and completed
9797269c-68a1-46cf-9b47-138bceb04b1e | checkpoint | Tidy up and reinstale surfaces as required to TCC IDC Standard – If asphalt repair make sure emulstion is used to join asphalt from new to old.
881795c3-31f8-4383-a577-9f3962acc721 | checkpoint | If a kerb connection is install a minimum of 1m wide off footpath is cut out and reinstated
ae7b655d-3150-4ddc-9a7e-eead4a75ffe4 | checkpoint | If a final inspection of manhole etc is required – make sure all liner joins, lids etc are expoxied, make Manhole covers are bolted down, if a concrete ring is to be poured make sure reinforcing ring is used . (photos taken
0055c43c-d5c0-4dd5-93a9-9178d8e323aa | checkpoint | On final inspection – make sure SCA is signed by inspection and completed form with asbuilts are passed back though the Kieran
70faa28e-0eed-4f4d-9c42-daff7ab66f9d | checkpoint | Make Sure SCA is approved and you have paperwork onsite
ad04cfbf-3eb1-4ea8-9079-e835a2ba249b | checkpoint | If working in roadway make sure CAR is applied for including TMP if required
01ec9855-03ed-4dd3-87ef-b583b62df4a5 | checkpoint | Organise Service Locate Including B4 you DIG
e9ee6a41-72a0-4c32-97f2-f14d10080dc6 | checkpoint | Hydro exvacate Service if required
c762953f-894d-41ba-b278-5d9e7d7d7cbe | checkpoint | If work over 1.5m Deep orginse notificable work form with Worksafe
2c94e3b3-71b3-4120-87ce-3934395ce9c8 | checkpoint | Complete Paperwork including – SWMS, Toolbox Talk, Digger Pre starts, Chain cerfication/ sling inspection and current
a9198463-1acf-48ea-8a95-a849aded746c | checkpoint | If working in a live manhole – Complete Confied space HS forms including Rescue plan. Make sure you have confined space gear – Gas Detector, Triodposd, Harness – (Check Harness is current)
391bdc21-f624-45e7-b277-f00b85a6b284 | checkpoint | Book inspection with the TCC Asset inspector for the area and explain what we are doing. (photos taken)
83ff8a6f-96f0-4514-9831-b7364cd8aeb1 | checkpoint | Work Complete – Before backfilling – make sure inspection has been undertaken and get inspecto to sign off SCA – if there are a few inspecitons required make sure they sign the form attached to state what they have witnessed,
a8ee9b69-cda4-4746-9188-663399b74bf3 | checkpoint | Complete asbuilts on SCA form
b4ce8044-8c35-4210-b510-9959ea873bc8 | checkpoint | Backfill and compact (photos taken) – Scala and Test results checked and completed
b51906ef-b345-40c4-b5e4-c2249ce76aff | checkpoint | Tidy up and reinstale surfaces as required to TCC IDC Standard – If asphalt repair make sure emulstion is used to join asphalt from new to old.
00446235-d56f-4cce-82a9-dccb0b4970ce | checkpoint | If a kerb connection is install a minimum of 1m wide off footpath is cut out and reinstated
f26284b0-e8e4-4b87-a0bc-f10baecb8a90 | section | Storm Water
467477a9-60bd-4afc-ab05-9a7af3ecfa6f | checkpoint | Plans correct issue and construction set
7fd1b87d-6d5f-4fc7-982e-4e270936ad27 | checkpoint | Check set out from builders
511ede64-4e02-4ab7-83c8-2b96717dd839 | checkpoint | Check Plans for correct sizing and pipe material
2f9201b0-4c01-4b34-9c47-ea1db1d8ce66 | checkpoint | All Falls achieved as per plans
de62cbfc-55e6-40b6-95c9-aca8a24987f0 | checkpoint | All Manholes hauched as per code
f5c1ac24-2b14-47e7-9d62-83157fafc357 | checkpoint | All Cesspits, Manholes installed to correct heights
627ade35-6782-4b38-a868-6a5c71155d24 | checkpoint | All Trenches compacted with compactor
9dfca077-d3d2-468a-8072-947236095cdf | checkpoint | Subgrade Scala test ever 10m - 3 Blows per 100mm
6aee75fa-c0b3-490f-aa38-c8619c290511 | checkpoint | Backfill in layers of 300mm and test every 10m - 3 Blows per 100mm
fa8599de-930f-4f2e-9e45-142f2584f066 | checkpoint | Pipes tested for inspection
39c1d34a-418e-49ef-9124-dca2b2297550 | checkpoint | Rainwater Tank installed as per engineers report
49e6f678-b3ab-426c-a229-9d1fe4d01a2d | checkpoint | Photos Taken
c0792018-561f-4b84-8480-aeb2372cd9bf | checkpoint | Inspection passed
2372e4fd-607b-4efb-828d-91be1c0dd618 | checkpoint | Engineer Inspected
689ab033-1dd7-4b5e-acdd-bf2a4e1a8f85 | checkpoint | Mark up drawings Done
3044159b-b1ed-4356-9ba0-4a054b1c3a6e | section | Sewer
ea8edd9d-9fdd-4d4a-81c3-c318894708bf | checkpoint | Plans correct issue and construction set
cb292f40-e242-44ea-9409-9b0f5f8329f5 | checkpoint | Check Plans for correct sizing and pipe material
04edbd9b-7a65-4e6f-9a80-026cdb198682 | checkpoint | All Falls achieved as per plans
cb1486e0-f27a-4e0e-8df5-2d3aad3556f0 | checkpoint | All Manholes hauched as per code
9b3927f6-77e8-4c30-9730-1340f2b50a6a | checkpoint | All Manholes installed to correct heights
48c5ddd7-ce47-4e86-92a5-f33eb013d4ea | checkpoint | All Trenches compacted with compactor
93f7ba4d-792d-4314-ac96-598425287af4 | checkpoint | Subgrade Scala test ever 10m - 3 Blows per 100mm
47b66eec-731d-46d7-a302-13208aed5661 | checkpoint | Backfill in layers of 300mm and test every 10m - 3 Blows per 100mm
7af580bc-dd54-4eec-9eb9-e9a1e9eb4187 | checkpoint | All ORG and RE installed as per plan
befb8295-ae8f-46ee-9656-03953b4d7a30 | checkpoint | Pipes tested for inspection
3e02b7de-c2b9-4d3b-9c3c-62a1650410c5 | checkpoint | Inspection passed
e0642bb1-1c4b-40f8-a31a-1d8a4aadb674 | checkpoint | Mark up drawings Done
efe47a89-c3d2-45ce-88cf-5e5dd98fcd68 | checkpoint | Photos Taken
6534efc2-66c0-4f61-8db1-8bf6748feb4f | section | Water Mains and Infrastructure
608374ae-7373-4509-8828-bf62a6ed3360 | checkpoint | Plans correct issue and construction set
7304fc5d-843c-47d2-bb0d-9d64ce9f7e4b | checkpoint | Check Plans for correct sizing and pipe material
8b1d2195-7e04-48b6-9d23-db7eaab0ed65 | checkpoint | EF welding completed by a certified welder
12b3baa1-6812-41b9-b13c-123379b1863e | checkpoint | Subgrade Scala test ever 10m - 3 Blows per 100mm
b819d3df-01f3-4d9a-bdbc-876ce156b35f | checkpoint | Backfill in layers of 300mm and test every 10m - 3 Blows per 100mm
7992c1c1-c216-4c08-a66d-93f19570c8d7 | checkpoint | Water Main flushed ready for connection - Fire Main 1600L/Min at 250KPA
65f87d62-22af-480d-9d84-5c1f3bafe7c8 | checkpoint | Pipes tested for inspection
8dd27ffb-d403-409b-88e0-e264bd64c157 | checkpoint | Chlorination of Pipe work completed as per TCC IDC Code
3b9142b3-bd59-4ad2-aaab-395d5b90f99c | checkpoint | E Coli Test done and Passed
a436a221-8678-4902-b0c8-6185bb86260f | checkpoint | Warning tape installed
3b5dd31a-c05d-4dd2-8e10-cdda52f15d44 | checkpoint | All Trenches compacted with compactor
2bdb3c50-5cfc-4478-8ff6-431a4fc1fea4 | checkpoint | Inspection passed
468fa407-fbb3-4004-bce1-bb6739908368 | checkpoint | Mark up drawings Done
b87cd4f9-82e3-4a2a-b27d-301c43eda4f6 | checkpoint | Photos Taken
bc77e03a-ea2c-4ddf-a9f4-a22e5b7bf14d | section | Dewatering
20c52e0b-8b0b-4ce5-aea9-15dbdce0a4bd | checkpoint | Pumps supplied able to do flow rates required
7f0582c4-3d66-4041-9b04-ab466c56b55d | checkpoint | Wells installed to heights slightly lower than cut
798285da-dc0d-4b66-9743-b7089bf8baca | checkpoint | Storage tanks install and linked dup to prevent overflow to street
4a6cdfd4-8429-49f5-b54d-ca8bad5b68c6 | checkpoint | Valves installed on tanks for Sludge removal
060d0d91-e78c-4df2-b556-39b21bbbdbef | checkpoint | Water Quanilty Monitored and checked daily
7304d476-7900-4321-bdd8-071485166739 | checkpoint | Balance pipes installed between tanks
1b2d8674-c810-4dcc-a102-e3de025ecdac | checkpoint | Water Flow rate checked daily
3ac3a1f7-4177-4ca6-ae3f-8af21af481c5 | checkpoint | Power supply checked for reliability