## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Sewer Pump Station: | [5 empty] | Add Sewer Pump Station checks
section | Sewer Pump Station
checkpoint | Plans Issues are correct
checkpoint | Pump Station plans issues and correct - showing components and IL
checkpoint | Check Plans for Sizing and pipe materials
checkpoint | Subgrade Test - Use Scala or Shear Vane - 3 Blows per 100mm or 60KPA
checkpoint | Holding Tank - Size and Spec correct
checkpoint | Imported filled correctly as per engineer spec
checkpoint | Backfilled in layers of 300mm - Test every 10m - 4 Blows per 100mm or over 30CIV on Clegg
checkpoint | All trenches compacted with Compactor
checkpoint | Services required for pump station - Power, Comms, Water, etc
checkpoint | Manholes Hauched as per Detail and Code
checkpoint | All pipes tested
checkpoint | Photos Taken
checkpoint | Engineer/ Council Inspection passed
checklist | Stormwater Water Catchment Discharge: | [5 empty] | Add Stormwater Water Catchment Discharge checks
section | Stormwater Water Catchment Discharge
checkpoint | Plans Issues are correct
checkpoint | Discharge Manholoe correct size and Depth
checkpoint | Check Plans for Sizing and pipe materials
checkpoint | Subgrade Test - Use Scala or Shear Vane - 3 Blows per 100mm or 60KPA
checkpoint | Discharge Pipes - Correct size
checkpoint | Imported filled correctly as per engineer spec
checkpoint | Backfilled in layers of 300mm - Test every 10m - 4 Blows per 100mm or over 30CIV on Clegg
checkpoint | All trenches compacted with Compactor
checkpoint | Anti-scour blocks installed as per engineer details
checkpoint | Manholes Hauched as per Detail and Code
checkpoint | Riprap installed around Discharge manhole as per Detail
checkpoint | All pipes tested
checkpoint | Photos Taken
checkpoint | Engineer/ Council Inspection passed