## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
7639e772-e021-4c52-b9dd-0f30241d221d | checklist | Tahunanui Back Beach Remediation ITP | itp | Tahunanui Back Beach Remediation ITP
04b3eb31-5c30-4d06-967e-529c0c27a897 | section | 1.1 - Pre Construction
3c08e01a-91cb-4884-bccd-edb54e571e90 | checkpoint | 1.2 - Vegetation Clearance
67432d55-0541-571d-a6e7-2cf3f80cdccb | note | Inspection Point: Quality Control Activity - Removal of trees, and other plants within the area of works
885362d9-95f5-502e-8261-002fcb0cec76 | note | Acceptance Criteria - Trees and plants removed in the area of works
0d25e83f-d1df-5fe2-aa56-6e568bfe54b9 | note | Verifying Document - Ecologist approval
e3d81e06-dee2-5a42-b084-cf3f88ced4f4 | note | Frequency - Pre Construction
9283566e-41d5-5ea0-9b42-75c9afeda89e | note | Inspection Type (Visual, other) - Visual, Hold point
b0f14966-0113-584e-8745-c88b1c9858ea | note | Inspection: Key - SUB
42aa6c37-e081-59e4-b215-c7ece7731348 | note | Inspection: By (Role Key) - Nelmac
b211afe1-79bb-48b1-a2d2-f2ad471cccbc | signoff | AUTHORITY HOLDPOINT
f277cf6d-13f0-40c2-bfe8-b6921703d896 | checkpoint | 1.3 - Ecological Clearance
b75ac592-412e-52eb-9dbf-ba7519e18370 | note | Inspection Point: Quality Control Activity - Pre-clearance surveys for nesting birds, implimentation of Lizard Management Plan and accidental discovery protocals for lizards and birds.
117478d1-6867-5b8f-858a-940b063666ac | note | Acceptance Criteria - Area has been demmed cleared of nesting birds and lizards
73c6f7d0-5f6d-5889-9b43-f5d096f46892 | note | Verifying Document - Ecologist approval
285a3779-43ea-5d68-bdea-8f7500190b5c | note | Frequency - Pre Construction
ffeb1d88-da73-516c-9543-f4a6ea2e2912 | note | Inspection Type (Visual, other) - Visual, Hold point
f3d5787c-886f-5696-a359-a56084448bc4 | note | Inspection: Key - ECO
4cf43d81-8676-59aa-96f9-d3ded268352e | note | Inspection: By (Role Key) - T+T
da2e3c9c-9e65-4ead-9921-a4f8c69a557e | signoff | AUTHORITY HOLDPOINT
df9c82cc-67a5-4ce5-a844-100fb055dc50 | checkpoint | 1.4 - Traffic Management
93784497-3032-5bd8-ab73-42ab66bbec3d | note | Inspection Point: Quality Control Activity - Implementation of Traffic Management
606a2dfb-cd98-5402-9bb7-85398787d464 | note | Acceptance Criteria - Traffic Management set up in accordance with approved TMP
6da57df9-1435-56e3-af9d-329e199afc51 | note | Verifying Document - Written confirmation from Eng Rep
d84e594c-154e-55ec-b733-47bec9098025 | note | Frequency - Constant monitoring
aeab2b36-f312-53eb-8fef-ab3b1ffd4aa7 | note | Inspection Type (Visual, other) - Visual verification, Hold point
952e9b6d-9814-5caf-b12c-554505c9d965 | note | Inspection: Key - STMS, ENG
6cebdb6b-06f3-5428-84d0-bc7dda497782 | note | Inspection: By (Role Key) - Downer, T+T
8aaaad4d-58d1-4934-9482-9bc3c0d42a7a | signoff | AUTHORITY HOLDPOINT
533d81b1-c9f7-443b-8222-f66aed32f950 | checkpoint | 1.5 - Service Location and Clearance
cd517c50-6b22-527c-a71b-0421c7c373ff | note | Inspection Point: Quality Control Activity - Service locations complete
04cf5933-dab4-59bc-863a-729d1867c7db | note | Acceptance Criteria - Services have been identified, approved controls are in place
dc666cae-a4d7-5308-aaeb-ffda7045e125 | note | Verifying Document - Locator record of confirmation
3167cf20-ac2b-54ce-874b-22f94d183a6e | note | Frequency - Pre Construction
ea9c5510-5903-57e1-9e81-f393f8c235c4 | note | Inspection Type (Visual, other) - Inspection, Hold point
9d9b4153-175f-5286-9194-360e681d3bf9 | note | Inspection: Key - CE, ENG
952a4226-86ef-5252-98a3-16fe69f84d6e | note | Inspection: By (Role Key) - Downer
791aba10-d72f-4c8e-b03f-f0094338a185 | signoff | AUTHORITY HOLDPOINT
2b74fc7b-fca0-435f-b0b5-c933a3b8dd52 | checkpoint | 1.6 - Survey and Set out
6afe6540-7a1c-54a3-9cfd-a1d7e5cdbaa8 | note | Inspection Point: Quality Control Activity - Pre construction survey and site set out
1637406d-ab43-5490-bfc8-5cc22aac7308 | note | Acceptance Criteria - Set out follows provided coordinates
596dac80-a6cf-5c85-968d-db266956b807 | note | Verifying Document - Written Confirmation
dfac3be1-e1c7-5467-a334-fe4ada697ba9 | note | Frequency - Pre Construction
d13a2dcf-dab1-57fd-898e-18c32cd268bb | note | Inspection Type (Visual, other) - Inspection, Hold point
890307d9-f51a-5d6e-a1f2-d67c8acc47b2 | note | Inspection: Key - CE, SV, ENG
09afca7d-ea19-5edb-9c25-a239a58fa7a3 | note | Inspection: By (Role Key) - Downer, T+T
a52be2df-4a8a-4fa0-b650-58fc6bed09c1 | signoff | AUTHORITY HOLDPOINT
e941409b-b480-4b05-9876-3a8f20aba838 | checkpoint | 1.7 - Equipment Free of Contamination
07eadaea-3fe3-5ac9-bb56-9e57cec788d6 | note | Inspection Point: Quality Control Activity - Any equipment coming onto the site shall be washed and cleaned of visible dirt prior to entering the site to manage potential biosecurity risks. Washdown area has been established on site.
c0e72485-cf69-588a-a647-fc4888b1f4c8 | note | Acceptance Criteria - No visible dirt, leaks, contamination
805a19fc-3595-5cea-be12-5c4ba14843b1 | note | Verifying Document - None
5a7be9d3-af09-5a4e-9d88-837bb10b6af7 | note | Frequency - Before Works
d550958c-6e40-5616-be70-5a6edd364cea | note | Inspection Type (Visual, other) - Visual
144cb1ba-683d-5a48-962f-f2a1bc314818 | note | Inspection: Key - PS
de1ac1d3-2c7b-5bc9-821b-6714baf99cbd | note | Inspection: By (Role Key) - Downer
b803644c-dac6-4191-b56f-383696e2fa4f | section | 2 - Stage 1
974c9cf5-980d-4023-bb69-325c8205795f | checkpoint | 2.1 - Ecological Clearance
db143b11-4046-5681-8c6b-8e53dfa18bdf | note | Inspection Point: Quality Control Activity - Ecologist to assess for any active nests above MHWS during peak bird breeding season.
c718d09d-322a-5e6f-8c66-8debe1d4b9ac | note | Acceptance Criteria - Area is clear of any active nests
abf94d3f-6978-5c9d-900f-689be0f1b9b0 | note | Verifying Document - Ecologist approval
30e02f04-5ef2-5ee0-afc6-b235712ccc15 | note | Frequency - Before Works
376dca9f-de3c-58c1-a624-8da17df6c789 | note | Inspection Type (Visual, other) - Confirmation
b59848bc-e582-535a-bcc0-ccaec89fc280 | note | Inspection: Key - ECO
c2f55d64-7829-5b0d-b330-8fa6b77f6fc4 | note | Inspection: By (Role Key) - T+T
39cfe3c9-f1c5-4f08-8cd8-756930767cc9 | checkpoint | 2.2 - Removal of carpark gravel and placement of new benched haul road area and capping layer to protect exposed contaminated material.
c1e2c868-cc3b-5fff-ae63-0ae8ba91c219 | note | Inspection Point: Quality Control Activity - Confirm protecting capping layer placed.
d3a5884c-e21f-5317-b622-00081cdce90c | note | Acceptance Criteria - Contaminated materials covered by capping layer
b01fb92a-3570-57c5-9d82-add1eeb458dc | note | Verifying Document - None
4c57b375-77ef-502e-9ae5-1262c9401e8f | note | Frequency - During Construction
2aff1abd-f3d7-5ed3-a0d9-ae98011d9721 | note | Inspection Type (Visual, other) - Visual, Action
e361b30e-605b-5905-a14e-4ca6aec91ee6 | note | Inspection: Key - FORE
83b23112-a931-5cc0-928b-aade415065b1 | note | Inspection: By (Role Key) - Downer
00bc7422-dfc1-4213-b146-780bd9720297 | checkpoint | 2.3 - Excavation has reached the proposed first cut level.
eb3293c0-b4ba-5dc6-9b97-03aec22162be | note | Inspection Point: Quality Control Activity - Confirm extents of excavation
3aaedd1f-41dd-5102-9b65-c9d89601662a | note | Acceptance Criteria - Survey check with excavator
8a9a1e6b-352b-5b0e-ae90-9c80b2e8c95a | note | Verifying Document - None
7c107a84-212f-50b9-b14d-0419d2e2b723 | note | Frequency - During Construction
102f5d60-b362-5cc8-ba79-03f360c5696b | note | Inspection Type (Visual, other) - Visual, Check with GPS
7a5af3c7-6ccf-5a24-ac5c-dbe0443b4966 | note | Inspection: Key - FORE
81a14d87-11d7-5850-8903-c85132cb4aeb | note | Inspection: By (Role Key) - Downer
6b5226d6-0361-46d2-984e-13a9b1bac5cc | section | 3 - Zone A Excavation - Stage 2A
a22696cf-ad15-4895-bbea-69241b4e30b0 | checkpoint | 3.1 - Confirmation of survey limits of excavation
f7d96e41-91ad-522d-84d7-ae745b8e6771 | note | Inspection Point: Quality Control Activity - Confirm extents of excavation
0e566156-ba2d-5e0c-820c-4ee0883a2ab0 | note | Acceptance Criteria - Survey check
d3879a5c-3805-5933-b634-49e3c3049ce4 | note | Verifying Document - Survey asbuilts
e611e570-c9d4-5ed2-89f9-b72bc4465bef | note | Frequency - During Construction
1f01e6de-7962-5826-8307-e2d32fe26d8f | note | Inspection Type (Visual, other) - Hold points
0da560d4-c9a9-5f35-a935-737eb13d6d7e | note | Inspection: Key - CE, SV
0d753762-36cc-57eb-be84-768a7cb88a47 | note | Inspection: By (Role Key) - Downer
f723a980-ed3f-4f07-b945-9ed6ca7b918c | signoff | AUTHORITY HOLDPOINT
6b67e428-7004-40e1-9652-7d5cb6ed78d1 | checkpoint | 3.2 - Final Excavation Level
8931c5d1-ae9b-586f-8505-9c153a65869a | note | Inspection Point: Quality Control Activity - Visual confirmation that visible sawdust is removed.
91974232-dec7-5355-86d2-ea6ffae17107 | note | Acceptance Criteria - No sawdust remaining in section of approval
640bc4a6-fc30-5442-b731-a142f7b63459 | note | Verifying Document - SQEP approval
e33d1f45-4d6b-51e8-be1b-8d15cfbe3994 | note | Frequency - Every 25m of the completed excavation on a 5m grid.
96fb3ce6-0037-5567-aaff-3cdb0cf2a1a3 | note | Inspection Type (Visual, other) - Inspection, Hold point
77c408c9-f566-5b15-99ae-8fb4efbc2dc3 | note | Inspection: Key - SQEP
90ec9274-d276-5672-8e49-b3e65de37970 | note | Inspection: By (Role Key) - T+T
8d3aadfe-265b-4839-97dc-7148bd82591f | signoff | AUTHORITY HOLDPOINT
9db0218b-f126-469f-8c69-a8db36a2c653 | checkpoint | 3.3 - Final Excavation Level
831d4f09-9c71-5d85-94dd-2037c9b9e059 | note | Inspection Point: Quality Control Activity - XRF Contamination Testing
57a7fef5-0ab2-5eb7-a13e-6a9675344cc8 | note | Acceptance Criteria - Excavation free of contaminants
5feefdd0-a181-5c9a-a188-7991619163dc | note | Verifying Document - SQEP approval
0a1d8364-c741-5760-a9e6-08d9c2b219dd | note | Frequency - Every 25m of the completed excavation on a 5m grid.
e3c51a6b-871e-58f6-aebf-52d37c8f103e | note | Inspection Type (Visual, other) - Inspection, Hold point
983fb406-b479-50b9-854c-59557187cc50 | note | Inspection: Key - SQEP
00714346-2e51-5fad-ba0e-3888b64f9ea1 | note | Inspection: By (Role Key) - T+T
b2c718b1-6fc0-412a-ab12-34d9a897d1bb | signoff | AUTHORITY HOLDPOINT
81323f8c-4994-4de1-b802-22a1ad16a873 | section | 4 - Sand Mining
31ec2cc2-3f72-4b04-8500-e69472d1eeff | checkpoint | 4.1 - Ecological Clearance
ab409f7a-43a1-55f5-9fc2-04bcab82772d | note | Inspection Point: Quality Control Activity - Ecologist to assess for any active nests above MHWS during peak bird breeding season.
a316c4f9-5fce-5f50-8315-222ce73c1ce4 | note | Acceptance Criteria - Area is clear of any active nests
8a35eef9-13b3-55d1-94b3-d3e4e022ead9 | note | Verifying Document - Ecologist approval
4091695d-20a7-5358-934b-4187669f302e | note | Frequency - Before Sand Mining
2fbf77d8-dfef-53fd-a41d-79f9fcacd3e1 | note | Inspection Type (Visual, other) - Confirmation
ff725033-ab07-5639-9786-cc01888a0c51 | note | Inspection: Key - ECO
b66588ba-fcc1-5f80-a319-235392b9e567 | note | Inspection: By (Role Key) - T+T
0a514b37-af96-4f34-87cb-af349b7169fc | checkpoint | 4.2 - Limits of excavation established
efca525b-bc17-54a1-988e-5210b72223a3 | note | Inspection Point: Quality Control Activity - Limits of excavations marked out for sand mining
f934b521-d9ce-5d97-88ec-d609f6d3bf00 | note | Acceptance Criteria - Survey check
4539d340-2203-5933-8d0a-44a76f897740 | note | Verifying Document - None
19524cc0-b37f-566a-9d50-1b5175815eda | note | Frequency - During Construction
0182f130-12bb-5631-8698-fff612e88aa7 | note | Inspection Type (Visual, other) - Visual, Check with GPS
6e67f99d-83c2-5dbb-b7e7-f26b57d27d9b | note | Inspection: Key - CE, SV
07ae8ea7-800a-5e4d-8a81-099c8c1bd2b5 | note | Inspection: By (Role Key) - Downer
a2d9b633-d847-45bc-bc48-e8819a56cf7b | checkpoint | 4.3 - Washdown of equipment between used beach and site
a4644980-1ad7-5dce-86d7-128e2c193316 | note | Inspection Point: Quality Control Activity - Equipment repurposed for sandmining to be cleaned on contaminants
6cc6ad43-9e33-5827-b66b-1a964f4903c6 | note | Acceptance Criteria - Equipment used for sand mining cleaned prior to works
df2be8b8-b5b1-51a5-a639-7b3df859d0c8 | note | Verifying Document - None
b1cd3678-7156-569d-8e9f-9a2f91b10920 | note | Frequency - Every Disestablishment
9e9c9756-7c33-5d73-a66b-97d2fb622dd3 | note | Inspection Type (Visual, other) - Action
f1211b8a-82e8-5fca-babd-030188a67be1 | note | Inspection: Key - PS
659c4605-6e1b-5a79-a89a-1ad2d53413d0 | note | Inspection: By (Role Key) - Downer
b5524ad7-d4de-4ae6-aa3e-024426f88c36 | checkpoint | 4.4 - Minimum 10 buffer established between MHWS and sand extraction area
1f5f5025-5277-58b2-8d6f-e167b5e62eca | note | Inspection Point: Quality Control Activity - Buffer confirmed
e1c768fd-1c3f-5695-bb1d-a219b6d8b2c4 | note | Acceptance Criteria - Survey check
4b36e10d-e2f1-5d67-878e-b63a783698b6 | note | Verifying Document - None
3c9ca8fc-19a9-5688-998f-3c89a173bc08 | note | Frequency - During Construction
db173706-5e23-50c3-9dc4-3b24b8ec37c3 | note | Inspection Type (Visual, other) - Action
d5a7a0c0-3afd-5b38-878d-d604d0ed5b8c | note | Inspection: Key - FORE
e3d115ae-c733-5899-a736-2988290909b4 | note | Inspection: By (Role Key) - Downer
441455b7-3aa4-4483-83df-d7093358ef29 | checkpoint | 4.5 - Haul Route demarcated and established in allignment with high tide mark.
8332b1c1-fd03-5e7d-a3dd-eb34ea4f194b | note | Inspection Point: Quality Control Activity - Haul route clearly delineated and confirmed to be in proper position
a550ea32-b41a-556b-8cf5-d0d96a920707 | note | Acceptance Criteria - Markers placed a long the haul route
8b72c691-260e-55ee-bbd6-7a0fdf79a46c | note | Verifying Document - None
d3d08016-c760-5e03-9824-42f700f02214 | note | Frequency - Before Sand Mining
9deb8960-84ae-570f-bb3b-7fec247ada76 | note | Inspection Type (Visual, other) - Confirmation
f2138f58-251f-5403-9572-9b819e5c0956 | note | Inspection: Key - FORE
e4bcb15a-c318-58e8-9743-de05bc43a1a6 | note | Inspection: By (Role Key) - Downer
1f47fe07-7414-42a3-90d0-dc1903382e38 | checkpoint | 4.6 - Sand deposited to create temporary bund adjacent to Stage 2B works.
422a6b67-cf25-57bd-969b-65bf621710b4 | note | Inspection Point: Quality Control Activity - Stockpiling target confirmed
00c07c5d-e641-5543-9c53-391aedddbca7 | note | Acceptance Criteria - Survey check w/ volume
c9c375c1-5c5a-55f3-8749-cfc44cb64bab | note | Verifying Document - None
5e8b021f-ade4-59ad-9b53-0046dbe936c1 | note | Frequency - During Construction
c0b0e779-eddb-543e-ba09-4360ce2098b4 | note | Inspection Type (Visual, other) - Confirmation
8c46ad76-035c-50bf-bb71-c4b92d60aef2 | note | Inspection: Key - FORE, CE, SV
1f5133d4-fce6-5013-907e-003b2e18b0c7 | note | Inspection: By (Role Key) - Downer
7a10b53f-bafd-4835-912f-c3b21066b09e | checkpoint | 4.7 - Site maintained in good order
6b84571b-66d0-5d6d-911b-699c4ff8fb6b | note | Inspection Point: Quality Control Activity - No construction materials shall be left in a position where they could be carried away by storms, floods, waves or other natural events; and All machinery, equipment, loose construction materials and surplus spoil shall be removed from the Coastal Marine Area at the completion of each day’s work and/or when the incoming tides dictates that work must be ceased.
8bd772df-78ae-5a1a-9e2b-a21ac192e8d1 | note | Acceptance Criteria - No loose construction debris present
2716bcc3-7bcd-571f-b5fe-e963ce98fa86 | note | Verifying Document - None
2eb2687e-7ebd-5cd9-883a-3a504321f071 | note | Frequency - Each Day
cd89b640-80cc-50a2-aa41-ad06f1e2c2b1 | note | Inspection Type (Visual, other) - Confirmation
74c34da6-d63e-58ef-9193-e7929d1592ce | note | Inspection: Key - FORE
dc9e8868-677e-5ecb-9508-0c6fbba6ff32 | note | Inspection: By (Role Key) - Downer
4b631845-f327-4643-ac03-d3a17b8af4d6 | section | 5 - Zone B Excavation - Stage 2B
f7c778a7-4322-4bef-9b50-b6502a4be9d9 | checkpoint | 5.1 - Sufficient sand stockpiles for Stage 2B excavation to commence.
ccc16721-3591-5a32-8711-dedf56813a2f | note | Inspection Point: Quality Control Activity - Prior to works ensure sufficient sand is stockpiled.
d8d314f7-4b66-5a4d-a3e3-140d529bce52 | note | Acceptance Criteria - Survey check for volume
195ce0d5-b0c7-50d8-97ee-b00c1c261ef7 | note | Verifying Document - None
13cdd418-a532-5d40-af40-482f6ff7766e | note | Frequency - Before Works
d76d36cb-1409-5628-9cb9-4e6a5a71a662 | note | Inspection Type (Visual, other) - Confirmation
fc3225de-31ca-5359-873a-3bb6fd2ad0a1 | note | Inspection: Key - FORE, CE, SV
9853b3e6-afcd-5dc5-8849-e697669b852a | note | Inspection: By (Role Key) - Downer
47961162-503b-498a-9902-d432753f8f24 | checkpoint | 5.2 - Confirmation of survey limits of excavation
d9b4cfc7-dcd6-5580-88c9-8845fac4e126 | note | Inspection Point: Quality Control Activity - Confirm extents of excavation
57b5d720-1735-5ba8-a6cf-9890c22326db | note | Acceptance Criteria - Survey check
8ac9e4d9-5a75-5d4f-84db-6da09b225095 | note | Verifying Document - Survey asbuilts
35d83468-37bb-5e58-83ce-3eb79d0581e2 | note | Frequency - During Construction
513017f1-67be-5645-8d19-974a931df61c | note | Inspection Type (Visual, other) - Hold point
20e548b1-2519-5eac-b67b-0da8dba6e90e | note | Inspection: Key - FORE, ENG, CE, SV
2f3ab645-4c9c-5729-bff4-e9752f081605 | note | Inspection: By (Role Key) - Downer, T+T
dc0edd3f-1382-4799-b0bd-908d7ac4dacc | signoff | AUTHORITY HOLDPOINT
9b950358-3d58-485d-8a13-cc281e3b3c56 | checkpoint | 5.3 - Excavation confirmed not to be performed under Highest Astronomical Tide.
2c554eb2-c748-5513-b8d9-3dcf38e153b6 | note | Inspection Point: Quality Control Activity - Confirm excavation duration does not fall under HAT.
34142905-3716-596a-8c47-7dc06dd2e7c3 | note | Acceptance Criteria - Site Eng to provide confirmation that works do not fall under HAT
018658fc-81ad-5433-8c4b-535527e2438a | note | Verifying Document - Written
56797d3b-da6e-5467-b554-718dea7aedac | note | Frequency - During Construction
cc6dc736-963b-502a-a422-e4f00dd66454 | note | Inspection Type (Visual, other) - Confirmation
cd6d6748-42b5-50dc-b0e6-2e4b87beeb7c | note | Inspection: Key - CE
1601db2d-9307-532d-84f5-a5b9e015f73e | note | Inspection: By (Role Key) - Downer
f0f678d1-624c-4441-a6b1-9c64301a2342 | checkpoint | 5.4 - Final Excavation Level
74fc82b2-9f0d-58db-8a46-4d3ebd76d4f4 | note | Inspection Point: Quality Control Activity - Visual confirmation that visible sawdust is removed.
8493e780-439a-537e-a8ac-5dca801299a8 | note | Acceptance Criteria - No sawdust remaining in section of approval
d571dfc0-ff37-5199-952e-865c0235e22a | note | Verifying Document - SQEP approval
dd1652e3-7d27-50fc-a08d-7abcb29105c5 | note | Frequency - Every 25m of the completed excavation on a 5m grid.
971946c6-536a-576d-b03e-718e7b174cfc | note | Inspection Type (Visual, other) - Inspection, Hold point
26d53151-6f2d-57ee-80be-db0fec65fb4d | note | Inspection: Key - SQEP
85a2fe56-9771-5f00-8ed3-7b5187e5ef87 | note | Inspection: By (Role Key) - T+T
b7d8a0b5-e2d0-463c-b938-4f4a63c0598e | signoff | AUTHORITY HOLDPOINT
1113e14a-2739-4d2f-9ef3-23c3e3be257b | checkpoint | 5.5 - Final Excavation Level
13030127-76c2-581c-95ed-a2131cf43e48 | note | Inspection Point: Quality Control Activity - XRF Contamination Testing
6d5dc3a0-0ec4-58ca-9792-a512571c4060 | note | Acceptance Criteria - Excavation free of contaminants
6b456d77-d425-5801-a7e3-8848c04c12df | note | Verifying Document - SQEP approval
c99a8fdf-7be8-51e9-b30f-0a5187cb444d | note | Frequency - Every 25m of the completed excavation on a 5m grid.
392b3486-c51e-5548-a4f7-01a63af8e952 | note | Inspection Type (Visual, other) - Inspection, Hold point
c695f166-dadf-54b9-865c-b7e364e8ceb1 | note | Inspection: Key - SQEP
492cd0eb-8867-58e2-8893-f95d50146b65 | note | Inspection: By (Role Key) - T+T
09c451db-fbae-4b3e-be1e-3aadc9d695d5 | signoff | AUTHORITY HOLDPOINT
bb2b6f35-7de1-47bc-9674-f5c41b056665 | section | 6 - Stage 2C
c6c27458-b6a5-4d7c-8db6-54183814faf2 | checkpoint | 6.1 - Stage 2B excavation and fill complete
bae04892-c12c-57cb-bc6a-eba84062c3e1 | note | Inspection Point: Quality Control Activity - Completion of activity / stage
db3aebe7-33ab-5309-a72e-ec875671a3a6 | note | Acceptance Criteria - Survey check with excavator
44b454c3-19d6-5193-9d75-5e1af3523ab7 | note | Verifying Document - None
bc267000-5f7a-514b-9e9d-c33995d328e4 | note | Frequency - Before Works
c39e9cfe-da39-565c-a57b-dedcd3cd0ef3 | note | Inspection Type (Visual, other) - Confirmation
7614ae7a-4779-5cf1-8764-e9f80f93eeeb | note | Inspection: Key - FORE
ded77dbb-3d2c-5e23-bba2-c34a8711f5f5 | note | Inspection: By (Role Key) - Downer
a42e0f49-033a-4265-b987-42b534cf6807 | checkpoint | 6.2 - Excavation to final level for all areas of Stage 2A and 2C.
35477040-b841-5782-b13a-242c9a0ccad8 | note | Inspection Point: Quality Control Activity - Survey confirmation.
036fb3d2-60fb-5e4f-a846-190b1305469e | note | Acceptance Criteria - Survey check with excavator
b014ddde-7654-5fa9-a36c-95d060ba7784 | note | Verifying Document - None
4e69ce6e-42da-5e17-b2c3-a2cdd2ccbc13 | note | Frequency - During Construction
f631a7f7-5b37-5855-80ef-29716a6fc2a3 | note | Inspection Type (Visual, other) - Visual, Check with GPS
528cf809-b0b5-56b6-97d1-b3a5c7bc2dd0 | note | Inspection: Key - FORE, ENG
60db15f1-bcc4-58bf-9089-a9fa0a61090b | note | Inspection: By (Role Key) - Downer, T+T
7e072bc9-b4ac-4e61-9642-86ca08183904 | checkpoint | 6.3 - Final Excavation Level
78829f9b-c1f6-559a-81b6-c8aaf2d7fa65 | note | Inspection Point: Quality Control Activity - XRF Contamination Testing
c91d10d2-8c31-54c8-b103-55c5aa2b9efd | note | Acceptance Criteria - Excavation free of contaminants
f7a672f4-aa28-5296-bf4e-c91d627c3e3b | note | Verifying Document - SQEP approval
849c29ac-bd22-5592-9132-575ecb6154cd | note | Frequency - Every 25m of the completed excavation on a 5m grid.
47ca1b10-d4c4-5d67-917e-7443816094f7 | note | Inspection Type (Visual, other) - Inspection, Hold point
c7902f26-246b-5fb5-b405-c9c405f1744c | note | Inspection: Key - SQEP
d1421cad-17ad-5d42-a55f-bfc8913ea559 | note | Inspection: By (Role Key) - T+T
58b34b3d-067b-4ea8-b946-06dd7285a952 | signoff | AUTHORITY HOLDPOINT
a86eb41a-3774-40a3-8081-942885d2d1c9 | checkpoint | 6.4 - Grading of site for subsequent reinstatment complete
0e0c0498-f83b-573f-90a6-c78d1f9fb3a0 | note | Inspection Point: Quality Control Activity - Grade prepared for enstatement of dune profile
f01df92c-9237-5caf-a83e-19118e51310f | note | Acceptance Criteria - Survey check
3a310d26-2e06-5ff9-9407-8efe5dae1b69 | note | Verifying Document - None
5bf2d2d2-5037-5482-ac2b-b838aefdc72d | note | Frequency - During Construction
0f036262-21f4-55c5-83b2-4d3c6f9f0c00 | note | Inspection Type (Visual, other) - Action
89575b80-02c7-551d-a90a-a193cf121816 | note | Inspection: Key - FORE
15c11db6-418c-5775-9f37-894da2e86ea8 | note | Inspection: By (Role Key) - Downer
802e50cf-73eb-444b-b4f0-fbaf64e6171b | checkpoint | 6.5 - New fill/ Dune profile enstated.
9edb0bed-6425-5111-92f5-8498e6f70c4c | note | Inspection Point: Quality Control Activity - Dune system has been reinstated using sand excavated from sand mining site.
a34e9e46-fd92-56aa-b801-9ccbc16b835f | note | Acceptance Criteria - Meets IFC Design
4f2b2921-a8c9-5068-88b0-1d7f3ed8f23a | note | Verifying Document - As-builts
cc82d3c0-81a2-554c-ae3c-9dcc3e600950 | note | Frequency - During Construction
7bed936a-24ee-5b6f-bd8f-e4bdb8213004 | note | Inspection Type (Visual, other) - Hold point
e2f0f05b-bd6b-5232-9c69-fcd73e7986d1 | note | Inspection: Key - FORE, CE, SV
4dbd9fac-e730-5ce4-9b04-b4429e150280 | note | Inspection: By (Role Key) - Downer
ab084222-5b09-4baf-8f5e-9212447b0718 | signoff | AUTHORITY HOLDPOINT
a5a7d686-43cd-497f-8886-aa98c79c3996 | section | 7 - Carpark Construction
6399ab42-56b5-4f51-9fc9-10c36bd537ff | checkpoint | 7.1 - Verify compaction testing records of compacted AP40. Compaction to be verified via CLEGG testing. 4 drop CIV to exhibit an average greater than or equal to 20 over 7 consecutive tests with no single test less than 18.
38738b5a-fa03-5786-bb3b-bb8027c61ef8 | note | Inspection Point: Quality Control Activity - NDM Testing
6c52b5e1-d73f-54fc-824b-ea31d40430f6 | note | Acceptance Criteria - Mean Value ≥98%, Min Value ≥95%
a6f5ae24-3008-5720-bd50-cf81f4906339 | note | Verifying Document - Lab Report
a681fc5c-4367-537f-b562-eb7ca1f61134 | note | Frequency - 1 lot ( 5 tests)
ce0333fc-01b7-5242-a023-f9d2b541b994 | note | Inspection Type (Visual, other) - Testing
ef6cafc8-dd79-5b20-a709-b637d6b716ef | note | Inspection: Key - SUB
76e87561-2759-5a28-9736-056c518e7c13 | note | Inspection: By (Role Key) - Civil Engineering Labs
e7273d9a-0953-4af7-a1a6-aa8f1432d046 | checkpoint | 7.2 - AP40 Compaction
fcffc84f-5b15-573c-941d-8d03820249ee | note | Inspection Point: Quality Control Activity - Beam Testing
f1a4bc04-0ad1-5f11-8d52-01adfb5eccbd | note | Acceptance Criteria - Maximum Deflection 2.0mm
94a47d24-4862-5892-a47a-ffaab6056b4a | note | Verifying Document - Lab Report
863f7e73-9de3-5fc7-963a-56802c1d50a6 | note | Frequency - Every wheel track at 20m intervals
26081b15-b781-5d20-a2ce-bdf12bb18023 | note | Inspection Type (Visual, other) - Testing
ae04c002-7363-5b01-b728-43a978d2e67d | note | Inspection: Key - SUB
f64e75df-1c50-579d-b2a2-20b9d340999e | note | Inspection: By (Role Key) - Civil Engineering Labs
be609d67-9fde-4022-9ee4-d7a93616c123 | checkpoint | 7.3 - Survey and Set out of carkpark timber fence, concrete pad, and gravel extents.
53a65bd6-4349-5cdd-8eed-a37f7bd0f6f8 | note | Inspection Point: Quality Control Activity - Construction survey and site set out
672478e6-2057-536e-a0a8-4ad47cfb3cc7 | note | Acceptance Criteria - Set out follows provided coordinates, meets IFC design
b3782b9f-bef1-5b84-b9c0-f17b9263050c | note | Verifying Document - Survey asbuilts
d43251ce-1371-5186-9d6f-d311b7ef7862 | note | Frequency - During Construction
e5092f58-917d-5ce1-8373-1836ae2075eb | note | Inspection Type (Visual, other) - Inspection, Hold point
53f47e4f-e64a-5edf-88e9-6764a4517a9a | note | Inspection: Key - SV, ENG, CE
5082e33b-e56c-51cc-b1cc-8fc4e2a94e78 | note | Inspection: By (Role Key) - Downer, T+T
ff639c13-9559-4859-93d1-fe9376da2118 | signoff | AUTHORITY HOLDPOINT
029f9240-edfa-4174-930b-664d8cbe61f7 | checkpoint | 7.4 - Waterworks
f6c2829f-78b7-50a1-bde8-cc6378702370 | note | Inspection Point: Quality Control Activity - Verify existing watermain is blanked off and installation of new tap for beach users on a 1.5m x 1.5m pad.
25492c0b-c5ca-5ab9-a3cb-96c9b9996a16 | note | Acceptance Criteria - Meets IFC design
adcbec52-7892-560d-9ff3-85891e554906 | note | Verifying Document - As-builts
16d5c5c7-2bf0-524b-a489-166d41df78aa | note | Frequency - During Construction
75b6c43a-f105-5726-b841-361f3a256476 | note | Inspection Type (Visual, other) - Hold point
914b6791-915e-5e59-a870-c387a07004d7 | note | Inspection: Key - PM, ENG, CE
d4d7b81d-3f78-51c2-ad02-df40dba7a23f | note | Inspection: By (Role Key) - Downer, T+T
76132ec0-4021-4f42-853e-dfff55fe2200 | signoff | AUTHORITY HOLDPOINT
9e44f8e9-ccdb-4eb1-a742-632ae2ce8710 | checkpoint | 7.5 - Reinstatement of existing post and rope fence around new gravel car park`
3618985c-17f4-5666-8a83-4f03de962e1c | note | Inspection Point: Quality Control Activity - Verify per Contract Drawings
9ef430ec-1675-5c6c-85af-00a48a381f2f | note | Acceptance Criteria - Per IFC Design
09d86f71-a163-593d-b3fc-fbdd191e8bd2 | note | Verifying Document - As-builts
60478638-7f8f-5bde-815b-125f94b04af5 | note | Frequency - During Construction
8e5dd083-0d1e-5960-97f9-91e815b1924f | note | Inspection Type (Visual, other) - Action
6db75ca8-1476-57a4-bbe9-4992b91dcb91 | note | Inspection: Key - PM, ENG, CE
f7884318-050b-5f62-b543-be662d341b91 | note | Inspection: By (Role Key) - Downer, T+T
97d2f8a8-9a7c-49c2-9099-615fa13a159b | section | 8 - Miscellaneous and Finishing
bfe18144-fe78-4a08-9e97-48f8e8ca0922 | checkpoint | 8.1 - As-built Survey
577ac48a-0924-5953-930f-eff1fe8c5ce1 | note | Inspection Point: Quality Control Activity - Summary asbuilts of contractor works
f2a298f7-78ca-5f8d-9528-f2db42206ef9 | note | Acceptance Criteria - Conforms to IFC design and engineer approvals
c10dd868-36da-5c58-8979-2958c18763a3 | note | Verifying Document - Summary as-built report and redline drawings
a0f5964c-340d-560f-955e-9fd993aeef9d | note | Frequency - Upon Completion of Works
5886b25d-7210-5106-87eb-a2b6c0749014 | note | Inspection Type (Visual, other) - Action
c6717454-442e-5d51-ba1f-7f1b03bb6519 | note | Inspection: Key - SV, CE
5a7f2674-86cf-53f8-bb8c-f53886e25a9a | note | Inspection: By (Role Key) - Downer
f112c228-5f7a-49c3-ac76-98a36027cb5b | checkpoint | 8.2 - Post Condition Assessment of existing infrastructure.
b8c794fe-a69d-5162-bcbb-690fceb7408d | note | Inspection Point: Quality Control Activity - Summary provided to client for consideration of acceptance
73eac9f2-f425-503b-a0c4-5b30f04fd8a4 | note | Acceptance Criteria - Client acceptance
a4fce978-4148-5690-8e35-bcf7c1eafb07 | note | Verifying Document - Video log / report
6746c680-9765-51de-910d-3de125373510 | note | Frequency - Upon Completion of Works
096c13d3-d7b1-54a4-8d20-627f23dbb78d | note | Inspection Type (Visual, other) - Inspection
963ae0e3-0bd4-5bf7-9fb3-48f4d110bc8c | note | Inspection: Key - CE
266db0aa-dcf2-5a4d-b392-bc190fafbbbf | note | Inspection: By (Role Key) - Downer
d2596499-7416-4006-9d43-55cd16f5c16d | checkpoint | 8.3 - Practical Completion Walkover
2a2a4044-949d-590e-8b00-33bec6c48ebc | note | Inspection Point: Quality Control Activity - Walkover with Eng, Client and Contractor
32d196b8-075e-557f-a504-590b80592222 | note | Acceptance Criteria - Contract works agreed to be practically complete with construction defects noted.
ea0003e0-a8c0-58d6-83ee-03482a3a2b51 | note | Verifying Document - Construction defects list, PC Cert
92b9b0fd-d13c-5229-b224-9adbb5775197 | note | Frequency - Upon Completion of Works
69a94996-e9e5-59e7-b094-6aeadbdea84c | note | Inspection Type (Visual, other) - Inspection
a71f040e-9803-53cb-bca8-de2de3c2ad4d | note | Inspection: Key - PM,ENG, Client Rep.
d701a13a-5b5e-54b7-95b6-cb412185987b | note | Inspection: By (Role Key) - Downer, T+T, NCC
f01049da-e5d9-493d-91ab-6ed46842a5c4 | checkpoint | 8.5 - All Site Fencing
cea5a69a-8821-5b30-a402-15d3b2fd4c68 | note | Inspection Point: Quality Control Activity - Check temporary fences
041a69f6-edd3-5390-87cb-333f48bad7e4 | note | Acceptance Criteria - Daily confirmation safety fences are continuous and per the approrved TMP. Ecological fences are continous and free of damages and gaps
18437178-4c7c-590a-8535-1a147742322a | note | Verifying Document - Photos, written record of completion
7ce0a017-5f34-5bc8-b2f3-4ca446fa5f76 | note | Frequency - Twice daily during construction
2725b334-81ac-5429-981e-610b913eac5e | note | Inspection Type (Visual, other) - Inspection
18aa176a-751a-5c6f-8c72-6ffeb21596d3 | note | Inspection: Key - STMS
476c305c-1650-5d5b-abfb-5835059ed44a | note | Inspection: By (Role Key) - Downer
3ec5bcc9-6eb5-40cd-a424-59dae4f726d6 | checkpoint | 8.6 - Topsoil and grass sowing
ea20551c-66ce-57e8-adb3-92f5fa8feb6c | note | Inspection Point: Quality Control Activity - Verify topsoil placement and grass sowing
6db577b7-954d-510d-93b0-e54731d1fea9 | note | Acceptance Criteria - Topsoil measured to a consolidated layer of 100mm. Designated areas have been grass seeded and fertilised.
f7175c6c-d41b-5fce-a782-023f0fffb835 | note | Verifying Document - None
c2c78b48-06dd-5deb-b710-75eba245e7c8 | note | Frequency - During Construction
f7e8a96e-e27c-5547-8e5a-1b355827974f | note | Inspection Type (Visual, other) - Inspection
e548ebe7-dd2c-57c4-b742-ede3334efd72 | note | Inspection: Key - FORE
40a28dae-9467-5711-9688-97e477573bb7 | note | Inspection: By (Role Key) - Downer
8da5274c-bd8f-42e5-9d99-cc882825d414 | checkpoint | 8.7 - Grass strike
fb5bc878-aec0-540c-971f-b2758ab204cf | note | Inspection Point: Quality Control Activity - Verify grass seed has struck
4f381f31-e00c-5e68-bbc0-f69aa3df8429 | note | Acceptance Criteria - Presence of grass.
df57c41d-2b83-57ba-910f-4ccc1fc65859 | note | Verifying Document - None
55e48bd2-839f-563c-8f4f-a085505ce2af | note | Frequency - Post Construction
80d7fa62-91c4-5910-b980-5d46c19fd76a | note | Inspection Type (Visual, other) - Inspection
aaa9ccb9-5d1d-5b59-a22f-230b4586a578 | note | Inspection: Key - PS
ce5e1eb4-4910-554f-af3a-f3a338b86937 | note | Inspection: By (Role Key) - Downer
dc9f706b-9c0a-49d0-a0fc-d7e03e693ee0 | checkpoint | 8.8 - Geofabric installation
a92b4cb1-e017-56e3-b669-ab20ad1590a8 | note | Inspection Point: Quality Control Activity - Verify placement of BIDIM A12, Terram 2000, or similar to bottom of subbase layer.
a0108147-4cd9-5ee6-8bfb-7cfc54aaa2f3 | note | Acceptance Criteria - Per IFC Design
d250d213-e83e-56ea-b9d3-e3244a1eab5e | note | Verifying Document - None
51c7b322-6e4e-51eb-a0bd-93fe9567a8f4 | note | Frequency - During Construction
65502e73-4f0b-5284-810d-9963fb217502 | note | Inspection Type (Visual, other) - Inspection
ed3d38a9-0a7e-59d9-8fd5-00df57f045ed | note | Inspection: Key - FORE
46d14628-0fc6-59f6-ae3f-49e80867b4e1 | note | Inspection: By (Role Key) - Downer
e50a4e9c-7690-4228-a247-218cc413ba24 | checkpoint | 8.9 - Sand bund protection during construction
076d9ef9-0440-57e3-a332-78457c0cedc1 | note | Inspection Point: Quality Control Activity - Confirm existing sand bund protection on each frontage for duration of works
2962412d-b42b-5454-86fe-207204c89938 | note | Acceptance Criteria - Per methodology
b039bc62-302d-59f9-892e-635c194af85b | note | Verifying Document - None
64498029-c33c-556c-8910-bb79cd6c4c6a | note | Frequency - Daily,during construction
8d7541ea-c246-5d4b-8b68-2afb3df3f967 | note | Inspection Type (Visual, other) - Inspection
613864fa-4b1b-5198-8fe2-ff7e026470ff | note | Inspection: Key - FORE
0ad0ba10-e34a-5965-8f67-fae21d69abab | note | Inspection: By (Role Key) - Downer
c3e6cf5a-6a33-47c2-8ac7-6cba55c45951 | checkpoint | 8.10. - Dust control
f4f5dd23-e79c-51f0-a9c1-a14aad91313c | note | Inspection Point: Quality Control Activity - Dust control measures in place and assessments performed to prevent airborne dispersion
b5aeb227-23fe-5e0e-a83b-e266f6b790eb | note | Acceptance Criteria - Per RAP
21657435-688e-51ed-8672-32b336689454 | note | Verifying Document - None
6ed943ce-209d-5b04-8cbf-6b3698981edc | note | Frequency - Daily,during construction
68af5f3a-2cd4-514a-a0e8-0a8f1368b64d | note | Inspection Type (Visual, other) - Hold point
e0d4a1e4-1981-5508-983a-e60445668733 | note | Inspection: Key - FORE, ENG
dbe35a1f-3fe7-5bf1-bac4-a4fe35b43040 | note | Inspection: By (Role Key) - Downer, T+T
80743100-e785-4086-894d-1804f171b0b1 | signoff | AUTHORITY HOLDPOINT
67a24def-04c5-4ad6-861d-b43d194ce699 | checkpoint | 8.11 - Dust control
0a3ccde6-2878-5f5d-8f88-fc07609bec18 | note | Inspection Point: Quality Control Activity - Exposed areas covered with appropriate geotextile or polythene, secured adequately against the weather if they are unattended for extended periods
f355683b-8874-53e5-a9c7-7ea379cfcd7c | note | Acceptance Criteria - Per Rap
8e026f4a-c233-57d8-ac8f-fcc729ca4004 | note | Verifying Document - None
1c850b80-191b-5e96-874d-1bc141d735ff | note | Frequency - Daily,during construction
5af34b9a-328e-54bc-8652-d091990adc48 | note | Inspection Type (Visual, other) - Inspection
b2998780-4bf0-5ec1-a706-502d142418ed | note | Inspection: Key - FORE
2a6caac4-1c08-5331-9afc-fda7115e9a3b | note | Inspection: By (Role Key) - Downer
1710a645-1e8f-4fb6-bc46-b9b821b7f19d | checkpoint | 8.12 - Stockpiling
b0bdccfb-28ac-50a8-b253-e3d6e3e5ff0a | note | Inspection Point: Quality Control Activity - Waste material shall be excavated directly to truck or from excavator to loader to truck. Where temporary stockpiling is required, stockpiles shall be formed on impermeable sheeting. Ideally stockpiles shall not be left overnight, but where this is not possible, stockpiles shall be covered with impermeable sheeting that is secured against wind.
5768f60f-ffe4-522f-a210-27a246df7332 | note | Acceptance Criteria - Per RAP
81996037-c70d-55cd-b0a6-484f058bf75a | note | Verifying Document - None
092a2848-b017-5ced-afcb-1bdab13354a5 | note | Frequency - Daily,during construction
1df4ae86-6d64-5757-a336-a792753461fb | note | Inspection Type (Visual, other) - Inspection
df020048-73c8-5593-b1b0-0ed5d9bce008 | note | Inspection: Key - FORE
860672cd-b33e-582a-9428-b7c79d59aa87 | note | Inspection: By (Role Key) - Downer
a4f6b69a-44f6-4a3e-989d-be4b36d1a8a8 | checkpoint | 8.13 - Equipment Decontamination
b7e9221f-3045-5984-9ed1-b9d946870613 | note | Inspection Point: Quality Control Activity - Any equipment coming into contact with contaminated sawdust/sand within the remediation area shall be decontaminated in a designated wash area prior to leaving the site.
acdc1fd1-63b2-5820-b163-5f330d91fc69 | note | Acceptance Criteria - Per RAP
33b7354c-2713-55e4-a767-ab2b9d8eb7da | note | Verifying Document - None
60f85bb6-10b6-5d76-8d24-f0e5b3997812 | note | Frequency - Upon Completion of Works/ between transferring equipment form site to adjacent work areas.
bf74fd2d-c232-52e5-b18d-dca9aa381efa | note | Inspection Type (Visual, other) - Inspection
8d43067c-00c1-5097-a489-70ca77989f57 | note | Inspection: Key - FORE, PS
ae4dfec5-1435-5e12-8e3c-d4b24a1d0163 | note | Inspection: By (Role Key) - Downer
ab38337e-ba7a-4305-ada8-bb8322e7ba73 | checkpoint | 8.14 - Offsite transport
64df89b7-befa-55a8-8ce6-673b6c3b7681 | note | Inspection Point: Quality Control Activity - Trucks transporting sawdust or sand offsite shall be decontaminated prior to leaving site (refer Section 5.4.7), shall be free of debris prior to leaving site, and there shall be no tracking of material onto roads or footpaths.
98a75bd6-da46-55f3-8a87-b8984ae21796 | note | Acceptance Criteria - Per RAP
4f1674b9-fdfc-580c-8366-d6ba885734e4 | note | Verifying Document - None
97d09fcb-1f8e-5fe2-8196-38485cb533f6 | note | Frequency - Daily,during construction
8d9caec8-145b-58eb-85b8-43a5894701c6 | note | Inspection Type (Visual, other) - Inspection
77d639fa-577a-509b-b144-6ae298118b6a | note | Inspection: Key - FORE, PS, SUB
3ead7e5d-33c2-5913-87cf-2e6de1f5d782 | note | Inspection: By (Role Key) - Downer, Sub Transport
a963d59b-8128-4d61-b4a0-aed65606d391 | checkpoint | 8.15 - Offsite transport
d298e77e-21d6-59da-89b4-b5950bbea50e | note | Inspection Point: Quality Control Activity - Loads are covered prior to leaving site.
f0f3196b-3d61-5c83-92b7-e4cb280c205a | note | Acceptance Criteria - Per RAP
b78faad6-5276-5a3f-964b-5ec71c0041a0 | note | Verifying Document - None
3b85bd4a-f697-5368-a14c-558e3cae2d6f | note | Frequency - Daily,during construction
f7679387-090b-5f7f-bd36-706259a7d194 | note | Inspection Type (Visual, other) - Inspection
4ac44cb2-bc78-5787-9a6f-6f24de26b3e2 | note | Inspection: Key - FORE, SUB
73f88943-5507-52f6-8525-b9a6aae24fd6 | note | Inspection: By (Role Key) - Downer, Sub Transport
fe1f305b-7199-4615-a867-275ff0ffb410 | checkpoint | 8.16 - Offsite transport Load Tracking
573a48f1-ac99-5175-907c-e254addd4b66 | note | Inspection Point: Quality Control Activity - Details of each load removed from site are recorded onsite to enable reconciliation against the disposal site weighbridge documentation.
32bebbb0-2dba-54ee-9670-ed40757d3488 | note | Acceptance Criteria - Per RAP
49c5ffe9-ebe3-5910-80c0-8803c3aa16c3 | note | Verifying Document - None
5be4f3a0-e450-5512-b926-b1329ad37d4d | note | Frequency - Daily,during construction
b2dad37b-241e-5303-a88e-960a78788266 | note | Inspection Type (Visual, other) - Inspection
771efabc-9add-5888-956c-9e7253589b22 | note | Inspection: Key - FORE, SUB
4a5ea194-696d-598f-8f20-8b2d9f187db7 | note | Inspection: By (Role Key) - Downer, Sub Transport
e16741c8-2f2a-45c8-9559-89ca0fe5daf5 | checkpoint | 8.17 - Unexpected Contamination
6170cec6-f416-5f9b-823c-df92102a4ce6 | note | Inspection Point: Quality Control Activity - Advise NCC and SQEP immedialty should evidence of unexpected contaminated be encountered during the works on site.
3bc96eba-c1c7-508d-9f51-d4732c6b0824 | note | Acceptance Criteria - Per RAP
22a65ca1-ec99-5a8e-ac5e-04376d9c7dfe | note | Verifying Document - None
dcff8f04-6081-5bac-9743-3ebb60fafec4 | note | Frequency - Daily,during construction
cef4f33e-8e41-5a55-8f83-a3a950a881c5 | note | Inspection Type (Visual, other) - Inspection
f6abb39b-0dcc-5543-8449-706b05e59381 | note | Inspection: Key - FORE, PS
02641b6c-2dea-511d-ac49-444148361a85 | note | Inspection: By (Role Key) - Downer