## ITP Cover Page
Temp works - Removal of Traffic islands and swale backfill - Inspection and Test Plan
Project: Tauriko Enabling Project
Number and Revision: DN1210 - SP2 - TEMP-003 - Rev 0
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Tauriko Enabling Project |  |  |  |  | ITP Number: |  |  | SP2 - TEMP-003
Project Number: |  |  | DN1210 |  |  |  |  | ITP Status: |  |  | IFC
ITP Description: |  |  | Temp works - Removal of Traffic Islands and Swale Backfilling Inspection and Test Plan |  |  |  |  | Revision: | 1000 |  | 0
Contract Number: |  |  | 8287 |  |  |  |  | Drawing Sets: |  |  | Temp works
Customer: |  |  | Waka Kotahi |  |  |  |  | Specification: |  |  | Temp works
Quality Specified: |  |  | ISO9001:2015
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
0 | Draft for Approval | 2024-09-10 |  | Nick Adams |  | Issued for construction |  |  |  | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
[10 empty] | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
[10 empty] | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM |  | Nick Adams | [5 empty] | Downer PM
Downer QM |  | Cordelia Girdler Brown | [5 empty] | Downer QM
Client (If Applicable) | [7 empty] | Client (If Applicable)

## ITP Master Body
Temp works - Removal of Traffic islands and swale backfill - Inspection and Test Plan
Project: Tauriko Enabling Project
Number and Revision: DN1210 - SP2 - TEMP-003 - Rev 0
Item No. | Inspection and Test Point | Detail | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Testing Quantity Required (based from schedule qtys) | Verification Activity |  | Downer Conformance of Compliance Signoff
[7 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details | ENGINEERS COMMENTS - Date: | DOWNER RESPONSE - Date:
SECTION 1 – PRE-CONSTRUCTION HOLD POINTS
1.1 | General
1.1.1 | Methodology | The Contractor shall submit the construction and QA methodology, for each element of Earthworks, incl construction, Site Access, dewatering, wet weather, testing, inspection and hold points for review and approval prior to works. | Engineers Approval | Appendix V | Approved Methodology | Prior to construction | HP | ENG
1.1.3 | Erosion & Sedimentation Controls | Confirm that the weather and environment will be suitable for works with the Environmental advisor. | As-built Completed | Internal Hold Point | ESC As-built | Prior to works commence | H | QM
1.2 | Geotextile and Geogrid
1.2.1 | Geotextile | The Contractor shall submit the full details of the geotextile they propose to use to the Engineer for approval prior to installation. | Engineers Approval | PS 16.5.7 Appendix V | Data Sheets | Results to Engineer for Approval | HP | ENG
1.3 | GAP65
1.3.1 | Source data | NZS4407:2015, Test 3.11 - Weathering Quality Index NZS4402:1988, Test 4.2.1 - Standard Compaction Result NZS4407:1991, Test 3.12 - Los Angeles Abrasion Test Result | As per specified criteria | PS 16.5.5 | IANZ Accredited Report | 2 Test per Source | HP | ENG
1.4 | Asphalt
1.4.1 | Dense Graded Asphalt | Conforming sieve size and Mix designation refer to clause 3.3.1 and Table 3.5 |  | NZTA M10: 2020 / PS 20.12 | IANZ Accredited Report | Prior to construction and during construction | H | SUP
1.5 | Subsoil Drainage
1.5.1 | Subsoil Pipes | Drainage pipes used in subsoil drainage shall be smooth bore perforated Landflow 100mm diameter complying with NZTA F5 unless otherwise stated on the drawings. Pipes shall not have a geofabric filter sock unless requested by the Engineer. | NZTA F5 |  | Verifying document to be copy of delivery dockets, photos of pipes onsite with tag showing class | During Installation | I | SE
1.5.2 | Catchpit | Catchpits are proposed to be precast concrete chambers with grate and frames shall be cycle-friendly Hynds Hydro Stormwater Grate and Frame or approved equivalent for all local roads and the state highway |  | PS 21.5.4 PS 21.6.12 | Site Photo / Checksheet | During Installation | I | SE
SECTION 2 – TEMPORARY CONSTRUCTION - EARTHWORKS
2.1 | Cut/Strip Top Soil - Subgrade Testing
2.1.1 | Cut Subgrade Testing - Cohesive Soil Scala Penetrometer | NZS4402:1988, Test 6.5.2 - Dynamic Cone Penetrometer Scala penetrometer testing to be undertaken instead of shear vane tests where shear vane is unable to penetrate subgrade material | Minimum 3 blows per 100mm penetration | Appendix XVIII | Scala Report | 4 test per 400M2 | I | SE
2.1.2 | Proof Roll | Visual Inspection of Proof Roll an d undercut surface | Visual Inspection | Appendix XVIII | Visual Site Record | Across Finished Area | I | SE
SECTION 3 – COMPACTION OF IMPORTED FILL
3.1 | Placement of Geotextile and Backfilling of Swale
3.1.1 | Placement of Geotextile | A layer of Class B Geotextile Fabric is to be placed between the cut surface and imported GAP65 Fill with minimum overlap 400mm between adjacent geotextile strips. | Geotextile to be placed across the undercut base and up the sides, with joints overlapped by 500mm minimum | Engineers Approval | PS 16.6.4 TNZ F/7: 2003 8.3 | As Required | I | SE
3.1.2 | Subsoil Drain inspection | Subsoils to be placed at base of cleaned-out swale to falls required to drain to existing road crossing drainage | Visual inspection | - |  | - | I | SE
3.3 | Backfill GAP65 Aggregate
3.3.1 | Backfill Installation | All backfill is to be installed in 250mm lifts and compacted to the following standards. | Visual Inspection | Appendix XVIII | Photo | Each Layer | I | SE
3.3.2 | Compaction - Clegg Hammer | ASTM D5874-16:2016 Clegg Hammer Testing | Structural Fill Min CIV 18 Ave CIV 20 Non-Structural Fill Min CIV 10 Max CIV 12 | Appendix XVIII | Clegg Hammer Report | 1 set (5 tests per 5x5m grid) per 1000m2 of placed per area worked each day, per lift | I | SE
SECTION 4 – SURFACING
4.1.1 | DG10 Asphalt | Layer thickness to be min. 40mm or approved by Engineer | Visual Inspection | NZTA M10: 2020 / PS 20.12 | Prior to Paving | During construction | I | SE
SECTION 5 – AS-BUILTS
5.1.1 | As-Builts | As-Built records and drawings shall accurately record the layout and extent of all the work and locations of subsurface drainage systems and their outlets. |  | PS 16.7.6 | Survey Records | Post Construction | D | SV
Note on C15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The range of tests as specified by section 16.5.5 of the specifications.