## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DN1210-SP2-003 ITP Temp works - Removal of Traffic islands and swale backfill | itp |  |  |  |  | DN1210-SP2-003 ITP Temp works - Removal of Traffic islands and swale backfill Rev 0
section | SECTION 1 – PRE-CONSTRUCTION HOLD POINTS
checkpoint | 1.1.1 - Methodology
label | Detail - The Contractor shall submit the construction and QA methodology, for each element of Earthworks, incl construction, Site Access, dewatering, wet weather, testing, inspection and hold points for review and approval prior to works.
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - Appendix V
label | Verifying Document - Approved Methodology
label | Testing Quantity Required (based from schedule qtys) - Prior to construction
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.3 - Erosion & Sedimentation Controls
label | Detail - Confirm that the weather and environment will be suitable for works with the Environmental advisor.
label | Acceptance / Conformance Criteria - As-built Completed
label | Standard / Specification - Internal Hold Point
label | Verifying Document - ESC As-built
label | Testing Quantity Required (based from schedule qtys) - Prior to works commence
label | Verification Activity: Activity - H
label | Verification Activity: By - QM
checkpoint | 1.2.1 - Geotextile
label | Detail - The Contractor shall submit the full details of the geotextile they propose to use to the Engineer for approval prior to installation.
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - PS 16.5.7, Appendix V
label | Verifying Document - Data Sheets
label | Testing Quantity Required (based from schedule qtys) - Results to Engineer for Approval
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3.1 - Source data
label | Detail - NZS4407:2015, Test 3.11 - Weathering Quality Index
label | ○ NZS4402:1988, Test 4.2.1 - Standard Compaction Result
label | ○ NZS4407:1991, Test 3.12 - Los Angeles Abrasion Test Result
label | Acceptance / Conformance Criteria - As per specified criteria
label | Standard / Specification - PS 16.5.5
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 2 Test per Source
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4.1 - Dense Graded Asphalt
label | Detail - Conforming sieve size and Mix designation refer to clause 3.3.1 and Table 3.5
label | Acceptance / Conformance Criteria -
label | – – – – – – – – – – – – –
label | Sieve Size (mm) ¦¦ Mix Designation: DG7 ¦¦ Mix Designation: DG ¦¦ Mix Designation: DG14
label | Percentage Passing Sieve Size (By Mass)
label | – – – – – – – – – – – – –
label | 19.0 ¦¦ – ¦¦ – ¦¦ 100
label | 13.2 ¦¦ – ¦¦ 100 ¦¦ 83 – 100
label | 9.5 ¦¦ 100 ¦¦ 79 – 100 ¦¦ 68 – 90
label | 6.7 ¦¦ 80 – 100 ¦¦ 63 – 90 ¦¦ 54 – 79
label | 4.75 ¦¦ 66 – 90 ¦¦ 50 – 79 ¦¦ 43 – 70
label | 2.36 ¦¦ 44- 75 ¦¦ 32 – 61 ¦¦ 28 – 55
label | 1.18 ¦¦ 29 – 60 ¦¦ 22 – 48 ¦¦ 19 – 43
label | 0.600 ¦¦ 19 – 47 ¦¦ 15 – 36 ¦¦ 13 – 32
label | 0.300 ¦¦ 12 – 33 ¦¦ 10 – 26 ¦¦ 9 – 23
label | 0.150 ¦¦ 8- 22 ¦¦ 6 – 17 ¦¦ 6 – 16
label | 0.075 ¦¦ 5 – 12 ¦¦ 4 – 11 ¦¦ 4 – 10
label | – – – – – – – – – – – – –
label | Minimum Layer Thickness (mm) ¦¦ 25 ¦¦ 35 ¦¦ 50
label | Binder Content ¦¦ 5.0 – 7.0 ¦¦ 4.5 – 6.5 ¦¦ 4.3 – 6.3
label | – – – – – – – – – – – – –
label | Standard / Specification - NZTA M10: 2020 / PS 20.12
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Prior to construction and during construction
label | Verification Activity: Activity - H
label | Verification Activity: By - SUP
checkpoint | 1.5.1 - Subsoil Pipes
label | Detail - Drainage pipes used in subsoil drainage shall be smooth bore perforated Landflow 100mm diameter complying with NZTA F5 unless otherwise stated on the drawings. Pipes shall not have a geofabric filter sock unless requested by the Engineer.
label | Acceptance / Conformance Criteria - NZTA F5
label | Verifying Document - Verifying document to be copy of delivery dockets, photos of pipes onsite with tag showing class
label | Testing Quantity Required (based from schedule qtys) - During Installation
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 1.5.2 - Catchpit
label | Detail - Catchpits are proposed to be precast concrete chambers with grate and frames shall be cycle-friendly Hynds Hydro Stormwater Grate and Frame or approved equivalent for all local roads and the state highway
label | Standard / Specification - PS 21.5.4, PS 21.6.12
label | Verifying Document - Site Photo / Checksheet
label | Testing Quantity Required (based from schedule qtys) - During Installation
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | SECTION 2 – TEMPORARY CONSTRUCTION - EARTHWORKS
checkpoint | 2.1.1 - Cut Subgrade Testing - Cohesive Soil Scala Penetrometer
label | Detail - NZS4402:1988, Test 6.5.2 - Dynamic Cone Penetrometer
label | ○ Scala penetrometer testing to be undertaken instead of shear vane tests where shear vane is unable to penetrate subgrade material
label | Acceptance / Conformance Criteria - Minimum 3 blows per 100mm penetration
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Scala Report
label | Testing Quantity Required (based from schedule qtys) - 4 test per 400M2
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 2.1.2 - Proof Roll
label | Detail - Visual Inspection of Proof Roll an d undercut surface
label | Acceptance / Conformance Criteria - Visual Inspection
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Visual Site Record
label | Testing Quantity Required (based from schedule qtys) - Across Finished Area
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | SECTION 3 – COMPACTION OF IMPORTED FILL
checkpoint | 3.1.1 - Placement of Geotextile
label | Detail - A layer of Class B Geotextile Fabric is to be placed between the cut surface and imported GAP65 Fill with minimum overlap 400mm between adjacent geotextile strips.
label | Acceptance / Conformance Criteria - Geotextile to be placed across the undercut base and up the sides, with joints overlapped by 500mm minimum
label | Standard / Specification - Engineers Approval
label | Verifying Document - PS 16.6.4, TNZ F/7: 2003 8.3
label | Testing Quantity Required (based from schedule qtys) - As Required
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 3.1.2 - Subsoil Drain inspection
label | Detail - Subsoils to be placed at base of cleaned-out swale to falls required to drain to existing road crossing drainage
label | Acceptance / Conformance Criteria - Visual inspection
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 3.3.1 - Backfill Installation
label | Detail - All backfill is to be installed in 250mm lifts and compacted to the following standards.
label | Acceptance / Conformance Criteria - Visual Inspection
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Photo
label | Testing Quantity Required (based from schedule qtys) - Each Layer
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 3.3.2 - Compaction - Clegg Hammer
label | Detail - ASTM D5874-16:2016 Clegg Hammer Testing
label | Acceptance / Conformance Criteria - Structural Fill
label | – Min CIV 18
label | – Ave CIV 20
label | ○ Non-Structural Fill
label | – Min CIV 10
label | – Max CIV 12
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Clegg Hammer Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests per 5x5m grid) per 1000m2 of placed per area worked each day, per lift
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | SECTION 4 – SURFACING
checkpoint | 4.1.1 - DG10 Asphalt
label | Detail - Layer thickness to be min. 40mm or approved by Engineer
label | Acceptance / Conformance Criteria - Visual Inspection
label | Standard / Specification - NZTA M10: 2020 / PS 20.12
label | Verifying Document - Prior to Paving
label | Testing Quantity Required (based from schedule qtys) - During construction
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | SECTION 5 – AS-BUILTS
checkpoint | 5.1.1 - As-Builts
label | Detail - As-Built records and drawings shall accurately record the layout and extent of all the work and locations of subsurface drainage systems and their outlets.
label | Standard / Specification - PS 16.7.6
label | Verifying Document - Survey Records
label | Testing Quantity Required (based from schedule qtys) - Post Construction
label | Verification Activity: Activity - D
label | Verification Activity: By - SV
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature