## ITP-01
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # FHC-ITP-000
[11 empty] | Revision : 01 | Date: 30/04/24
Client: |  | Yarra Trams |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Montague St Northern Crash Beam |  | Contract Hold Points - Pre Construction |  | Name: | Jake Cardillo | Name: | Patrick Fagan |  | Name: Shaun Kent
Contract No: |  | 8B5400 |  | Specifications: As outlined
|  |  |  | Structure / Component: |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: |  | Date : 30/04/24 |  | Date : 30/04/24 |  |  | Date : 30/04/24
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Design and Submissions
1.1 | Submission & approval of concrete mix design prior to commencement of project |  | Prior to first concrete pour | Concrete mix design submitted and approved at least 2 weeks prior to first pour. Mix grade shall be VR 400/40. Concrete shall be manufactured, transported and handled in accordance with the requirements of AS 3600, AS3600 & AS 1379 | DN S002 P&S IFC | Verify | Mix Design ITP | HP | FH Engineer / Superintendent | N/A |  | N/A
1.2 | Submission & approval of epoxy adhesive product prior to commencement of project |  | Prior to first epoxy pour | Ensure product adheres to notes specified in the P&S DRG S004 | DN S004 P&S IFC | Verify | Superintendent approval Completed ITP | HP | Site Engineer / Superintendent | N/A |  | N/A
1.2 | Submission & approval of high-strength non-shrink mortar prior to commencement of project |  | Prior to first grout pour | Ensure product adheres to notes specified in the P&S DRG S005 | DN S005 P&S IFC | Verify | Superintendent approval Completed ITP | HP | Site Engineer / Superintendent | N/A |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent