## ITP-01
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # FHC-ITP-026
[11 empty] | Revision : 01 | Date : 21/10/2024
Client: Yarra Trams |  |  |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: Montague St Northern Crash Beam |  |  |  | Structural Grout Construction |  | Name: | Leo Watson | Name: | Patrick Fagan |  | Name: | Shaun Kent
Contract No: 8B5400 |  |  |  | Specifications: AS 3600-2018, VicRoads Standard Specification Section 606, 607, 610, 611, 614
|  |  |  | Structure / Component: |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: |  | Date : | 2024-10-22 | Date : | 2024-10-22 |  | Date : | 2024-10-22
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Design and Submissions
1.1 | Check for correct documentation |  | Prior to commencing any activity | Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision | Drawings and drawing registers | Visual inspection | This ITP signed | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: PMP, EMP, TMP, SWMS & WP | PSP, EMP, TMP, JSEA, SWMS, WP | Visual Inspection | This ITP signed | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.3 | Approval of concrete mix design |  | Prior to the first concrete pour | Concrete Mix is Registered with VicRoads. Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings. | 610.07 P&S IFC | Verify | This ITP signed | IP | Fulton Hogan Engineer | N/A |  | N/A
1.4 | Reinforcement |  | Prior to concrete pour | Reinforcement schedule has been prepared for the reinforcement supply, to ensure that it achieves the specified tolerances on member dimensions, concrete cover and specified locations | 611.04 | Verify | This ITP signed | IP | Fulton Hogan Engineer | N/A |  | N/A
2 | Construction Activities
2.1 | Formwork Design and Construction |  | Each Element | Dimensions in plan as per drawings to achieve the desired grout profile. Formwork rigid, sufficiently braced to support the pressure of the product and sealed to prevent leaks. | IFC Drawings | Verify | This ITP signed | SCP HP* | Fulton Hogan Engineer | N/A |  | N/A
2.2 | Pre-pour Inspection |  | Each Element | Concrete substrate surface moisture condition as per the Product's TDS, with no ponding of water. Formwork location and RLs comply. Where applicable, any reinforcement is clean and has the required cover. | IFC Drawings Product TDS 610.20 | Verify | This ITP signed | HP | Fulton Hogan / Yarra Trams |  |  | N/A
2.3 | Weather Conditions |  | Each Element | All freshly finished surfaces shall be protected where required from the sun, wind or rain, until curing is implemented. The temperature of the cementitious products, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C. Enter: Required information on the Grout Pour Record. | 610.17 610.17 (a) & (e) Table 610.171 | Verify | This ITP signed | IP | Fulton Hogan | N/A |  | N/A
2.4 | Mixing Product |  | Each Batch | Size of mixer should match the application. Only whole bags to be mixed with potable water. Volume of water matches the required amount for flowable consistency and accurately measured. Product poured into the mixer slowly. Mixing time as per TDS so that a smooth, even consistency is obtained. | Product TDS 610.28 | Visual inspection | This ITP Signed | IP | Fulton Hogan | N/A |  | N/A
2 | Construction Activities (Continued)
2.5 | Product Testing - Compressive Strength Cubes |  | Each Element | Cube moulds to be 75mm x 75mm maximum, made from rigid steel moulds and require lids due to the expansive nature of shrinkage compensating products. Testing is be in accordance with the following frequencies: First batch = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength) Every 100kg of product thereafter = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength) | 610.28 610.33 | Test | This ITP signed | IP | Fulton Hogan / Tester | N/A
2.6 | Placement & Compaction |  | Each Element | All batches are traceable. Product poured from one side of the formwork to eliminate the entrapment of air or surplus pre-soaking water. Product should flow to all areas and self consolidate. Product that stiffens or is showing signs of stiffening shall not be used. | Product TDS | Visual inspection | This ITP signed. Accurate Site Notes & Load Mapping | IP | Fulton Hogan | N/A |  | N/A
2.7 | Curing |  | Each Element | Curing to commence immediately after finishing operations and continue for the duration specified in table 610.231. Curing methodology to be in accordance with the approved procedure and manufacturer's TDS. | Curing Methodology 610.23 Table 610.231 | Visual inspection | This ITP signed | IP | Fulton Hogan | N/A |  | N/A
3 | Post-Pour Details and Inspection
3.1 | Formwork removal |  | Each concrete pour | Formwork shall be removed carefully and in such a manner as to avoid damage to the member or the grout surfaces and maintain safety at all stages of removal. Formwork and formwork supports shall not be disturbed or adjusted during the grouting operation | 610.25 | Verify | This ITP signed | IP | Fulton Hogan | N/A |  | N/A
3.2 | Concrete Sampling and Testing |  | Prior to lot closure | Grout sampled and tested for Compressive Strength. | IFC Drawings Product TDS 610.28 610.33 | Verify | This ITP signed | TP | Fulton Hogan | N/A |  | N/A
3.3 | As Built Drawings |  | Prior to lot closure | Recorded of as-built drawings | Fulton Hogan Procedure | Verify | This ITP signed | IP | Fulton Hogan | N/A |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent