## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
ecc24e6e-876d-4450-8df7-c5343206fcb6 | checklist | ITC&ITP No.1 - Speedpanel & Pre-hang Fire Rated Plasterboard - Rev B | itp | ITC&ITP No.1 - Speedpanel & Pre-hang Fire Rated Plasterboard
7a520064-62e7-4a02-9d32-89e6310d799f | section | Speedpanel & Pre-hang Fire Rated Plasterboard
078741d0-becf-4051-948a-2b65f56e2d12 | checkpoint | 1 - Address Safety
f34ff053-a31f-5d68-b068-16f9efbe487f | note | Reference Documents - SWMS
ded8f2c0-427d-5045-a47c-7100933a6e98 | note | Acceptance Criteria - Safety Method Work Sheet approved by Georgiou Group Pty Ltd
0719510c-6721-509c-926a-05d9445feea8 | note | Frequency - Each location
ab021d91-3335-50ce-988d-243a5bb01403 | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
73329bdd-319d-5242-b16a-8de53c48c59a | note | Inspection By: Subcontractor - S
90858bfe-fcb8-5f6a-8bc0-f7f6c9fd3391 | note | Inspection By: Georgiou - S
bc78f3ba-48f4-456d-ac0c-41c9deb250b6 | checkpoint | 2 - Set out Speedpanel walls
680ca943-49ff-57ee-987a-214d44663cb4 | note | Reference Documents - Architect drawings
ae7c76a2-5ff3-5326-85f6-438275ab9246 | note | Acceptance Criteria - Light Weight Wall Plan approved by Georgiou Group Pty Ltd Speedpanel installation guide revision 1
32216ffd-05e1-5f88-8210-21c617e2b392 | note | Frequency - Each location
298256e3-7cb5-5b94-98be-d89aba378081 | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
2f37739c-b402-5c05-8df8-94caa9f1e38b | note | Inspection By: Subcontractor - S
9536c148-967b-5c6e-b686-8e31fee2cd5b | note | Inspection By: Georgiou - S
b74fa149-cc91-4fa8-92f8-97a290a29ba6 | checkpoint | 3 - Install Speedpanel
b1c9be02-4010-56f2-8e0b-7b8c3ccb95e3 | note | Reference Documents - Architect drawings
5c07d0d9-7092-5fa1-9c43-6978aff99bb7 | note | Acceptance Criteria - Light Weight Wall Plan approved by Georgiou Group Pty Ltd. Speedpanel installation guide revision 1
36b91514-778d-5e95-a290-67f02d649575 | note | Frequency - Each location
2264a157-d304-54da-b6d0-015b14f7dc76 | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
259250a9-b53f-5a5c-b1cc-54c9f562566d | note | Inspection By: Subcontractor - S
a07fe817-c565-5895-ae7e-77cd17a52097 | note | Inspection By: Georgiou - S
03fe4f62-fccc-44ea-8a28-041717ed382d | checkpoint | 4 - Caulking
7d74270f-9e11-556e-8f61-aa442be116d4 | note | Reference Documents -
a3bc818c-8b08-5654-9c2e-2520f086c21a | note | Acceptance Criteria - Speedpanel installation guide revision 1
c9869dd5-1bc2-5afa-9d73-acbce8354216 | note | Frequency - Each location
750b5f6a-c3dc-5f42-a822-bea02ded8ebf | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
a8669e38-c5c0-5338-b147-8d6ec2238782 | note | Inspection By: Subcontractor - S
c22a59bc-dccb-5366-af8f-e93b77103f9a | note | Inspection By: Georgiou - S
9cebbb83-d5ff-4d0b-acfd-95f22144df0d | checkpoint | 5 - Clean up
6fcc80f8-6aba-5c82-81b7-ceea6a260aaa | note | Reference Documents -
0e962e7a-554e-5b5c-b8a3-3bba3bc1f6c5 | note | Acceptance Criteria - Waste all cleaned. Tools and materials placed well.
1a6b135b-f585-546b-a4ce-d52495dbef22 | note | Frequency - Each location
cb4fe1a5-7b64-549c-9856-dcf358132b77 | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
5cbdfce9-4972-5bb8-87d9-00ab0ac4209f | note | Inspection By: Subcontractor -
c0492336-7c26-59d5-acd1-1cf6e3982b19 | note | Inspection By: Georgiou - R
dddb5585-3635-4b44-af46-d482430e4283 | checkpoint | 6 - Pre-hang fire rated plasterboard
0b96d1db-3842-5185-8a00-f445b1e126ea | note | Reference Documents - Architect drawings
82fa8c98-aad5-5d6a-b2c7-fd6afe8669ed | note | Acceptance Criteria - Light Weight Wall Plan approved by Georgiou Group Pty Ltd. GTEK Ceiling & Wall Solution Rev. March 2024
fa56ee50-249e-58e9-987f-3753ce8d0b0d | note | Frequency - Each location
83eea8d7-9203-5f89-b0b4-bcf978c21691 | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
db7190a6-84aa-5b9a-99ac-35038562ab00 | note | Inspection By: Subcontractor - S
7c8366e7-6f25-52cf-a7ce-55dd7c59298f | note | Inspection By: Georgiou - S
38115a20-4f4f-44ac-bbcf-11f7071ab87e | checkpoint | 7 - Taping and stopping
5e085573-8c9a-5e92-b7c4-961b752efe6e | note | Reference Documents - Architect drawings
685f4103-e038-5c5a-9d18-45a3b2093c34 | note | Acceptance Criteria - GTEK Ceiling & Wall Solution Rev. March 2024
b96ae856-313e-53bc-859f-08e299501dfe | note | Frequency - Each location
b0c815d3-2bfa-59da-83f5-c6aa1bc4d9f4 | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
7de3a5cc-aac3-528e-a369-3b2e08f0e230 | note | Inspection By: Subcontractor - S
61ff5c67-081d-5bd5-9165-80ea8d2b4044 | note | Inspection By: Georgiou - S
4827aefb-c5dd-4dbf-a706-62a756618fea | checkpoint | 8 - Clean up
9056b38a-4edb-5133-8a82-872a0645a359 | note | Reference Documents -
1fff8573-ec34-5802-a9af-0c02d2d1e34a | note | Acceptance Criteria - Waste all cleaned. Tools and materials placed well.
f622b85c-f0e8-563a-83fc-f319bf141af5 | note | Frequency - Each location
e4ae95b6-8c39-5bfd-a94e-ce61829222ce | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
06de5b62-8d27-5a30-ab4a-4ae1b0103c17 | note | Inspection By: Subcontractor -
daabaf4b-8683-5a87-9fec-c999a8b7be0e | note | Inspection By: Georgiou - R
c7d6782b-55fc-4af2-955c-3115fa7a77e3 | checkpoint | Verification Statement
55740713-a5cd-50a2-9b69-5528a9db24d8 | note | This is to confirm that the nominated representative of L&D Commercial Interiors Pty Ltd, responsible for overseeing the works, has carried out all necessary inspections as listed above, and will be able to verify with documented evidence that the work has been completed and confirms to the contract specification(s)
114b855f-1cd8-5698-a513-9047832fe847 | date | Date of Inspection:
a02b19d9-8a0d-5279-ae8f-bfb84d4f8d79 | textbox | Carried out by:
809ae0b1-6ce2-51a3-9886-2bbea278c2ed | note | Attachments
79aab211-b49a-5a39-a34b-6e4521fcf0ed | tickbox | Checklists
09bba186-0dc8-5e94-b405-8b4d57015f84 | tickbox | Photos
09284f15-6942-552f-bb07-947def167825 | tickbox | Dockets
7e59b577-0290-56ea-a239-0da411f8cd1d | tickbox | Sample Material
a8cea8ad-80cc-5c17-8555-83044b38b2ed | tickbox | Drawings
8106490b-fe7c-5223-bcb9-fedacbeb4e63 | tickbox | Calibration Certificates
41758343-1135-5a72-9054-dd2a911a5101 | tickbox | Test Results / Certificate
cf93863f-e49f-5174-a31c-963ae595cfe8 | tickbox | Inspection reports
10ff1444-bb2c-545f-bd56-6fdbd45d7ecc | tickbox | Others:
bfcdacc5-3cd2-58a0-b3da-c99ce79c9fdf | textbox | Others
fede7c2e-89d9-49e0-9ddf-45607f122b3e | signoff | Signed:
5b2e5117-a198-4b8c-8d04-33d22d33dbc3 | checklist | ITC&ITP No.2 - Frame All Walls - Rev C | itp | ITC&ITP No.2 - Frame All Walls
84735f25-a53b-4242-b9a8-461274c82abd | section | Frame All Walls
ea0401f6-7576-4121-99cd-a2c55f4e9359 | checkpoint | 1 - Address Safety
5f8f0b9e-b797-5ea4-ae71-e097ab80c4e1 | note | Reference Documents - SWMS
9bdb0b61-54a8-588f-b667-e5f1aa948ade | note | Acceptance Criteria - Safety Method Work Sheet approved by Georgiou Group Pty Ltd
6b6da525-afc7-5489-b8d7-ee413e5fed0d | note | Frequency - Each location
3bd6c1b6-dac0-59e3-92ee-d6a553df455c | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
d12e3ddb-5436-5ec9-af7f-fdefaf4d9aeb | note | Inspection By: Subcontractor - S
3e1e8353-b4bb-5756-8b1b-cd922348e843 | note | Inspection By: Georgiou - S
bc40bc86-5fb4-4740-9f77-ae4bb1bff6c2 | checkpoint | 2 - Set out walls
87208efb-d6f0-5b6a-b02d-bf54b46582cd | note | Reference Documents - Architect drawings
423a3756-3f2f-5468-a968-20a033f3aa62 | note | Acceptance Criteria - Light Weight Wall Plan approved by Georgiou Group Pty Ltd. Studco Wall design & installation manual Volume 3.2
f27ba6a0-c29f-5bd9-9405-94152e033307 | note | Frequency - Each unit
994f5ca6-4878-59f1-95f7-c07a413bc72a | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
423df6fd-b006-57b2-b807-6bedf03a906d | note | Inspection By: Subcontractor - S
4217cdef-5288-5a25-b103-6ea0d9fcb039 | note | Inspection By: Georgiou - S
ab175d44-0acf-4d2a-aba6-edd0e281b86d | checkpoint | 3 - Furring channel to walls
8de0be0d-3d78-58ea-b7a6-7fafb9b12cf2 | note | Reference Documents - Architect drawings
96743ec7-e915-5add-9488-f83ef417b105 | note | Acceptance Criteria - Light Weight Wall Plan approved by Georgiou Group Pty Ltd. Studco Wall design & installation manual Volume 3.2
bf86895d-25f1-5c07-8952-1801983dddb5 | note | Frequency - Each unit
f2169988-ac8e-58bf-8528-9bdc9d4eb626 | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
0b5f3a3c-1041-5da7-a5fa-3bac4792f683 | note | Inspection By: Subcontractor - S
db411214-6b10-5a79-913a-ddb40333fd52 | note | Inspection By: Georgiou - S
48bb6f24-7555-4db7-a1a1-03024a3f428f | checkpoint | 4 - Metal stud wall frame
4fe3a568-0544-5c13-a006-3cc514be1f3f | note | Reference Documents - Architect drawings
84b82984-ecbf-59bd-9f2c-57dde441b21f | note | Acceptance Criteria - Light Weight Wall Plan approved by Georgiou Group Pty Ltd. Studco Wall design & installation manual Volume 3.2
bf5210e3-2f79-581e-9121-6eba3678d6c2 | note | Frequency - Each unit
d9c0413b-a494-5a1c-85b4-cf14b268ab58 | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
6c3c4fa9-e940-580a-a682-21926f6d78b5 | note | Inspection By: Subcontractor - S
8c066ae5-35af-5a57-bffe-4c689d625a35 | note | Inspection By: Georgiou - S
153a0823-dc02-4280-ae05-623c0b1f7785 | checkpoint | 5 - Noggins
91272922-5703-5328-b711-0420985d5549 | note | Reference Documents -
64cf1caa-077d-56c9-92c0-22de98b1a651 | note | Acceptance Criteria - As per scope of work. Studco Wall design & installation manual Volume 3.2
4f904a88-a6ae-5f6e-9e8e-1cf56fdc9d0b | note | Frequency - Each location
d0624b15-97f8-5725-8594-a17e886cedf8 | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
17e53ef9-e233-5cfd-8f6c-fa1477babf82 | note | Inspection By: Subcontractor - S
ef9dd80d-c51b-5a77-9ba0-117af565f4bf | note | Inspection By: Georgiou - S
1c78da23-f53c-4a70-8209-e42be1bb56c7 | checkpoint | 6 - Check no screws in deflection head
86925647-654f-53c7-9c70-c48c6389afcf | note | Reference Documents -
887dae12-6107-5e2d-bf19-a6b0b9d1d9d2 | note | Acceptance Criteria - No screws in deflection head
ef7e092e-af18-5866-bb95-3dc832047ff3 | note | Frequency - Each location
2632ed0f-9860-54bc-9ad2-a0dbfc46c943 | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
916d0849-317b-50b1-989a-07e202821c42 | note | Inspection By: Subcontractor - S
311d2fb5-363d-51a6-b937-d3d185bbde0a | note | Inspection By: Georgiou - S
f9ff840a-23e3-4c42-881b-d47f948481fe | checkpoint | 7 - Clean up
c56c826e-3083-5585-84cb-7a61ce633ead | note | Reference Documents -
934e5ddc-ffce-520a-abb4-999953e7fe55 | note | Acceptance Criteria - Waste all cleaned. Tools and materials placed well.
4df904d5-3e00-5d89-bb08-f36ff84e183f | note | Frequency - Each location
0f2122bd-586a-5ac0-969e-d68d0dace118 | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
52d65ab8-e167-57e4-be56-f318c4875d6a | note | Inspection By: Subcontractor -
8570434d-65ff-5a6d-90e6-805860b68698 | note | Inspection By: Georgiou - R
4d24d81e-7ab0-4b4a-92ea-8987079e2034 | checkpoint | Verification Statement
8da3bb37-8265-5428-99e2-acad5df615e6 | note | This is to confirm that the nominated representative of L&D Commercial Interiors Pty Ltd, responsible for overseeing the works, has carried out all necessary inspections as listed above, and will be able to verify with documented evidence that the work has been completed and confirms to the contract specification(s)
0399b127-4c03-512f-8df1-2688124dd8fb | date | Date of Inspection:
d9757f9c-5cea-5351-af73-98691ee3e89d | textbox | Carried out by:
69f7c744-f344-5eb5-bdf3-cc5562ff0907 | note | Attachments
db4f80d1-2a16-5c2c-b6ec-f609c57a9d80 | tickbox | Checklists
1c8d7eb8-2f5e-54a2-a86f-a9bf85f80fc5 | tickbox | Photos
39b63cab-cd5b-5126-a8d9-1c5c9f1a8cd0 | tickbox | Dockets
7591a821-8147-56e1-b521-e50575989022 | tickbox | Sample Material
a1c7979d-f7ce-5b60-a2a9-7b9761b17268 | tickbox | Drawings
73eee53d-b12b-50c3-a74d-a802ebecdcc9 | tickbox | Calibration Certificates
2ed71f6a-11d2-5f49-af53-d75b3799df85 | tickbox | Test Results / Certificate
d0566ca1-d1d6-5bb1-91d7-2dd8909faf57 | tickbox | Inspection reports
3803b0c7-740e-5765-b020-103f249bd8d5 | tickbox | Others:
11b03e82-e0ff-5695-bcd9-222ca7ad60e3 | textbox | Others
389fff98-4fcf-409b-bf21-5b98417c4444 | signoff | Signed:
cd6f77bd-055e-4254-8bfb-4f10cfa3d798 | checklist | ITC&ITP No.3 - Sheet All Walls & Frame Ceiling - Rev D | itp | ITC&ITP No.3 - Sheet All Walls & Frame Ceiling
7f3aa059-6d57-4c09-abce-f406badeda70 | section | Sheet All Walls & Frame Ceiling
f47a9b70-cc97-4d51-aca9-57e4c161dd4f | checkpoint | 1 - Address Safety
36bf84bc-8b02-5da2-b93a-ea445eb8289d | note | Reference Documents - SWMS
53b342cf-98b5-5344-8422-9fd6186a7a7c | note | Acceptance Criteria - Safety Method Work Sheet approved by Georgiou Group Pty Ltd
05459c55-ecec-5367-8908-08a299a268b8 | note | Frequency - Each location
8c1f344c-b67d-5d22-9234-9f8412e81c4a | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
ad880be7-5280-5294-9d73-18c1268ef570 | note | Inspection By: Subcontractor - S
4019d235-21c3-5fec-8579-f1130c7ba496 | note | Inspection By: Georgiou - S
029ab2e2-b809-42df-9987-9926d8253a44 | checkpoint | 2 - Install insulation
dd609517-cdd7-5942-b9b4-5b7b2c3d3ba9 | note | Reference Documents - Architect drawings
dff744a6-168c-5c03-8be1-d4df47db3ee5 | note | Acceptance Criteria - Light Weight Wall Plan approved by Georgiou Group Pty Ltd. EcoTherm & Ecowool insulation installation guide
48d8ed6f-3712-570e-b9bd-333acd2d140d | note | Frequency - Each location
bd3342a9-99e7-5018-8d23-ce640c421a91 | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
97a6deec-2cb8-5158-8cf9-f387af0da79e | note | Inspection By: Subcontractor - S
b3bcf891-6820-5938-96b9-d3715f7a9af6 | note | Inspection By: Georgiou - S
974dacb3-5cbb-4ee3-a077-973a39a60a27 | checkpoint | 3 - Sign off for closing wall by Georgiou Group Pty Ltd
06023685-0b23-5320-bc3c-7dccdbc61ab7 | note | Reference Documents - Architect drawings
8786c91f-9736-52f9-8c9b-fbc111b5742f | note | Acceptance Criteria - Light Weight Wall Plan approved by Georgiou Group Pty Ltd. Studco Wall design & installation manual Volume 3.2
d5421561-027e-557b-a5d7-06dbaab3004f | note | Frequency - Each location
be55bdc9-6437-5b72-b2f9-2d85976b867b | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
879b1bb0-9a74-5293-9ed6-cab979b50f08 | note | Inspection By: Subcontractor - S
e1a659fc-ab15-5dec-b11a-2e6b8dbc21d8 | note | Inspection By: Georgiou - S, R
baffd223-3422-415d-9e70-db89e715888f | checkpoint | 4 - Sheet fire walls
356d5738-12ee-59fc-bd19-fbbc22269c55 | note | Reference Documents - Architect drawings
3456a401-e176-5978-8255-48fe9b820a86 | note | Acceptance Criteria - Light Weight Wall Plan approved by Georgiou Group Pty Ltd. GTEK Ceiling & Wall Solutions Rev. Mar 2024
6b6e9480-7ecf-59e5-8e38-8d4727a04390 | note | Frequency - Each unit
2e509cad-0375-5e02-b493-90b3a75e6d2c | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
817bff30-f009-5c05-ae83-9c6c55ccbb97 | note | Inspection By: Subcontractor - S
429afd16-be03-5aca-9414-a7d62d1e20f7 | note | Inspection By: Georgiou - HP
792234e8-db04-4e80-820b-ae578e0e80f5 | signoff | HOLD POINT
11f6e619-4d38-4ead-926d-a07e4c8922ef | checkpoint | 5 - Caulking fire walls
01438552-e1bd-5a38-bfdc-f600c99c3257 | note | Reference Documents - Architect drawings
0e035b9b-a401-5631-8dc7-2bee332abed0 | note | Acceptance Criteria - GTEK Ceiling & Wall Solutions Rev. Mar 2024
bbebbead-a7dd-51c1-a569-3385b8fdd5bd | note | Frequency - Each unit
d9d4a60e-152c-5f14-b8fa-b048873eb03c | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
4980238e-6c79-54a4-9170-2dcd185292a7 | note | Inspection By: Subcontractor - S
f03b3b23-59cb-5671-a2c4-ea60d3e305c9 | note | Inspection By: Georgiou - S
a2487dff-95c4-4262-b5af-6874fe0e07ea | checkpoint | 6 - Sheet remaining walls
119ac841-f856-5d98-9185-84e0225ba841 | note | Reference Documents - Architect drawings
87efeae0-69dd-5174-af85-6866f2803b13 | note | Acceptance Criteria - Light Weight Wall Plan approved by Georgiou Group Pty Ltd. GTEK Ceiling & Wall Solutions Rev. Mar 2024 Class 2-9 Building. EcoTherm & Ecowool insulation installation guide
782d0caa-cfe2-5dbb-93d8-a28fed90ff16 | note | Frequency - Each unit
cbb67261-5009-58fb-b1cb-f8b19e0892c7 | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
8bfd4fad-4009-52f7-9c91-4569d94d1c54 | note | Inspection By: Subcontractor - S
c96c4489-871e-5dbc-b59f-953a614c0468 | note | Inspection By: Georgiou - HP
49d7c2f1-3702-4d27-b4f0-b2b8d57d00df | signoff | HOLD POINT
086e57ee-9b07-4527-8099-a3a7c6cb88e1 | checkpoint | 7 - Frame ceiling
b146e6da-b9d9-5184-ae63-28cb91410c9f | note | Reference Documents - Architect drawings
d83a31c2-6aa4-5ce5-9704-20f95ae92fd0 | note | Acceptance Criteria - Architect RCP drawings approved by Georgiou Group Pty Ltd. Studco Wall design & installation manual Volume 3.2
22dd5c19-ca81-5517-9976-5b64a066e1c4 | note | Frequency - Each unit
28b46963-fd29-5962-a687-39808b50f5d6 | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
d8778b26-aa58-5976-a8f8-4d3a2590887a | note | Inspection By: Subcontractor - S
8e112b7a-e9ee-5235-9685-56741fbcce98 | note | Inspection By: Georgiou - S
38ed0e3c-a66e-487f-ad8e-dd58ae408c8f | checkpoint | 8 - Trim out access hatches
43408432-0078-53ef-b6cb-2504d42c4541 | note | Reference Documents - Architect drawings
3e3787d5-a908-5255-878a-ca6a55b628d4 | note | Acceptance Criteria - Architect RCP drawings approved by Georgiou Group Pty Ltd.
59f43905-245f-5e7b-9076-e38c94551604 | note | Frequency - Each location
df149fdf-1b10-5520-abd7-eef9d89df5d8 | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
a60cc610-40b5-5306-8700-f68dc5ab8264 | note | Inspection By: Subcontractor - S
74597de3-b4d0-5766-afb7-fada6ab85e7c | note | Inspection By: Georgiou - S
b39e8b5e-cee0-4a52-b1c2-5cbcc115a867 | checkpoint | 9 - Clean up
18c47fba-2bab-58a1-846b-92d6ef36aa7a | note | Reference Documents -
97a99c13-1b42-5c84-af8d-aaeeb6994faa | note | Acceptance Criteria - Waste all cleaned. Tools and materials placed well.
8f491bc9-140d-51c4-a64d-bb2a1073e4d8 | note | Frequency - Each location
070d396b-cb43-58bc-9c8a-1631014a8c52 | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
d7829e1e-772b-599f-97b2-1d91390fbaa5 | note | Inspection By: Subcontractor -
2d5c5648-9c54-519f-ac7d-2285b12b2a10 | note | Inspection By: Georgiou - R
8cce7867-886d-4bd8-a886-955c0f1a150c | checkpoint | Verification Statement
40a451ab-df42-5c12-8896-bfe3052e8c47 | note | This is to confirm that the nominated representative of L&D Commercial Interiors Pty Ltd, responsible for overseeing the works, has carried out all necessary inspections as listed above, and will be able to verify with documented evidence that the work has been completed and confirms to the contract specification(s)
b4e3a3e3-371b-5c1e-84b0-837cb3722c9f | date | Date of Inspection:
255d5c7a-7bf2-5faa-85b2-055ada9ff900 | textbox | Carried out by:
b56bbad3-e1d6-5168-9d18-63b3bbd863b1 | note | Attachments
dc18020b-8d18-5b50-afb5-5a40537459b0 | tickbox | Checklists
f0854afc-6acc-5e1c-a0b8-28c32f57c032 | tickbox | Photos
594eeb5a-286b-55f0-a5a8-33fa57980a61 | tickbox | Dockets
1268267b-d0c1-5e7b-a8d3-a5ae071b6f52 | tickbox | Sample Material
08791751-15bf-52d4-bfe0-6187590cda8f | tickbox | Drawings
d57b6255-2548-5728-b44a-0f038783d5b7 | tickbox | Calibration Certificates
9a663702-e4b3-5695-8903-080ab92240e2 | tickbox | Test Results / Certificate
d454f2a3-1fea-53f0-8704-80951b4196ad | tickbox | Inspection reports
c99827b8-d625-57ff-aae5-9d9510e88bdd | tickbox | Others:
db27f3d0-30be-57df-8fba-e08c514d959e | textbox | Others
6d5d66e3-360b-4cbf-9fb4-8f477e6e63a5 | signoff | Signed:
a67c7961-1fbe-4b00-a8b2-50c9ca1dd0ef | checklist | ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings - Rev B | itp | ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings
2a658e20-b2bc-4984-a130-155875ac753c | section | Hang Ceilings and Stop, Sand Walls & Ceilings
4372607c-c458-47a3-8c07-18e6f5686ce7 | checkpoint | 1 - Address Safety
19c772e8-def9-5278-81fb-0d4aaa4c04b6 | note | Reference Documents - SWMS
c3d4a6c6-b341-57fa-b6a8-1827f720003c | note | Acceptance Criteria - Safety Method Work Sheet approved by Georgiou Group Pty Ltd
2ea17fd4-8f51-52c5-9ef0-5b1d45518ee0 | note | Frequency - Each location
37e519c8-ead5-5df3-abd2-5c0235bdcb9b | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
0db92638-0949-53cf-82ab-5422448ee39b | note | Inspection By: Subcontractor - S
40e5b974-52e3-59fd-aa78-031758a69d99 | note | Inspection By: Georgiou - S
97595959-6ef0-45b9-8a54-7f51ec100cbf | checkpoint | 2 - Insulation to ceilings
25e8b886-1236-5acf-8ae7-f8f8cf4aa469 | note | Reference Documents - Architect drawings
ebcd1bb9-85f1-57ac-b430-1b6e510bdcd0 | note | Acceptance Criteria - Architect RCP drawings approved by Georgiou Group Pty Ltd. EcoTherm & Ecowool insulation installation guide
51fc169b-6d16-535d-baee-075393b4a5e3 | note | Frequency - Each unit
dda3371a-87d5-5a1d-a966-22983cbbdc00 | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
138c9bcd-6308-5a36-9716-12fb6329c748 | note | Inspection By: Subcontractor - S
55cdf9e8-492a-5f35-b0b6-83a7b6ed0543 | note | Inspection By: Georgiou - S
aa67bce4-e56c-4b1e-9243-19c751952b96 | checkpoint | 3 - Sign off for closing ceiling by Georgiou Group Pty Ltd
472d73ef-f9f2-59d7-a988-fb99d0b558e8 | note | Reference Documents - Architect drawings
a1e341c0-ffd8-565f-8024-72e20e0dad45 | note | Acceptance Criteria - Architect RCP drawings approved by Georgiou Group Pty Ltd
100d1447-e2e6-53ef-9889-328159461209 | note | Frequency - Each location
c78cb736-32bd-5254-9474-ea6f3f6ef4dd | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
a27ba9c3-a0e0-5bd9-90c3-9788c6278450 | note | Inspection By: Subcontractor - S
b175b792-9bfe-5f52-8367-a024994ff36d | note | Inspection By: Georgiou - S, R
c0e9a837-b804-4519-90de-ea4b8ccf0e5c | checkpoint | 4 - Sheets to ceiling
20f0d390-ed8c-5b93-8e85-ae63f20b5085 | note | Reference Documents - Architect drawings
4c2d3e87-58bd-59b6-966b-ae0a828fea60 | note | Acceptance Criteria - Architect RCP drawings approved by Georgiou Group Pty Ltd. GTEK Ceiling & Wall Solutions Rev. Mar.2024
a0f58512-ef13-5394-9fa6-f3b3c6fc4d73 | note | Frequency - Each unit
d0977c07-02a0-5898-9643-94f1fac1fce6 | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
030561e4-513e-5a0f-8d49-8c5ef8ec9c21 | note | Inspection By: Subcontractor - S
f4392488-948d-59de-becb-e2896af89a92 | note | Inspection By: Georgiou - HP
3c5ca3b3-c7b4-4714-ad41-2423bbb7fc14 | signoff | HOLD POINT
0dbee0ed-242a-4752-8e15-47d27370e925 | checkpoint | 5 - Stopping to walls & ceilings
eff5915b-9405-59cc-a391-692058bb90ae | note | Reference Documents - Architect drawings
26c4cab9-a644-510d-a30b-a4db42ef7290 | note | Acceptance Criteria - GTEK Ceiling & Wall Solutions Rev. Mar.2024
28776e10-cebd-5031-bea3-d11488c437f8 | note | Frequency - Each location
0bda5f3b-19d1-5a2e-b2cc-d5c3c2968dbd | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
3bb1347b-1b6e-5e30-a2f4-e6b4a8b3d5a5 | note | Inspection By: Subcontractor - S
158b8417-03dc-549f-bd0c-d9262c978e92 | note | Inspection By: Georgiou - S
090edaa3-ed36-4c89-bed9-feb25c3f5a9b | checkpoint | 6 - Sanding to walls & ceilings
92a805c2-d0e4-518e-a600-2d99236aa7f7 | note | Reference Documents - Architect drawings
bcb7624f-767b-5168-ac1f-acbc4120ffad | note | Acceptance Criteria - GTEK Ceiling & Wall Solutions Rev. Mar.2024
9c5bb835-12b7-502d-a8c0-c9bcfb252565 | note | Frequency - Each location
4e8ee841-a89c-5bce-9a6e-c192fff4b462 | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
3654eec9-c626-5abe-8d8f-b555e8b44dbe | note | Inspection By: Subcontractor - S
cdbbaa52-4054-50db-b6a4-65be9d2e978c | note | Inspection By: Georgiou - S
7a369f69-2849-43a1-a809-2544845882c2 | checkpoint | 7 - Fit access hatch frame
0502fd98-4f86-517d-9296-a74557169a91 | note | Reference Documents - Architect drawings
1f910b95-dc4a-526a-8f33-a94d97ff6407 | note | Acceptance Criteria - Architect RCP drawings approved by Georgiou Group Pty Ltd.
6026db66-4504-5d90-bd38-5c2667bd1186 | note | Frequency - Each location
19be1d2d-5179-5035-a38b-06de29d71ea9 | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
56463dcc-9241-5645-bb24-8dc50c7a1c41 | note | Inspection By: Subcontractor - S
37c3f456-1ea1-5acc-8ef0-2cd8905ca436 | note | Inspection By: Georgiou - S
f4c25e85-61cb-4b50-8c84-b1a67caa3d39 | checkpoint | 8 - Cut out for lights
8d75add7-8628-53d0-bdde-eedbda0658ca | note | Reference Documents - Architect drawings
c9f633d7-ea75-5d1e-9beb-13429113905e | note | Acceptance Criteria - Architect RCP drawings approved by Georgiou Group Pty Ltd.
8cc5f982-24b4-503b-b18d-d6d9dce909f4 | note | Frequency - Each location
e2ba6fa3-b973-50ec-b394-707dfc8c10c5 | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
6d3bb97f-b05b-560d-83ae-4483b1a9a6d4 | note | Inspection By: Subcontractor - S
e219128f-38fb-5c11-aba1-c3c1370e002b | note | Inspection By: Georgiou - S
7b9d856e-efcf-49bc-ac56-49c49f525f54 | checkpoint | 9 - Clean up
9a2c45be-c0f4-5ed1-93c2-c880e83cbd76 | note | Reference Documents -
7ebb974c-ab67-5e6e-8d0e-3c307abca952 | note | Acceptance Criteria - Waste all cleaned. Tools and materials placed well.
e945cff7-9d26-5e79-9d94-f593c89331c9 | note | Frequency - Each location
da3a6596-5343-5033-9d9f-fa1a4889355d | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
4f188bda-6aad-5c34-9259-c7032b9b2401 | note | Inspection By: Subcontractor -
c18302ad-23f3-59aa-9d2e-413c95c8090a | note | Inspection By: Georgiou - R
3c2d40f1-3639-4256-90a6-f286587c6771 | checkpoint | Verification Statement
f63af80c-9b1e-52fd-a5c1-7db908ec9513 | note | This is to confirm that the nominated representative of L&D Commercial Interiors Pty Ltd, responsible for overseeing the works, has carried out all necessary inspections as listed above, and will be able to verify with documented evidence that the work has been completed and confirms to the contract specification(s)
d8051f07-3020-5ce4-af04-20a53abcab5f | date | Date of Inspection:
1bdce783-179e-51a7-ae23-82a3c1c11d68 | textbox | Carried out by:
f4492602-f57b-521b-8ee3-4990150a868a | note | Attachments
5d823226-2123-5b24-8dbc-35c624c46934 | tickbox | Checklists
b723481d-19fd-57fb-a254-e05e4bd404a1 | tickbox | Photos
d9199de6-7d6c-5084-9306-58bf9f7b2385 | tickbox | Dockets
4c7833a1-0ad6-5f14-87c2-4d1cd037b8d9 | tickbox | Sample Material
70f2851d-2ccf-53c5-863a-76ee5c439422 | tickbox | Drawings
64c8b855-7c7d-5f83-b7b3-fef6f4e7d076 | tickbox | Calibration Certificates
a8bde526-5171-5566-9d68-258a54ceb9db | tickbox | Test Results / Certificate
dce7a1eb-b991-5cba-b73c-94c3773c032e | tickbox | Inspection reports
d3d0edb4-06aa-5627-81bd-89d184f30cfc | tickbox | Others:
8ad038d9-b28a-505e-9b07-fe15585c0145 | textbox | Others
459c7c58-521a-42c1-a030-06a226d0e12c | signoff | Signed:
62d777af-dfd5-478c-86d1-7292c3352630 | checklist | ITC&ITP No.5 - Patching - Rev B | itp | ITC&ITP No.5 - Patching
ea159e51-e1dc-41e8-a6aa-da243380f840 | section | Patching
02a4589d-0837-4309-8454-23a682818c25 | checkpoint | 1 - Address Safety
5225dc76-2b8e-5dbe-a39f-9a2fbb35710e | note | Reference Documents - SWMS
a06883bd-5813-5bf0-8d11-4aac3429c43a | note | Acceptance Criteria - Safety Method Work Sheet approved by Georgiou Group Pty Ltd
44243d31-2eec-5288-90fe-bd1eb349a596 | note | Frequency - Each location
9cdb44dd-eed7-5518-9510-f4e589ea08e2 | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
c25d00da-8280-5a1e-8a80-a5bbad33a3df | note | Inspection By: Subcontractor - S
424dbfbd-9f09-5218-ae22-1f66aca59b8a | note | Inspection By: Georgiou - S
c3b0f16d-910e-4947-85a0-8ae0802b6931 | checkpoint | 2 - Check ceilings
f6cd3e6e-3ec2-597e-8657-dd115842dd85 | note | Reference Documents - Architect drawings
d2263f99-6833-5e79-965e-45285e0942c6 | note | Acceptance Criteria - Architect RCP drawings approved by Georgiou Group Pty Ltd.
6dc1e0a4-72f4-589b-b45d-8f997b5aba93 | note | Frequency - Each unit
59d892e2-b6d0-5dab-ac01-3cedc99f5c57 | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
45bd77d7-1370-5df0-a2bc-f440ab59c0f9 | note | Inspection By: Subcontractor - S
ad0f33c9-b13b-54f2-8709-0232616c12df | note | Inspection By: Georgiou - S
9f215e88-4cfb-41ec-8d1f-94f983a2f7e3 | checkpoint | 3 - Check walls
feed91a7-c4c8-5939-9e17-1300547065df | note | Reference Documents - Architect drawings
d5015f8c-afa5-565d-b9fb-c08768218098 | note | Acceptance Criteria - Architect GA plan & wall type drawings approved by Georgiou Group Pty Ltd.
1458b23b-ba5e-5706-9581-a77a19309654 | note | Frequency - Each unit
6c6f8bde-44c4-5a02-88df-d476aa368dc2 | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
13619624-0713-53a1-8d07-50d2a82e76bb | note | Inspection By: Subcontractor - S
c1deeea8-21c3-51c0-96d7-abbdc50249b9 | note | Inspection By: Georgiou - S
52f0374d-863b-4c7a-a759-2aa844350deb | checkpoint | 4 - Clean up
4cdf9aae-4038-56d0-87d9-92ef116ce61e | note | Reference Documents - Architect drawings
2fc0d139-19a1-52e4-8107-4e6e86a0d17f | note | Acceptance Criteria - Waste all cleaned. Tools and materials placed well.
de4e79a1-3c34-5b37-8438-ab5e15d43232 | note | Frequency - Each location
7f0ac0c0-6c54-5966-a646-ff6b11bb7bfc | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
80114669-df04-5a74-91c5-d46bad4d4771 | note | Inspection By: Subcontractor -
516ada35-78be-5f32-9bc7-1f542a2d61b1 | note | Inspection By: Georgiou - R
5431a4cf-a417-468e-8bfc-5d1072dd510a | checkpoint | Verification Statement
a8da75aa-d159-5900-a167-81d3a457d81b | note | This is to confirm that the nominated representative of L&D Commercial Interiors Pty Ltd, responsible for overseeing the works, has carried out all necessary inspections as listed above, and will be able to verify with documented evidence that the work has been completed and confirms to the contract specification(s)
5c2cecd8-13a2-5d69-b26e-918ca0a8a91d | date | Date of Inspection:
1f723861-fa02-5993-8fee-99b638c7f2a0 | textbox | Carried out by:
44f96f75-a733-505d-ab0f-47dee6c8e484 | note | Attachments
605ed7a6-3de5-5c6a-83bb-f62cd0d81a98 | tickbox | Checklists
cdcb3063-88f2-55a3-8ef1-539cab5da4aa | tickbox | Photos
c443dea4-0b13-5db7-a97b-ab0df05fd2c3 | tickbox | Dockets
f29bcd2f-9bcc-50c3-a7ed-1eb016c0d9cf | tickbox | Sample Material
544d7e95-19b7-50ba-a577-b0daf0affe2c | tickbox | Drawings
16efc317-e27a-5699-bbf1-b1d7ec081632 | tickbox | Calibration Certificates
36c2eb62-9223-55c4-886d-55ca00e4a008 | tickbox | Test Results / Certificate
8369fc08-d81b-5ade-8a05-8c2cda51be26 | tickbox | Inspection reports
887e1ada-6f4f-56bb-a559-a6072a3a06bf | tickbox | Others:
ead19a33-315f-5120-9f5a-2370d4598550 | textbox | Others
f7d01424-6465-47fb-beb4-3c7facc731c6 | signoff | Signed:
586f643c-16f8-4602-8497-e7c2e48734ba | checklist | ITC&ITP No.6 - Rigid Board - Rev B | itp | ITC&ITP No.6 - Rigid Board
0ddb76fb-bbe5-4930-a581-59be49f13268 | section | Rigid Board
5ab1d814-7235-4442-ab20-135dc521d740 | checkpoint | 1 - Address Safety
cf127308-afa6-5a58-b2c0-20d7c980adc0 | note | Reference Documents - SWMS
af046edc-d1d4-5782-896b-71c5ef7ed4b8 | note | Acceptance Criteria - Safety Method Work Sheet approved by Georgiou Group Pty Ltd
72b6ef8e-91ad-5ef4-8148-2fe211c92a17 | note | Frequency - Each location
53e6fe10-f9e3-5764-b571-5de4eebbadde | note | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
3fc1f60a-dd86-59dd-91e9-830f5d9b84ff | note | Inspection By: Subcontractor - S
4569a454-f1ca-5017-96a2-13edfb74d6bb | note | Inspection By: Georgiou - S
270fbc95-ba35-45e7-8dcf-044ba9c93346 | checkpoint | 2 - Set out Rigid Board
b5a6eeef-e303-5bde-a80e-f96e9022fafc | note | Reference Documents - Architect drawings
080358ae-419a-5df1-bcc9-e467ccfd4dc7 | note | Acceptance Criteria - Reflected Ceiling Plan approved by Georgiou Group Pty Ltd
66bb7014-6046-5593-bcaf-9fcb59c514af | note | Frequency - Each location
e76e7a16-2aa8-500e-ac3f-492e4da15b9c | note | Verification Records/Comments - Visual Checklist
896fe11c-a4b0-531b-92f3-0d580bb2494a | note | Inspection By: Subcontractor - S
dfbdfcec-6255-5ef4-863f-8efbe4556559 | note | Inspection By: Georgiou - S
fd4b927b-3d2a-491a-87b0-940a4131e115 | checkpoint | 3 - Install Rigid Board
c4b31699-31af-5042-82c0-4591c8863195 | note | Reference Documents - Architect drawings
e7be9eb7-49ce-5d77-bed2-4638c337db5e | note | Acceptance Criteria - Reflected Ceiling Plan approved by Georgiou Group Pty Ltd. Kingspan Kooltherm K10 installation guide 2021
e1963ddf-4693-5c66-9330-8e5cfc5b9cb1 | note | Frequency - Each location
eec43ecc-e183-587b-8935-d5c3efe788e6 | note | Verification Records/Comments - Visual Checklist
adaa7129-f181-5efa-932b-44bf0a5edb7c | note | Inspection By: Subcontractor - S
1ea83747-d513-5cec-b4a1-747c944b7bc1 | note | Inspection By: Georgiou - S
f776c502-5a89-46a0-9913-354451d534c9 | checkpoint | 4 - Tape & Seal
2debd0c5-8c02-5eb2-9665-6c985caf5c43 | note | Reference Documents -
bb4106e4-3f3b-5769-9a99-348fef0f3b04 | note | Acceptance Criteria - Kingspan Kooltherm K10 installation guide 2021
44a3a989-22a2-5e27-8ad7-046c529747c8 | note | Frequency - Each location
337e6c15-9f1c-544e-a467-97a58b16a34a | note | Verification Records/Comments - Visual Checklist
a497a7c2-9728-59d4-98c0-fe66ada5f89f | note | Inspection By: Subcontractor - S
399b9006-2a94-567e-93e6-2ee29171964e | note | Inspection By: Georgiou - S
8a7b9d52-0d34-488a-8bd1-257c836d5be1 | checkpoint | 5 - Clean up
4e1eb786-5e4c-5fe0-b55c-6dfccbdff2ee | note | Reference Documents -
6ad9c0d3-8dbb-5b1d-94c5-76c9e7be8d38 | note | Acceptance Criteria - Waste all cleaned. Tools and materials placed well.
cd63d657-98f8-580f-85ad-1701a2e47434 | note | Frequency - Each location
7e4ba94a-c269-583c-91b1-a6b6769bd0a4 | note | Verification Records/Comments - Visual Checklist
162eeca8-446a-58c6-9073-81c7631d083b | note | Inspection By: Subcontractor -
cb8477b6-0baa-5f5c-bb46-56b2a1d07488 | note | Inspection By: Georgiou - R
768a5d08-51ba-4c49-aed7-78dd27c53003 | checkpoint | Verification Statement
524ebe77-dc7d-5261-9b95-825115db4323 | note | This is to confirm that the nominated representative of L&D Commercial Interiors Pty Ltd, responsible for overseeing the works, has carried out all necessary inspections as listed above, and will be able to verify with documented evidence that the work has been completed and confirms to the contract specification(s)
3e5433a9-3bcc-50fe-86fb-c98c624e2a2b | date | Date of Inspection:
557d2090-7ca2-5b87-aaad-cc2eb25343aa | textbox | Carried out by:
45b8572e-0fd0-544e-8db6-fae55585a719 | note | Attachments
6db4ac9c-9ece-593b-94fc-065baf2c255e | tickbox | Checklists
345cb253-d4f9-55fc-bd79-cc970b4915d5 | tickbox | Photos
3e27a46c-b2d9-5775-98c8-3bef526039c2 | tickbox | Dockets
016c637a-83c8-52fa-8499-cabded7ebfd9 | tickbox | Sample Material
22bc1258-97e5-5bfb-bab1-e239f2da0ad6 | tickbox | Drawings
fdeb4e89-26cd-5e4f-b48d-a2bab0f0b143 | tickbox | Calibration Certificates
866cd8b1-0f29-5368-a97e-8cfedff3e7be | tickbox | Test Results / Certificate
8703307c-4c0a-5533-b000-5ba6d58b9aed | tickbox | Inspection reports
d5ce901f-9ab4-52a3-a0f1-1df36cce1e91 | tickbox | Others:
89ddb105-08db-5e9f-8c0c-eb6996b8f119 | textbox | Others
77b683a8-b707-45d7-9513-452f47947c0f | signoff | Signed: