## Checklist Template Builder
Component | Name | Values
checklist | Rigid Board
checkpoint | Address Safety
Reference Documents - SWMS
Acceptacne Criteria - Safety Method Work Sheet approved by Georgiou Group Pty Ltd
Frequency - Each location
Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
Inspection By : Subcontractor - S
Inspection By : Georgiou - S
checkpoint | Set out Rigid Board
Reference Documents - Architect Drawings
Acceptacne Criteria - Reflected Ceiling Plan Approved by Georgiou Group Pty Ltd
Frequency - Each location
Verification Records/Comments - Visual Checklist
Inspection By : Subcontractor - S
Inspection By : Georgiou - S
checkpoint | Install Rigid Board
Reference Documents - Architect Drawings
Acceptacne Criteria - Reflected Ceiling Plan Approved by Georgiou Group Pty Ltd, Kingspan Kooltherm K10 Installation guide 2021
Frequency - Each location
Verification Records/Comments - Visual Checklist
Inspection By : Subcontractor - S
Inspection By : Georgiou - S
checkpoint | Tape and Seal
Reference Documents - N/A
Acceptacne Criteria - Kingspan Kooltherm K10 Installation guide 2021
Frequency - Each location
Verification Records/Comments - Visual Checklist
Inspection By : Subcontractor - S
Inspection By : Georgiou - S
checkpoint | Clean up
Reference Documents - N/A
Acceptacne Criteria - Waste all cleaned. Tools and materials placed well
Frequency - Each location
Verification Records/Comments - Visual Checklist
Inspection By : Subcontractor
Inspection By : Georgiou - R
signoff | Verification Statement

## Template Components
checklist |  |  |  | This is where you specify the name of the checklist. It is a required field on all checklist templates
| section |  |  | This breaks your checklist up into collapsible sections. These are not necessary, but when used, each section must contain at least one checkpoint.
|  | checkpoint |  | This is a necessary component, all checklist templates must include at least one checkpoint. A checkpoint is where you can set the status, add comments and attach files.
|  | checkpoint-no-status |  | This can be used the same way as a checkpoint, the only difference is that it does not have a status attached. You might use this when you want to attach photos but not have them linked to a PASS/FAIL
All of the below datapoints must be attached to a checkpoint. You do this by simply making sure there is a checkpoint in your checklist template. The data point will then attach to the above checkpoint.
|  |  | button | You can set specific button values, of which only one can be selected at a time. Specify these in the 'values' column, separating each with a comma (e.g: 1, 2, 3)
|  |  | date | Provides a date input box with a calendar picker to select a date
|  |  | dropdown | This gives multiple specific answer types, of which only one (or none) can be selected at time. Specify these in the 'values' column, separating each with a comma (e.g: One, Two, Three)
|  |  | signoff | This prompts for a signature to be added, either on site, or a digital request for a signature to be sent via email to someone off site. If required these can be made mandatory.
|  |  | label | This is a text label that shows under the parent checkpoint
|  |  | number | A short text field allowing for only numerical input
|  |  | radio | You can set specific response values, of which only one can be selected at a time. Specify these in the 'values' column, separating each with a comma (e.g: A, B, C)
|  |  | note | A free text input field that allows users to write notes and add comments to the above checkpoint
|  |  | tickbox | Add a single check box that can be checked or left empty