## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Rigid Board | [5 empty] | ITC&ITP - No.4 Rigid Board - Rev.C
section | ITC&ITP - No.4 Rigid Board - Rev.C
checkpoint | Address Safety
label | Reference Documents - SWMS
label | Acceptacne Criteria - Safety Method Work Sheet approved by Georgiou Group Pty Ltd
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By : Subcontractor - S
label | Inspection By : Georgiou - S
checkpoint | Set out Rigid Board
label | Reference Documents - Architect Drawings
label | Acceptacne Criteria - Reflected Ceiling Plan Approved by Georgiou Group Pty Ltd
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist
label | Inspection By : Subcontractor - S
label | Inspection By : Georgiou - S
checkpoint | Install Rigid Board
label | Reference Documents - Architect Drawings
label | Acceptacne Criteria - Reflected Ceiling Plan Approved by Georgiou Group Pty Ltd, Kingspan Kooltherm K10 Installation guide 2021
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist
label | Inspection By : Subcontractor - S
label | Inspection By : Georgiou - S
checkpoint | Tape and Seal
label | Reference Documents - N/A
label | Acceptacne Criteria - Kingspan Kooltherm K10 Installation guide 2021
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist
label | Inspection By : Subcontractor - S
label | Inspection By : Georgiou - S
checkpoint | Clean up
label | Reference Documents - N/A
label | Acceptacne Criteria - Waste all cleaned. Tools and materials placed well
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist
label | Inspection By : Subcontractor
label | Inspection By : Georgiou - R
signoff | Verification Statement