## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-212-CIV-SSB-Gurd Rail Installation
ITP Description: |  | SSB-Gurd Rail Installation
Discipline (e.g. CIV/STR/RAIL: |  | 212-CIV
Revision Number: |  | 0
Revision Date: |  | 2024-11-11
ITP created by: |  | Romualdo Magpantay
ITP approved for use by: |  | VM
Special Notes to ConQA Team : |  | ITP for Station Street, Beaconsfield
Inspection & Test Plan - Guard Rail Supply and Install
|  |  | Document No.: | [5 empty] | Revision: | 0
[9 empty] | Date: | 2024-11-11
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | VicRoads Section 708 November 2018 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.2 | Non Dependent | VicRoads Section 703 April 2019 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Preliminaries - Materials
2.1 | Accepted Products and material confirmation | VicRoads Spec. Cl.708.04 | Only safety barrier products listed in VicRoads Road Design Note 06-04 shall be used. Check design drawing for correct type of barrier, transitions and/or end connection and any additional material component requirements | Document Review | Each member material component | HP* | Nominated Authority | ConQA Hold Point Release
2.2 | Identification of guard fence components | VicRoads Spec. Cl.708.05 (a) | w-beam sections, both ends of posts and all plastic components of proprietary end treatments unotrusively and permanently marked in text not more than 20mm high with: name of manufacturer, batch number or date of manufacture and strength grade and base metal thickness of steel w-beams | Visual | Each member material component | IP | SE/PE/SPE | This ITP
2.3 | Obtain and submit Material Test Certificate of Compliance for the barrier systems | VicRoads Spec. Cl.708.05(b & c) AS/NZS 1594, AS1627, AS 4680 ISO/IEC 17025 a | W-beams and terminal sections shall comply with AS/NZS1594 Grade HA350. Steel posts and blocks shall comply with AS/NZS1594 Grade HA250. Treated in accordance with AS1627- Parts 1 & 4. All test reports shall be endorsed in accordance with the AS ISO/IEC 17025 accreditation for that laboratory. | Document Review | Min 14 days prior to commencing, 1 per 1000m of material | HP* | Nominated Authority | ConQA Hold Point Release
2.5 | Verification of Protective treament/ galvanisation records | VicRoads Spec. Cl.708.05(d) | Surface preparation in accordance with AS1627 parts 1 & 4. and finished by Hot-dipped galvanizing in accordance with AS 4680 or for components of proprietary end treatments as per the manufacturer's recommendations/ requirements. All galv coatings to be smooth, adherent and free from stains, gross surface imperfections, markings, brand names and/or inclusions. Colour shall be uniform. Hot-dipped galvanized coating on bolts, nuts & washers shall comply with AS 1214 | Document Review | Min 14 days prior to commencing, 1 per 1000m of material | HP* | Nominated Authority | ConQA Hold Point Release
2.6 | Concrete mix design | VicRoads Spec. Cl.703 Cl.708.05(g) AS1379 | Concrete to comply with the requirements of AS 1379 and VicRoads Section 703, for either: (i) Portland cement-based concrete, N20 strength grade, or (ii) Geopolymer binder-based concrete, 20 MPa strength grade. | Document Review | Prior to Commencing | IP | SE/PE/SPE | This ITP
5 | Construction Activities
3.1 | Survey Set-out | Project Spec. Cl.1190.07 IFC Drawings | Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.463 (November 2018) / 610.473 (March/June 2019) as applicable to the element. Attach: Survey As-builts / Survey Report | Measure Visual | Prior to Commencing Excavation | IP | Surveyor SE/PE/SPE | This ITP
3.2 | Obtain approval of location and length | VicRoads Spec. Cl.708.08 IFC Drawings | The required location and length of all guard fence shall be confirmed with the Superintendent. | Measure Visual | Prior to Installation | HP* | Nominated Authority | ConQA Hold Point Release
3.3 | Install posts, rails and terminations | IFC Drawings VicRoads Spec. Cl.708 .07(a & d ) IFC Drawings | Posts shall be installed to the depth, line and spacing shown on the drawings. Ensure line and level are within tolerance: true plan position of posts ±20mm, line of w-beams from vertical profile ±10mm, w-beams from horizontal alignment ±20mm, posts from vertical ±15mm, orientation of block and /or post to w-beam +0, -15mm, dimension of holes +50, -0mm, top of bolt head relative to w-beam +5, -0mm, top of rail shall be within 25mm of level and 50mm of line. Variations from specified line and level shall not occur at a rate exceeding 15 mm in any 5 m length. | Measure Visual | During construction. | IP | SE/PE/SPE | This ITP
3.4 | Construct crushed rock base for maintenance strip | VicRoads Spec. Cl.708 .11 Cl.812 | Min 75mm thick class 3 CR, min 2% crossfall away from road. All bedding material used for cast in place concrete construction works shall be in accordance with Section 812 for Class 3 Crushed Rock | Measure Visual | During construction. | IP | SE/PE/SPE | This ITP
3.5 | Construct concrete maintenance strip | VicRoads Spec. Cl.708.12a Cl.708.5g Cl.703.11 | Min 75mm thick N20 grade portland cement-based concrete, finished to Class 3 crushed rock, 300mm clear of rear of post and face of w-beam, Concrete testing at 1/50m3 per day, expansion joints 200mm either side of posts. Fresh concrete to be protected from rain or other damage until hard set | Measure Visual | During construction. | IP | SE/PE/SPE | This ITP
3.6 | Curing of concrete maintenance strip | VicRoads Spec. Cl.708.16 Cl.703 | Concrete shall be cured either by water curing,wet hessian,polyethlyene sheeting adequately sealed against moisture losses, curing compound or combination thereof. Curing compounds to be in accordance with AS3799. | Measure Visual | no less than 7 days after concrete placement | IP | SE/PE/SPE | This ITP
4 | Post-construction Activities
4.1 | Delineators | VicRoads Spec. Cl.708.11 Cl.703.12 | Appropriately coloured delineators fastened to top of w-beam at 15m spacings, comprising flexible plastic mounting brackets fitted with 100 cm2 of Class 1A retro-reflective material, as defined in AS/NZS 1906.2 | Visual Document Review | Once, immediately following the installation and prior to any Work commencing on the members | IP | SE/PE/SPE | This ITP
4.2 | Existing Sign & markings Reinstatement | VicRoads Spec. Cl.708.17 IFC Drawings | The Contractor shall reinstate all signs to a standard not less than the pre-existing condition and to the satisfaction of the Superintendent | Document Review | Each element | HP* | Nominated Authority | ConQA Hold Point Release
4.3 | Compliance Audit of Safety Barrier System Installation | VicRoads Spec. Cl.708.10 | A safety barrier compliance audit on all proprietary guard fence end treatments constructed under the Contract shall be undertaken and a report prepared by the Australian Licensed Supplier of the safety barrier system. A Certificate of Compliance(CoC) shall be provided certifying that the products have installed in accordance with the manufactures installation Manual and specifiction for each end treatment installed. A signed copy of the manufacturer’s Installation Checklist / Inspection and Test Plan as per the manufacturer’s Product and Installation Manual shall be completed and submitted to the Superintendent.. | Visual Document Review | Each bridge beam | HP* | Nominated Authority | ConQA Hold Point Release
4.4 | Survey data captured for as-built purposes | IFC Drawings VicRoads Spec. Cl.708 | As-built Drawings Tolerances as per VicRoads Specifications, Clause 708. | Visual Document Review | Where applicable | IP | Surveyor SE/PE/SPE | This ITP
4.5 | Non-conformance Report (NCR) Closure | MRPA Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs. | Document Review | Once, prior to closure of this lot / element / Work area | HP* | Nominated Authority | ConQA Hold Point Release
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /