## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-212-CIV-SSB-Guard Rail Installation | itp |  |  |  |  | ITP-212-CIV-SSB-Guard Rail Installation Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-212-CIV-SSB-Gurd Rail Installation
label | ITP Description: SSB-Gurd Rail Installation
label | Discipline (e.g. CIV/STR/RAIL): 212-CIV
label | Revision Number: 0
label | Revision Date: 11/11/2024
label | ITP created by: Romualdo Magpantay
label | ITP approved for use by: VM
label | 1.1 Non Dependent
label | Reference: VicRoads Section 708 November 2018
label | 1.2 Non Dependent
label | Reference: VicRoads Section 703 April 2019
section | Preliminaries - Materials
checkpoint | 2.1 Accepted Products and material confirmation
label | REFERENCE: VicRoads Spec. Cl.708.04
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Only safety barrier products listed in VicRoads Road Design Note 06-04 shall be used.
label | ○ Check design drawing for correct type of barrier, transitions and/or end connection and any additional material component requirements
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each member material component
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
checkpoint | 2.2 Identification of guard fence components
label | REFERENCE: VicRoads Spec. Cl.708.05 (a)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: w-beam sections, both ends of posts and all plastic components of proprietary end treatments unotrusively and permanently marked in text not more than 20mm high with: name of manufacturer, batch number or date of manufacture and strength grade and base metal thickness of steel w-beams
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each member material component
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 2.3 Obtain and submit Material Test Certificate of Compliance for the barrier systems
label | REFERENCE: VicRoads Spec. Cl.708.05(b & c) AS/NZS 1594, AS1627, AS 4680 ISO/IEC 17025 a
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: W-beams and terminal sections shall comply with AS/NZS1594 Grade HA350. Steel posts and blocks shall comply with AS/NZS1594 Grade HA250. Treated in accordance with AS1627- Parts 1 & 4. All test reports shall be endorsed in accordance with the AS ISO/IEC 17025 accreditation for that laboratory.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Min 14 days prior to commencing, 1 per 1000m of material
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
checkpoint | 2.5 Verification of Protective treament/ galvanisation records
label | REFERENCE: VicRoads Spec. Cl.708.05(d)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Surface preparation in accordance with AS1627 parts 1 & 4. and finished by Hot-dipped galvanizing in accordance with AS 4680 or for components of proprietary end treatments as per the manufacturer's recommendations/ requirements. All galv coatings to be smooth, adherent and free from stains, gross surface imperfections, markings, brand names and/or inclusions. Colour shall be uniform. Hot-dipped galvanized coating on bolts, nuts & washers shall comply with AS 1214
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Min 14 days prior to commencing, 1 per 1000m of material
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
checkpoint | 2.6 Concrete mix design
label | REFERENCE: VicRoads Spec. Cl.703, Cl.708.05(g) AS1379
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Concrete to comply with the requirements of AS 1379 and VicRoads Section 703, for either:
label | (i) Portland cement-based concrete, N20 strength grade, or
label | (ii) Geopolymer binder-based concrete, 20 MPa strength grade.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Prior to Commencing
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 3.1 Survey Set-out
label | REFERENCE: Project Spec. Cl.1190.07 IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.463 (November 2018) / 610.473 (March/June 2019) as applicable to the element.
label | ○ Attach: Survey As-builts / Survey Report
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Prior to Commencing Excavation
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 3.2 Obtain approval of location and length
label | REFERENCE: VicRoads Spec. Cl.708.08 IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The required location and length of all guard fence shall be confirmed with the Superintendent.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Prior to Installation
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
checkpoint | 3.3 Install posts, rails and terminations
label | REFERENCE: IFC Drawings VicRoads Spec. Cl.708 .07(a & d) IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Posts shall be installed to the depth, line and spacing shown on the drawings. Ensure line and level are within tolerance: true plan position of posts ±20mm, line of w-beams from vertical profile ±10mm, w-beams from horizontal alignment ±20mm, posts from vertical ±15mm, orientation of block and /or post to w-beam +0, -15mm, dimension of holes +50, -0mm, top of bolt head relative to w-beam +5, -0mm, top of rail shall be within 25mm of level and 50mm of line. Variations from specified line and level shall not occur at a rate exceeding 15 mm in any 5 m length.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: During construction.
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 3.4 Construct crushed rock base for maintenance strip
label | REFERENCE: VicRoads Spec. Cl.708 .11, Cl.812
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Min 75mm thick class 3 CR, min 2% crossfall away from road. All bedding material used for cast in place concrete construction works shall be in accordance with Section 812 for Class 3 Crushed Rock
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: During construction.
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 3.5 Construct concrete maintenance strip
label | REFERENCE: VicRoads Spec. Cl.708.12a, Cl.708.5g, Cl.703.11
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Min 75mm thick N20 grade portland cement-based concrete, finished to Class 3 crushed rock, 300mm clear of rear of post and face of w-beam, Concrete testing at 1/50m3 per day, expansion joints 200mm either side of posts. Fresh concrete to be protected from rain or other damage until hard set
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: During construction.
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 3.6 Curing of concrete maintenance strip
label | REFERENCE: VicRoads Spec. Cl.708.16, Cl.703
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Concrete shall be cured either by water curing,wet hessian,polyethlyene sheeting adequately sealed against moisture losses, curing compound or combination thereof.
label | ○ Curing compounds to be in accordance with AS3799.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: no less than 7 days after concrete placement
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 4.1 Delineators
label | REFERENCE: VicRoads Spec. Cl.708.11, Cl.703.12
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Appropriately coloured delineators fastened to top of w-beam at 15m spacings, comprising flexible plastic mounting brackets fitted with 100 cm2 of Class 1A retro-reflective material, as defined in AS/NZS 1906.2
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual, Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once, immediately following the installation and prior to any Work commencing on the members
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 4.2 Existing Sign & markings Reinstatement
label | REFERENCE: VicRoads Spec. Cl.708.17 IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The Contractor shall reinstate all signs to a standard not less than the pre-existing condition and to the satisfaction of the Superintendent
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each element
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
checkpoint | 4.3 Compliance Audit of Safety Barrier System Installation
label | REFERENCE: VicRoads Spec. Cl.708.10
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: A safety barrier compliance audit on all proprietary guard fence end treatments constructed under the Contract shall be undertaken and a report prepared by the Australian Licensed Supplier of the safety barrier system. A Certificate of Compliance(CoC) shall be provided certifying that the products have installed in accordance with the manufactures installation Manual and specifiction for each end treatment installed. A signed copy of the manufacturer’s Installation Checklist / Inspection and Test Plan as per the manufacturer’s Product and Installation Manual shall be completed and submitted to the Superintendent..
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual, Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each bridge beam
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
checkpoint | 4.4 Survey data captured for as-built purposes
label | REFERENCE: IFC Drawings VicRoads Spec. Cl.708
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: As-built Drawings
label | ○ Tolerances as per VicRoads Specifications, Clause 708.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual, Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Where applicable
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 4.5 Non-conformance Report (NCR) Closure
label | REFERENCE: MRPA Quality Management Plan
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP