## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Metro TH Window
section | Opening check
checkpoint | Visual inspect opening prepration, report any damages
checkpoint | Check R/O Size (RL, Width,Hight, dimensions to C/L) based on QA opening handover&shop drawing(ADD survey drawings in here if not as per drawings)
section | Flashing Install
checkpoint | Select&Check flashing type agasint drawing
checkpoint | Visual inspect flashing if any damages
checkpoint | Sill flashing install as per RL&detail
checkpoint | Jamb flashing install plumb&align as per drawing&detail
checkpoint | Head flashing install as per RL&detail
checkpoint | All flashings fixings install as per drawing&detail
checkpoint | All flashings seal as per drawing&detail
checkpoint | Flashings trade clean
section | Joinery Install
checkpoint | Check the joinery if any damages
checkpoint | Frame installed in correct posistion & Level
checkpoint | All joinery fixings install as per drawing&detail
checkpoint | All fixings oversealed on frame and no tooling damage on frame
checkpoint | No packers visable out of line where airseal is to be installed
checkpoint | Joinery trade clean
section | Airseal seal Install
checkpoint | PEF Rod install correctly and sealant ratio achieved
checkpoint | SIKA AT Façade applied as per spec
section | Weather seal Install
checkpoint | PEF Rod install correctly and sealant ratio achieved
checkpoint | SIKA WS-605 S applied as per spec
section | Glass
checkpoint | Glazed refer GPL QA
section | Installer sign off
checkpoint | All elements completed correctly as per drawing
checklist | Metro TH Slider
section | Opening check
checkpoint | Visual inspect opening prepration, report any damages
checkpoint | Check R/O Size (RL, Width,Hight, dimensions to C/L) based on QA opening handover&shop drawing(ADD survey drawings in here if not as per drawings)
section | Flashing Install
checkpoint | Select&Check flashing type agasint drawing
checkpoint | Visual inspect flashing if any damages
checkpoint | Sill flashing install as per RL&detail
checkpoint | Jamb flashing install plumb&align as per drawing&detail
checkpoint | Head flashing install as per RL&detail
checkpoint | All flashings fixings install as per drawing&detail
checkpoint | All flashings seal as per drawing&detail
checkpoint | Flashings trade clean
section | Joinery Install
checkpoint | Check the joinery if any damages
checkpoint | Support angle install correctly
checkpoint | All joinery fixings install as per drawing&detail
checkpoint | Frame installed in correct posistion & Level
checkpoint | All fixings oversealed on frame and no tooling damage on frame
checkpoint | No packers visable out of line where airseal is to be installed
checkpoint | Sliding panel installed and level adjusted
checkpoint | All Hardware in working order and lockable
checkpoint | Joinery trade clean
section | Airseal seal Install
checkpoint | PEF Rod install correctly and sealant ratio achieved
checkpoint | SIKA AT Façade applied as per spec
section | Weather seal Install
checkpoint | PEF Rod install correctly and sealant ratio achieved
checkpoint | SIKA WS-605 S applied as per spec
section | Glass
checkpoint | Glazed refer GPL QA
section | Installer sign off
checkpoint | All elements completed correctly as per drawing