## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Precast | itp |  |  |  |  | ITP - Precast
section | 1.0 - SITE PRELIMINARIES
checkpoint | 1.1 - Management Plans
label | Specification / Drawing Reference -
label | Inspection Procedure and Acceptance Criteria - Management Plans Submitted and approved
label | Verification Document -
label | Aquatec: Insp. - H
label | Aquatec: Resp. - PM
label | Skerman Civil: Insp. - H
label | Skerman Civil: Resp. - C
label | Urban Utilities: Insp. - H
label | Urban Utilities: Resp. - I
holdpoint | HOLD POINT
checkpoint | 1.2 - Permit to Work
label | Specification / Drawing Reference -
label | Inspection Procedure and Acceptance Criteria - ○ All required permits received
label | Verification Document -
label | Aquatec: Insp. - H
label | Aquatec: Resp. - PM
label | Skerman Civil: Insp. - H
label | Skerman Civil: Resp. - C
label | Urban Utilities: Insp. - H
label | Urban Utilities: Resp. - I
holdpoint | HOLD POINT
checkpoint | 1.3 - Drawings
label | Specification / Drawing Reference - Aquatec Civil/Mech Drawings
label | Inspection Procedure and Acceptance Criteria - ○ IFC Drawings confirmed latest revision and approved
label | Verification Document - IFC Drawings
label | Aquatec: Insp. - H
label | Aquatec: Resp. - PM
label | Skerman Civil: Insp. - H
label | Skerman Civil: Resp. - C
label | Urban Utilities: Insp. - H
label | Urban Utilities: Resp. - I
holdpoint | HOLD POINT
checkpoint | 1.4 - Backfill Design Approval
label | Specification / Drawing Reference - Aquatec Civil/Mech Drawings
label | Inspection Procedure and Acceptance Criteria - ○ Foundation and Backfill design has been reviewed and modified where necessary with letter of endorsement from RPEQ Geotech (Must be site- specific)
label | Verification Document - RPEQ Letter of Endorsement
label | Aquatec: Insp. - H
label | Aquatec: Resp. - PM
label | Skerman Civil: Insp. - H
label | Skerman Civil: Resp. - C
holdpoint | HOLD POINT
checkpoint | 1.5 - Backfill Materials Approval
label | Specification / Drawing Reference - Aquatec Civil/Mech Drawings
label | Inspection Procedure and Acceptance Criteria - ○ All backfill material certificates submitted and approved for use by Geotechnical Engineer
label | Verification Document - Material Certificates
label | Aquatec: Insp. - H
label | Aquatec: Resp. - PM
label | Skerman Civil: Insp. - W
label | Skerman Civil: Resp. - C
holdpoint | HOLD POINT
section | 2.0 - PRECAST CONCRETE INSTALLATION
checkpoint | 2.1 - Excavation set-out
label | Specification / Drawing Reference - Aquatec Civil/Mech Drawings
label | Inspection Procedure and Acceptance Criteria - Setout points established and offset for recovery
label | Aquatec: Insp. - W
label | Aquatec: Resp. - SS
label | Skerman Civil: Insp. - W
label | Skerman Civil: Resp. - C
checkpoint | 2.2 - Excavation to Base R.L
label | Specification / Drawing Reference - Aquatec Civil/Mech Drawings
label | Inspection Procedure and Acceptance Criteria - ○ Shoring and benching completed as required ○ Where over-excavation occurs, excavation shall be filled with suitable material to satisfaction of geotechnical engineer
label | Verification Document -
label | Aquatec: Insp. - W
label | Aquatec: Resp. - SS
label | Skerman Civil: Insp. - H
label | Skerman Civil: Resp. - C
label | Urban Utilities: Insp. - W
label | Urban Utilities: Resp. - I
holdpoint | HOLD POINT
checkpoint | 2.3 - Testing of Base
label | Specification / Drawing Reference - Aquatec Civil/Mech Drawings
label | Inspection Procedure and Acceptance Criteria - 2 x DCP tests completed on excavation floor and bearing capacity of >100kPa confirmed
label | ○ If excavation base material deemed unsuitable, unsuitable foundation to be replaced with suitable material with approval.
label | Verification Document - DCP Report
label | Aquatec: Insp. - H
label | Aquatec: Resp. - SS
label | Skerman Civil: Insp. - H
label | Skerman Civil: Resp. - C
label | Urban Utilities: Insp. - W
label | Urban Utilities: Resp. - I
holdpoint | HOLD POINT
checkpoint | 2.4 - Sub-Base Preparation
label | Specification / Drawing Reference - Aquatec Civil/Mech Drawings
label | Inspection Procedure and Acceptance Criteria - Approved Sub-Base material placed and compacted
label | ○ Sump and pump set up to keep excavation dry (if required)
label | ○ Pump Station Base R.L, centre and orientation set out and confirmed
label | Aquatec: Insp. - W
label | Aquatec: Resp. - SS
label | Skerman Civil: Insp. - W
label | Skerman Civil: Resp. - C
label | Urban Utilities: Insp. - W
label | Urban Utilities: Resp. - I
checkpoint | 2.5 - Testing of Sub-Base
label | Specification / Drawing Reference - Aquatec Civil/Mech Drawings
label | Inspection Procedure and Acceptance Criteria - Sub-base confirmed at 98% compaction
label | Verification Document - Compaction Test Report
label | Aquatec: Insp. - H
label | Aquatec: Resp. - SS
label | Skerman Civil: Insp. - H
label | Skerman Civil: Resp. - C
label | Urban Utilities: Insp. - W
label | Urban Utilities: Resp. - I
holdpoint | HOLD POINT
checkpoint | 2.6 - Precast Items Check
label | Specification / Drawing Reference - Aquatec Coring Drawings
label | Inspection Procedure and Acceptance Criteria - Precast items checked for damage
label | ○ Precast items checked against drawings for correct dimensions, cast-ins, coatings and penetrations
label | Aquatec: Insp. - S
label | Aquatec: Resp. - SS
label | Skerman Civil: Insp. - W
label | Skerman Civil: Resp. - CS
label | Urban Utilities: Insp. - W
label | Urban Utilities: Resp. - I
checkpoint | 2.7 - Base and Increment Placement
label | Specification / Drawing Reference - Craning and Excavation Plan Aquatec Civil/Mech Drawings
label | Inspection Procedure and Acceptance Criteria - Precast items lifted into chamber as per craning and excavation plan
label | ○ Precast items jointed as per drawings
label | ○ Orientation of inlet stub and penetrations as per drawings
label | Aquatec: Insp. - S
label | Aquatec: Resp. - SS
label | Skerman Civil: Insp. - W
label | Skerman Civil: Resp. - CS
label | Urban Utilities: Insp. - W
label | Urban Utilities: Resp. - I
checkpoint | 2.8 - Cover Slab Installation
label | Specification / Drawing Reference - Craning and Excavation Plan, Aquatec Civil/Mech Drawings
label | Inspection Procedure and Acceptance Criteria - Cover Slab lifted onto pump station as per craning and excavation plan
label | ○ Cover Slab orientation and alignment correct as per drawings
label | ○ Cover Slab sealed to pump station as per drawings
label | Aquatec: Insp. - S
label | Aquatec: Resp. - SS
label | Skerman Civil: Insp. - W
label | Skerman Civil: Resp. - CS
checkpoint | 2.9 - Placement of Ballast Concrete
label | Specification / Drawing Reference - Aquatec Civil/Mech Drawings
label | Inspection Procedure and Acceptance Criteria - 25MPa Concrete Used
label | ○ Correct Volume Used
label | ○ Sufficient Vibration
label | Verification Document - Concrete Dockets
label | Aquatec: Insp. - S
label | Aquatec: Resp. - SS
label | Skerman Civil: Insp. - W
label | Skerman Civil: Resp. - CS
checkpoint | 2.10 - Placement and Compaction of Backfill
label | Specification / Drawing Reference - Aquatec Civil/Mech Drawings
label | Inspection Procedure and Acceptance Criteria - Backfill placed and compacted in 200mm layers to 95% as per drawings
label | ○ Compaction test taken every 5th layer (1m)
label | Verification Document - Compaction Test Reports
label | Aquatec: Insp. - S
label | Aquatec: Resp. - SS
label | Skerman Civil: Insp. - W
label | Skerman Civil: Resp. - CS
checkpoint | 2.11 - As Built Pickup
label | Specification / Drawing Reference - Aquatec Civil/Mech Drawings
label | Inspection Procedure and Acceptance Criteria - Survey pickup completed
label | ○ All as-constructed data recorded.
label | Verification Document - Survey Pickups, Redlined Drawings
label | Aquatec: Insp. - S
label | Aquatec: Resp. - SS
label | Skerman Civil: Insp. - W
label | Skerman Civil: Resp. - C
section | 3.0 - PUMP STATION MECH FITOUT
checkpoint | 3.1 - Materials check
label | Specification / Drawing Reference - Aquatec Civil/Mech Drawings
label | Inspection Procedure and Acceptance Criteria - Pumps, Pipework, valves, fittings, fasteners, brackets, etc. as per drawings and specifications
label | ○ Materials checked for damage
label | Verification Document - Delivery Dockets Material Certificates
label | Aquatec: Insp. - H
label | Aquatec: Resp. - SS
label | Skerman Civil: Insp. - W
label | Skerman Civil: Resp. - C
holdpoint | HOLD POINT
checkpoint | 3.2 - Pump and Pipeline set out
label | Specification / Drawing Reference - Aquatec Pipework Layout Drawings
label | Inspection Procedure and Acceptance Criteria - Layouts and IL's are consistent with drawings
label | Aquatec: Insp. - S
label | Aquatec: Resp. - SS
label | Skerman Civil: Insp. - W
label | Skerman Civil: Resp. - C
checkpoint | 3.3 - Pump Pedestal Installation
label | Specification / Drawing Reference - Aquatec Civil/Mech Drawings
label | Inspection Procedure and Acceptance Criteria - Anchors installed to correct depth and as per manufacturers recommendation
label | ○ Pumps level
label | ○ Pedestal anchors torqued
label | ○ Guide rails installed and plumb
label | Aquatec: Insp. - S
label | Aquatec: Resp. - SS
label | Skerman Civil: Insp. - W
label | Skerman Civil: Resp. - C
label | Urban Utilities: Insp. - W
label | Urban Utilities: Resp. - I
checkpoint | 3.4 - Pipe and Pipe Support Installation
label | Specification / Drawing Reference - Aquatec Civil/Mech Drawings
label | Inspection Procedure and Acceptance Criteria - Pipe and fittings installed as per project drawings
label | ○ Pipe supports erected as per drawings with neoprene gaskets between metal and PE liner
label | ○ Fasteners torqued correctly and marked
label | ○ Dissimilar metals isolated
label | ○ Pipework flushed, drained and dried as required
label | ○ HDPE Vactor pipe vacuum tested to confirm no leaks
label | ○ PE Welding spark testing
label | Aquatec: Insp. - S
label | Aquatec: Resp. - SS
label | Skerman Civil: Insp. - W
label | Skerman Civil: Resp. - C
checkpoint | 3.5 - Valve Installation
label | Specification / Drawing Reference - Aquatec Civil/Mech Drawings
label | Inspection Procedure and Acceptance Criteria - Valves installed as per drawings
label | ○ Handles fitted and secure
label | ○ Valve operation checked
label | ○ Valve orientation correct
label | ○ Fasteners torqued correctly and marked
label | Aquatec: Insp. - S
label | Aquatec: Resp. - SS
label | Skerman Civil: Insp. - W
label | Skerman Civil: Resp. - C
checkpoint | 3.6 - Ladders and misc. installation
label | Specification / Drawing Reference - Aquatec Civil/Mech Drawings
label | Inspection Procedure and Acceptance Criteria - Anchors installed to correct depth and as per manufacturers recommendation
label | ○ Ladders and misc. steelwork plumb and level
label | ○ Bracket anchors torqued with neoprene gaskets between metal and PE liner
label | Aquatec: Insp. - S
label | Aquatec: Resp. - SS
label | Skerman Civil: Insp. - W
label | Skerman Civil: Resp. - C
checkpoint | 3.7 - Grouting
label | Specification / Drawing Reference - Aquatec Civil/Mech Drawings
label | Inspection Procedure and Acceptance Criteria - Confirm grout product has not passed expiry date
label | ○ Concrete surfaces scrabbled as required
label | ○ All penetrations and pipe supports grouted as per manufactures specification
label | Aquatec: Insp. - S
label | Aquatec: Resp. - SS
label | Skerman Civil: Insp. - W
label | Skerman Civil: Resp. - C
checkpoint | 3.8 - Thrust Blocks
label | Specification / Drawing Reference - Aquatec Civil/Mech Drawings
label | Inspection Procedure and Acceptance Criteria - Reinforcing placed as per drawings
label | ○ 2 x layers hydrotite used
label | ○ Walls scabbled
label | ○ Adequate Vibration used
label | Verification Document - Concrete Dockets
label | Aquatec: Insp. - H
label | Aquatec: Resp. - SS
label | Skerman Civil: Insp. - H
label | Skerman Civil: Resp. - C
label | Urban Utilities: Insp. - H
label | Urban Utilities: Resp. - I
holdpoint | HOLD POINT
checkpoint | 3.9 - Trench Fill and Compaction
label | Specification / Drawing Reference - Aquatec Civil/Mech Drawings
label | Inspection Procedure and Acceptance Criteria - Marker tape installed as required
label | ○ Trench backfilled with imported suitable trench fill
label | Aquatec: Insp. - S
label | Aquatec: Resp. - SS
label | Skerman Civil: Insp. - W
label | Skerman Civil: Resp. - C
checkpoint | 3.10 - As Built Pickup
label | Specification / Drawing Reference - Aquatec Civil/Mech Drawings
label | Inspection Procedure and Acceptance Criteria - Final inspection of mechanical works completed
label | ○ Survey pickup completed
label | ○ All as-constructed data recorded.
label | Verification Document - Survey Pickups Redlined Drawings
label | Aquatec: Insp. - H
label | Aquatec: Resp. - SS
label | Skerman Civil: Insp. - H
label | Skerman Civil: Resp. - C
label | Urban Utilities: Insp. - H
label | Urban Utilities: Resp. - I
holdpoint | HOLD POINT
section | 4.0 - DRAINS, CONDUITS & VENTS
checkpoint | 4.1 - Materials check
label | Specification / Drawing Reference - Aquatec Civil/Mech Drawings
label | Inspection Procedure and Acceptance Criteria - Pipework, fittings and adhesives as per drawings
label | Aquatec: Insp. - H
label | Aquatec: Resp. - SS
label | Skerman Civil: Insp. - W
label | Skerman Civil: Resp. - C
holdpoint | HOLD POINT
checkpoint | 4.2 - Pipeline set out
label | Specification / Drawing Reference - Aquatec Civil/Mech Drawings
label | Inspection Procedure and Acceptance Criteria - Layouts and IL's are consistent with drawings
label | Aquatec: Insp. - W
label | Aquatec: Resp. - SS
label | Skerman Civil: Insp. - W
label | Skerman Civil: Resp. - C
checkpoint | 4.3 - Pipework Connections
label | Specification / Drawing Reference - Aquatec Civil/Mech Drawings
label | Inspection Procedure and Acceptance Criteria - Pipework installed as per project drawings
label | ○ Invert, grade and alignment checked
label | ○ Connections completed with no excessive loading exerted onto cast-ins.
label | Aquatec: Insp. - S
label | Aquatec: Resp. - SS
label | Skerman Civil: Insp. - W
label | Skerman Civil: Resp. - C
checkpoint | 4.4 - Trench Fill and Compaction
label | Specification / Drawing Reference - Aquatec Civil/Mech Drawings
label | Inspection Procedure and Acceptance Criteria - Marker tape installed as required
label | ○ Trench backfilled with imported suitable trench fill
label | Aquatec: Insp. - W
label | Aquatec: Resp. - SS
label | Skerman Civil: Insp. - W
label | Skerman Civil: Resp. - C
checkpoint | 4.5 - As Built Pickup
label | Specification / Drawing Reference - Aquatec Civil/Mech Drawings
label | Inspection Procedure and Acceptance Criteria - Survey pickup completed
label | ○ All as-constructed data recorded.
label | Verification Document - Survey Pickups, Redlined Drawings
label | Aquatec: Insp. - S
label | Aquatec: Resp. - SS
label | Skerman Civil: Insp. - W
label | Skerman Civil: Resp. - C
section | 5.0 - PUMP STATION CONCRETE SLABS
checkpoint | 5.1 - Slab set-out
label | Specification / Drawing Reference - Aquatec Civil/Mech Drawings
label | Inspection Procedure and Acceptance Criteria - Setout points established and offset for recovery
label | Skerman Civil: Insp. - W
label | Skerman Civil: Resp. - C
checkpoint | 5.2 - Excavation for slab
label | Specification / Drawing Reference - Aquatec Civil/Mech Drawings
label | Inspection Procedure and Acceptance Criteria - Bearing Capacity confirmed as per drawings
label | ○ If excavation base material deemed unsuitable, unsuitable foundation to be replaced with suitable material with approval.
label | ○ Where over-excavation occurs, excavation shall be filled with material to satisfaction of geotechnical engineer
label | Skerman Civil: Insp. - W
label | Skerman Civil: Resp. - C
checkpoint | 5.3 - Formwork
label | Specification / Drawing Reference - Aquatec Civil/Mech Drawings
label | Inspection Procedure and Acceptance Criteria - Formwork installed as per drawings
label | ○ Form release applied as required
label | Skerman Civil: Insp. - W
label | Skerman Civil: Resp. - C
checkpoint | 5.4 - Reinforcement
label | Specification / Drawing Reference - Consultant Drawings MW Specifications
label | Inspection Procedure and Acceptance Criteria - ○ Correct reinforcing sizes and spacing
label | ○ Minimum cover as per drawing
label | ○ Appropriate lap / cog lengths
label | ○ Cover to conduits as per drawings
label | Skerman Civil: Insp. - W
label | Skerman Civil: Resp. - C
checkpoint | 5.6 - Pre-Pour
label | Specification / Drawing Reference - Consultant Drawings MW Specifications
label | Inspection Procedure and Acceptance Criteria - Relevant persons notified of pour
label | ○ Inspection and certification completed (as applicable)
label | ○ all debris removed from formwork
label | ○ Correct bar chairs and qty in place
label | ○ Conduits positioned correctly
label | Aquatec: Insp. - W
label | Aquatec: Resp. - SS
label | Skerman Civil: Insp. - H
label | Skerman Civil: Resp. - C
label | Urban Utilities: Insp. - H
label | Urban Utilities: Resp. - I
holdpoint | HOLD POINT
checkpoint | 5.7 - Concrete Pours
label | Specification / Drawing Reference - Consultant Drawings MW Specifications
label | Inspection Procedure and Acceptance Criteria - Concrete docket checked to confirm mix is as per drawings
label | ○ Free dropping not permitted
label | ○ Adequate vibration used
label | ○ Finish as per specification and drawings
label | Verification Document - Pour record /Docket
label | Skerman Civil: Insp. - S
label | Skerman Civil: Resp. - C
checkpoint | 5.8 - Post-Pour
label | Specification / Drawing Reference - MW Specifications AS 3600
label | Inspection Procedure and Acceptance Criteria - Compressive strength adequate prior to stripping
label | ○ Curing agent applied immediately after stripping
label | Skerman Civil: Insp. - W
label | Skerman Civil: Resp. - C
checkpoint | 5.9 - As Built Pickup
label | Specification / Drawing Reference - MW Specifications
label | Inspection Procedure and Acceptance Criteria - Survey pickup completed as required
label | ○ All as-constructed data recorded.
label | Verification Document - Survey Pickups, Redlined Drawings
label | Aquatec: Insp. - W
label | Aquatec: Resp. - SS
label | Skerman Civil: Insp. - W
label | Skerman Civil: Resp. - C
section | 6.0 - ELECTRICAL INSTALLATION
checkpoint | 6.1 - Switchboard check
label | Specification / Drawing Reference - Electrical Drawings
label | Inspection Procedure and Acceptance Criteria - Switchboard and instruments as per drawings and specifications
label | ○ Materials checked for damage
label | Verification Document - Delivery Dockets Material Certificates
label | Aquatec: Insp. - H
label | Aquatec: Resp. - PM
label | Skerman Civil: Insp. - H
label | Skerman Civil: Resp. - C
label | Urban Utilities: Insp. - H
label | Urban Utilities: Resp. - I
holdpoint | HOLD POINT
checkpoint | 6.2 - Switchboard check
label | Specification / Drawing Reference - Electrical Drawings
label | Inspection Procedure and Acceptance Criteria - FAT test results received
label | Verification Document - FAT Results
label | Aquatec: Insp. - H
label | Aquatec: Resp. - PM
label | Skerman Civil: Insp. - H
label | Skerman Civil: Resp. - C
label | Urban Utilities: Insp. - H
label | Urban Utilities: Resp. - I
holdpoint | HOLD POINT
checkpoint | 6.3 - Switchboard Installation
label | Specification / Drawing Reference - Aquatec Civil/Mech Drawings AS 3000
label | Inspection Procedure and Acceptance Criteria - Conduits are installed as per drawings
label | ○ Communications GeoSCADA
label | ○ Mastic sealant used on underside of switchboard
label | ○ Switchboard fixed down using correct dyna bolts
label | Aquatec: Insp. - S
label | Aquatec: Resp. - SS
label | Skerman Civil: Insp. - S
label | Skerman Civil: Resp. - C
checkpoint | 6.4 - Switchboard Installation
label | Specification / Drawing Reference - Aquatec Civil/Mech Drawings AS 3000
label | Inspection Procedure and Acceptance Criteria - Pre SAT
label | Aquatec: Insp. - S
label | Aquatec: Resp. - SS
label | Skerman Civil: Insp. - S
label | Skerman Civil: Resp. - C
label | Urban Utilities: Insp. - H
label | Urban Utilities: Resp. - I
holdpoint | HOLD POINT
checkpoint | 6.5 - Switchboard Installation
label | Specification / Drawing Reference - Aquatec Civil/Mech Drawings AS 3000
label | Inspection Procedure and Acceptance Criteria - SAT
label | Aquatec: Insp. - S
label | Aquatec: Resp. - SS
label | Skerman Civil: Insp. - S
label | Skerman Civil: Resp. - C
label | Urban Utilities: Insp. - H
label | Urban Utilities: Resp. - I
holdpoint | HOLD POINT
checkpoint | 6.6 - Earthing
label | Specification / Drawing Reference - Electrical Drawings AS 3000
label | Inspection Procedure and Acceptance Criteria - Main earth stake correctly installed and labelled
label | ○ Earthing cables terminated safely and correctly
label | Aquatec: Insp. - S
label | Aquatec: Resp. - SS
label | Skerman Civil: Insp. - S
label | Skerman Civil: Resp. - C
checkpoint | 6.7 - Consumer Mains
label | Specification / Drawing Reference - Electrical Drawings AS 3000
label | Inspection Procedure and Acceptance Criteria - Conduits meet AS 3000 requirements and are free of obstructions
label | ○ Conduit penetration into POS is sealed and at correct depth
label | ○ Consumer mains installed to conduits and labelled as requried
label | ○ Cable testing and terminations completed
label | ○ Sealing of conduits completed
label | Aquatec: Insp. - S
label | Aquatec: Resp. - SS
label | Skerman Civil: Insp. - S
label | Skerman Civil: Resp. - C
checkpoint | 6.8 - Instrumentation and Control
label | Specification / Drawing Reference - Electrical Drawings AS 3000
label | Inspection Procedure and Acceptance Criteria - Flowmeter installed, labelled and terminated as per drawings
label | ○ Level control instrumentation installed, terminated and labelled as per drawings
label | ○ Pump controllers terminated and labelled as per drawings
label | ○ Sealing of conduits completed
label | Aquatec: Insp. - S
label | Aquatec: Resp. - SS
label | Skerman Civil: Insp. - S
label | Skerman Civil: Resp. - C
checkpoint | 6.9 - Lighting and power
label | Specification / Drawing Reference - Aquatec Drawings Electrical Drawings AS 3000
label | Inspection Procedure and Acceptance Criteria - Lighting setout as per drawings
label | ○ Light & Power components are as per drawings
label | Aquatec: Insp. - S
label | Aquatec: Resp. - SS
label | Skerman Civil: Insp. - S
label | Skerman Civil: Resp. - C
checkpoint | 6.10 - As Built Pickup
label | Inspection Procedure and Acceptance Criteria - All as-constructed data recorded.
label | Verification Document - Redlined Drawings
label | Aquatec: Insp. - S
label | Aquatec: Resp. - SS
label | Skerman Civil: Insp. - W
label | Skerman Civil: Resp. - C
section | 8.0 - CLOSEOUT
checkpoint | 8.1 - Non Conformances
label | Inspection Procedure and Acceptance Criteria - Non-conformances closed out
label | Aquatec: Insp. - H
label | Aquatec: Resp. - PM
label | Skerman Civil: Insp. - H
label | Skerman Civil: Resp. - C
label | Urban Utilities: Insp. - H
label | Urban Utilities: Resp. - I
holdpoint | HOLD POINT
checkpoint | 8.2 - Hydrostatic Testing
label | Specification / Drawing Reference - AS3735
label | Inspection Procedure and Acceptance Criteria - AQT Test Record Documentation
label | Aquatec: Insp. - H
label | Aquatec: Resp. - PM
label | Skerman Civil: Insp. - H
label | Skerman Civil: Resp. - C
label | Urban Utilities: Insp. - H
label | Urban Utilities: Resp. - I
holdpoint | HOLD POINT
checkpoint | 8.3 - Final Site Inspection
label | Specification / Drawing Reference - Project Specifications and Drawings
label | Inspection Procedure and Acceptance Criteria - Site Clean and Clear of all Construction Waste and Debris disposed of legally and in accordance with legislation
label | ○ 100% Visual Inspection of install by PM, Client and MW
label | ○ Installation checked against drawings to confirm all works are as per design
label | ○ Site Reinstated to a standard equal to or better than existing in accordance with Project specification
label | Aquatec: Insp. - H
label | Aquatec: Resp. - PM
label | Skerman Civil: Insp. - H
label | Skerman Civil: Resp. - C
label | Urban Utilities: Insp. - H
label | Urban Utilities: Resp. - I
holdpoint | HOLD POINT
checkpoint | Project Completed
date | Date:
textbox | Signed By Aquatec Representative
textbox | Signed By Water Authority Representative
textbox | Signed By Civil Contractor Representative
holdpoint | Signatures