## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | INF-HSEQ CC0375-ITP-028 Spray Seal - Rev.1 | itp |  |  |  |  | INF-HSEQ CC0375-ITP-028 Spray Seal - Rev.1
section | 1.0 Preliminaries
checkpoint | 1.1 - Documentation
label | Ref docs - Issued drawings / Site copy drawings
label | Acceptance criteria - Check that you have the latest site and engineering drawings BEFORE starting each task/set of tasks.
button | Acceptance | Yes,No,N/A
label | Key - S
label | HPP CON Key - S
label | HPP QA Key - S
checkpoint | 1.2 - Lot Traceability
label | Ref docs - Spec. 0161 Quality [Cl 7.3]
label | Acceptance criteria - Prepare a lot map for traceability of the work area
button | Acceptance | Yes,No,N/A
label | Key - S
label | HPP CON Key - S
label | HPP QA Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Lot map
checkpoint | 1.3 - Material
label | Ref docs - TfNSW 3151, 3252,3253, 3258, 3259, ,3268, 3269
label | Acceptance criteria - Correct class & type been supplied and free of contaminations.
button | Acceptance | Yes,No,N/A
label | Key - S
label | HPP CON Key - S
label | HPP QA Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Material Test Report
checkpoint | 1.4 - Underlying Lot Conformance
label | Ref docs - Underlying Lot ITP
label | Acceptance criteria - Underlying services and/or assets have been installed prior to commencing works over and/or above.
label | ○ Refer underlying lot ITP(s)
button | Acceptance | Yes,No,N/A
label | Key - S
label | HPP CON Key - S
label | HPP QA Key - S
checkpoint | 1.5 - Set out
label | Ref docs - Drawings
label | Acceptance criteria - Setout to the location and levels on the drawings. This shall be presented for inspection by the superintendent.
button | Acceptance | Yes,No,N/A
label | Key - S
label | HPP CON Key - S
label | HPP QA Key - S
checkpoint | 1.6 - Nominated Application Rates
label | Ref docs - TfNSW R106.3 & R107.3, 5.4
label | Acceptance criteria - 1. Selection of Spray Seal Types and Binder Types - TfNSW R106 Annexure R106/L & R107 Annexure R107/L specifies Seal and Binder Types
label | 2. Submission of Nominated Application Rates for each Segment.
label | (Hold Points)
button | Acceptance | Yes,No,N/A
textbox | Acceptance: |  |  | litres/m2
label | Key - H
label | HPP CON Key - H
label | HPP QA Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.7 - Bitumen Sprayer Certification
label | Ref docs - TfNSW 106 6.1& 6.2 & TfNSW R107.6.1 & 6.2
label | Acceptance criteria - Current Sprayer Certificate
button | Acceptance | Yes,No,N/A
label | Key - R
label | HPP CON Key - R
label | HPP QA Key - R
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Certificate (within 12 Months of Test)
section | 2.0 Application of Spray Seal
checkpoint | 2.1 - Pavement Temperature & Weather Conditions
label | Ref docs - TfNSW R106 5.3 & TfNSW107.5.3
label | Acceptance criteria - Prior to Commencing and throughout Operations. Spraying shall be undertaken only if the pavement > 10oC for at least 1 hour and > 20oC for at least 1 hour for PMB
textbox | Acceptance (air): |  |  | °C
textbox | Acceptance (pavement): |  |  | °C
label | Key - S
label | HPP CON Key - S
label | HPP QA Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Monitor -Thermometer
checkpoint | 2.2 - Preparation of Pavement Surface
label | Ref docs - TfNSW R106 & TfNSW R107
label | Acceptance criteria - Surface visual inspection by Superintendent as per job specific requirements prior to operations.
label | ○ Ensure protection of existing services & fixtures Prior to Commencing Sprayed Bituminous Surfacing
label | ○ Sweep surface with rotary broom 300mm beyond edge of seal
button | Acceptance | Yes,No,N/A
label | Key - S
label | HPP CON Key - S
label | HPP QA Key - S
checkpoint | 2.3 - Preparation of Binder - Incorporation of Cutter, Flux, Adhesion Agent
label | Ref docs - TfNSW R106 6.7 & TfNSW R107.6.7
label | Acceptance criteria - Prior to each spraying surface, check Bitumen to cutter and circulate for 700 L/min for 20 minutes. For PMB circulate at 700l/min for 15 minutes.
button | Acceptance | Yes,No,N/A
label | Key - S
label | HPP CON Key - S
label | HPP QA Key - S
checkpoint | 2.4 - Binder Temperatures (for Spraying)
label | Ref docs - TfNSW R106.6.6
label | Acceptance criteria - Bitumen must be within the temperature range shown in Table R106.2 when cutter oil is incorporated
label | – – – – – – – – – – – – – – – –
label | Table R106.2 - Bitumen Temperature
label | Class ¦¦ Temperature Range (°C)
label | – – – – – – – – – – – – – – – –
label | 170, Multigrade 600/170 ¦¦ 160 - 190
label | 320 ¦¦ 170 - 200
label | – – – – – – – – – – – – – – – –
label | ○ Cutback bitumen must be within the temperature range shown in Table R106.3 at the time of spraying.
label | – – – – – – – – – – – – – – – –
label | Table R106.3 - Cutback Bitumen Spraying Temperatures
label | Grade ¦¦ Equivalent Cutter (%) ¦¦ Temperature Range (°C)
label | – – – – – – – – – – – – – – – –
label | AMC00 ¦¦ 56 ¦¦ 10 - 30
label | AMC0 ¦¦ 44 ¦¦ 35 - 55
label | AMC1 ¦¦ 34 ¦¦ 60 - 80
label | AMC2 ¦¦ 27 ¦¦ 75 - 100
label | AMC3 ¦¦ 21 ¦¦ 95 - 115
label | AMC4 ¦¦ 16 ¦¦ 110 - 135
label | AMC5 ¦¦ 11 ¦¦ 120 - 150
label | AMC6 ¦¦ 7 ¦¦ 120 - 150
label | AMC7 ¦¦ 3 ¦¦ 150 - 175
label | FC2 ¦¦ 25 ¦¦ 70 - 95
label | FC3 ¦¦ 20 ¦¦ 80 - 95
label | FC4 ¦¦ 15 ¦¦ 95 - 110
label | FC5 ¦¦ 10 ¦¦ 120 - 140
label | FC6 ¦¦ 7 ¦¦ 130 - 150
label | FC7 ¦¦ 3 ¦¦ 140 - 160
label | – – – – – – – – – – – – – – – –
button | Acceptance | Yes,No,N/A
label | Key - S
label | HPP CON Key - S
label | HPP QA Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Monitor -Thermometer
checkpoint | 2.5 - Binder application and aggregate
label | Ref docs - TfNSW R106 7.0 & TfNSW R107.7.0
label | Acceptance criteria - ○ Period between application Seal over Prime/Primeseal
label | – Apply - Seal > 48 hours after Prime
label | – Seal > 12 months after Primerseal
label | ○ Application Rate of Binder
label | – Binder + / - 5% of Target Application Rate
label | ○ Spread Rate of Aggregate
label | – Target Spread Rate
button | Acceptance | Yes,No,N/A
label | Key - S
label | HPP CON Key - S
label | HPP QA Key - S
checkpoint | 2.6 - Rolling of Sprayed Sealing
label | Acceptance criteria - Initial Rolling shall be carried out by 2 or more multi tyred rollers (mass min 1 tonne per wheel, tyre pressures 550kPa) until agg embedded, backrolling at 1 hr per 1,500m2 for > 500 V.L.D. and 1 hr per 1,000m2 for < 500 V.L.D. (for 1 multi tyred roller)
button | Acceptance | Yes,No,N/A
label | Key - S
label | HPP CON Key - S
label | HPP QA Key - S
checkpoint | 2.7 - Sweeping of Sprayed Seal (if required)
label | Ref docs - TfNSW T277
label | Acceptance criteria - All Loose Stone to be removed, as a minimum the final sweep shall be with a suction broom as long as the suction broom does not damage the fresh seal.
label | ○ Measurement of loose aggregate for 10 & 14mm seals after sweeping operation.
label | ○ Urban areas = 20 particles/m2: Medium - High areas = 30 particles/m2: Low traffic areas = 40 particles/m2
button | Acceptance | Yes,No,N/A
label | Key - S
label | HPP CON Key - S
label | HPP QA Key - S
section | 3.0 Conformance check
checkpoint | 3.1 - Acceptance and closure of non-conforming items
label | Ref docs - Spec. 0161 Quality [Cl 3.8]
label | Acceptance criteria - NCRs to be opened for non-conforming items and closed prior to closing construction lot.
label | HOLD POINT
button | Acceptance | Yes,No,N/A
label | Key - H
label | HPP CON Key - H
label | HPP QA Key - H
holdpoint | AUTHORITY HOLDPOINT