## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | 702 - ITP - Subsurface Drainage | itp |  |  |  |  | 702 - ITP - Subsurface Drainage
section | Details
checkpoint | 1 - Work Lot
label | Applicable Standard / Reference Document - VR173.02
label | Acceptance Criteria - A single layer, batch or area of like work, shall not exceed one day's production.
label | Frequency - Each lot
label | Verification Records - Lot Map
label | Action, Respon. - SE
date | Date:
checkpoint | 2 - Conformity With Drawings
label | Applicable Standard / Reference Document - VR702.03
label | Acceptance Criteria - The invert of the subsurface drainage pipe or the geocomposite drain shall be not more than 25 mm from the specified level and not more than 50 mm from the specified line. Changes of grade shall not be abrupt, or occur at a rate exceeding 10 mm in any 3 m length, or lead to ponding of water within the drainage pipe.
label | Frequency - Each lot
label | Verification Records - Visual
label | Action, Respon. - SE
date | Date:
checkpoint | 3 - Inspection of Base of Trench Prior to Placing Bedding
label | Applicable Standard / Reference Document - VR702.08
label | Acceptance Criteria - The base of the trench shall be inspected to verify compliance with the requirements in this clause prior to placing bedding in completed excavations. The Superintendent shall be notified at least 24 hours prior to the inspection.
label | Frequency - Each Lot
label | Verification Records - Photos
label | Action, Respon. - SE
date | Date:
holdpoint | HOLD POINT
checkpoint | 4 - Installation- Grade
label | Applicable Standard / Reference Document - VR702.09 (b)
label | Acceptance Criteria - The grade of conduits shall be not flatter than 1 in 250
label | Frequency - Each Lot
label | Verification Records - Measurement
label | Action, Respon. - FM
date | Date:
checkpoint | 5 - Compaction Process
label | Applicable Standard / Reference Document - VR702.09(g)
label | Acceptance Criteria - The method of compaction shall be in accordance with the Contractor's quality procedures and shall be submitted for review by the Superintendent.
label | ○ Where no fines concrete is used as filter material the Contractor shall submit quality procedures for review by the Superintendent which detail the method of placing the no-fines concrete to prevent segregation and the formation of a slurry layer at the surface of the concrete which may prevent the passage of water into the filter material.
label | Frequency - Once
label | Verification Records - Sub Surface Drainage Trench Compaction Procedure
label | Action, Respon. - SR, SE
date | Date:
holdpoint | HOLD POINT
checkpoint | 6 - Granular Filter Material
label | Applicable Standard / Reference Document - VR702.05 (b) & Table VR702.051
label | Acceptance Criteria - p H shall be between 6.0 & 10
label | ○ Sand Equivalent Value not less than 80.
label | ○ Grading Requirements for Granular Filter Material should be as per table VR702.051
label | Frequency - Each Batch
label | Verification Records - Dockets
label | Action, Respon. - FM
date | Date:
checkpoint | 7 - Access points and Inspection openings
label | Applicable Standard / Reference Document - VR702.10 & IFC Dwgs
label | Acceptance Criteria - Inspection openings shall be located between 100m and 150m along drainage run.
label | ○ Where stormwater pits are used as access points, the invert at the beginning of each drainage run shall be located above the top of the pit outlet & the invert at the end of each drainage run, when not shown on drawings, shall be located not less than 100mm above the invert of the pit outlet.
label | Frequency - Each Lot
label | Verification Records - Measurement
label | Action, Respon. - FM
date | Date:
checkpoint | 8 - CCTV Inspection of Subsurface Drainage Lines
label | Applicable Standard / Reference Document - VR702.09 (i)
label | Acceptance Criteria - All subsurface drainage lines constructed shall be inspected, after completion of the flushing test as stated in clause 702.09(h) and prior to placement of any pavemet including sub-base layer, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
label | ○ Placement of ashphalt shall not proceed until the CCTV inspection and flushing test have been completed, damaged or deformed subsurface drainage pipe has been removed and replaced and the waste and defects free condition of subsurface drainage lines has been verified by the Superintendent.
label | Frequency - Each Lot
label | Verification Records - Hold Point Approval CCTV Report, CCTV Footage
label | Action, Respon. - SR, SE
date | Date:
holdpoint | HOLD POINT
checkpoint | 9 - Flush out Risers & Pits
label | Applicable Standard / Reference Document - VR702.10 & IFC Dwgs
label | Acceptance Criteria - Flushout risers for drainage pipes shall have the same diameter as the pipe.
label | ○ Flushout risers for geocomposite drains shall consist of a preformed riser fitting, or a pipe of diameter not less than 100 mm.
label | ○ Flushout risers shall have surface fittings as shown on the drawings
label | ○ Inspection openings as shown on the drawings shall consist of pits having a diameter not less than 600 mm. Pits shall be fitted with concrete or cast iron frame covers as shown on the drawings.
label | Frequency - Each Lot
label | Verification Records - Visual
date | Date:
checkpoint | 10 - Flushing
label | Applicable Standard / Reference Document - VR702.09 (h)
label | Acceptance Criteria - Flushing test shall be witnessed by rep nominated by Superintendent.
label | ○ On completion of SSD, flushers & Outlets, flushing tests shall be performed and record must be kept for every sub-surface drainage line including date and time of notification to the Superintendent, date and time of flushing, and witnesses to the Flushing by the Contractor.
label | Frequency - Each Lot
label | Verification Records - Record
label | Action, Respon. - SE
date | Date:
checkpoint | 11 - Minimum Testing Frequency for Granular Filter Material
label | Applicable Standard / Reference Document - VR702.13 & Table 702.131
label | Acceptance Criteria - Grading and Unsound rock content
label | ○ Unsound Rock Content
label | ○ Sand Equivalent
label | ○ pH
label | ○ Total Dissolved Solids (glass fines only)
label | Frequency - One per 5000 tonnes of product
label | Verification Records - Quary Test Results
label | Action, Respon. - SE
date | Date:
section | Lot Conformance
checkpoint | Lot Fully Conforms
textbox | PRINT NAME:
checkpoint | Lot Conforms except for approved dispositions detailed in Corrective Actions/NCR
textbox | DETAILS:
date | DATE:
holdpoint | SIGN