## Table 1
Inspection INSITU/CORE WALLS Test Record PREPOUR, PLACEMENT & FINISH 004
Contract: Client: Job No: | Wellington Health Maxcon IM0124 | Level / Location: Drawing Reference: Concrete Strength: |  |  |  | I&D Rep: Initial: Date:
No. | Process |  |  | Pass | Fail | NCR Ref | Initial | Date
1 | Check Setting Out For: | [7 empty] | S E T O U T
| RL (top of wall) RL may vary depending on location of work. |  | RL
Set-out of all walls to IFC architectural drawing; Core Plans, Elevations, Struct.
2 | Check Existing Slab Conditions For: | [7 empty] | F O R M W O R K
Confirm correct RL of slab/core wall below and compliance with ITR of slab below.
Confirm wall transition below is correct.
3 | Check Formwork For:
All in-situ wall services have been installed and are in the correct location.
Ensure wall formwork has a suitable release agent applied.
All penetrations and cast-in items are installed and in the correct location.
Formwork/Jumpform has been inspected/signed off by a competent person/engineer.
4 | Check Reinforcement For: | [7 empty] | R E I N F O R C E M E N T
All reinforcement to be placed in accordance with the IFC structural drawings.
Reinforcement securely fixed in place.
Where reinforcement has been tack welded, it must comply with welding procedure.
Correct bar spacing.
Correct bar diameter.
Correct bar lap lengths.
Correct concrete cover.
Wall starter bars comply with size and spacing for wall over.
Keyboxes / inserts are installed as per approved supplier shop drawings.
5 | Check Preparation For Pour: | [7 empty] | P R E P O U R
Pour area cleaned before pour to ensure wall is free of standing water, debris, oils, objectionable coatings & fragments.
Ensure temperatures when pouring are within acceptable criteria.
Tester ordered - (7 and 28 day samples) 1 batch of tests or thereof for every 50m3 placed or one test sample per day each day
Placing of concrete (method) - Chute, Kibble or Pump.
Concrete vibration to be completed with use of vibrator motor (minimum requirement of 300rpm).
Formwork design/certification has been received (if applicable).
| HOLD | Signature by I&D Representative
| HOLD | Signature by Client Representative
6 | Stripping Of Formwork: | [7 empty] | P L A C E M E N T
Visual check on walls once stripped to ensure no cracking has occurred.
Visual check on walls once stripped to ensure that there are no boney concrete areas due to lack of vibration.
Ensure patching to walls has been undertaken for any defect areas that are visible.
Date Poured: | 2022-10-26 |  |  | Total m3:
Attached:
Comments: