## Sheet1
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITR 006 - SUSPENDED SLABS PREPOUR, PLACEMENT & FINISH | [5 empty] | I&D ITR 006 - Suspended Slabs
section | SETOUT
checkpoint | Nominate formwork soffit class of finish
textbox | Formwork soffit class of finish:
textbox | Class 2:
textbox | NCR Ref:
textbox | Initial:
date | Date:
checkpoint | Check for all penetrations (set-out and location)
textbox | NCR Ref:
textbox | Initial:
date | Date:
checkpoint | Nominate SFL to top of pour.
textbox | SFL |  |  | to top of pour.
textbox | NCR Ref:
textbox | Initial:
date | Date:
section | FORMWORK
checkpoint | Concrete profile drawing - A205 Rev C6, IVPT21235-00910-A
textbox | NCR Ref:
textbox | Initial:
date | Date:
checkpoint | All in-situ slab setdowns/shower bases/hobs have been installed in the correct location.
textbox | NCR Ref:
textbox | Initial:
date | Date:
checkpoint | Ensure all beam and slab depths are correct as per IFC structural drawings.
textbox | NCR Ref:
textbox | Initial:
date | Date:
checkpoint | Ensure bondeck and / or formwork pans have the correct lap and are securely fastened.
textbox | NCR Ref:
textbox | Initial:
date | Date:
checkpoint | All frames, bases and formwork tables to be correctly aligned (frames vertical) and sole plates secured in place.
textbox | NCR Ref:
textbox | Initial:
date | Date:
checkpoint | Installation of cast-ins (facade unistruts, crane and hoist ties)
textbox | NCR Ref:
textbox | Initial:
date | Date:
checkpoint | Ensure all penetrations have been installed in accordance to the architectural concrete profile plan.
textbox | NCR Ref:
textbox | Initial:
date | Date:
checkpoint | Ensure that formwork (frames, bases, tables, pans) has been inspected, items rectified, and signed off by a formwork engineer prior to any suspended slab pour.
textbox | NCR Ref:
textbox | Initial:
date | Date:
checkpoint | Signature by I&D Representative
holdpoint | ADD SIGNATURE
checkpoint | Signature by Client Representative
holdpoint | ADD SIGNATURE
section | REINFORCEMENT
checkpoint | All reinforcement to be placed in accordance with the IFC structural drawings.
textbox | NCR Ref:
textbox | Initial:
date | Date:
checkpoint | Reinforcement drawings: IVPT21235-00912-913 & 914-A
textbox | NCR Ref:
textbox | Initial:
date | Date:
checkpoint | Correct bar spacing.
textbox | NCR Ref:
textbox | Initial:
date | Date:
checkpoint | Correct bar diameter.
textbox | NCR Ref:
textbox | Initial:
date | Date:
checkpoint | Correct bar lap lengths.
textbox | NCR Ref:
textbox | Initial:
date | Date:
checkpoint | Correct concrete cover.
textbox | NCR Ref:
textbox | Initial:
date | Date:
checkpoint | Column/wall starter bars comply with size and spacing for columns/wall over.
textbox | NCR Ref:
textbox | Initial:
date | Date:
checkpoint | Engineers reinforcement inspection received and all items are closed out.
textbox | NCR Ref:
textbox | Initial:
date | Date:
section | POST TENSIONING
checkpoint | All post tensioning to be placed in accordance with the IFC structural drawings.
textbox | NCR Ref:
textbox | Initial:
date | Date:
checkpoint | Post tensioning drawings: IVPT21235-00911-A
textbox | NCR Ref:
textbox | Initial:
date | Date:
checkpoint | P.T. ducts, strands, anti-burst & trimmer bars are installed and securely fixed in place.
textbox | NCR Ref:
textbox | Initial:
date | Date:
checkpoint | Correct P.T. size and spacing.
textbox | NCR Ref:
textbox | Initial:
date | Date:
checkpoint | Correct P.T. duct level in concrete.
textbox | NCR Ref:
textbox | Initial:
date | Date:
checkpoint | Engineers P.T. inspection received and all items are closed out.
textbox | NCR Ref:
textbox | Initial:
date | Date:
section | PRE POUR
checkpoint | Pour area cleaned before pour to ensure suspended slab is free of standing water, debris, oils, objectionable coatings & fragments.
textbox | NCR Ref:
textbox | Initial:
date | Date:
checkpoint | Ensure temperatures when pouring are within acceptable criteria.
textbox | NCR Ref:
textbox | Initial:
date | Date:
checkpoint | Tester ordered - (1, 4, 7 and 28 day samples)
label | 0 - 50m3 - 1 batch of tests or thereof 50-100m3 - 2 batch of tests or thereof
label | >100m3 - add 1 batch of tests for every 50m3
textbox | NCR Ref:
textbox | Initial:
date | Date:
checkpoint | Placing of concrete (method) - Kibble or Pump.
textbox | NCR Ref:
textbox | Initial:
date | Date:
checkpoint | Concrete vibration to be completed with use of vibrator motor.
textbox | NCR Ref:
textbox | Initial:
date | Date:
checkpoint | Signature by I&D Representative
holdpoint | ADD SIGNATURE
checkpoint | Signature by Client Representative
holdpoint | ADD SIGNATURE
section | PLACEMENT
checkpoint | A minimum of one of vibrator must be used at all times while the pump is in operation. Ensure vibrators are long enough to ensure full compaction.
textbox | NCR Ref:
textbox | Initial:
date | Date:
checkpoint | Competent concreters will be used to vibrate the concrete using the immersion vibrators, ensuring full compaction is achieved.
textbox | NCR Ref:
textbox | Initial:
date | Date:
checkpoint | Approved concrete curing has taken place for tempretures above 25 degrees celsius.
textbox | NCR Ref:
textbox | Initial:
date | Date:
checkpoint | Slab level asbuilt has been completed and provided to client.
textbox | NCR Ref:
textbox | Initial:
date | Date:
checkpoint-no-status | Date Poured:
date | Date:
textbox | Total m3: