## Sheet1
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITR 008 - PRECAST PANEL / COLUMN INSTALLATION | [5 empty] | I&D ITR 008 - Precast Panel & Column Installation
section | PRE ERECTION
checkpoint | Panel shop drawings are approved and IFC.
textbox | NCR Ref:
textbox | Initial:
date | Date:
checkpoint | Precast panel / column propping design has been approved by a qualified independent engineer.
textbox | NCR Ref:
textbox | Initial:
date | Date:
checkpoint | Grouting procedure / product has been approved by engineer.
textbox | NCR Ref:
textbox | Initial:
date | Date:
checkpoint | Welding procedure has been approved by engineer.
textbox | NCR Ref:
textbox | Initial:
date | Date:
checkpoint | Precast panels / columns are lifted from the approved lifting points.
textbox | NCR Ref:
textbox | Initial:
date | Date:
checkpoint | Precast panel / column birth certificates have been sighted/received prior to erection.
textbox | NCR Ref:
textbox | Initial:
date | Date:
checkpoint | Precast panels / columns are clearly numbered and or identified.
textbox | NCR Ref:
textbox | Initial:
date | Date:
checkpoint | Concrete slab being propped to has reached the required design/propping strength.
textbox | NCR Ref:
textbox | Initial:
date | Date:
checkpoint | Mobile crane set up as per approved lift study (if applicable).
textbox | NCR Ref:
textbox | Initial:
date | Date:
checkpoint | Signature by I&D Representative
holdpoint | ADD SIGNATURE
checkpoint | Signature by Client Representative
holdpoint | ADD SIGNATURE
section | INSTALLATION
checkpoint | Correct survey and set out of precast panels / columns.
textbox | NCR Ref:
textbox | Initial:
date | Date:
checkpoint | Dowel bars are the correct size, spacing, and installed in correct location.
textbox | NCR Ref:
textbox | Initial:
date | Date:
checkpoint | Dowel bars have the correct lap length.
textbox | NCR Ref:
textbox | Initial:
date | Date:
checkpoint | R.L. to the underside of precast panels / columns - Varies
textbox | NCR Ref:
textbox | Initial:
date | Date:
checkpoint | Propping / bolts are installed as per the approved propping design.
textbox | NCR Ref:
textbox | Initial:
date | Date:
checkpoint | 4.6 Fasteners have been used and torqued to the manufactures specifications.
textbox | NCR Ref:
textbox | Initial:
date | Date:
checkpoint | Approved grouting product has been mixed, handled and applied in accordance with manufacturers specification.
textbox | NCR Ref:
textbox | Initial:
date | Date:
checkpoint | Precast panels / columns have been installed to the IFC design location.
textbox | NCR Ref:
textbox | Initial:
date | Date:
checkpoint | Precast panels / columns have been installed plumb and level.
textbox | NCR Ref:
textbox | Initial:
date | Date:
checkpoint | Signature by I&D Representative
holdpoint | ADD SIGNATURE
checkpoint | Signature by Client Representative
holdpoint | ADD SIGNATURE
section | POST ERECTION
checkpoint | Stitch plates have been welded in accordance with IFC structural drawings and approved welding procedure.
textbox | NCR Ref:
textbox | Initial:
date | Date:
checkpoint | Prop bracing removed post welding of stitch plates, grout has achieved required strength, and in consultation with temporary works engineer.
textbox | NCR Ref:
textbox | Initial:
date | Date:
checkpoint | Caulking, grouting, and patching of stitch plates has been carried out in accordance with project documentation/specifications.
textbox | NCR Ref:
textbox | Initial:
date | Date:
checkpoint-no-status | Installation Date:
date | Date:
label | Precast Numbers: As Per Load List