## ITP
|  |  | Inspection and Test Plan - SUP Installation (HCC) | [7 empty] | Document # 1145-C200-FUL-QAC-ITP-0085
[11 empty] | Revision: A | Date: 18/08/2022
Client: | MRPV |  | Construction Process: | SUP Installation (Hume City Council) |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: | Craigieburn Road Upgrade |  | Specifications: | EDCM 401 |  | Name: | Omar El Khub | Name: | Taj Minhas |  | Name:
Contract No: | CONS-1145 |  | Structure / Component: | Shared Use Path (Hume City Council) |  | Position: | Project Engineer | Position: | Senior Project Engineer |  | Position:
|  |  | Location: |  |  | Date : | 2022-07-07 | Date : | 2022-07-07 |  | Date : | 2022-07-07
Lot No: | ITP-085-AX-LOT-XXX |  | Lot Title: |  | Location: |  |  | Lot Size/ Quantity: |  |  | Lot Opened Date:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Superintendent | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check that current revision drawings are being used |  | Prior to Commencing | Issued For Construction (IFC) and latest available revision used | Project Drawings / Drawing Register | Document review | Latest Revision Drawings | AP | Site Engineer / Site Foreman | N/A |  | N/A
1.2 | Bedding Material / Base Layer |  | Once, for each mix design, prior to placement of material | 20mm Class 3 bedding material conforms to specified requirements applicable to the class of product as detailed on the drawings. Material is registered with VicRoads in accordance with Code of Practice RC500.02. Enter: Teambinder Material Approval number [free text box] | IFC Drawings 703.21 812.04 | Document Review | Teambinder reference number | IP | Site Engineer Superintendent | N/A |  | N/A
1.3 | Concrete Mix |  | Once, for each mix design, prior to placement of concrete | Concrete mix meets strength, grade, and maximum aggregate size as detailed on the drawings. Paving concrete mix conforms to AS1379. SUP concrete mix is registered with VicRoads. No air entraining chemical admixtures shall be used without approval from the Nominated Authority. Concrete mix designs shall remain valid for 12 months from the date of registration, unless constituent materials and material proportions cease to comply with the specified requirements. Enter: Teambinder Material Approval number [free text box] | IFC Drawings 703.05 (a) 703.07 | Document Review | Teambinder reference number | IP | Site Engineer | N/A |  | N/A
1.4 | Evaporative Retardant | 703.09 | Once, for each product, prior to placement of concrete | Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority. Enter: Teambinder Material Approval number [free text box] | 703.09 | Document Review | Teambinder reference number | IP | Site Engineer | N/A |  | N/A
1.5 | Curing Compound | 703.10 (a) | Once, for each product, prior to placement of concrete | Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority. Enter: Teambinder Material Approval number [free text box] | 703.10 (a) | Document Review | Teambinder reference number | IP | Site Engineer | N/A |  | N/A
2 | Construction Works
2.2 | Temporary Drainage Provisions (if required) |  | Prior to Commencing | Before obstructing any waterway, channel or culvert, the Contractor shall make appropriate provision for its temporary diversion, and obtain prior written approval from the relevant waterway authority. The Contractor shall make provision for the safe discharge of drainage and stormwater at all times during construction. | IFC Drawings VicRoads Spec Cl.703.18 | Site Inspection | Written approval from relevant waterway authority ITP Signed | AP | Supervisor / Site Engineer | N/A |  | N/A
2.3 | Pavement Thickness Increases for Crossings |  | Prior to Commencing | Where applicable, excavation to allow for increase in the bedding and slab thicknesses at: i. Pram crossings ii. Vehicle crossings (residential and/or commercial) iii. Established / existing mature trees Consult the Relevant Council drawings for dimensional tolerances for thicknesses, grades and ramp lengths. | IFC Drawings VicRoads Spec 703.16 703.24 EDCM 401 | Site Inspection | ITP Signed | IP | Superintendent/ Supervisor / Site Engineer | N/A |  | N/A
2.4 | Subgrade Preparation |  | Each Lot | Subgrade to be test rolled to ensure the substrate is adequate for bedding and concrete placement | WP 011 | Site Inspection | ITP Signed | *HP | Supervisor / Site Engineer | N/A |  | N/A
2.5 | Bedding Preparation |  | Each Lot | All bedding material shall be as specified on design drawings. Where not specified, bedding material used for cast in place concrete paving works shall be compacted size 20 mm Class 3 or Class 4 crushed rock or Class 3 or Class 4 crushed concrete, manufactured and supplied in accordance with Sections 812 or 820 respectively. Immediately before concrete is placed, the bedding shall be moist but shall have no free water on the surface. Bedding to be compacted to 98% standard. | VicRoads Spec Cl.703.21 812, 820 IFC Drawings | Site Inspection | ITP Signed | IP | Supervisor / Site Engineer | N/A |  | N/A
2.6 | Formwork |  | Prior to Commencing | Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation. | VicRoads Spec Cl.703.12 | Site Inspection | ITP Signed | IP | Supervisor / Site Engineer | N/A |  | N/A
2.7 | Steel Reinforcement |  | Prior to Commencing | Steel reinforcement shall be placed in accordance with drawings and AS/NZS 4671. If not specified, mesh shall be placed as per VicRoads Spec Cl. 703.16. The minimum cover of any steel reinforcement to the nearest concrete surface shall be 50 mm unless shown on the drawings. Reinforcement shall be supported using either concrete or plastic chairs. | VicRoads Spec Cl.703.13 & Cl.703.13 AS/NZS 4671 | Site Inspection | ITP Signed | IP | Supervisor / Site Engineer | N/A |  | N/A
2.8 | Pre-pour inspection |  | Each Lot | Inspection to ensure that forms, reinforcement dowels and other embedments conform to the requirements of the specifications and drawings. | VicRoads Spec Cl.703.05 Cl.703.09 Cl.610.17 (a)(b) (c)(d) AS 1379 | Site Inspection | ITP Signed | HP | Project Engineer, Superintendent/Council & Surveyor |  |  | N/A
2.9 | Concrete Testing |  | Each Lot | Concrete Testing Frequency: 0m³ to 50m³ = 1 sample Each sample shall consist of 1 no. slump test and 2 no. compressive strength cylinders minimum. Compressive strength cylinders = 2 no. 28 day strength. Slump Testing Tolerances: <60mm = ±10mm ≥60mm to ≤80mm = ±15mm >80mm to ≤110mm = ±20mm >110mm to ≤150mm = ±30mm >150mm = ±40mm | VicRoads Spec 703.11 | Site Inspection | Concrete Pour Record ITP Signed | IP | Supervisor / Site Engineer | N/A |  | N/A
2.1 | Curing |  | Each Lot | The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed and shall continue uninterrupted for a period of not less than 7 days after placing the concrete Concrete shall be cured either by water curing, wet hessian, polyethylene sheeting which is adequately sealed, curing compound or a combination of these | VicRoads Spec Cl. 703.10 | Site Inspection | ITP Signed | IP | Supervisor / Site Engineer | N/A |  | N/A
2.11 | Tolerances |  | Each Lot | Concrete paving to match existing fixtures (e.g. pit covers, edgings and vehicle crossings) within 5mm. Deviation of finished work shall not exceed; 10mm from line or level; or 5mm from a 3m straightedge for curves and shaped areas. Deviation of section dimensions shall not exceed 5mm (except for overall width); 25mm for the overall width; and +/- 3mm for dimensions less than 25mm. | VicRoads Spec. Cl 703.15 | Site Inspection | ITP Signed | IP | Supervisor / Site Engineer | N/A |  | N/A
2.12 | Joints |  | Each Lot | Expansion Joints: shall be placed at intervals as specified by the drawings. Control Joints: at least 25% of the paving thickness deep and 5 mm wide shall be formed with a cutting tool at 2.5 m intervals along the full width of footpaths, other surfacings and shared use paths. Between Concrete Paving and Shared Use Path: Except for medians <2.0m wide, bonding between the concrete paving or shared use path and the edging shall be prevented by painting the back of the edging with bitumen, or by using a strip of bituminous felt (ableflex). | VicRoads Spec Cl. 703.26 (b) | Site Inspection | ITP Signed | IP | Supervisor / Site Engineer | N/A |  | N/A
2.13 | Stripping Formwork |  | Each Lot | Formwork shall not be stripped until the minimum times have elapsed from the time of completion of the placing of concrete: i. 2 days for vertical formwork on external surfaces; and ii. 1 day for vertical forms on permanently hidden surfaces | VicRoads Spec 703.12 AS3610 Table C2 | Site Inspection | ITP Signed | IP | Supervisor / Site Engineer | N/A |  | N/A
2.14 | Protection of Newly Poured Concrete |  | Each Lot | All concrete shall be protected from damage from early loading by pedestrians, animals, vehicles and from rain or any other cause. Suitable flagging, signage or bunding shall be erected to prevent vehicles from crossing over residential and/or commercial vehicle crossings a minimum of four days after completion of casting of the concrete. Vehicles greater than 1.5 tonnes may be permitted to cross after 7 days. | VicRoads Spec 703.27 | Site Inspection | ITP Signed | IP | Supervisor / Site Engineer | N/A |  | N/A
3 | Post-Construction
3.1 | Survey data captured for as-built purposes |  | Completion of each lot | Survey to ensure and validate that all works meet level and location requirements. Review of existing survey control marks and any additional control marks providing verification of conformity of as constructed features with design. As built survey recorded to confirm installation within tolerances in the latest IFC drawings. | IFC Drawings / survey records | Document review | As-built survey records | SCP | Project Engineer | N/A |  | N/A
3.2 | Cracking of Concrete |  | Each Lot | The concrete shall have no surface cracks at any stage after construction of width greater than 0.2 mm. Cracked sections of concrete shall be either removed and replaced, or repaired in accordance with Section 687 | VicRoads Spec. Cl. 703.30 687 | Site Inspection | ITP Signed | IP | Supervisor / Site Engineer | N/A |  | N/A
3.2 | Compressive Strength Test Results |  | Completion of each lot | 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength. Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength. | IFC Drawings Relevant Council Drawings 703.11 Table 703.111 | Site Inspection | Attach: Compressive Strength Test Results | IP | Supervisor / Site Engineer | N/A |  | N/A
3.3 | Backfilling |  | Completion of each lot | Where required, as soon as concrete has cured sufficiently and not earlier than three days after placing, topsoil shall be placed and firmly compacted in layers not exceeding 150mm and to a width not less than 300mm behind the edging to the top of the edging. | VicRoads Spec. Cl 703.29 | Site Inspection | ITP Signed | IP | Supervisor / Site Engineer | N/A |  | N/A
4 | Completion
4.1 | As-built Survey |  | Completion of each lot | Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below: Departure from RL = ±10mm Departure from alignment = ±10mm Rate of change of deviation from RL or alignment = 10mm in 10m Irregularities in alignment = 5mm in 3m Section dimensions = ±5mm Section dimensions (less than 25mm) = ±3mm Width of pavement = -5mm, +15mm Where median surfacings are to be constructed between edge sections of the same level, paving shall be crowned to produce a crossfall between 1% and 3% towards the edges. Attach: Survey As-builts / Survey Report | IFC Drawings VicRoads Spec 703.15 | Document Review | ITP Signed | IP | Site Engineer | N/A |  | N/A
4.2 | Red-Line Markup |  | Completion of each lot | Capture any changes in design or RFI's as per approved red-line markup procedure | Quality Management Plan | Document Review | ITP Signed | IP | Site Engineer | N/A |  | N/A
4.3 | Non-conformance Report (NCR) Closure |  | Completion of each lot | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs. | Quality Management Plan | Document Review | ITP Signed | IP | Site Engineer | N/A |  | N/A
Notes
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
Print Name: |  | Position: |  | Signature: |  |  |  |  | Date:
Work Completed On:
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
AP | Approval Point | Written or verbal approval given by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
[5 empty] | WP | Witness Point |  | An inspection which must be witnessed by the Superintendent
Note on A13: Escalona, Sandy: ITEMS 1.1 TO 1.5 ARE STANDARD FOR ALL ITPs